Project Implementation Year
Project Implementation Year
Filter by Budget
## Network_Projects
Project Title	Project Description	Status	Comments	PMT	PMO	SME	Start	End	2014 Resource Hour Est.	2015 Resource Hour Est.	2016 Resource Hour Est.
Calibration Solution Assessment	Replace existing CalMan ISG tool due to obsolence	Active	012714 - URS, Vendor Assessment and selection in 2014. Design, realization and implementation 2015-2016	Ops Support	John Keller	Mark Martinez	Q1-2014	2015-2016	88 hours (2014 only)	tbd	tbd
Syncade Retirement (MES)	Retirement of the old "Syncade" system (part of the MES project)	Delayed	012414 - Minimal progress being made due to the back log of CR's in QA. The project team is not able to submit new CR's per their schedule.	Production	Deidre Dunham	Steve Bengis	Q1-2014	Q3-2014	48 (SME's only)	na	na
EMIS	Network replacement for the "STARI" system	Active	013014 - Training is 1 hour for Supervisors (34), 30 minutes for IC's (380), 224 hours total, Web based	Ops Support	John Keller	Juan Aragonez	Q1-2014	Q2-2014	224	na	na
Process Data Management	Network project to test the feasibility of generating a common data model using product information from various sites. 30 parameters identified. OCN is one of the sites providing data.	Active	User requirements drafted in March 2013. CA approved to continue with programming and beta testing on the 30 selected criteria. PDM user meeting scheduled for November which will provide further project updates	Quality	Melanie Yevilov	Michael Villacorta	Q1-2013	Qx-2014?
Global Freeze Thaw Tank Visibility	Improve network ability to manage the FT tank fleet.	Active	012414 - Anticipate CR submission Q2-2014 per the SME	Ops Support	John Keller	Marco Baca	Q1-2013	Q2-2014	40 (estimated)	na	na
CMC Continuum	Define process robustness for filing, and how to ensure reliable processes./products after launch, from development to commercialization	Active	121713 - Three workstreams associated with this project: 1) Resource Activity Map (end to end); 2) Overlapping Handover Process; 3) Dedicated/Designated Launch Facilities (OCN being one of them). OCN will become a CHO Launch Facility. Will require capital investment in QC infrastructure. Eric F. and Monique B. currently involved in developing the end to end business process	Quality	Melanie Yevilov	Eric Fallon, Monique Bobadilla	Q4-2012	Q2-2014		na	na
Lab Execution System (LES)	Electronic system to reduce paperwork, documentation errors, simplify anaylst activities, address compliance gaps around control and reconciliation of test datasheets	Active	012414 - Project is approved at the network level. OCN was part of the initial pilot program in 2013 and is now included in the 2014 roll out strategy. OCN Quality leadership working with the network to clarify specific resources for supporting this project.	Quality	Melanie Yevilov	Jessica Justice (network lead), Brad Lambert	Q3'2013	2015	TBD	na	na
MTI Interactive SAP E-form (IR667)	Effort to improve efficiency by promoting paperless systems (2014 IPC Top 20 Projects)	Active	012414 - Delayed in 2013 due to funding shortage. 2014 funds approved therefore project has restarted	Ops Support	John Keller	Jaci Johnson	Q1-2014	Qx-2014?	92 (FOS SME's), 106 (FOS training estimate)	na	na
Coremap Phase 2	Global Records Management Initiative (Coremap 1= training/intro. Coremap 2=roll out)	Delayed	121413 - Roll out to OCN will likely occur in Q2-2014. SME will leverage VV roll out plan, mostly high level compliance, some OCN areas already compliant, survey to be completed by the SME in Q2-2014	Quality	Melanie Yevilov	Donna Bloch	Q2-2014	Q4-2014?	TBD	na	na
PTB Portfolio Management Business Process	Strategic PPM tool for PTB	Active	012714 - PT PPM process training being rolled out. Web based training is available 01/27 with instructor led training is SSF on Feb 19 and 27. This process will holistically have minimal impact to OCN, however certain OCN resources leading cross site projects will need to use this new process.	Ops Support	Mel Davis	Gail Chen (PT PPM)	Q1-2014	Q2-2014	10 (training estimated)	na	na

End to End Logistics (Execute, deferred from 2012)	Improve end to end logistics efficieny. Improve service level to customers	pending	071313 - not an active project at OCN per the SME. 121413 - requested update from the SME	Ops Support	Mel Davis	Richard Dimler
ATTEST (Ambient Time & Temperature Tracking System)	A system to track "time-outside-of-storage-temperatures" throughout the supply chain for all temperature-sensitive drug products (commercial and clinical)	pending	071313 - not an active project at OCN per the SME. 121413 - requested update from the SME	Ops Support	Mel Davis	Richard Dimler
Supply Chain Simplification	Simplify tools and processes of the Demand to Supply process. Rreduce product complexity. Simplify product movement. Simplify materials movement.	pending	071313 - not an active project at OCN per the SME. 121413 - requested update from the SME	Ops Support	Mel Davis	Richard Dimler
SHE "K" Directives (K1 and K9)	K Directive assessment and mitigation. SHE compliance	in work	110413 - Directives K1 and K9 initial assessments have been completed. These are now part of normal operations. The remaining directives require further gap assessment	Ops Support	Juan Aragonez	Juan Aragonez

MES Upgrade	Pilot program to replace the Syncade system	Complete	Parent CR closure planned for Q4-2013 2013.	Production	Deidre Dunham	Steve Bengis	2008	Q4-2013
Maintenance Based Shutdowns	Network initiative to plan, schedule and execute plant shutdowns on a rotating basis to minimize disruptions to supply chain plant capacity and supply to patients	Complete	101813 - project completed, transitioned to normal ops per the SME	Ops Support	Mel Davis	Carl Hixon	2013	2013

## Legend
	Status (old)					Status (New)
	Idea	New network, site or department project not yet endorsed by L2, L1, PMT or IMPACT					Idea	Idea identified (below Line*)
	Proposal	Evaluate idea					Proposal	Proposal evaluated (below Line*)
	Endorsed	L1 or Network endorses business driver and problem statement.					Endorsed	PMT (IMPACT Delegate) endorses business driver and problem statement.
	Assess	Project Team or PMT Review (gather data for approval). Resources ($ and headcount)					Approved	Approved for execution
	Approved	IMPACT Approved (submit funding request, start execution).					Complete	Delivered and realized.
	Execute	In Work					Hold	Resource constrints ($ and/or headcount)
	Close Out	Punch list complete, finance close, lessons learned, TOP approved, project documents to library, etc					Cancel	Business value not evident.
	Complete	All project deliverables completed. No additional procurement or resource support required
	Hold	Project inactive for business reasons					* Line and above is actively managed projects.
	Cancel	Project does not meet business needs

	CDPL, EM77 Milestones	Resource Plan					Status (NewPrime)	Status (old)		Status (New)
PI	Project Initiation	yes					Idea	Idea		Idea	Idea created (Scope Sheet)
CD	Conceptual Design	no					Proposal	Proposal		Proposal	Develop Resource Plan/Budget/Schedule/Prioritization (IMPACT Slidedeck)
DD	Detailed Design	NA					Endorsed	Endorsed		Endorsed	IMPACT or IMPACT delegate (L2 PMT) endorses business driver and problem statement for the proposal.(should do)
CC	Construction & Commissioning					Assess
CD	Close-Out					Approved	Approved		Approved	Approved for execution IMPACT (assumes it is in execution)
				Execute
				Close Out	Close Out				(09/27/12, MD, add this to the drop down option)
	DMAIC Milestones	Scope Sheet					Complete	Complete		Complete	Delivered and realized.
D	Define	yes					Hold	Hold		Hold	Constraints ($ and/or headcount, plant availability/production schedule impacting)
M	Measure	no					Cancel	Cancel		Cancel	Value not evident.
A	Analyze	NA
I	Improve
C	Control					Above the line = "Fully defined, able to be assessed"
				Budget List = Formerly "IMPACT-Endorsed" List
	PMT Assigned	Type					"Proposal" Status = Not yet to PMT
	Operations Support	Network
	Production	Site
	Quality	Dept
		CAPA
		STARI					IF				THEN
		LIA					IMPACT-Budgeted Project				Approve at PMT - okay to proceed
				Blank				Requires Resources & Timing ONLY- no impacts to other projects/schedule				Present to IMPACT - "INFORM" Only
	Minimum Projects Requirements	Health	Green					Example: 3K Solera project feasibility study
	Scope	Financial	less than +/- 20%
	Prioritization	Schedule	Red
	Resource Plan		greater than +/- 20%
	Funding +/- 50%					IF				THEN
				Network Project (Intake Assessment)				PMT (Team) Review NOT required, but Portfolio Manager review needed
	Corporate Goals					Requires Resources & Timing ONLY- no impacts to other projects/schedule				Project lead Present to IMPACT (INFORM ONLY) to understand detailed resources breakdown (and impacted L1 team)
				Requires Resources & Timing ONLY- impacts other projects/schedule				PMC site representative resolve conflicts with network and INFORMS IMPACT of status
	Supply to Patients					Example: PDM project
	Contribution to Target

	Status Key (Updated 112912)
	Status	Definitions
	Idea	Conceptualized
	Endorsed	T0 / T3 Budgeted
	Approved	Funded
	Close Out	Execution Completed
	Financial Closed	Invoices Paid, POSs and WBS are Closed
	Complete	ALL Deliverables Requirements Mets
	Hold	Pending Go / No Go Decsion
	Cancel	Project Terminated

## Lookups
PMO		Delivery Lead			Credit		Status		Program		DRIVER		Number	Title	Type
Alister Huffton		Blake Brown			Department		BMLT Appr		Highly Capable Workforce		RTO		64643	OCN B311 Microscopic Visual Examination (MVE) Implemenmtation	FAE
Deidre Dunham		Charlie Bisbee			Global		Budgeted		Launch and Commercial Excellence		QSP		73316	OCN B311 20L Bionet Cabinet
Jim Neeleman		Ching Lee			Individual		CA Routing		Exceptional Culture		CTT		73323	OCN B311 Stainless Steel HMI Replacement	FAC
John Keller		CRB			Start-up		CA Submitted		Reliability and Value		TBD		73325	OCN B311 Agitator Seal Reliability	FAC
Juergen Kemeter		CRB Partial			TBD		Canceled		Fit for Purpose				73328	OCN B311 Filter Integrity Testers
Mel Davis		Dave Stewart			Expense		Close Out		TBD				73337	OCN B321 Support Equipment to Delta V
Melanie Yevilov		DBX			N/A		Complete				Finance		73345	B300 Autoclave Optimization	FAC
N/A		Dirk Ellison					Concluded				T0		73350	OCN B300 BMS (MCS) Upgrades	FAC
Scott Fields		Dona Bloch			Category		Execute		Approved		MO5		73355	OCN B311 CAPA 732540 - Agitator Mechanical Seal Flush	FAC
TBD		Greg Crecely			Improvements and Efficiencies		Execute 1		Canceled		T3		73356	OCN B311 BDU Supplemental BDU Sampling
Zaymar Sedra		Jessica Justice			New Technologies		Execute 2		Complete				73361	OCN B341 Demand Flow CW VSD Upgrades
		Jim Koons			SHE and K-Directives		Expense		Execute				73363	OCN B311 Bioreactor Piping Corrections (CAPA)	FAC
		John Urban			Stay in Business		Financial Closed		Hold		Budg		73364	OCN B300 Fall Protection Improvement	FAC
		M. Gabrenas			Strategic		FXNL LT Appr		Idea		Estm		73366	OCN B300 MCS (PCS and MES) System Access and Account Management Enhancement	FAC
		Marcus Espinoza			Tech Transfers		Hold						73367	OCN B300 PCS Automated Documentation (DeltaV)
		Melanie Yevilov					Idea						73368	Cooling Tower Water Filtration System
		N/A					IMPACT Appr						73348	Freeze Thaw Skids, Return HTF Filter	FAC
		Nicole Nepomuceno					In Realization						74111	OCN Debottlenecking
		No CRB					JPMT Appr						74119	Harvest Modifications (New)
		Pamela Baker					Placeholder						74126	OCN B300 Debottlenecking Start-up
		Pete Magill					PTAA						74127	OCN B311 Harvest Modifications Start-up
		Rami Barghout					TBD						74162	TDS Remediation
		REM			Column1								74198	OCN B311 3k Solera
		Rich Johnson			Delayed								74241	OCN B300 Delta V PCS
		Scott Brier			Estimate Decrease (2016)								74244	OCN B311 Cell Culture Sampling - NovaFlex
		Siu Fai Tsang			Estimate Increase (2016)								74246	OCN B311 G6 Tech Transfer
		Steve Novak			New Project								74265	OCN B311 Harvest Depth Filtration
		TBD			Removed								74268	OCN B311 P2 Downstream Processing Expansion
		Tony Rico			Scope Reduction								74275	OCN B341 WFI Still Drive Upgrade	FAC
		Tucker Creighton			Cashflow Timing - Up (2016)								76585	OCN B300 Fan Wall Implementation	FAC
					Cashflow Timing - Down (2016)								P22	OCN B341 WFI Pump Autostart	FAC
					Estimate Decrease (2016)								P23	B300 Mezzanine Lift Phase 1B	FAC
					Estimate Increase (2016)								P24	OCN B321 Actemra Freezers Air Dryer	FAC
Factor					New Line Item (Adj)								P25	TMAC Re-design	FAC
A1 Automation Improvement													P29	OCN B311 Microbial Risk Assessment CAPAs(500k)	FAC
A2 Business Efficiency													P32	OCN B311 Automate Centrifuge Shot Volume	FAC
A3 Class A Sustainment													P40	OCN B311 GWR 1080/1090	FAC
A4 Continuous Improvements													P42	OCN B311 Optimize the Column Movement Device	FAE
A5 Product Change Over													P44	OCN B331 Sievers TOC Analyzers	FAE
A6 Quality of work/life improvements													P45	OCN B331 Ion Chromatogram Replacement	FAE
A7 SWP													P46	OCN B331 Refrigerators for Microbiology	FAE
C1 Cost Saving Projects with NPV													P47	OCN B331 Incubators for Microbiology	FAE
C2 Cost Saving Projects w/o NPV													P48	OCN B331 Turbidmeter	FAE
C3 Compliance Cost Avoidance													P49	OCN B331 20c Freezers	FAE
C4 Manufacturing Cost Avoidance													P52	AV Refresh	FAC
C5 Quality Cost Avoidance													64709	MES Load Balanceers (F5)	FAC
C6 Process Cost Avoidance													P59	Electric Cart Replacement	FAE
L1 Launch Capability													P60	Data Analytics DEV/VAL System	FAE
L2 Launch Capacity													P61	Tower Secondary Containment
L3 P2 Cost													74392	OCN B300 Water Reclaim System
L4 P2 Resource													P63	Asphyxiant Gas Engineering Improvements and Detection
L5 P2 Schedule													P64	Ventilation Installation in SE Lab	FAC
L6 Tech Transfer Cost													P65	Ventilation Installation in QC Lab	FAC
L7 Tech Transfer Resource													P66	Fall Protection (Clean Space)
L8 Tech Transfer Schedule													P67	Bio Hoods	FAE
R1 Asset Replacement													P68	Benchtop Equipment	FAE
R10 SHE audit closing													P69	Lift	FAE
R2 Business Continuity													P70	Analyzer	FAE
R3 Directly supporting IFL effort to 95%
R4 Quality finding avoidance
R6 Quality inspection closing
R7 Reducing Eco-Balance points
R8 Reducing injury / illness rate
R9 SHE audit avoidance

## Instructions_
				INSTRUCTIONS:
			Snapshot of the Master Portfolio in charts

			Total Number of Projects			Project Status (Graph)
PORTFOLIO			Total Portfolio Amount			Credit Application Type (Graph)
DASHBOARD			Number of Ideas and Total Amount			Start-up Projects (Graph)
			Latest Approved Budget (T0, MO5, T3)
			Budget Report (Graph)
			Portfolio by Business Driver (Graph)

			Outlines all the basic information for all projects including Ideas, Placeholdors, Hold and Network Projects					1	If you want to filter ONLY the projects that were included on a specific budget report. Select the report on cell AC4 and then filter the same report in column D (D5)
				2	The projects stating with letter "P" are temporary numbers until we receive the official CA number.
			Business Driver		SME			Estimated Project Cost					3	The Total Estimated Project Cost (Column AG) is the the Actual Expenditure plus the Latest Approved Budget
MASTER PORTFOLIO			Business Case		Credit Application			Network Projects					4	The Latest Budget Approved is the columns in pink (AA-AD)
			Status		Scoring					5	Column Z 20XX Expend reflects the actual expenditure for that year
			PMO Lead		Actual Expenditure					6	Column AI Current Estimate is the updated budget to be reported in the next Financial Cycle (T0, MO5, T3). The breakdown is found on the tab Budget by Finance Cycle.
			Credit Type		Approved Budget (Total by Year)					7	Projects 90024 and 6DM show the Total for the Global Projects (Bucket Projects or NIMO Small Projects). Under $500k. Only for the present year this bucket is brokendown
				8	To display the different Budget Reports, select from the drop down list on cell AD4
			Delivery Lead		Total Current Estimate					9	The Network Projects are identified as "Network" in colunm D. They are all listed below the black line.

			Displays the approved budgets by project by Finance Cycle (T0, MO5, T3) and the Current Estimate (projection for next cycle)
			Budget approved for each Finance Cycle in the five-year outlook
BUDGET BY FINANCE CYCLE			The budget and current estimate is brokendown by Capital and Expense ONLY for the current and following year, the rest shows the total.
			Budget by Finance Cycle		Capital	Detailed Approved Budget
			T0		Expense	Detailed Current Estimate
			MO5			Detailed Five-Year Otlook
			T3

			Displays the approved budget (T0, MO5, T3) by project by Year (five-year outlook)
			It is useful to compare the progress or variance of the budget for each Finance Cycle in the five-year outlook
BUDGET BY YEAR
			Budget by Year		Capital	Detailed Five-Year Otlook
			T0		Expense	Detailed Approved Budget
			M05
			T3

			Diplays the Resource Demand by Year by Quarter by PTB and PTQ for the current and following year

RESOURCE PLAN			PTB
			PTQ
			Resource Demand

LEGEND on column C					STATUS
Filter Legend for Column "C"					BMLT Appr = Approved by BMLT
This is for Internal Use most likely					Budgeted = Reported in last Budget Report but not necessarily approved by IMPACT
E = Execution					Canceled = Canceled
N = New add-ons					Close Out = Hand-off of the project when it is complete
SU = Start-up					Complete = 100% executed. Deliverables are completed. Not Financially Closed.
PI = Pull-In					Concluded = End of the project life. All phases completed and closed.
A = Automation					Execute = WBS Code Received. Ready to Execute. (Non-Phased Projects)
SSP = Scope Sheet in Process					Execute 1 = WBS Code Received. Ready to Execute Phase 1. (Multi-Phase Projects)
EXP = Expense					Execute 2 = WBS Code Received. Ready to Execute Phase 2. (Multi-Phase Projects)
WR = Waiting for Reply					Expense = Expense Proejct. It is removed from the Portfolio and added to the Expense tab
RC = Revision Complete					Financial Closed = Closed in books and all admin processes
				FXNL LT Appr = Approved by Funcional Leadership (Signed Scope Sheet Submitted)
				Hold = Project in Stand-By
				Idea = Potential Projects. Need to go through the PPM process for approval
				In Realization = Performance and outcome evaluation. Analysis of KPIs, benefits and measurements
				IMPACT Appr = Approved by IMPACT
				JPMT Appr = Endorsed by jPMT
				Placeholder = Projects that have been added to the budget as placeholder

				PROGRAMS
				1. MultiProduct - Commercial product production
				2. Reliable - Product release, 3.0 rpw
				3. Agile - PCO, adjusts to MPS changes
				4. Launch Facility - Pipeline, clinical, develop and establish local Tech T.
				5. Controllable Cost - Efficiency, add-value, upgrades

## Portfolio_Dashboard
MASTER PORTFOLIO DASHBOARD

			Total Number of Projects				Total Portfolio Amount					Ideas				Latest Approved Budget

			137		119		$485,721,013					#REF!		17		$497,714,305

			All Included Active				Including Actual Expendeture					5-Year Outlook				T3

	BUDGET REPORTS ($K)					PORTFOLIO BY BUSINESS DRIVER

	Total ($k)

	PORTFOLIO BY BUSINESS DRIVER (exc. P2, DBX2)					PROJECT STATUS

	PROJECTS BY CATEGORY					CREDIT APPLICATION TYPE

	PROJECTS BY CATEGORY (Exc. P2, DBX, G6)					APPROVED BUDGET BY PROGRAMS

	CURRENT ESTIMATE BY PROGRAMS					CURRENT ESTIMATE BY DRIVERS

	RESOURCE DEMAND BY PROGRAMS					PROJECT COUNT BY PROGRAMS

## 2016_Master_Portfolio
				MASTER PORTFOLIO
				2016
				MO5				(AA+AH)	Estimate					(AK+AQ)	(AA+AH)
			Budget Time	Global Type	Deprec CC	Prefix	Project No.	Project Title	Comments	Approval / Changes Notes	Credit Type	Business Driver	Category	Program	Factor	Business Case	Status	SPPM	CRB	PD	SME	Approved CAs	Capital	Expense	Oustand CA? (Y/N)	Carry over 2016	Benefit / P-Score	Cost/ Effort / P-Score	Overall P-Score	Total RR 2016	Expend.	2014	2016	2017	2018	2019	2020	2021	TOTAL	Total Estimated Proj. Cost	2014	2015	2016	2017	2018	2019	2020	2021	Total Current Estimate	Total Estimated Proj. Cost
1			MO5	FAE			6DM	GNE Oceanside Prod Ops	Total Global FAC		Global Bucket					$3,581k		$3,179k	$3,325k	$3,658k	$4,024k	$4,426k	$4,426k	$23,037k	$22,192k	#REF!	$786k	$3,613k	$3,325k	$3,658k	$4,024k	$4,426k	$1,385k	$26,183k	#REF!
1			MO5	FAC			90024	NIMO Small Projects - Misc	Total Global FAE		Global Bucket					$14,427k		$2,402k	$1,791k	$1,970k	$2,167k	$2,383k	$2,383k	$13,095k	$25,139k	#REF!	$9,766k	$2,331k	$1,791k	$1,970k	$2,167k	$2,383k	$5,979k	$46,792k	#REF!
1	1		MO5			Y160	64899	Engineering Library TOP Storage Unit		6/01/15 Changed to Exec. Mel working with CRB on the estimate.	Global	QSP	Improvements and Efficiencies	Reliable		Installation of a new vertical carousel system to store apporved project Turn Over Package (TOPs). Existing TOP storage capacity will be depleted by the end of 2015.	Execute	Jim Neeleman	Tucker Creighton	Mel Davis	Jeff Walcher	$85k	$82k	$3k		No	N/A	N/A	N/A	0.05			$4k					$4k	$4k	#REF!	$67k	$4k					$71k	#REF!
1	2		MO5			Y160	64901	MCS Peripheral Asset Replacement - 2015		6/08/15 CA Appr. 6/05/15 CA submitted. 6/01/15 CA issued. 5/07/15 Appr by PMT. 5/04/15 Project budgeted as expense but has been reclassified as capital. Repalcing 45 carts for mobile HMI (capital >$5k) and ipad cases with scanners (expense <$5k).	Global	QSP	Stay in Business	Reliability and Value		Resolves OSHA Regulatory Agency finding which required OCN to cease use of HMIs. The improvement of the HMI platform will also give operators access to Syncade, Doclink, and DeltaV on four windows displayed on two screens.	Execute	Scott Fields	N/A	Alister Hufton	Matt Hunt	$325k	$225k	$100k			0.0	0.9	0.0	0.05			$100k					$100k	$100k	#REF!	$223k	$43k					$266k	#REF!
1	3		MO5		583	Y160	64914	QC M9 TOC Analyzers	Asset Replacement	7/14/15 CA Appr. 7/09/15 Changed to CA Submitted.	Global	QSP	New Technologies	Launch and Commercial Excellence		There is a global effort to harmonize all GNE/Roche sites to use the same GE model for the TOC assay testing.The intent of this project is to replace the existing TOC analyzers in the lab which are at the end of their lifecycle and purchase the recommended GNE/Roche model. Scope of work includes: Purchase two TOC analyzers, qualification, GMP release and turnover package for each.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	$106k	$106k				N/A	N/A	N/A				$19k					$19k	$19k	#REF!	$87k	$17k					$105k	#REF!
1	4				583	Y160	64923	QC Met-One Air Sampler Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2016	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Launch and Commercial Excellence		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	$68k	$65k	$3k			N/A	N/A	N/A				$16k					$16k	$16k	#REF!	$44k	$16k					$60k	#REF!
1	5				583	Y160	64925	QC UV Vis Spectometer Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2018	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Reliable		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	$28k	$28k				N/A	N/A	N/A				$22k					$22k	$22k	#REF!		$22k					$22k	#REF!
1	6				583	Y160	64927	QC Gel Imager Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2020	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Launch and Commercial Excellence		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	$16k	$16k				N/A	N/A	N/A				$3k					$3k	$3k	#REF!	$12k	$1k					$13k	#REF!
1	7		MO5		1275	G160	73356	Supplemental BDU Sampling	6/13/14 Needs to come back to jPMT before resolving some issues. Network Portfolio Key Site Project. "Green Planning" approved at IMPACT $1,782,500 ... $350,500 for PI phase, will return to IMPACT in Feb 2014 for final funding request. Per CAPA 746996 and recent regulatory commitments to the EMA, additional testing of the Actemra drug substance is required at the end of the dispensing operation to ensure product homogeneity. Furthermore, a separate sample of the drug substance is required by Chugai for the QC testing in Japan. Optimization of the sample volumes is critical so as to mitigate the impact to the inventoried bulk yield and drug substance supply. CAPA 746966	9/22/14 Approved WBS for Phase II. 8/22/14 Changed budget according to appr CA. 7/22/14 Apprd by IMPACT CA2 $2,304 CAP $2,292 $12.5 EXP Total Project $2,690,092. 7/17/14 Appr at jPMT. 7/11/14 According to Deidre's input, this project will be executed and we will keep the same budget. 6/11/14 - Changed to Exec. JN	Individual	CTT	Stay in Business	Launch and Commercial Excellence		CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Execute 2	Jim Neeleman	Greg Crecely	Mel Davis	Paul Crowley	$386k	$355k	$31k	Yes	Yes	3.3	3.0	19.5				$158k					$158k	$158k	#REF!	$1,421k	$158k					$1,837k	#REF!
1	8		MO5		1275	L160	73367	FS & DS Automation Integration	Maria's email these two projects Functional Specification Development (P36) - $280k and PCS Automation Documentation project (73367) - $650k / are capitalized, and both projects are combined into one project - titled FS & DS automation integration.	12/16/14 Changed to Execure 2. 11/22/14 CA Submited. 11/18/14 CA issued. 11/04/14 Appr by IMPACT for Phase 2 on the PCS Autom. Doc. . 10/30/14 Appr by jPMT Phase 2 for PCS Automation Documentation portion. Total project $612,547.	Individual	CTT	Tech Transfers	Fit for Purpose		Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Execute 2	Zaymar Sedra	John Urban	Mel Davis	Pat Sraubol / Ravi M.	$325k	$325k		Yes	Yes	3.9	2.8	24.4				$27k					$27k	$27k	#REF!	$477k	$27k					$750k	#REF!
1	9		MO5		1198	G160	73384	Caustic Bath Upgrade	Project reviewed and treated as pull-in. This project was present along the Optimize Column Movement Device, but was requested to be submit by itself.	11/7/14 WBS received. 10/31/14 CA Submitted. 10/22/14 CA on Hold as it needs to be prioritized for 2015 budget.	Global	QSP	Stay in Business	Highly Capable Workforce		The increased run rates, and the column packing activities require a safer, more reliable method for out of place cleaning. A safety job hazard assessment was performed comparing a score of 60 (high risk priority) for the current operation, to a score of 16 (low risk priority) for the proposed solution. / It is the right thing to do for our employees.	Execute	Melanie Yevilov	N/A	N/A	Bahar Dahi / Juan Pacio	$34k	$34k			No	2.0	0.8	16.5				$12k					$12k	$12k	#REF!	$1k	$k					$2k	#REF!
1	10		MO5		1586	G160	73387	MCSBACKUP Phase 2 Tape Retrieval		11/27/14 WBS received. 11/11/14 CA submitted.	Global	QSP	New Technologies	Reliability and Value	A2 Business Efficiency	Phase 2 for the MCSBACKUP deployment. Need to ensure data can be retrieved and stored per GMP requirement.	Execute	Deidre Dunham	John Urban	Mel Davis	Myles Sumlin	$64k	$60k	$4k		No	N/A	N/A	N/A	0.01			$5k					$5k	$5k	#REF!	$42k					$46k	#REF!
0	11				659	G160	73388	SIMCA Online Real Time Process Monitoring System		12/10/14 WBS received. 12/02/14 CA Submitted. 11/20/14 CA issued. 11/18/14 Appr by IMPACT. 11/13/14 Appr by jPMT.	Global	QSP	New Technologies	Launch and Commercial Excellence		As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Execute	Jim Neeleman	John Urban	Mel Davis	Michael Villacorta	$321k	$299k	$22k	No	No	1.2	2.5	7.8	0.47					$k	#REF!	$263k					$263k	#REF!
1	12		MO5			G160	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Asset Replacement. Repalcing 49 units and adding 15 new ones.	7/14/15 CA Appr. 7/09/15 Changed to CA Submitted. 6/12/15 Changed to CA Routing. 6/04/15 Changed to Appr PMT. 11/12/14 SS submitted. 10/16/14 P-scored at jPMT.	Global	QSP	Stay in Business	Reliability and Value		Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Execute	Scott Fields	John Urban	Mel Davis	Shane Smith	$274k	$274k			No	1.4	2	10.5	0.83			$205k					$205k	$205k	#REF!	$13k	$216k					$229k	#REF!
1	13		MO5			G161	73399	Frit Handling and Storage	04/29/16 Total reflects approved CA amount, in addition to $60k for design change. 03/04/15 It has been moved to above the line and need to come to IMPACT for approval. Below the line. Budget $113k 2015. This project was presented along the Optimize Column Movement Device, but was requested to be submitted by itself.	7/21/15 CA Appr. 7/15/15 CA Submitted. 07/13/15 CA Routing. 07/7/15 Changed to IMPACT Appr. 06/18/15 Changed to PMT Appr. 05/07/15 Per Juan, this project is deffered for bandwith reasons and vendor shop load. 03/04/15 Changed to FXNL Appr per Dave email. 12/18/14 Changed to on Hold. 10/22/14 CA on Hold as it needs to be prioritized for 2015 budget.	Global	QSP	Tech Transfers	Highly Capable Workforce	A2 Business Efficiency	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Execute	Melanie Yevilov	N/A	N/A	Bahar Dahi / Juan Pacio	$154k	$154k			No	1.4	0.6	11.3	1.13			$207k					$207k	$207k	#REF!	$19k	$153k					$172k	#REF!
1	14		MO5			G160	73406	Guided Wave Radar V-4045 & V-4055		8/10/15 CA Appr. 8/6/15 CA Submitted. 7/23/15 CA Routing. 7/16/15 PMT Appr. 7/15/15 Revised SS submitted to include V-4055 on the scope. 6/4/15 SS submitted.	Global	QSP	New Technologies	Agile		Ongoing issue which can directly impact product quality and yield. To mitigate the issue the load cells are not being used anymore, instead V-4040 load cells and the BDU are used to estimate weight. Provides more robust process with less external influence and less human intervention.	Execute	Zaymar Sedra	John Urban	Alister Hufton	Juan Pacio / Tammy Price	$61k	$61k				1.5	1.0	12.0				$17k					$17k	$17k	#REF!	$32k	$17k					$49k	#REF!
s	15					73409	Solar Power Enabling Project	Original named Fencing Solar Power Panel Area. Presented at PMT with a range of $460-576k incl. 20% contg.	9/4/15 CA Appr. 8/30/15 CA Submitted. 8/13/15 CA Routing. 8/04/15 IMPACt Appr. 7/30/15 PMT Appr. 7/16/15 PMT approval deferred. 3/23/15 Cashflow and RR updated.	Global	QSP	SHE and K-Directives	Highly Capable Workforce		OCN has made the decision to do a Solar Lease Agreement (SPPA). This project facilitates the installation of solar panels and associated infrastructure as required by the lease agreement. The solar project supports the Roche Eco-Balance network initiative for sustainability. Projected energy savings over the life of the lease are estimated at $10 million (or higher as energy rates continue to increase).	Execute	Melanie Yevilov	Jim Koons	Mel Davis	Sumner Tison	$570k	$461k	$109k	No	No	0.8	2.2	5.1	0.11			$306k					$306k	$306k	#REF!	$132k	$307k					$439k	#REF!
1	16		MO5		1359	L160	74119	Harvest Upgrade (New Centrifuge)	In MO5 and T3 the these three projects were reported separately. For 2015 T0 were combined (Centrifuge, Seed Lab, New HCCF). For 2015 MO5 will be seperated again as three projects.	9/04/15 CA2 Appr. 8/13/15 Full green CA submitted. 8/10/15 CA Routing for full green. 02/25/15 CA Appr. 11/10/14 Ken will submit reviewed cashflow by 11/19 No SS necessary. 8/11/14 OLT and PMs decided to combined all three projects in one, so this one includes Add New HCCF and Seed Lab (Six 20L Bioreactors) 7/3/14 Per Ken's input, we will leave the same budget as we are still defining the scope. 7/2/14 Sent out email to Ken.	Individual	QSP	Strategic	Fit for Purpose		Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Execute 2	Zaymar Sedra	N/A	PTAA	Ken Hamilton Mark Jones	$15,479k	$476k	$15,003k	Yes	No	N/A	N/A	60.0				$7,039k	$4,885k					$11,924k	$11,924k	#REF!	$3,555k	$4,636k	$7,288k					$15,479k	#REF!
1	17		MO5			L160	74127	Harvest Modifications Start-up		7/3/14 Per Ken's input, we will leave the same budget as still we are defining the scope.	Start-up	QSP	Strategic	Launch Facility			Budgeted	Deidre Dunham	Rich Johnson	Alister Hufton	Ken Hamilton				Yes	No	N/A	N/A	60.0				$125k	$2,275k					$2,400k	$2,400k	#REF!		$125k	$2,275k					$2,400k	#REF!
1	18		MO5		1275	B160	74268	P2 Downstream Processing Expansion	Network Portfolio Key Site Project. CA1 approved for $3,377,000 - PI Phase only. M05 2015=$63,700,000 + $1,000,000 Expense. 2016 = $44,390,917. 2017= $234,619. Total project costs = $121,365,536	8/13/15 Full green CA submitted. 8/10/15 CA Routing for final phase. 7/2/14 Followup with Mark and Paola regarding budget adjustment. 6/11/14 - Changed to Exec. JN	Individual	QSP	Strategic	Fit for Purpose		The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Execute 2	Zaymar Sedra	Dirk Ellison	PTAA	Mark Jones / Dirk Ellison	$193,916k	$185,694k	$8,222k	Yes	Yes	N/A	N/A	60.0				$93,652k	$34,280k					$127,932k	$127,932k	#REF!	$58,485k	$93,629k	$34,280k					$193,094k	#REF!
1	19		MO5			B160	74277	P2 DPE Start-Up		8/13/15 Full green CA submitted.	Start-up	QSP	Strategic	Fit for Purpose		Site support for the design, testing for the engineering runs, plant time for 12 runs, and materials that can be used for both engineering runs and qualification runs. The ISD is based on licensure of the potential product candidates for OCN according to the CMContinuum Designated Launch Facility Strategy.	Execute	Zaymar Sedra	Rich Johnson	Alister Hufton	Dirk Ellison/ Ken Hamilton	$51,500k	$51,100k	$400k		No	N/A	N/A	60.0				$4,461k	$40,281k	$6,755k				$51,497k	$51,497k	#REF!		$4,461k	$40,281k	$6,755k				$51,497k	#REF!
1	20		MO5			B160	74278	K6 Program - Project 3 - Replace Cold Room Compressors	Change -20 freezer compressors. Phase 2 of the k6 proejcts. Phase 1 would be Replace DX Units.	11/17/14 Project reviewed. 7/1/14 Budget confimed by Sumner. Dave confirmed not SS will be needed for now. Sent out email asking for it. 6/30/14 Changed SME to Sumner.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Complies with Roche K6 directive to reduce R-41A and R-22 refrigerants. Will reduce R-22 refrigerant in all cold rooms across the site by 2018 and R-404 refigerant in the main freezer by 2022. Free standing lab freezers are out fo scope.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Geoff Wing					No	4.4	5.2	16.5					$603k	$4,828k	$4,828k	$500k	$500k	$11,259k	$10,759k	#REF!			$603k	$4,828k	$4,828k	$500k		$10,759k	#REF!
1	21		MO5		1275	L160	74279	New Media Technology - HTST / Adventitious	04/03/15 HTST options reviewed by OLT and received endorsement to proceed with the next phase of funding approval with a project total of $9.5MM. In order to achieve this project total, several items were removed (slides 5 & 6) and the contingency was reduced. In order to maintain a working contingency, each of the project components like install, design, project management, etc. will be judged-down by 10% and the project costs and accountable disciplines. That 10% will be combined with and held as contingency to provide a management reserve. CAPAs 577402 and 740579. Network Portfolio Key Site Project. M05 2015 = $0 Capital + $0 Expense. CAPA - commitment to FDA. Leptospira mitigation. Implement additional adventitious agent barriers (e.g. solution autoclaving, heat treatment, or viral filtration) for solutions which are not HTST compatible. M05 2015 = $7,000,000 Capital + $75,000 Expense. Implement HTST for spinner through N-2 cell culture stages for all solutions which are compatible with HTST treatment. CAPA - commitment to FDA. Leptospira mitigation. To address improved viral control ($2M = 2014, $5M 2015)	06/02/15 WBS confirmed. 05/22/15 CA Appr. 04/30/15 CA submitted. 04/24/15 CA issued. 03/31/15 Appr by IMPACT but will be subject to SMART & OLT endorsement. 03/26/15 Phase 2 Appr by PMT10/7/14 CA Appr. Changed to Exc 1. 9/17/14 Budget updated accord. CA. 6/30/14 Budget updated according to Scott's input. 6/11/14 Changed to RTO- JN. 6/10/14 Appr by IMPACT. 6/05/14 - Appr by jPMT. CA1 $1,321k, CA2 $7,961k inc Contingency. Total $9,282k.	Individual	RTO	New Technologies	Reliability and Value		In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Execute 2	Scott Fields	John Urban	Alister Hufton	Will Jimenez	$1,115k	$1,095k	$20k		Yes	3.7	3.8	19.2				$4,813k	$1,603k					$6,415k	$6,415k	#REF!	$1,984k	$4,947k	$1,591k					$9,046k	#REF!
0	22				1275		74280	Spare Hasstelloy Columns	M05 2015 = $1,700,000 Capital + $10,000 Expense. Need column strategy and matrix of current columns to show need for new. Confirm if this is risk mitigation, essential for PCO/run rate. Buy new Hasstelloy Columns (to avoid having to unpack between campaigns and provide backups, 1.8 and 1.4 minimum needed 2014, 1.6 2015)	7/17/14 Changed to Exec. Budget adjusted according to the IMPACT Presentation and CA.	Individual	QSP	Stay in Business	Agile	A5 Product Change Over	Project reduces risk to 5 day PCO my mitigating operation risk at ProA step for both Actemra and Rituxan campaigns. To maintain run rate of 3.p rpw a 3rd column needs to be packed to support the ProA step. With this project the risk of not achieving 5 day PCO is minimized.	Execute	Melanie Yevilov	John Urban	Mel Davis	Bahar/Karen	$2,500k	$2,499k	$1k	No	Yes	1.8	2.4	11.6					$k	#REF!					#REF!
1	23		MO5		659		74302	Waterpooling Remediation	9/08/15 Project will be susprended until S/D 16. The total project estimate for the MP and BP is $$2,068, if the adittional areas are added to the scope the total estimate woud be $3,06M. Decision from quality council determined a phased implementation approach and the total cost is being reassessed. Uncertatinty on this project as it was partially approved for Buffer and Media Prep Areas, but depending on the results and lessons learned, the second phase might follow. Network Portfolio Key Site Project. $500K requested, cut to $490K during budget review. This figure to increase to $1.1M to account for all the required external support (viz automation, val & QEV). Note, the early estimate did not have have the fuller analysis that has now been done. Revised to $1.3M, $650K in 2013, $650K in 2014. CAPA 719091	12/09/14 WBS received. 11/17/14 CA submitted. 11/04/14 CA issued. 10/10/14 Appr by BMLT for Phase II. 9/23/14 Appr by IMPACT for Pahse II 9/17/14 Appr by jPMT Phase II with a funding request of $378k inc 10% conting. 7/15/14 Adjust budget according to IMPACT, back to $3,190k. Changed Status to Appr. 7/14/14 Partially approved for Media Prep and Buffer Prep Areas. Phase 2 execution will depend on progress and results of Phase 1 NN. 6/24/14 - Per IMPACT Meeting this project has been canceled by Quality Council. They will come back to IMPACT on 7/08/14 with Close Out Report and Fianancial Summary . 6/11/14 - Changed to Exec. JN	Individual	RTO	Stay in Business	Reliability and Value		Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Execute 2	Jim Neeleman	John Urban	Alister Hufton	Ken Hmilton / Tim Chen	$1,690k	$1,665k	$25k	No	Yes	3.4	2.3	23.0				$370k	$52k					$421k	$421k	#REF!	$470k	$370k	$50k					$2,085k	#REF!
1	24		MO5		1275	L160	74368	Dev/Val Automation Capacity Expansion	6/19/14 - Per Maria's email PCS Development and Validation Environments Capacity Expansion (DeltaV) (74368) is combined with LivePoint Data Analyzer Software Expansion. Both projects are capitalized into one project Dev/Val Automation Capacity Expansion.	7/07/14 Purchase additional development and validation license for Data Analytics System (DA) was added to this project $24k capital. Combined 74368, LivePoint, Data Analytics DEV/VAL System	Individual	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	A1 Automation Improvement	The DEL/VAL system expansion in order to increase the amount of project work, reduce delays in projects, allow MAR charges that correct current automation issues. Evaluation of system indicated we will fall short of required resources for MAR work with upcoming projects.	Execute	Jim Neeleman	Greg Crecely	Alister Hufton	Matt Hunt / Ravi M.	$24k	$24k		Yes	No	?		N/A				$10k					$10k	$10k	#REF!	$56k	$10k					$555k	#REF!
1	25		MO5				74371	Odor Treatment	12/10/15 Susan/Sumner get OLT decision to defer. 2016 = $1,000,000 Capital. M05 2017 = $4,000,000 Capital	12/15/15 Originally called Waste Water Recovery 11/11/15 PI to start Mid-2016. 03/25/15 Feasibility study will be done in June with a potential to be combined with TDS Remediation. 03/20/15 Per Tim's email this project is pushed out one year. 11/18/14 SC submitted. 11/07/14 Project reviewed, Tim to submit SS by 11/18/14 we will do p-score then. 10/27/14 Changed to Budgeted. 6/30/14 Changed to CTT and budget according to Tim input. Tim will work on the SS for Phase 1 & 2. Will be split on two projects. Later, he will submit Phase 3 SS. TL	Individual	CTT	SHE and K-Directives	TBD		Strategic project to detoxify/purify the water and reuse it in the different processes as conservation plan.	FXNL LT Appr	Melanie Yevilov	Jim Koons	Mel Davis	Tim Lai					No	2.9	6.6	6.8					$750k	$4,750k				$5,500k	$5,500k	#REF!				$750k	$4,750k			$5,500k	#REF!
1	26		MO5		1891	B160	74373	WFI Generation and Storage System / CUB Expansion	This project has been approved by jPMT in combination with CUB Expansion & Storage Tank for a CA1 of $3.9M. $2.9M Equipment and $1M Design.	06/05/15 WBS confirmed. 06/04/15 CA Appr. 04/30/15 CA submitted. 04/21/15 Appr by IMPACT and CA Routing. 04/09/15 Changed to PMT Appr for Phase 2. 11/04/14 WBS received. 11/03/14 CA approved. 10/10/14 Original CA was rejected and NPV was modified. REVISED CA was submitted today. 9/29/14 CA Submitted. 9/5/14 Appr by BMLT. 8/19/14 Appr by IMPACT. 8/14/14 Apprd by jPMT. 7/18/14 Changed to FLT Appr. 7/17/14 Adjusted budget according to Tim's email 20% for 2014. 7/14/14 Changed PMO Lead. 7/03/14 Sent out email. 6/30/14 It will be executed during P2. Start date Q4 2014. Finish date towards the end of 2015. We need to pull in budget to 2014/2015. The SS will be developed once the project is determined to de during P2. TL	Individual	QSP	Strategic	Fit for Purpose		The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Execute 2	Zaymar Sedra	Jim Koons	Alister Hufton	Tim Lai	$4,682k	$4,625k	$57k		Yes	2.9	5.1	11.1				$5,536k					$5,536k	$5,536k	#REF!	$6,526k	$5,536k					$13,801k	#REF!
1	27		MO5		1198	L160	74382	Sci&Eng Lab Mods and Equipment	MO5 / T3 = $13,600k. Total Assesed Project was $13,621k and it was judged down to $12,721k which it is the maount presented to Capital.	7/20/15 CA Appr. 6/25/15 Changed to CA Subm. 06/10/15 CA issued. 05/07/15 Phase 2 Appr by PMT. 01/30/15 WBS Received. 10/28/14 CA Submitted. 10/10/14 Appr by BMLT. 9/30/17 Appr by IMPACT. 9/17/14 Appr by jPMT. Changed budget accordingly. 9/10/14 Changed name removing "QC".8/27/14 Changed to Budgeted. From 8/21/14 meeting, this name might change to reflect that this project will be for Sci&Eng lab only. 7/120/14 Adjusted estimate according to Semsi's email. 7/01/14 SS was received but needs to be approved. 6/25/14 - Working on the Scope Sheet. Changed DL to Greg and PMO Lead Jim - JN/DS	Individual	QSP	Strategic	Launch and Commercial Excellence		To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Execute 2	Jim Neeleman	Greg Crecely	Alister Hufton	Fikret Kulenovic	$4,073k	$3,652k	$421k		Yes	2	5.1	7.6				$6,690k	$489k					$7,179k	$7,179k	#REF!	$6,009k	$7,610k	$391k					$14,010k	#REF!
1	28		MO5				74385	Media Prep Endotoxin/Bioburden Sampling	CAPA 734576. Total Project Cap $3M. 03/09/15 Project included on the SBP with an estimate of $2.5M over 2018-19 with great potential to pull it in.	6/20/16 Project put on hold due to lack of scope, per Matt's email. 11/13/15 PI phase 2016 no Capital. Planned for 2017 Capital. 8/17/15 SS Submitted missing signature. 4/09/15 Changed to Idea. 6/27/14 Per email this project is removed for lack of definition at this point. 6/25/14 - Working on Scope Sheet. Change DL to Greg and SME to Fikret and PMO Lead Jim - JN/DS	Individual	QSP	Stay in Business	Reliability and Value		Risk of microbial contamination exists in media prep operations for cell culture media. Contaminants can have a negative impact on product output, product quality and patient safety. facilities. Fail to comply with the committment could result in regulatory. The expected benefit of routine monitoring of bioburden and endotoxin is action. that cell culture media can be confirmed to be free of harmful levels of bacteria, exotoxins and endotoxins. This future state results in increased patient safety, improved undestanding and microbial control of open process.	Hold	Melanie Yevilov	Greg Crecely	TBD	Matt Forbes					1.4	4.2	6.5				$250k	$2,750k					$3,000k	$3,000k	#REF!					#REF!
1	29		MO5		1891	G160	74392	Water Reclaim System	04/29/16 AW, ST, TL, and AH decided to only spend remaining funds from PO. It is not required for P2, but due to structural and piping changes it is highly recommended to execute the overlapped portion with P2 to minimize downtime and system impact. There are two phases for the project, the 1st phase is in B341 and the 2nd phase is in B311. The 2nd phase can be staged out further into 2015 or 2016. The business driver is the water reduction goal that has been set forth by SHE corporate, as well as resource conservation.	03/22/16 Project rescoped and reduced by $332k per MD. 12/14/15 Scope reduction, removed $800k from 2016 to 2017 per AH. 01/14/14 Changed to Exec. 12/02/14 CA Submitted. 10/14/14 CA issued. 9/2/14 Appr by IMPACT. 8/21/14 Appr by jPMT. 7/14/14 Changed PMO Lead. 7/08/14 Budget updated according to Pull In Meeting. We still need to confirm with estimate. 6/30/14 Entered budget according to Tim input. Tim will work with John on the SS.	Individual	CTT	SHE and K-Directives	Reliability and Value		There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Execute	Scott Fields	Jim Koons	Mel Davis	Tim Lai	$344k	$323k	$21k		Yes	0.9	2.3	6.1				$162k					$162k	$162k	#REF!	$179k	$144k					$323k	#REF!
1	30		MO5		659	L160	74404	Mezzanine Lift Media Prep: Phase 1B	8/19/14 CA1 $707,729 incl 20% Contg. 2014 it might start work with the gate for 1A lift and purchase of equipment and 2015 the installation of the new lift. Improvements and additional lift for Media Prep. 3/11/16 Have to wait for eletrical shutdown to tie in 480V, per MD.	10/13/14 WBS Received. 9/24/14 CA Submitted. 9/15/14 Updated the budget according to CA. 8/19/14 Appr by IMPACT. 7/03/14 Appr by jPMT coming to IMPACT. 7/2/14 John input is that they will come to jPMT for approval of additional funding	Individual	QSP	SHE and K-Directives	Highly Capable Workforce		To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Execute	Melanie Yevilov	Tucker Creighton	Mel Davis	Dick Sloan	$686k	$656k	$30k		Yes	1.5	1.9	10.7				$201k					$201k	$201k	#REF!	$265k	$270k					$553k	#REF!
1	31		MO5		1238	L160	74406	Corrosive Chemical Compliance	Pull-In a portion in 2014 (PI) for around $150K. 3/11/16 Planned to do 3 phases (separate projects); 311 in 2016, 341 in 2017, and 321 in 2018 as per MD.	6/16/16 Will be requesting $2M additional funding, CRB firming up amounts. 01/16/15 WBS Received. 01/14/15 Changed to CA submitted. 11/04/14 Appr by IMPACT. 10/23/14 Appr by jPMT. 10/9/14 Needs to come back to jPMT with the modifications on presentation, estimated 10/23/14. 8/21/14 Changed to LT Appr. 7/14/14 Change the PMO. 7/08/14 Added according to our Pull-In meeting	Individual	RTO	SHE and K-Directives	Reliability and Value		Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Execute	Scott Fields	Jim Koons	Mel Davis	Tim Lai	$1,953k	$1,901k	$52k		No	6.6	3.9	34				$1,596k	$84k					$1,680k	$1,680k	#REF!	$103k	$1,724k	$84k					$1,911k	#REF!
1	32		MO5			L160	74409	K6 Program - Project 1 - Replace DX HVAC Units	9/17/15 Planning Phase for PI/CD for the K6 Program. Project for Chillers and -20 compressors will request funds independently. 05/01/15 Per Mel's email Phase 1 will only address HVAC DX replacement for B-341 CUB. (6) units total to be replaced. Add CW, HHW, BMS to these (6) units. Phase 2 will be re-defined during the T3 2016 budgeting exercise. These numbers came from the CRB Estimator based on the revised scope of work. / Phase 1 of the K6 Project. Nine (9) units in total. Two (2) in Building 361, one (1) in Building 371, six (6) in Building 341. Estimate calculated $72,000 /Each + 45% of CRB commission and 20%	01/12/16 Project deferred per IMPACT discussion. 10/16/15 CA Routing. 10/06/15 IMPACT Endorsed. 9/17/15 PMT Appr. 03/25/15 Project cashflow and RR reviewed. 11/10/14 Project reviewed. 8/21/14 Changed to LT Appr. 7/17/14 Changed to Global JK. 7/11/14 Added to prtofolio according to John's email.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Execute	Zaymar Sedra	John Urban	Alister Hufton	Geoff Wing / Pierre Luong					No	1.8	2.7	11.3	21.21				$332k	$1,592k				$1,924k	$1,924k	#REF!			$332k					$332k	#REF!
1	33		MO5		1234	L160	74416	Asphyxiant Gas Remediation	SHE project. Jim working with SHE to define the SME to coordinate with CRB and getting an estimate. K16. 3/11/16 Project will connect to UPSS; project is currently about 3 months behind, per MD.	12/8/15 Reduced by $400k per IMPACT discussion. 7/15/15 CA Appr. 7/10/15 Changed to CA Submitted. 6/16/15 IMPACT Appr. 6/11/15 Appr by PMT. 04/10/15 Per Gary, scope has been reduced from 11 rooms to 5 rooms, budget has been reduced by 40% Project expected to be complete in 2015. 11/06/14 Project reviewed. 8/21/14 Changed to LT Appr. 8/11/14 Change SME. 7/16/14 Changed to Idea. 7/08/14 High Risk project. It will be not executed this year. IT requires a K-9 Study. 6/30/14 Added according to Liza pull-in list.	Individual	RTO	SHE and K-Directives	Highly Capable Workforce		OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Execute 1	Melanie Yevilov	Marcus Espinoza	Mel Davis	Gary Merrill	$54k	$54k			No	1.5	1.6	11.1	0.02			$142k	$400k					$542k	$542k	#REF!	$37k	$126k					$163k	#REF!
1	34		MO5		583	L160	74418	QC Lab Reconfiguration & Equipment	Phase 1 Planning $480,452. Phase 2 expected to start in May. Total Project $4,160k. P2 fall off and it has been endorsed by the Steering Committee	03/24/16 Capital and expense portions changed to align with better cash flow forecasting. 11/05/15 PMT Endorsed. 02/16/15 CA Submitted. 01/13/14 CA isued. 12/03/14 BMLT Appr. 11/18/14 Appr by IMPACT. 11/13/14 Approved by jPMT. 8/27/14 Changed to Budgeted. From 8/21/14 meeting, the portion that might be included in 74382 will be rolled up.	Individual	QSP	Tech Transfers	Launch and Commercial Excellence		Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Execute 1	Jim Neeleman	Greg Crecely	Mel Davis	Amanda Gutierrez	$481k	$467k	$14k		No	3.4	4.4	15.8				$2,031k	$1,568k					$3,599k	$3,599k	#REF!	$225k	$3,275k	$290k					$3,789k	#REF!
1	35		MO5			L160	74426	Process VSD and SOV Replacement - 2015	Asset Replacement - CRB heavely driven	6/25/15 Changed to Execute. 06/10/15 CA Submitted. 05/5/15 Appr by IMPACT. 04/23/15 jPMT Appr. 10/16/14 P-scored at jPMT.	Individual	QSP	Stay in Business	Reliability and Value		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Execute	Scott Fields	Tucker Creighton	Alister Hufton	Jonathan Clark	$707k	$707k			No	N/A	N/A	N/A				$495k					$495k	$495k	#REF!	$195k	$590k					$784k	#REF!
1	36		MO5			L160	74427	MCS Network Infrastructure Asset Replacement - 2016	S/D critical project. Asset Replacement - The project will proceed with the PI Phase for a feed study.Since the requested amount is expense and less than $500k, a CA is not required. A PO will be requested for $300k. Eric Fallon will be added to the approval chain to endorse the project as the functional leader before the authorized approvers review the shopping cart. / When the project returns for the next phase of funding, it should be split into two projects. The MES and PCS activities will become one project while the infrastructure activities will be the other. Please see E07.	03/22/16 moved above Execution line. 10/01/15 PMT Endorsed. 6/25/15 Changed back to FXNL Appr according to Team decision. 6/15/15 Changed to Canceled. Rolled over to E07 - Automation System Lifecycle MCS Upgrade	Individual	QSP	Stay in Business	Reliability and Value		The Network is the backbone of the Manufacturing Control System (MCS). The infrastructure must be kept up to date to avoid downtime. Lifecycle for equipment is 5 - 7 years. Last replacement was 2009. Project implementation requires shutdown.	Execute	Scott Fields	John Urban	Alister Hufton	Myles Sumlin					No	N/A	N/A	N/A	0.02			$1,944k					$1,944k	$1,944k	#REF!		$1,466k					$2,340k	$3,806k
1	37		MO5			L160	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	Asset Replacement.	03/03/15 Projects has been push out to 2016 to provide bandwith for Automation I&C. 11/18/14 SS submitted.	Individual	QSP	Stay in Business	Launch and Commercial Excellence		Per site prioritization, this project is necessary to support high run rates at OCN, Currently, the skids are in paper records and do not support release by exception.	FXNL LT Appr	Jim Neeleman	Tucker Creighton	Alister Hufton	Hieu Ton					No	N/A	N/A	N/A	0.20				$200k	$900k	$900k	$935k	$935k	$3,870k	$3,870k	#REF!			$200k	$900k	$900k	$935k		$2,935k
1	38		MO5		1586	L160	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Asset Replacement - CRB heavely driven	7/10/15 CA Appr. 7/01/15 Changed to CA Submitted. 6/10/15 CA issued. 5/28/15 Appr by PMT. 11/18/14 SS submitted. 10/16/14 P-scored at jPMT.	Individual	QSP	Stay in Business	Reliability and Value		Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Execute	Scott Fields	Tucker Creighton	Alister Hufton	Jonathan Clark	$662k	$662k			No	1.5	3.9	7.7	3.08			$198k	$23k					$221k	$221k	#REF!	$243k	$205k	$23k					$471k
1	39		MO5			L160	74431	Buffer Prep Mezzanine Lift Construction	Below the line. Budget 2015 Cap $100k; 2016 Cap $428k Exp $30k	03/15/16 Project moved above the line. 11/05/15 PMT Endorsed. 05/18/15 Endorsed by Don to be included in MO5 budget and bring it to execution in 2015. 05/04/15 Great potential to bring this budget above the line. It will be rested to OLT. 12/18/14 Changed to On Hold. 11/12/14 Project reviewd. Total estimate $465k + 20%	Global	RTO	SHE and K-Directives	Reliability and Value		Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	JPMT Appr	Scott Fields	Tucker Creighton	Mel Davis	Tyler Krol					No	1.5	1.9	10.7				$442k					$442k	$442k	#REF!		$442k					$442k
1	40		MO5			B160	74432	K6 Program - Project 4 - Replace Chillers		2/13/15 Changed to Budgeted.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Four (4) existing chillers in B-341 Central Utilities are not K6 compliant due to R-134A refigerant.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Geoff Wing					No	4.4	5.2	16.5	0.06				$3,000k	$6,650k	$6,000k	$3,650k	$3,650k	$22,950k	$22,950k	#REF!				$3,000k	$6,650k	$6,000k	$3,650k	$19,300k
1	41		MO5			L160	74435	Hastelloy Chromatography Column (160cm)		2/12/15 It was decided to passivate the column to extend its useful life On the ARR this column is scheduled to be replaced in 2017, so budget has been shifted accordingly.	Individual	QSP	Improvements and Efficiencies	Fit for Purpose		Only one chromatography column is needed per stage to run the process. The second column is a backup to replace expired resin on the column being used. If a third packed column is not vailable, there is the risk that the second column fails while the first one is being packed. Such an issue would incapacitate production to continue.	FXNL LT Appr	Zaymar Sedra	Jim Koons	Alister Hufton	Bahar Dahi / Juan Pacio					No	2.9	3.0	17.1	0.06				$1,549k					$1,549k	$1,549k	#REF!		$400k	$1,149k					$1,549k
1	42		MO5		1359	L160	74453	NPI Pool Tanks		03/30/15 WBS Received. 03/19/15 CA Submitted.	Individual	QSP	Strategic	Fit for Purpose		Purchase and set three additional pool tanks into the P2 now together with the P2 project. Additional pool tank capacity is a known requirement for a significant portion of the PTD pipeline currently under development. This will minimize overall cost by 60% and eliminate the need for future shut down to set these tanks.	PTAA	Zaymar Sedra	N/A	N/A	Ken Hamilton	$1,223k	$1,223k			No	N/A	N/A	60.0	2.39			$687k	$4k					$691k	$691k	#REF!	$581k	$604k	$38k					$1,223k
1	43		MO5			L160	74454	Seed Lab (20L Bioreactor)	Project related to P2 and it has been endorsed by the Steering Committee.	05/22/15 CA Appr. 04/29/15 CA Submitted. 03/16/15 Per Christian email, this project is back and split from Harvest Upgrade. ROLLED OVER. This project was combined with Harvest Mods 74119.	Individual	QSP	Strategic	Fit for Purpose		The additional six 20l bioreactors are due to: (a) the site and network practice of having backups to the seed labs to reduce operationnal risk;. and (b) we use multiple thaws for product launch; this reduces risk to, and duration of, the qual campaign, and therefore provides a stronger package to submit to the regulatory authorities. And, qual campaigns would take longer without this capability. It is established practice in the network to run multiple thaws.	Execute	Zaymar Sedra	TBD	PTAA	Mark Jones / Paul Coon	$2,604k	$2,567k	$37k		No	N/A	N/A	60.0	5.15			$1,096k	$355k					$1,451k	$1,451k	#REF!	$1,387k	$1,010k	$441k					$2,838k
1	44		MO5			L160	74455	3rd HCCF Vessel	Project related to P2 and it has been endorsed by the Steering Committee.	05/22/15 CA Appr. 04/29/15 CA Submitted. 03/16/15 Per Christian email, this project is back and split from Harvest Upgrade. ROLLED OVER. This project was combined with Harvest Mods 74119.	Individual	QSP	Strategic	Fit for Purpose		The 3rd HCCF vessel is required to provide a buffer for manufacturing to stabilize the current operation; The requirement gets accentuated with P2 due to the need	Execute	Zaymar Sedra	TBD	PTAA	Mark Jones / Paul Coon	$3,722k	$3,693k	$29k		No	N/A	N/A	60.0	0.36			$2,071k	$114k					$2,185k	$2,185k	#REF!	$1,536k	$1,704k					$3,240k
1	45		MO5			L160	74486	PCS Controller Cabinet Asset Replacement	Asset Replacement with Safety and Compliance componenets. CAPA 7046	03/22/16 moved above Execution line. 10/20/15 IMPACT Endorsed. 10/08/15 PMT Endorsed. 10/05/15 Appr SS submitted. 5/18/15 3/19/15 SS in progress	Individual	RTO	Stay in Business	Highly Capable Workforce		Genentech standards require that all controller cabinets shall be fully UL508 listed. CAPA 7046 was generated. PCS Delta Controller Cabinet legacy design represents a safety concern to personnel my means of electrocution, and to equipment resulting in critical failure.	Execute	Melanie Yevilov	Tucker Creighton	Alister Hufton	Jonathan Clark					N/A	0.42			$2,294k	$110k					$2,404k	$2,404k	#REF!		$2,294k	$110k					$2,404k
1	46		MO5		1586	L160	74487	Process VSD and SOV Asset Replacement	CAPA 982343. Asset Replacement - CRB heavely driven	03/22/16 moved above Execution line. 12/8/15 Subtracted Process VSD and SOV Replacement - 2015 Capital portion per IMPACT discussion. 10/27 IMPACT Endorsed. 10/22/15 PMT Endorsed.	Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Execute	Melanie Yevilov	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A	0.21			$3,599k	$2,943k					$6,542k	$6,542k	#REF!		$3,600k	$2,943k					$6,543k
1	47		MO5			L160	74489	4040 Avenida Conference Center Acquisition		11/04/15 CA issued. 05/18/15 Changed to Budgeted. Endorsed by Don to be included in MO5 budget and bring it to execution in 2015.	Individual	QSP	Strategic	Exceptional Culture	A2 Business Efficiency		Execute	Deidre Dunham	N/A	Alister Hufton	Kara Swedberg					0.5	2.1	3.1				$687k					$687k	$687k	#REF!	$2,701k	$686k					$3,387k
1	48		MO5		1198	L160	74490	Hyfish Material Screening Operation		8/06/15 CA Appr. 7/31/15 CA Submitted. 7/29/15 CA Routing. 7/14/15 Project presented at Don requested an offlione meetng for final endoresement. 7/02/15 PMT Appr. 6/12/15 SS submitted.	Individual	QSP	Improvements and Efficiencies	Reliability and Value		Actemra runs have experienced a reduction in yields starting in Q4/2013. An 8% reduction in yield represents a loss of $20 million per 100 runs and potentially impact on site commercial schedule.	Execute	Jim Neeleman	Greg Crecely	Alister Hufton	Fikret Kulenovic	$1,367k	$1,367k				5.0	5.7	16.3				$423k					$423k	$423k	#REF!	$860k	$601k					$1,461k
1	49		MO5			B160	74491	Etro Tech Transfer	4/14/16 Currently includes ER/QR cost in P2 CA 2 ($17.3M+$6,935,642). 12/18/15 Direction from IMPACT to move resin and its contingency amount of $1.7M from expense to capital may be over estimated by $300k per SE. SE to work with project team to remove spend to avoid double counting. X/X/15 Partial Asset Replacement.	05/13/16 Cash flow reverted back to original forecast. 03/31/16 Cash flow updated according to latest estimates. 12/21/15 Added $500k into capital to account for resins and buffer expenditures per VG. 12/15/15 Moved $1.7M from expense into Capital per IMPACT. 05/05/15 SS Submitted. 05/06/15 CA Routing.	Start-up	QSP	Tech Transfers	Launch and Commercial Excellence		6/14/16 Change to On Hold due to the uncertatnty with this project.	Hold	Deidre Dunham	N/A	N/A	Semsi Ensari					N/A	N/A	60.0				$6,212k	$12,837k	$3,347k	$508k	$66k	$66k	$23,036k	$23,036k	#REF!		$1,364k	$12,837k	$3,347k	$508k	$66k		$18,122k
1	50					G160	74510	PCS Asset Replacement - 2016		03/22/16 moved above Execution line. 10/01/15 PMT Endorsed. 9/02/15 Originally called Automation System Lifecycle MCS Upgrade. 6/19/15 PMT Appr only feed study for $300k.	Individual	QSP	Stay in Business	Fit for Purpose		Upgrade PCS hardware and software for Development, Validation and Production environments. Coordinate with P2 Project Team to deploy during the 2016 Plant Shutdown.	Execute	Zaymar Sedra	TBD	Alister Hufton	Myles Sumlin					N/A	N/A	N/A	0.75			$1,746k	$149k					$1,895k	$1,895k			$1,766k	$149k					$1,915k
1	51					L160	74511	QR018 Compliance Steam and Condensate Containment	CAPA 969326	03/24/16 Cash flow updated according to latest estimates. 2/19/16 Project name changed to match CA. 10/27 IMPACT Endorsed. 10/22/15 PMT Endorsed. 10/12/15 Submitted SS.	Individual	QSP	Stay in Business	Reliability and Value		Compliance with QR018, meeting CAPA 939326 requirements, and to mitigate equipment degradation due to splashing, pooling and vapor condensation. Mitigation of slipping hazards for personell from condensate pooling and drain splashing. Scope includes both P1 and P2.	Execute	Jim Neeleman	Rich Johnson	Mel Davis	Anastasia Gandrik / Sumner Tison					2.6	3.8	13.3				$1,943k	$3,075k					$5,018k	$5,018k			$1,943k	$3,075k					$5,018k
1	52					G160	74512	K6 Program - Project 2 - B381 Compliance	4/15/16 Prefer to couple with project 74278 to reduce risk of cost overruns, pending general manager endorsement.	11/6/15 SS pending signature.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Existing DX HVAC units in B-381 Conference Center use R-410A refrigerant. This refrigerant is on the list of materials to be eliminated per the Roche K6 directive.	FXNL LT Appr	Zaymar Sedra	John Urban	Mel Davis	Geoff Wing					$356k	$444k				$800k	$800k					$356k	$444k			$800k
1	53					G160	74513	Electric Vehicle Charging Stations		10/20/15 Presented to IMPACT, however it was put on hold. 8/31/15 SS Submitted.	Individual	CTT	Improvements and Efficiencies	Exceptional Culture		There are no EV charging stations on the site at OCN. This project will install up to five on-site EV charging stations to serve up to 20 vehicles. allowing OCN to remain competitive and a desired employer near talent competititors. Inline with other large local innovative companies. Benefit for Great Place to Work. Reduce Ecobalance contribution. Supports advancement of green vehicles.	Hold	Deidre Dunham	Scott Brier	Mel Davis	Sumner Tison					0.3	1.5	2.2					$730k					$730k	$730k				$730k					$730k
0	54					G160	74524	Bioburden 2606 IPA Exhaust Improvement	SHE - Project identified during SBP Review. Might change name to IPA Exhaust Improvement (STARI 16830)	6/25/15 Changed to FXNL.	Expense	RTO	SHE and K-Directives	Reliability and Value		Over exposure to IPA can lead to major health complications. Currently Roche and OSHA "Alert" and "Action" levels of exposure have been exceeded.	Execute	Melanie Yevilov	Marcus Espinoza	Mel Davis	Geoff Wing					2.3	1.0	18.0					$k	#REF!		$15k					$15k
1	55					G160	74526	Utility and Process Safety System	2/25/16 Assumptions for T0, unaware of the full scope of the project. Was assumed to be a project-by-project basis, not "full ring" basis--will deliver on Freeze Thaw and CCC projects. 12/10 Renamed from SIL II System. 11/10/15 Potentially replace Asphyxiant Gas Remediation project; P2 Critical. Mel to submit SS by 11/15/15.	03/24/16 Capital portion changed to align with better cash flow forecasting.	Individual	RTO	SHE and K-Directives	Reliability and Value		The OCN site lacks a dedicated Safety Instrumented System to avoid issues with code compliance, avoid accidental trips, maintain and test instruments.	FXNL LT Appr	Scott Fields	John Urban	Mel Davis	Charles Fuller					2.6	3.8	13.3				$1,190k	$510k					$1,700k	$1,700k			$1,882k	$58k					$1,940k
1	56		MO5			B160	74527	Vessel 1020 Upgrade	4/14/16 Project is for Actemra.	11/11/15 Will J. to work on SS. 05/18/15 Changed to Budgeted. Endorsed by Don to be included in MO5 budget and bring it to execution in 2015.	Individual	QSP	Stay in Business	Fit for Purpose		The media is being made in a hastelloy tank in buffer prep and then needs to be packed out to be used in the upstream. Technically, we are crossing the US/DS barrier - this is a bad practice and will get more complex when we are mfg concurrent products. The pack out line in buffer prep is also stainless and is currently pitted due to the upstream solution. Replacement of the V1020 will replace the entire piping and media filter with the higher alloy metal.	Idea	Zaymar Sedra	John Urban	Mel Davis	Will Jimenez					2.3	3.0	13.5					$4,859k					$4,859k	$4,859k	#REF!				$3,800k	$100k			$3,900k
1	57		MO5		1198	G160	76643	Optimize Column Movement Device	Optimization of the Column Moving Device (RTO, CTT). Caustic Bath (RTO, CTT) and Frit Handling & Storage (CTT) were presented all together, however, IMPACT decided to approved only the CMD and asked for the other two items be submitted separately through the PPM process. The Business Driver could be RTO or QSP as is STARI project. It needs a SHA Checlist for each piece.	10/30/14 WBS received. 10/23/14 CA submitted. 9/23/14 Partially appr by IMPACT. Only the CMD.Name changed back to original. 9/11/14 Appr by jPMT. 9/4/14 Name changed according to Bahar input. 7/3/14 dded same budget as MO5. We need to confirm by Sep. 6/24/14 Sent email.	Global	RTO	SHE and K-Directives	Highly Capable Workforce		With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Execute	Melanie Yevilov	John Urban	Mel Davis	Bahar Dahi	$353k	$353k			Yes	2.4	1.3	18.6				$143k					$143k	$143k	#REF!	$126k	$143k					$270k
0	58					96022	WFI Pump Autostart	Put it on hold. Original Estimate $286k. Confirm acceptable risk? * We are doing this on HWFI 2 in DBx. Prove program on HWFI 2 and carry over to HWFI 3 / *AWFI and HWFI systems, including circulation pumps, do not restart automatically after power loss and recovery. WFI service cannot be disabled for more than 240 minutes. Automation request to include a download parameters from Delta V to pump VFDs, during plant re-start following power loss recovery. New cost includes commisioning/validation/CRB	11/03/14 Per Tim's email, this projects needs to be removed giving priority to P2 and WFI. 7/28/14 Changed PMO Lead 6/17/14 - It can't be done in 2014. Needs IT and Q resources	Global	RTO	Improvements and Efficiencies	TBD		The Oceanside facility needs a robust and efficient auto start procedure for the WFI pumps after a power outage. Power outages causes the WFI pumps to shut down and reboot. The current reset sequence is complicated and time consuming and can take approximately 15 minutes per loop. This project makes significant contribution towards plant reliability and supply to patients.	Hold	Deidre Dunham	CRB	TBD	Tim Lai					N/A	0.6	1.2	4.3	0.31					$k	#REF!
0	59					96040	GWR 1080/1090	Below the line. Budget Cap $170k Exp $10k 2015. SS has been submitted. Need NPV. Process Improvement, Material Loss, compliance	12/18/14 Changed to on Hold. 11/11/14 Project reviewed. Linda to submit RR and signed SS by Nov 19. 8/27/14 Changed to Budgeted. 6/30/14 Added budget. Confirmed with Scott it will be executed in 2015. 6/11/14 Changed to Hold - JN. To make room for Agitator Seal Flush. Changed to QSP	Global	QSP	Improvements and Efficiencies	Agile		This continuous improvement project for media prep tanks V1080/V1090 will provide an accurate method to measure tank level. Guided wave radar transmitters will ensure solution preparations are prepared to target specification while utilizing industry/company best practices to minimize operational risk. Currently, not having a reliable and accurate method for measuring tank level increases the risk of producing material outside of acceptable limits with low detectability (potential compliance risk).	Hold	Zaymar Sedra	CRB Partial	TBD	Linda Hope					No	1.3	1.3	10.1					$k	#REF!
1	60		MO5	FAE	484		96069	Warehouse Crown Forklift Asset Replacement	Asset Replacement	12/07/15 On Hold until 2017 per Rich Dimler. 7/07/15 CA put on hold. 6/03/15 CA issued. 11/05/14 Put on hold for 2015. 10/30/14 CA on hold. 8/2/14 Infom to IMAPCT. 8/21/14 Inform to jPMT. Budget has been adjusted. 7/3/14 Added budget according to Liza's pull in list	Global	QSP	Life Cycle Mgmt	Fit for Purpose		The lift is needed to assist in the transport of materials within the warehouse for storage or placement. The fit is used to alleviate a person from lifting heavy items that may cause severe injury. Doing nothing it will not ensure safe operations within the warehouse. Part of the 2013 Asset Life Cycle Management Report.	Hold	Zaymar Sedra	Tucker Creighton	Alister Hufton	Richard Dimler					No	N/A	N/A	N/A					$144k					$144k	$144k	#REF!			$144k					$144k
0	61					96105	TMAC Tenderizer	SHE- Project identified during SBP Review.	4/15/16 Project on Hold pending Rituxan being added to the production plan.	Individual	QSP	Stay in Business	Highly Capable Workforce			Hold	Melanie Yevilov	Marcus Espinoza	Mel Davis	Pierre Luong					0.02					$k	#REF!
0	62					96109	Sci&Eng Lab Equipment for NPI and Launch Capability	Technology - Project identified during SBP Review.	10/08/15 PMT Endorsed.	Individual	QSP	Tech Transfers	Launch and Commercial Excellence			Canceled	Jim Neeleman	Greg Crecely	Alister Hufton	Fikret Kulenovic					$k	#REF!
1	63		MO5				96112	Maintenance Ops Shop Buildout	2016 Cap $1M, 2017 Cap. $2M FOS -Project identified during SBP Review.	6/14/16 Deferred to 2019 per Hayden. Deferred to 2017. On Hold.	Individual	QSP	Improvements and Efficiencies	Fit for Purpose	A1 Automation Improvement		Budgeted	Zaymar Sedra	TBD	TBD	Hayden Knox					0.33				$500k	$2,500k				$3,000k	$3,000k	#REF!					$500k	$2,500k		$3,000k
1	64		MO5				96113	Bulk Product Storage -20/-40	Technology - Project identified during SBP Review.		Individual	QSP	Improvements and Efficiencies	Launch Facility			Placeholder	Deidre Dunham	TBD	TBD	TBD					$10,000k	$10,000k	$20,000k	$20,000k	#REF!					$10,000k		$10,000k
0	65					96114	QC Testing Equipment for Launch Capability and Storage Requirements	Quality - Project identified during SBP Review.		Individual	QSP	Tech Transfers	Launch and Commercial Excellence			Canceled	Jim Neeleman	TBD	TBD	TBD					$k	#REF!
1	66		MO5				96116	PCS Process Support Equipment Integration			Individual	QSP	Improvements and Efficiencies	TBD	A1 Automation Improvement		Idea	Deidre Dunham	TBD	Alister Hufton	Sarah Maruccia					25.97					$1,500k	$1,500k			$3,000k	$3,000k	#REF!				$1,500k	$1,500k			$3,000k
	67				1586	G160	96117	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2019			Global	QSP	Life Cycle Mgmt	Reliable			Idea	Deidre Dunham	TBD	TBD	Myles Sumlin					N/A	N/A	N/A					$440k	$440k	$880k	$880k	#REF!					$440k		$440k
	68					96124	Perjeta Tech Transfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Jim Neeleman	N/A	TBD	Semsi Ensari					60.0					$8,941k	$78,779k	$1,431k	$369k	$369k	$89,890k	$89,890k	#REF!			$8,941k	$78,779k	$1,431k	$369k	$79k	$89,600k
	69					96125	Flu A TechTransfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Deidre Dunham	N/A	TBD	Semsi Ensari					$8,941k	$31,170k	$31,170k	$71,280k	$71,280k	#REF!					$8,941k	$31,170k	$1,431k	$41,542k
	70					96126	Flu B Tech Transfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Deidre Dunham	N/A	TBD	Semsi Ensari					0.10					$8,941k	$8,941k	$17,881k	$17,881k	#REF!					$8,941k	$28,753k	$37,694k
	71					G160	74546	Mezzanine Safety Shower/Eye Wash Station Install		5/26/16 cash flow updated from PMT presentation. 5/10/16 project moved above the line per IMPACT discussion. 07/01/2015 SS submitted.	Individual	RTO	SHE and K-Directives	Highly Capable Workforce		Cal/OSHA requires that Safety Showers / Eye Wash stations be within 55' or 10 secs. Currently Manufacturing is using a Manual Liuid Add Process which presents a risk hazardous materials coming into contact with employees.	IMPACT Appr	Melanie Yevilov	TBD	Mel Davis	Marcus Espinoza					0.5	2.5	2.9				$100k	$786k					$886k	$886k	#REF!		$450k	$436k					$886k
	72				583		96133	QC Rapid Scan RDI System	2016 $210,000	07/01/2015 SS submitted.	Global	QSP	New Technologies	Launch and Commercial Excellence		Install and qualify Rapid Scan RDI System for GMP use in QC Lab. This is a global effort to harmonize Rapid Bioburden equipment to test pre filtration media that can measure and detect small measures of bioburden.	Hold	Jim Neeleman	TBD	TBD	Siu Fai Tsang					2.3	2.2	15.3					$210k					$210k	$210k	#REF!			$210k					$210k
	#REF!				583		96135	QC Spectrophotometers	2016 $327,522	6/2/16 Canceled. Project duplicated. See 64925 07/01/2015 SS submitted.	Global	QSP	Improvements and Efficiencies	Highly Capable Workforce		Install and qualify spectrophometers for GMP use in QC Lab to maintain and fast pace on testing for potency assay and reduce risk of job injuries for repetitive motion.	Canceled	Melanie Yevilov	TBD	TBD	Siu Fai Tsang					1.8	1.0	14.4				FALSE	FALSE	FALSE	FALSE	FALSE	FALSE		$k	#REF!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!
	#REF!					96136	V-3007 Replacement	4/19/16 SPPM to assess business case prior to T3 updates. 10/05/15 Project being evaluated to dfetermine if it can be done before S/D.	07/01/2015 SS submitted.	Global	QSP	Life Cycle Mgmt	Fit for Purpose		TMAC vessel has been determined to have corrosion and needs to be replaced. Upsizing the pumps and piping for offloading is required to shorten the TMAC waste transfer period. This project is needed to maintain out TMAC system in a reliable and efficient operational state. TMAC vessel is needed for Rituxan. P2 tie-in associated with this vessel.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Pierre Luong					N/A	N/A	N/A					$120k	$120k				$240k	$240k	#REF!			$120k	$120k				$240k
	#REF!					96137	Security Systems Upgrade	5/12/16 Name changed from Security Cameras Improvement on Parking Lot, per JA. 2016 Cap $200k	6/23/16 Endorsed by PMT. 5/10/16 project moved above the line per IMPACT discussion. 4/14/16 Project cashflow updated according to latest estimates. 07/01/2015 SS submitted.	Global	QSP	SHE and K-Directives	Exceptional Culture		Current security cameras will be obstructed with the installation of the new solar power panels and awnings, raising potential safety and security issues. Security cameras will be installed and tied in to the existing units in order to allow monitoring of the site more effectively.	JPMT Appr	Deidre Dunham	TBD	Mel Davis	Juan Aragonez					0.9	1.6	6.7				$175k					$175k	$175k	#REF!		$200k					$200k
	#REF!					96139	Trash Bin Storm Water Mitigation	12/10 renamed Trash bins storm water remediation. / Study done in 2015 $100k funded by SHE. This is required to meet compliance due to changes introduced by the solar project. This will be all capital and will be about 4-500K. I don't have a scope sheet yet, but this definitely needs to get done next year due to a compliance issue with the City	03/17/16 Project moved above the line per AW. 7/16/2015 SS sumitted.	Global	RTO	SHE and K-Directives	Exceptional Culture		Regional Water Board and City of OCN regulation states the need for an approved SWMP. Genentech OCN does not have a documented plan in place. This project will Identify plan requirements. Subsequent activity to include detailed design and construction to implement site changes.Regulatory requirement.	FXNL LT Appr	Deidre Dunham	TBD	Mel Davis	Gary Merrill					1.2	1.0	9.6					$200k					$200k	$200k	#REF!			$200k					$200k
	#REF!					96143	Paperless Metone	$250k	07/01/2015 SS submitted.	Global	CTT	Improvements and Efficiencies	ACCR		Improvements on data management and storage of Metone. Current system is unreliable and inefficient. Paperless system will upload results into LIMS and eliminate transcription error, use of paper and improve data storage.	Hold	Scott Fields	TBD	TBD	Rick Learn					$k
	#REF!					Y160	65066	Appleton Tank Mover		5/10/16 project moved above the line per IMPACT discussion. 11/12/15 Deferred until 2017. 11/02/15 Canceled as it is not needed for Actemra campaings. 10/15/10 CA Routing.	Global	QSP	SHE and K-Directives	Highly Capable Workforce		Significant risk is involved on moving heavy tanks manually.These movers will mitigate risk of injuries and allow more efficient evolution of moving freeze thaw tanks.	Hold	Melanie Yevilov	Marcus Espinoza	Mel Davis	Marcus Espinoza					1.1	0.5	8.9				$73k					$73k	$73k			$73k					$73k
	#REF!					Y160	65021	Hazardous Material Response Cart		02/22/16 Project moved above the line.	Global	RTO	SHE and K-Directives	Highly Capable Workforce		Site has committed to Performance Based Standards with the Fire Department and could be cited for non-compliance or failure to enforce stardards. Clean harbors is in need of a dedicated Hazardous Materials Response Cart to due the increased hours of emergency spill responjse.	Execute	Melanie Yevilov	Marcus Espinoza	Mel Davis	Gary Merrill					0.5	0.4	3.9				$19k					$19k	$19k			$18k					$18k
	#REF!					Y160	64992	QC Osmometer Asset Replacement			Global	RTO	Stay in Business	Reliable		This project is to replace two osmometers for QC in preparation of method transfer and testing for the new product coming into Oceanside manufacturing facility.The model installed in the lab has failed. Service was called and supplier (Advanced Instrument) has informed the model in the lab is obsoleted and beyond service.	Execute	Jim Neeleman	TBD	TBD	Siu Fai Tsang					N/A	N/A	N/A					$k
	#REF!					Y160	64994	Helium Sniffer Replacement			Global	QSP	Stay in Business	Reliable		Helium sniffers are needed to ensure vessel integrity. Currently, there is one functional unit on loan from the vendor. Having two additional units will allow performance of helium testing quickly and provide a back up in case of failure.	Execute	Jim Neeleman	TBD	TBD	Chris LeTourneau					$k
	#REF!					96159	OCC Network Remediation			Global	TBD	Improvements and Efficiencies	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	Kelly Calderwell					2.9	1.0	22.8				$150k					$150k	$150k			$150k					$150k
	#REF!					96163	MFG Depth Filter Housing			Global	TBD	Stay in Business	Reliability and Value			Idea	Zaymar Sedra	TBD	TBD	Ed Montoya / Clarence Flowers					$400k					$400k	$400k				$400k					$400k
	#REF!					96164	Hazardous Materials Containers Washing Station		4/18/16 Project on Hold. Determined that the contractors who perform the cleaning would be using a current wash roomt o perform this work and that project was not moved above the line, per Marc Espinoza.	Global	TBD	SHE and K-Directives	Highly Capable Workforce			Hold	Melanie Yevilov	TBD	Marcus Espinoza	Gary Merrill					$30k					$30k	$30k				$30k					$30k
	#REF!					96165	WAN Link Redundancy	Original estimate $2M.	6/27/16 Put on Hold due to lack of response from team and no SS.	Individual	TBD	Improvements and Efficiencies	Reliability and Value			Hold	Scott Fields	TBD	TBD	Kelly Calderwell					2.1	2.3	14.1					$2,000k					$2,000k	$2,000k
	#REF!					96167	Emergency Generator High Level Alarm			Global	TBD	SHE and K-Directives	Reliability and Value			Idea	Melanie Yevilov	TBD	TBD	TBD					$25k					$25k	$25k			$25k					$25k
1	#REF!					96168	Replace Warehouse #321 Sprinkler Heads			Global	TBD	SHE and K-Directives	Highly Capable Workforce			Idea	Melanie Yevilov	TBD	TBD	TBD					$20k					$20k	$20k			$20k					$20k
	#REF!					Y160	65005	Analytical Scale	1/20/16 This project is asset replacement per ZS.	03/17/16 Funded by Material Ops AR bucket, as per AW. 01/12/16 Project moved above the line per IMPACT discussion.	Global	QSP	New Technologies	Reliability and Value		Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	Execute	Scott Fields	TBD	TBD	Tyrone White					$24k					$24k	$24k			$24k					$24k
	#REF!					Y160	65009	Drum Mover/Raw Material Tenderizer		01/12/16 Project moved above the line per IMPACT discussion.	Global	CTT	SHE and K-Directives	Highly Capable Workforce		This project will eliminate the unsafe work environment for employees because they will no longer need to lift drums or use the current raw material tenderizer which has been deemed unsafe. This machine can also be a solution for other sites across the network who are looking for the same solution.	Execute	Jim Neeleman	TBD	TBD	Tyrone White					$34k					$34k	$34k			$34k					$34k
	#REF!					Y160	65020	QC Auto-Pipettor for Potency Assay		03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio. Funded by QC AR Bucket.	Global	CTT	SHE and K-Directives	Reliability and Value		The auto-pipettor will be used for sample dilution in the new BaF cell line to replace manual pipetting to avoid any repetitive injury from manual pipetting.	Execute	Melanie Yevilov	TBD	TBD	Siu Fai Tsang					$28k					$28k	$28k			$28k					$28k
	#REF!					Y160	65023	QC Plate Washer for Potency Assay		03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio. Funded by QC AR Bucket.	Global	CTT	New Technologies	Launch and Commercial Excellence		Etrolizumab will be starting the method transfer to Oceanside by SSF in Q1, 2016. This type of plate washer is unique for this assay with a 7 degree angle head to wash off cell during potency assay.	Execute	Jim Neeleman	TBD	TBD	Siu Fai Tsang					$57k					$57k	$57k			$57k					$57k
	#REF!					Y160	65018	Spare Bowl for Hermetic Centrifuge		02/12/16 Project added and moved above the line per IMPACT discussion.	Global	TBD	Improvements and Efficiencies	Fit for Purpose			Execute	Zaymar Sedra	TBD	TBD	TBD					$320k					$320k				$320k					$320k
	#REF!					Y160	65015	Lower Solid Collector for Centrifuge		02/11/16 Project added and moved above the line.	Global	TBD	Improvements and Efficiencies	Reliability and Value			Execute	Scott Fields	TBD	TBD	TBD					$245k					$245k				$142k					$142k
	#REF!					Y160	65024	Sci&Eng Lab Incubator and Freezer Asset Replacement		03/17/16 Funded by Engineering AR bucket, as per AW. 03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio.	Global	TBD	Stay in Business	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD					$140k	$489k					$629k				$129k					$129k
	#REF!					96169	Level Indicator Transmitters		03/10/16 Project added to portfolio.	Global	TBD	New Technologies	Fit for Purpose		Need to replace the level indicator transmitters (LIT-004) on the following CIP systems, as the existing level indicators are obsolete and one is malfunctioning: 7110, 7210, 7150, 7160, and 7170. These systems impact multiple other systems, so it would be ideal to complete the replacement during shutdown. Replacing 7170 while up and running would be particularly difficult, if not impossible.	Idea	Zaymar Sedra	TBD	TBD	John White					$70k					$70k				$70k					$70k
	#REF!					G160	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)		3/16/17 Project amount changed from $842,280 to $1M, as per AW.	Individual	RTO	Stay in Business	Reliability and Value		To align with network commitment per the Multi-Site Assessment #1105078.	Execute	Jim Neeleman	TBD	John Urban	Juan Pacio					$306k	$654k					$960k				$306k	$654k					$960k
	#REF!					Y160	65044	Additional MCS Backup Storage		04/05/16 15K moved from Capital to Expense. 03/17/16 Funded by Engineering AR bucket, per AW. 03/15/16 Project added to portfolio and moved above the line.	Global	RTO	Improvements and Efficiencies	Reliability and Value		Currently, there is not enough backup capacity to perform system backup for MES at Oceanside. Data and system backup is a requirement as part of regulatory compliance.	Execute	Scott Fields	TBD	TBD	Michael Loh					$62k					$62k				$62k					$62k
	#REF!					Y160	65037	Analytical Scales (CAPA 1150248)		03/22/16 Project moved above Execution line. 03/16/16 Project added to portfolio and above the line.	Global	QSP	New Technologies	Reliability and Value		Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	Execute	Scott Fields	TBD	TBD	Tyrone White					$24k					$24k				$24k					$24k
	#REF!					96174	Fall Protection Phase II		03/17/16 Project added to portfolio and moved above the line.	Global	TBD	SHE and K-Directives	TBD			CA Routing	TBD	Marcus Espinoza	TBD	Marcus Espinoza					0.5	1.0	3.6				$135k					$135k				$130k	$5k					$135k
	#REF!					Y160	65040	Sci&Eng Cryofreezer		03/17/16 Project added to portfolio and above the line. Funded by Engineering AR Bucket per AW.	Global	TBD	Stay in Business	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD					$20k					$20k				$20k					$20k
	#REF!					65048	Process Maintenance Boroscope		03/31/16 Project moved above the line. 03/28/16 Project funded by Engineering AR bucket, per AW. 03/25/16 Project added to portfolio.	Global	TBD	Stay in Business	Reliability and Value			Execute	Jim Neeleman	TBD	TBD	Dennis Chavez					$37k					$37k				$35k					$35k
	#REF!					96177	Efficiency Projects			Global	TBD	Improvements and Efficiencies	Reliability and Value			Placeholder	Scott Fields	TBD	TBD	TBD					60.0					$3,000k	$3,000k	$3,000k	$3,000k	$3,000k	$15,000k					$3,000k	$3,000k	$3,000k	$3,000k	$3,000k	$15,000k
	#REF!					TBD	PAIR			Individual	TBD	Stay in Business	Reliability and Value			Execute	Scott Fields	TBD	TBD	Samuel Calhoun					$3,102k	$4,788k					$7,891k
1	#REF!		MO5				96178	Process VSD and SOV Replacement - Phase 2	Asset Replacement - CRB heavely driven	10/26/15 Project rolled-over to 74487.	Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Idea	Deidre Dunham	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A	0.09					$2,500k	$3,000k			$5,500k	$5,500k	#REF!				$2,500k	$3,000k			$5,500k
1	#REF!		MO5				96179	Process VSD and SOV Replacement - Phase 3	Asset Replacement - CRB heavely driven		Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Idea	Deidre Dunham	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A	0.05					$458k	$5,000k	$5,000k	$10,458k	$10,458k	#REF!					$458k	$5,000k		$5,458k
	#REF!					96180	TMAC Waste System Improvements	SHE Identified Project on 5/9/16 - Dig up truck path to extend secondary containment to save offload time; Pierre recommends cancel due to ROI.		Individual	CTT	Stay in Business	TBD			Hold	TBD	TBD	TBD	Pierre Luong					0.75				$1,500k					$1,500k					$1,500k					$1,500k
	#REF!					96181	Fall Protection Phase III	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	Highly Capable Workforce		OSHA standard 1900.66 App C states, "Horizontal lifelines may, depending on their geometry and angle of sag, be subjected to greater loads than the impact load imposed by an attached component." In order to meet the intent of the OSHA guidelines, the site needs to reduce the angle of horizontal lifelines as much as possible.	FXNL LT Appr	Melanie Yevilov	TBD	Marcus Espinoza	Marcus Espinoza					1.8	0.6	15.1					$100k					$100k					$150k					$150k
	#REF!					96183	Site Signage Upgrade	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD					1.8	1.4	13.7					$200k					$200k					$200k					$200k
	#REF!					96191	Utility and Process Safety System Phase 2	SHE Identified Project on 5/9/16 - Can't scope until Phase 1 is designed.		Individual	RTO	Stay in Business	TBD			Idea	TBD	TBD	Mel Davis	Charles Fuller / Scott Breier					2.6	3.8	13.3					$2,000k					$2,000k					$2,000k					$2,000k
	#REF!					96193	Column Packing Fall Hazard	SHE Identified Project on 5/9/16	6/28/16 Canceled. Project duplicated. See Column Maintenance Platform Installation	Global	RTO	SHE and K-Directives	TBD			Canceled	TBD	TBD	TBD	TBD					$300k					$300k
	#REF!					96201	Storm Water BMP for Upper Lot	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD					$200k					$200k					$200k					$200k
	#REF!					96204	322 MRO Racks	SHE Identified Project on 5/9/16 - Not enough room to house spare parts if we reduce current racks to be 5ft or below; Pierre suggests vendor assessment of sprinkler system in MRO.		Individual	RTO	SHE and K-Directives	TBD			Hold	TBD	TBD	TBD	Pierre Luong					$500k					$500k					$500k					$500k
	#REF!					96207	Weigh and Dispense Sink (CAPA1123109)	Submitted after MO5 on 5/9/16.	5/10/16 project moved above the line per IMPACT discussion and funded by Engineering AR bucket. 5/9/16 Project added to portfolio. 4/19/16 Submitted but not signed.	Global	RTO	Stay in Business	Reliability and Value		To maintain our right to operate and supply to patients the facility must be operated per cGMP's and respond to regulatory agency findings. The EMA observation at SSF for hand washing was reviewed by Oceanside SME's and it was determined that Oceanside needed to make changse to avoid similar observation.	FXNL LT Appr	Scott Fields	TBD	Mel Davis	Joseph Semiklose					$30k					$30k				$165k					$165k
	#REF!					65082	RF Sealer Generator	Submitted after MO5 on 5/11/16.	06/17/16 Project moved above the line. 05/11/16 Project added to portfolio.	Global	QSP	TBD	Reliability and Value		MFG currently has one RF sealing generator that is shared by Media Prep and Buffer Prep. Sharing of this unit reduces efficiency and the additional transportation and handling of this unit increases risk of malfuntion. We currently don't have a backup unit in the case of malfunction. This project is needed to provide adequate dedicated resources to the areas.	Execute	Scott Fields	TBD	TBD	Mark Maruccia					$17k					$17k				$22k					$22k
	#REF!					96208	Work Space Project	Identified by Kara Swedberg on 5/13/16.		TBD	TBD	TBD	TBD			Idea	TBD	TBD	TBD	Kara Swedberg
	#REF!					96209	Harvest Depth Filter Installation Tool	SHE Identified Project on 6/20/16		Global	QSP	New Technologies	Highly Capable Workforce		SHE JSA assessments have found that Depth Filter Installation activities are an ergonomic risk. Empployees are at risk for slips, trips, falls, and over exertion performing filter installation operations.	FXNL LT Appr	Melanie Yevilov	Marcus Espinoza	TBD	Marcus Espinoza					1.8	0.6	15.1					$100k					$100k
	#REF!					96210	P2 User Furnished Equipment Procurement	Project Identified by Alister Hufton on 6/21/16.		Individual	CTT	TBD	TBD		This project directly impacts Oceanside's Contribution to Target for its ability to manufacture Etro.	FXNL LT Appr	TBD	TBD	Alister Hufton	Ben Chmielewski					1.4	2.3	9.0					$1,100k	$1,100k					$2,200k
	#REF!					96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting	Project Identified by Bahar Dahi on 6/22/16.		Individual	QSP	Improvements and Efficiencies	Reliability and Value		This fitting should have been installed from the beginning.	FXNL LT Appr	Scott Fields	TBD	TBD	Bahar Dahi					1.8	1.6	20.0					$1,000k					$1,000k
	#REF!					96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000	Project Identified by Bahar Dahi on 6/22/16.		Individual	QSP	Improvements and Efficiencies	Reliability and Value		The proper functionality of Back Pressure Control Valve is essential for the UF operation.	FXNL LT Appr	Scott Fields	TBD	TBD	Bahar Dahi					2.7	2.4	17.8					$550k					$550k
	#REF!					96213	Replacement of Obsolete Benchtop Horiba pH Meter	Project Identified by Bahar Dahi on 6/22/16.		Individual	QSP	Improvements and Efficiencies	Fit for Purpose		Actemra will be run at OCN through 2020.	FXNL LT Appr	Zaymar Sedra	TBD	TBD	Bahar Dahi					1.7	2.7	10.4					$1,200k					$1,200k
	#REF!					96215	20L Bioreactors and NovaFlex Analyzer			Global	QSP	Tech Transfers	Fit for Purpose		This equipment applied to OLP small scale and pilot scale studies will ensure successful current and future tech transfers with a potential of reducing large scale ER/QRs.	FXNL LT Appr	Zaymar Sedra	TBD	TBD	Fikret Kulenovic					2.7	1.6	20.0					$450k					$450k
	#REF!					96216	Frit Handling and Storage Phase 2		6/21/16 IMPACT approved second phase.	Global	QSP	Tech Transfers	Highly Capable Workforce	A2 Business Efficiency	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	FXNL LT Appr	TBD	TBD	TBD	TBD					2.4	0.6	20.2
	#REF!					96217	Pallet Wrapper			Global	QSP	Improvements and Efficiencies	Highly Capable Workforce		This project is necessary to enable efficient operation in the warehouse.	FXNL LT Appr	Melanie Yevilov	TBD	Marcus Espinoza	George Groza					1.4	0.4	11.6					$50k					$50k
	#REF!					96218	Column Maintenance Platform Installation			Global	RTO	Improvements and Efficiencies	Highly Capable Workforce		Based on JSA results, a high level of risk for slips, trips, and falls exists with this activity. Currently, the site is at risk for employee injury and an OHSA Recordable event.	FXNL LT Appr	Melanie Yevilov	TBD	Marcus Espinoza	Marcus Espinoza					1.8	1.6	13.3					$75k	$100k					$175k
	#REF!					96219	Harvest Filter Housing A Removal/Installation Improvements			Individual	QSP	Improvements and Efficiencies	Highly Capable Workforce		Based on JSA results, a high level of risk for injury is present. Should the employee lose contrl of the suspended load they could be severely injured. The result of an incident could result in an OSHA recordable incident and also impact production opereations.	FXNL LT Appr	Melanie Yevilov	TBD	Marcus Espinoza	Marcus Espinoza					1.8	0.6	15.1					$500k					$500k
	#REF!					96220	400L Mixing Vessel			Global	QSP	Improvements and Efficiencies	Launch and Commercial Excellence		Firstly, this project will avoid the need for disruptive at-scale mixing studies during the engineering runs. And, it is most important that the engineering runs have as few issues as possible so they can serve as a reliable prediction of performance of the qualification runs. This is very important: the Etrolizumab campaign is proposing to have 5 qualification runs - less than in the past product transfers to OCN. / Secondly, this tank will permit cleaning cycles to be tested during cleaning validation. And, such issues can contribute to the complexity of qualification runs. A thorough product license application has cleaning validation complete during the qualification runs. / It is anticipated the cost of the tank will enable saving in cleaning validation time & resource and will increase the effectiveness of the engineering runs. This almost certainly contributes to lowering the risk of requireing an additional qualification run.	FXNL LT Appr	Jim Neeleman	TBD	TBD	Ken Hamilton					2.4	1.8	17.3					$340k	$62k					$402k
	#REF!					96221	Corrosive Chemical Compliance - CUB and Warehouse			Individual	RTO	SHE and K-Directives	Reliability and Value		To meet control and monitoring requirements as requested by the Oceanside Fire Department.	FXNL LT Appr	Scott Fields	TBD	Mel Davis	Susan Schmidt					6.6	3.9	34.0					$2,900k	$20k				$2,920k
	#REF!					96222	Pressure Safety Program - Mechanical			Individual	RTO	SHE and K-Directives	Highly Capable Workforce			FXNL LT Appr	Melanie Yevilov	Marcus Espinoza	Mel Davis	Nick Loebs					3.8	4.0	18.8					$2,000k					$2,000k
	#REF!					96223	Pressure Safety Program - Automation			Individual	RTO	SHE and K-Directives	Highly Capable Workforce			FXNL LT Appr	Melanie Yevilov	Marcus Espinoza	Mel Davis	Nick Loebs					2.7	4.8	11.3					$2,500k				$2,500k
	#REF!					$k	#REF!
	#REF!
	#REF!
	#REF!
	#REF!
	#REF!
	#REF!					96991	Asset Replacement 2016 - Engineering (cc642)		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$1,007k					$1,007k	$1,007k			$1,007k	$505k					$1,512k
	#REF!					96992	Asset Replacement 2016 - Material Ops (cc484)		03/17/16 $4k moved to Material Ops AR Bucket above the line. 02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$126k					$126k	$126k			$126k	$1,178k					$1,304k
1	#REF!		MO5				96993	Asset Replacement 2016 - Manufacturing (cc1359)		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$50k					$50k	$50k	#REF!		$50k	$365k					$415k
1	#REF!		MO5				96994	Asset Replacement 2016 - Manufacturing		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$268k					$268k	$268k	#REF!		$268k	$158k					$426k
1	#REF!		MO5				96995	Asset Replacement 2016 - Quality	See breakdown on the Idea tab.	02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment - The total comes from ARR minus the $393k that were tried to pull-in in 2014 (Project P68) + the new assets that need to be repalced for $396k + 45% escalation	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$408k					$408k	$408k	#REF!		$408k	$723k					$1,131k	#REF!
0	#REF!					96996	Asset Replacement 2016 - Technology			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A					$k	#REF!					#REF!
1	#REF!		MO5				96997	Asset Replacement 2016 - Facilities Ops		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.	Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A				$31k					$31k	$31k	#REF!		$31k	$56k					$87k	#REF!
0	#REF!					96998	Asset Replacement 2016 - BMSO		BMSO has only one AR on the report- Warehouse Forklift. This is not reflected on this line as it has been identified and it is disclose as a single line P69	Global	QSP	Stay in Business	Reliable		Asset Replacment - The only replacement under this department for 2015 is the Warehouse Forklift which is project P69	FXNL LT Appr	Jim Neeleman	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A					$k	#REF!			$202k					$202k	#REF!
1	#REF!		MO5				96999	Site Management Adjustments (if any)			Individual					TBD					-$1,685k					-$1,685k	-$1,685k	#REF!	-$10,662k					-$14,509k	#REF!
1	#REF!		MO5				T					$291,952k	$267,348k	$24,604k					$18,008k		$161,099k	$151,782k	$122,366k	$32,466k	$69,471k		$537,184k	$485,721k	#REF!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#REF!

	140		Expense				97042	CRB Project Budget Estimating		4/15/15 Estimate for 2015 was adjusted to $360k. $90k billed in Q1, and we assumed that same expedinture for Q2,Q3 & Q4. 6/17/14 - Added budget $178k for the five year outlook per Dave's email. DS	Expense	QSP	Improvements and Efficiencies	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A			N/A	N/A	N/A					$k	#REF!		$250k	$250k					$501k
	141		Expense				97043	Travel Expenses	It is expense. Placeholder for 4368		Expense	QSP	Stay in Business	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A					$k	#REF!		$10k	$10k					$20k
	142		Expense				97001	Lunches			Expense	QSP	Stay in Business	Reliability and Value	A6 Quality of work/life improvements		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A					$k	#REF!		$4k	$4k					$8k
	143		Expense				97002	Office Supplies inc. Laptops			Expense	QSP	Stay in Business	Reliability and Value	A6 Quality of work/life improvements		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A					$k	#REF!		$45k	$45k					$90k
	144		Expense				97044	IMPACT Support		6/17/14 - Added budget for the five year outlook. MD	Expense	QSP	Stay in Business	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A					$k	#REF!		$8k	$8k					$16k
	145		Expense		1586	S160	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		7/15/15 CA Appr. 7/10/15 Changed to CA Submitted. 6/10/15 CA issued.	Expense	CTT	Stay in Business	Reliability and Value	A1 Automation Improvement	With parallel project execution a browser I&C database allows concurrent queries and updates to be made. If nothing is done there is added overhead to maintain and outdated system.	Execute 1	Deidre Dunham	John Urban	Alister Hufton	Jonathan Clark					0.6	3.4	3.4					$k	#REF!	$70k	$866k	$575k					$1,511k
	146		Expense				97003	MFG Systems Integration Improvement Phase 1 - 2015	This project is an consolidation of MES related projects icl. 74413 that was originally a Capex project.	11/02/15 CA was put on hold, still trying to bring this project to execution. 6/01/15 CA issued. 04/23/15 PMT Appr. 03/05/15 Project name changed from MES Enhancement Project - 2015 to current.	Expense	CTT	Improvements and Efficiencies	Reliability and Value	A1 Automation Improvement	Process Waste: Currently no ability to waste process materials that don’t exist in Syncade. When material cannot be wasted, it must be scrapped which requires justification and labor intensive forms.QC Sample Plan:Sample Plans have no user-viewable format specific to material and type that can be stored and managed in the DCA. Precludes that ability to use the DCA workflow for document approval. Order Locator: Inability to filter EBR review based on batch information creates inefficient process. The system is flooded with batch reports each day which makes targeting reports ready for review extremely difficult.	Execute 1	Deidre Dunham	N/A	N/A	Eric Davis					2.3	2.2	15.3	1.17					$k	#REF!		$292k	$135k					$427k
	147		Expense				97005	MCS Peripheral Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!				$312k				$312k
	148		Expense				97006	MCS Peripheral Asset Replacement - 2019			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					$k	#REF!					$332k		$332k
	149		Expense				97063	MCS Peripheral Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					$k	#REF!					$351k
	150		Expense				97007	Automation System Lifecycle MCS Upgrade	9/02/15 Renamed Automation System Lifecycle MCS Upgrade. 6/15/15 Originally called PCS Upgrade - 2015. Changed name and consolidated with MES Upgrade 2015. It was decided all three will be governed by P2 and paid by the site. Which is further reason to combine them into one project. 74427. /01/15 Per Steven, only PI/CD Phase will be done in 2015. The project will proceed with the PI Phase for a feed study. Since the requested amount is expense and less than $500k, a CA is not required. A PO will be requested for $300k. Eric Fallon will be added to the approval chain to endorse the project as the functional leader before the authorized approvers review the shopping cart. / When the project returns for the next phase of funding, it should be split into two projects. The MES and PCS activities will become one project while the infrastructure activities will be the other.	11/30/15 Changed to Execution as the shopping cart was approved by AW for the PI phase for PCS Asset Replacement and the MCS Network Infrastructure. 9/02/15 Classified as Capex per Steven and changed name to PCS Asset Replacement 2016. 7/2/15 PMT Appr only feed study. 6/15/15 Name changed and consolidated.	Expense	QSP	Improvements and Efficiencies	Reliability and Value			Execute	Deidre Dunham	TBD	TBD	Myles Sumlin					4.6	3.0	27.6	2.14					$k	#REF!		$296k					$296k
	151		Expense				97008	PCS Asset Replacement - 2019			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!				$488k	$488k			$975k
	152		Expense				97064	PCS Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!					$463k	$463k
	153		Expense				97009	MES Asset Replacement - 2017		9/02/15 This project comes back as a single and deferred to 2017. Roughly originally estimated for $1.1M 6/15/15 Rolled over to Automation System Lifecycle MCS Upgrade - E07.	Expense	QSP	Stay in Business	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!			$400k	$575k				$975k
	154		Expense				97010	MES Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!					$500k	$525k	$1,025k
	155		Expense				97012	Site Data Historian Asset Replacement - 2017	8/7/15 Per Myles' email this project has been deferred to 2017.		Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Myles Sumlin					N/A					$k	#REF!			$366k					$366k
	156		Expense				97013	Site Data Historian Asset Replacement - 2019	9/02/15 Per Steven this projects has been deferred to 2019.		Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin					N/A					$k	#REF!					$488k			$488k
	157		Expense				97065	Site Data Historian Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin					N/A					$k	#REF!					$488k	$488k
	158		Expense				97015	MCS Backup System Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Myles Sumlin					N/A					$k	#REF!			$390k					$390k
	159		Expense				97016	MCS Backup System Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin					N/A					$k	#REF!					$439k		$439k
	160		Expense				97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!				$488k				$488k
	161		Expense				97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu					N/A					$k	#REF!					$488k		$488k
	#REF!		Expense				97030	MFG Systems Integration Improvement Phase 3 - 2017	Including MES/SAP System Integration - Real time Manufacturing Scheduling in SAP	05/31/16 Per RM, "The following project is no longer needed since this project is split into other projects which is already in the list."	Expense	QSP	Improvements and Efficiencies	Fit for Purpose	A1 Automation Improvement		Canceled	Zaymar Sedra	TBD	TBD	TBD					$k	#REF!
	#REF!		Expense				97031	MCS Data Analytics Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	TBD					N/A					$k	#REF!			$325k					$325k
	#REF!		Expense				97032	MCS Data Analytics Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD					N/A					$k	#REF!					$360k		$360k
	#REF!		Expense				97033	PCS Automated Documentation Upgrade			Expense	QSP	New Technologies	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD					$k	#REF!				$325k				$325k
	#REF!		Expense				97066	PCS Automated Documentation Asset Replacement - 2021			Expense	QSP	New Technologies	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD					$k	#REF!					$360k	$360k
	#REF!		Expense				97037	Recipe Reconfiguration Alignment for Operating Systems			Expense	QSP	Improvements and Efficiencies	Launch and Commercial Excellence		Current automation recipe design is not aligned to Network SAP Planning & Scheduling platform. The misalignment results in delayed material consumptions, elevated raw material inventory, inadequate detailed production schedules, multiple manual alternate mechanisms and increased risk to production. Accelerated production run rates and product launch add a new level of complexity which demands appropriate alignment of operating systems to minimize risk exposure, ensure success and align with network supply chain processes.	FXNL LT Appr	Jim Neeleman	TBD	N/A	Marco Baca					2.7	4.2	13.0					$k	#REF!			$250k	$1,500k	$1,750k			$3,500k
	#REF!		Expense				97038	PCS Functional Specification Development Project (CAPA 960297)		6/26/15 Classified as Expense according to Automation Team. 4/13/15 SS Submitted. 3/19/15 SS in progress	Expense	RTO	Strategic	Reliability and Value		PCS Functional Specification do not exist for the majority of the existing process systems at OCN, incurring in human errors. Creating of FSs for all impact system will ensure robust documentation on the integration of equipment, utilities, manual procedures, instrumentation and process control logic at the site.	FXNL LT Appr	Deidre Dunham	TBD	Alister Hufton	Sarah Maruccia					2.3	3.0	13.5					$k	#REF!			$500k	$2,250k	$2,250k	$3,000k		$8,000k
	#REF!		Expense				97039	PCS Remediation for EBR Review by Exception - PI	Technology - Project identified during SBP Review.	4/15/16 Project start slides to 2017, to be confirmed with SH. 11/23/15 No approved SS. 6/26/15 Classified as Expense according to Automation Team.	Expense	QSP	Improvements and Efficiencies	Highly Capable Workforce	A1 Automation Improvement		Idea	Melanie Yevilov	John Urban	Alister Hufton	Malou Jacinto / Stephanie Huntress					2.7	4.2	13.0					$k	#REF!			$250k	$2,250k	$3,375k			$5,875k
	#REF!		Expense				97040	Tech Transfer: Master Data Management		4/12/16 Project will be funded by PTD, per MB. 12/15/15 Reduced 2016 amount by $306k and moved into 2017 per Dave Stewart. 11/23/15 Feed Study to be paid by cc 644 (Eric Fallon).	Expense	RTO	Tech Transfers	Launch and Commercial Excellence		Creates a single source of information that will standardized and streamline the business process of importing and exporting data. OCN will soon become a Launch Facility with the completion of P2 and having a validated system to manage the new/existing data is imperative to reduce errors and create user accountability.	FXNL LT Appr	Jim Neeleman	N/A	N/A	Marco Baca					4.1	3.0	24.3					$k	#REF!
	#REF!		Expense				97045	Site Exterior Lighting Upgrade - Title 24	4/15/16 Follow up with Charles Fuller for updated SS.	6/27/14 Per Maria's email, this project is expense. 6/26/14 Is it a EXPENSE or not? Each light will be under $5k. It is a replacement 6/25/14 CRB doing the estimate Mel working with Tucker/Mike for the SS. DS 6/17/14 - Need Scope Sheet. Jim will work with the SME	Expense	CTT	SHE and K-Directives	Reliability and Value		This is retrofitting the existing light mounts and poles with new LED fixtures. It is energy savings. Title 24 requires that once you change 10% of your exterior lighting, you need to do the remainder - about half of the lighting is being changed due to the solar project so this will change out the remainder.	FXNL LT Appr	Scott Fields	TBD	Mel Davis	Charles Fuller					0.3	1.0	2.4					$k	#REF!		$100k	$100k					$200k
	#REF!		Expense				97046	Hazardous Waste Storage Bunker	2015 Cap $40k; 2016 Cap $40k		Expense	QSP	SHE and K-Directives	Reliable			Execute	Jim Neeleman	Marcus Espinoza	Mel Davis	Marcus Espinoza					0.8	1.0	6.0					$k	#REF!
	#REF!		Expense				97047	Flammable Storage Cabinets Upgrade			Expense	RTO	SHE and K-Directives	Reliable		Replace current cabinet with one that complies with Fire Code. If nothing is done the cite remains at risk of citation which could result in fines.	Execute	Jim Neeleman	Marcus Espinoza	Mel Davis	Marcus Espinoza					0.5	0.4	3.9					$k	#REF!
	#REF!		Expense				97048	Arc Flash Prevention		11/23/15 Check with Marcus on monthly cash flow. 11/05/15 PMT Endorsed.	Expense	RTO	SHE and K-Directives	Highly Capable Workforce		Multiple device settings, ciurcuit breakers and cable feeds were identified as being undersized operating above 95% of their operating capacity rate.	Execute	Melanie Yevilov	John Urban	Mel Davis	Marcus Espinoza					0.9	2.5	5.9					$k	#REF!		$318k					$318k
	#REF!		Expense				97049	SIMCA Online - Downstream Application		10/30/15 IMPACT e-reviwed.	Expense	QSP	New Technologies	TBD			Execute	Jim Neeleman	N/A	N/A	Chris Johnson					$k	#REF!
	#REF!		Expense				97051	MFG Electronic Use Logs (Syncade)			Expense	RTO	Strategic	Launch and Commercial Excellence			Placeholder	Deidre Dunham	TBD	TBD	Ravi Medandravu					1.1	2.5	6.8					$k	#REF!
	#REF!		Expense				97052	MFG P1 Actemra Horiba Replacement			Expense	TBD	Stay in Business	TBD			Placeholder	TBD	TBD	TBD	TBD					N/A					$k	#REF!
	#REF!		Expense				97053	Pressure Safety Program - PI			Expense	RTO	SHE and K-Directives	Highly Capable Workforce			Execute	Melanie Yevilov	Marcus Espinoza	Mel Davis	Nick Loebs					3.8	4.0	18.8					$k	#REF!		$100k					$100k
0	#REF!		Expense				97054	HVAC Retro Commissioning	Below the line - Budget Cap $25k Exp $5k 2015.	10/1/15 Project renamed from Reduce Reheat Requirements. 12/18/14 Changed to On Hold. 11/10/14 Project reviewed.	Expense	CTT	Stay in Business	Reliability and Value		Project wll reduce energy consumption as a requirement of K-18. Projected annual savings of $220k in energy costs and reduced CO2 emissions of approx. 1210 metric tons.	FXNL LT Appr	Scott Fields	TBD	TBD	Geoff Wing / Scott Breier					No	2.0	1.0	15.6	2.28					$k	#REF!			$113k	$44k				$157k
	#REF!		Expense				97057	Conference Room 315 Expansion		5/10/16 project moved above the line per IMPACT discussion.	Expense	TBD	Improvements and Efficiencies	Exceptional Culture			Idea	Deidre Dunham	TBD	Alister Hufton	N/A					$k	#REF!		$150k					$150k
	#REF!		Expense				97058	Parking Pavement Repair			Expense	CTT	Stay in Business	Reliability and Value			Execute	Scott Fields	Blake Brown	Mel Davis	Sumner Tison					$k	#REF!		$245k					$245k
	#REF!		Expense				97059	B311 & B321 Gowning Room Modifications		3/17/16 Project amount changed from $75k to $131k. 01/13/16 Project added to portfolio. PO's approved by AW.	Expense	RTO	Stay in Business	Reliability and Value		Revised manufacturing gowning SOP becomes effective in February 2016, necessitating modifications to existing lockers and shoe storage to support this SOP.	Execute	Zaymar Sedra	TBD	Mel Davis	TBD					0.05					$k			$100k					$100k
	#REF!		Expense				97060	QC Gas Cabinet Removal			Expense	QSP	TBD	TBD		QC cold storage capacity demand increases each year. Therefore additional space is required for cold storage equipment.	FXNL LT Appr	TBD	TBD	Mel Davis	Joe Molon					$k	#REF!		$75k					$75k
	#REF!		Expense				97062	PI- Ammonia RMP Study	SHE Identified Project on 5/9/16		Expense	RTO	TBD	TBD			Idea	TBD	TBD	TBD	TBD					$k	#REF!
	#REF!		Expense				97067	OCN Lean Implementation			Expense	CTT	TBD	Highly Capable Workforce		Formal implementation of LEAN across business operations as well as manufacturing operations will engrain behaviors to identify and quantifiably eliminate wastes that can be translated to hard dollar savings while building on Class A foundation.	Idea	Melanie Yevilov	TBD	TBD	Jim Szepesy					$k	#REF!			$85k	$40k				$125k
	#REF!		Expense				97068	OCN Resource Planning and Management Tool			Expense	CTT	TBD	Highly Capable Workforce		Transparency and clarity on how the site’s workforce supports the business will lead to better prioritization, allocation of resources, and agility to adjust its workforce to support business demands. / Site projects drive accomplishment of site goals and addressing site priorities. Ensuring appropriate resources are allocated to project related work will help regulate volume of work and ensure priority projects are resourced to be successful.	Idea	Melanie Yevilov	TBD	TBD	Melanie Yevilov / Michael Herrler					$k	#REF!			$85k	$15k	$15k	$15k		$130k
	#REF!		Expense				97069	Manufacturing Bullpen			Expense	TBD	TBD	TBD			Idea	TBD	TBD	TBD	TBD					$k	#REF!		$150k					$150k
			Expense				97070	Pressure Safety Program Automation - PI			Expense	RTO	SHE and K-Directives	Highly Capable Workforce			FXNL LT Appr	Melanie Yevilov	Marcus Espinoza	Mel Davis	Nick Loebs					2.7	4.8	11.3
	#REF!		Expense				97071	Pipe Labelling Improvement	SHE Identified Project on 5/9/16		Expense	RTO	Stay in Business	Highly Capable Workforce			FXNL LT Appr	Melanie Yevilov	Marcus Espinoza	Mel Davis	Marcus Espinoza					1.8	1.6	13.3					$2,100k					$2,100k
	1					97072	Tangential Flow Filtration Cassettes Management		11/20/15 Automation does not have resources to support project until 2017. Priority projects will be to complete current CAPA and shutdown related projects for 2016.	Individual	RTO	Improvements and Efficiencies	Reliability and Value		An inspection could bring the problem to surface that not full genealogy is followed for the TFF cassettes which are product contacting. Human error in data input could impact ability to continue production under validated cassettes use.	FXNL LT Appr	Scott Fields	N/A	Juan Pacio	Stephanie Huntress					5.4	1.6	40.0					$k	#REF!			$1,030k					$1,030k
	2		Expense					$k	#REF!
1	3		MO5				E					$k		$6,135k	$16,905k	$10,420k	$4,683k	$1,787k	$2,187k	$39,929k	$39,929k	#REF!	$70k	$3,010k	$7,021k	$8,287k	$8,366k	$5,134k	$1,836k	#VALUE!	#REF!

	193		Initiative			PTD	98001	CMC Continuum	Some of the Tier 1 solutions (and resources) endorsed by PTLT will go into 2015. Deliver a clear, transparent, and streamlined CMC lifecycle management process from start of PhIII Development to end of Warranty Period in order to enhance our capabilities to commercialize new products. In combination with implementation, a realization plan will be developed including the needed shifts in behavior and mindset (WS1 Develop PTx Resource Activity Model to reflect baseline new product commercialization activities across PT, WS2 Create an effective and overlapping handover process from development to commercial for robust and HA acceptable processes, and WS3 Develop designated launch facility(ies) concept and plans)	We need info. Needs SME - MY. Potential fall out from P2.	N/A	QSP	Capacity	Launch Facility			Complete	Deidre Dunham	TBD	TBD	TBD					#REF!					#REF!
	194		Initiative				98005	Empower 3 Rollout	6/10/14 Sent email to SME. Waiting for feedback. Network that needs Capital - MY. OCN must purchase 5 HPLCs b/c Emplower 3 not compatible with our current HPLCs which also are approaching end of life.		N/A	TBD	New Technologies				Hold	TBD	Jessica Justice	TBD	Siu Fai Tsang					#REF!					#REF!
	195		Initiative				98006	GMP Document Lifecycle - 2014/2015	Create a unified definition / process / procedure to define the overall lifecycle of GMP records.	Network Project. Issues with Resource plan.	N/A	RTO	Improvements and Efficiencies	Reliable			Complete	TBD	Dona Bloch	TBD	Esther Pohlscheidt					#REF!					#REF!
	196		Initiative				98009	PTB-006 Material of Construction (MOC) Program (GSP100 Implementation)	Project Addresses New requirements and processes introduced by GSP100 / Objective: Fully implement and integrate the MOC Program / Proposed Solution (Deliverable): Develop a phased approach for implementation of GSP100		N/A	RTO	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	Carl Hixon					#REF!					#REF!
	197		Initiative				98010	PTB-011 Microbial Task Force (GSP085 Implementation) Project	Revision of Bioburden test methods to align with compendial requirements, including define sample test volumes. / Validation of bioburden method across all sites within scope		N/A	QSP	Stay in Business				Hold	TBD	TBD	TBD	TBD					1.07		#REF!					#REF!
	198		Initiative				98011	PTQ-xxx PQS: GSP085 - Microbiological Testing of Non-Sterile Material	MCTF will serve as a focused work team to implement GSP085, Microbiological Testing of Non-Sterile Materials.		N/A	RTO	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD					#REF!					#REF!
	199		Initiative				98013	PTB-002 Gentamicin Removal Strategy for Commercial Processes	"Commercial CHO processes utilizing gentamicin / -Outside of network: Activase (BIP), Xolair (Novartis, shared with VV starting in 4Q 2014) / -Within network: Avastin, Herceptin/Kadcyla, Perjeta, Pulmozyme, Rituxan, TNKase DS (SC/IV formulations and second brands) / Multi-product implementation strategy needs to be defined by end of 2013 and communicated to FDA in a Type C meeting in 1Q 2014 / ""Kadcyla - 2015 RSTO / Avastin - 2018 SSF / MabThera/Rituxan - 4Q2014 Samsung; 1-2Q2015 CCP2; 2019 CCP1 (possible that CCP1 might move up pending SC strategy) / Xolair - 4Q2016 CCP1 / Activase - 2016 BI / TNKase - 2016 SSF / Herceptin - IP Lonza (IV); 2015 RSTO (SC) / Pulmozyme - 2016 SSF / Perjeta - 2016 CCP1 / NOTE: All new TTs will be G-"""		N/A	QSP	Strategic	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD					#REF!					#REF!
	200		Initiative				98014	PTB-003 Analysis of Global Tank Management Process and System Improvements	To conduct an end to end analysis of the tank management processes and develop a strategy / roadmap of improvement activities that will result in a more predictable performance and higher degree of assurance that tanks will be in the right place at the right time and at the desired level of quality.	5/12/15 Changed to Canceled per Melanie's email.	N/A	QSP		Multi Product			Canceled	TBD	TBD	TBD	TBD					#REF!					#REF!
	201		Initiative				98015	PRC-xxx Visible Particle Method Standardization	All Biologics -- pilot Herceptin first		N/A	TBD	Improvements and Efficiencies				Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
	202		Initiative			PTQ	98017	PTQ-005 Coremap	Systematically control all records at Roche, regardless of media format, from initial creation to final disposition.		N/A	CTT	Improvements and Efficiencies	Multi Product			Execute	Melanie Yevilov	TBD	TBD	Donna Bloch					#REF!					#REF!
	203		Initiative				98018	PTQ-xxx PQS: GSP034 - Biologics Cleaning Initiative			N/A	QSP	Strategic	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD					#REF!					#REF!
	204		Initiative			PTQ	98019	PTQ-017 GMP Livelink to Condor	The project includes evaluating and adding new functionality to condor if needed by the business processes currently supported by DocLink and CEDM, migrating data (transactional, master and documents) from GMP LiveLink applications (DocLink, CEDM and BRES) to condor and other repositories, harmonization of document types/units, and decommissioning GMP Livelink when the data migrations are complete.		N/A	QSP	Improvements and Efficiencies	Multi Product			Hold	Melanie Yevilov	TBD	TBD	Donna Bloch					#REF!					#REF!
	205		Initiative			PTQ	98022	PTQ-002 ALEX LES (Lab Execution System) Project	Reduce current challenges around paper management and simplify analyst activities in Biologics and Small Molecules QC labs.		N/A	CTT	Improvements and Efficiencies	ACCR		Paperless lab system to increase iffeciency and ability to meet demand.	Execute	Scott Fields	TBD	TBD	TBD					#REF!					#REF!
	206		Initiative				98024	PTB-013 Resource Transparency Project	Data will be provided by Danielle Golay			TBD					Canceled	TBD	TBD	TBD	TBD					#REF!					#REF!
	207		Initiative				98026	Launch Capability Program (LCP)			N/A	QSP	Tech Transfers	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD					3.79		#REF!	$800k					#REF!					$800k
	208		Initiative				98027	PCR Based Adventitious Agents		Replace all cell-based and growth-based adventitious agents tests with PCR-based detection methods using the same “state-of the art”, fully automated Roche platform (MagNA Pure for nucleic acid purification and LightCycler 480 II for real-time target amplification and detection)					Canceled	TBD	TBD	TBD	TBD					#REF!					#REF!
	209		Initiative				98028	CalMan Replacement		The project will replace CalMan 4 with the current supportable Blue Mountain Regulatory Asset Manager (BMRAM) version R3 SR3. CalMan 4 is utilized by the Genentech regional sites (SSF, HTO, OCN, VAC, KDC), / & Roche Singapore Technical Operations (RSTO). Both solutions are owned by vendor Blue Mountain Quality / Resources.	N/A	QSP	New Technologies	Reliable		Calibration software replacement	Execute	TBD	TBD	TBD	Mark Martinez					#REF!					#REF!
	210		Initiative			PTA	98029	PTA-008 Business Continuity Management			N/A	QSP	Stay in Business	ACCR			Execute	Scott Fields	TBD	TBD	TBD					#REF!					#REF!
	211		Initiative				98031	PTB-016 PDM DS Phase II Project Resource Collection (TL)					Canceled	TBD	TBD	TBD	TBD					#REF!					#REF!
	212		Initiative				98032	PTQ-035: Automating Non-Routine Sample Management in LIMS			N/A		Improvements and Efficiencies				Hold	TBD	TBD	TBD	TBD					#REF!					#REF!
	213		Initiative				98034	PTS201416-Global Warehouse Capacity Management	Original name PTS201416-Global Logistic Transparency and Capacity		N/A	QSP	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD					#REF!					#REF!
	214		Initiative			PTB	98035	Biologics Commercial DS Investigation Reduction Project	03/10/15 Original name PTB-009 Investigation Free Lots. Changed to current per Melanie's email.		N/A	QSP	Strategic	Reliable		Improvement, root-cause analysis to reduce volume of products held up for investigation.	Idea	Jim Neeleman	TBD	TBD	TBD					#REF!					#REF!
	215		Initiative				98036	REMIS Pilot		6/25/2015 SS submitted.	N/A	RTO	New Technologies	Launch Facility		Support the global initiative, lead the network for data management inovation and effeciency. Data aggregation and analysis is manual and labor intensive. All data for validation and process monitoring must be manually compliance check by Quality.	FXNL LT Appr	Deidre Dunham	TBD	TBD	TBD					#REF!					#REF!
	216		Initiative			PTB	98037	PTB-023: Rapid Bioburden Method for Pre-filtration Media			N/A	QSP	Stay in Business	Multi Product		A rapid bioburden method for pre-filtration media is needed at DS sites to stay within bioburden limits, reduce holds steps, prevent loss of batches and increase reliability of fermentation processes by early detection of contaminated media.	Execute	TBD	TBD	TBD	Mike Russ					#REF!					#REF!
	217		Initiative			PTB	98038	PTB-025: Warehouse Business Continuity Mgt			N/A	CTT	Stay in Business	ACCR		The NA DS supply network is currently subject to constraints that limit our ability to ransport and store product. In times of crisis or during demand shifts, these limitations increase our risks of not having enough supply and/or not having the right product in the right amoutns in the right places at the right times.	Execute	Scott Fields	TBD	TBD	TBD					#REF!					#REF!
	218		Initiative			PTB	98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay			N/A	RTO	Stay in Business	Reliable		There have been 9 drug substance investigations related to P. acnes, an aerotolerant anaerobe, within the past ~1.5 years across multiple sites in the network resulting in a multisite significant investigation (DMS# 931144). There is a risk that P. acnes may elude our DS detection systems as it is not typically detected by the aerobic bioburden assay. Detection of these contaminations has occured via 1) mycoplasma test 2) low DO2 alarms or 3) microscopic visual examination (MVE). This has been identified as one of the top 5 cGMP compliance risks for the BIO OU.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	219		Initiative			PTB	98040	PTQ-038: Quality Compliance Scorecard (QCS) Phase 2			N/A	CTT	Stay in Business	Agile		Compliance Scorecard is a critical system used by PTQ to track identified issues with potential Health Authority impact. This system is used by all PT sites and provides key compliance metrics to PT LT. This project will focus on improving the system for users by simplifying the workflow and improving the usability. Reports will also be adapted based on the updated workflow.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	220		Initiative			PTB	98041	PTQ-041: Simply Core for PT			N/A	CTT	New Technologies	ACCR		The Simply Core IT project covers the migration of documents to future repositorites meeting the Coremap requirements from LiveLink/ShareWeb (non-validated instances only) and shared drivers (V:, G: Drive). The legacy repository will be decommissioned. Reduction of number of repositories supported by IT and PT and annual cost savings of 4-5.5 mil CHF.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	221		Initiative			PTB	98042	PTQ-046: Quality and Compliance Risk roll up			N/A	QSP	Stay in Business	Agile		Quality and Compliance risks are consolidated and rolled up to different levels of the organization (including PTLT) where business decisions on the top risks including prioritization for resource allocation are made. A simplified, more integrated business process will allow an easier process to collect, consolidate, and report critical Quality and Compliance risks for making these decisions with increased visibility throughout the PT organization.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	222		Initiative			PTB	98043	PTQ-050: QC Network Capacity Model			N/A	QSP	Strategic	ACCR		Insufficient QC capacity has been identified as a #1 PT risk. No standard QC capacity plannning and management model exists across the Bio and SM network. Inputs to existing capacity planning models/tools are compromised by workload volatility, absence of strategies within labs to level this workload and sub-optimal historical averages rather than standard work.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	223		Initiative			PTB	98044	PTQ-051: FileNet Replacement Assessment			N/A	CTT	Strategic	ACCR		Project will provide a global scalable image storage solution that will allow the destruction of paper files which reduces the costs and resources needed to maintain paper files.	Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	224		Initiative			PTB	98045	PTB-022: LER De-Masking			N/A	CTT	Stay in Business	ACCR			Execute	TBD	TBD	TBD	TBD					#REF!					#REF!
	225					#REF!					#REF!
	226					#REF!					#REF!
	227					#REF!					#REF!
	228					#REF!					#REF!
			#REF!					#REF!	$800k					#REF!					$800k

			OE				99001	SMART: 5 Day PCO Goal				RTO	Strategic	Reliable		Enhance multiple product capabilities for partially overlapping campaign modes (attain and maintain ≤ 5 days PCO, update documentation, define segregation, etc.) by Q2.	Execute	Cary Weisenberger			Robert Safarik					0.00
			OE				99002	SMART: Multi Product Segregation				RTO	Tech Transfers	Reliable		Enhance multiple product capabilities for partially overlapping campaign modes (attain and maintain ≤ 5 days PCO, update documentation, define segregation, etc.) by Q2.	Execute	Cary Weisenberger			Lou Luna					0.00
			OE				99003	SMART: Asset Replacement Plan				RTO		Reliable		World Class manufacturing is driven by planned, predictable performance. Asset Replacement Planning ensures the facility is sustainable for its intended purpose. A thorough and realistic analysis enables short and long term risk analysis and capital planning to support future objectives in the OCN site and network business plan.	Complete	Cary Weisenberger			Carl Hixon					1.00
			OE				99004	SMART: FOS PM Slow Down Assessment				RTO		Reliable		Currently the site has 3 weeks allocated in the master schedule to slow down production to 1.0 run per week (RPW) for 3 weeks each year, with a full shutdown for 1 week every third year, to allow time for routine Preventive Maintenance (PM) activities that cannot be performed during higher run rates. This results in a potential loss of up to 6 runs per year (up to 15 runs every 3 years). The exact slow down duration and run rate has not been validated against the planned work to be done to allow for the maximum annual production.	Complete	Cary Weisenberger			Tracy Tyler					0.10
			OE				99005	SMART: Spare Parts Stocking Strategy	through 2016			RTO	Strategic	Reliable		Oceanside is contributing to network targets by increasing plant capacity through DBX activities. Oceanside needs to be able to consistently deliver product on time, in full at run rates higher than previously demonstrated. If there is an adverse event at the site, the entire supply chain is in jeopardy. Spare parts are needed to avoid failure, shutdown, which can impact the supply chain and eventually the supply to the patient.	Execute	Cary Weisenberger			Carl Hixon					2.60
			OE				99006	SMART: Cycle Time Analysis				RTO	Improvements and Efficiencies	Reliable		OCN SMART goal to attain and sustain operational capability at 3.0 rpw for MRA SC and RIT.	Execute	Cary Weisenberger			Mark Baldwin					0.25
			OE				99007	SMART: Validation Enhancement				RTO	Improvements and Efficiencies	Reliable		World Class companies build flexible manufacturing to support changing markets. This facilitates on time and full delivery of the right product to the network at the right time and ultimately to the patient. Flexible production systems allow quick adjustments to changing needs.	Execute	Cary Weisenberger			Amr Ragui					0.10
			OE				99008	New Worker Cycle Time				QSP	Improvements and Efficiencies	Reliable		The Oceanside strategic goals are facilitated by timely arrival of incoming qualified, ready to work people. Complex processes under local, network, and corporate control challenge that timeliness.	Execute	Cary Weisenberger
			OE				99009	Class A Sustainment: Business Process Maintenance	through 2016			QSP	Strategic	Agile	A3 Class A Sustainment	Sustainment of Class A at the site has been a result of the efforts of those that went through certification and inertia. Moving forward, a refresh, maintenance, and update to the site's business processes, related metrics and behavior required to execute will prepare the site to become a launch facility.	Execute	Scott Fields
			OE				99010	Class A Sustainment: Governance Update	through 2016			QSP	Strategic	Reliable		Class A Behaviors and Performance provide a foundation to execute Oceanside’s vision and strategy	Execute	Cary Weisenberger
			OE				99011	Class A Sustainment: Site Refresh	through 2016			QSP	Strategic	Agile	A3 Class A Sustainment	Sustainment of Class A at the site has been a result of the efforts of those that went through certification and inertia. Moving forward, a refresh, maintenance, and update to the site's business processes, related metrics and behavior required to execute will prepare the site to become a launch facility.	Idea	Zaymar Sedra			Cary Weisenberger / Scott Fields
			OE				99012	PIF Development and Engagement	through 2016			QSP	Strategic	Agile	A4 Continuous Improvements	There is a need for a distribution of engaged employees with the skill sets to lead and foster a culture of Continuous Improvement. Our leadership has made a commitment to invest in the development of its people that have the attitude and aptitude to become champions of change.	Execute	Scott Fields
			OE				99013	OCN IFL Project Portfolio Support				RTO	Strategic	Reliable		Production Performance (PP) is the primary reliability measure for the DS manufacturing plants. The baseline performance analysis of PP showed that Investigation was the primary driver of poor performance. By their nature, Investigations are inherently “special cause” so to improve overall IFL performance we need to address the major themes at the site with coordinated improvement actions. OCN has IFL improvement as a 2015 strategic goal.	Execute	Scott Fields
			OE				99015	LCP/P2 Process Assessment Support	through 2017			QSP	Tech Transfers	Launch Facility		A launch facility concept here in OCN is new and untested. We must effectively transition to a launch facility, becoming capable of manufacturing and globally licensing new products while concurrently manufacturing mature commercial products. LCP will help us meet our network wide capacity goals so that we can continue to reliably deliver the pipeline and ensure uninterrupted supply of quality products to our patients. OE/BPM methods and tools will need to be effectively deployed to maximize LCP and P2 potential.	Idea	Deidre Dunham			Scott Fields
			OE				99016	Causal Analysis and Human Factor Assesment				RTO	Improvements and Efficiencies	Reliable		Discrepancy events have direct cost to Oceanside operations in the form of rework, lost product, and increased lead time. At best, actions to address human error (e.g. retraining or counseling) may reduce the number of events, but will not prevent occurrence. High, systemic discrepancy rates which conclude human error may be challenged by Health Authorities, posing a risk to maintaining our Right to Operate and ability to Supply Quality Product to patients.	Execute	Scott Fields

			#REF!					#REF!	$800k					#REF!					$800k

			Deptartmental
1			Deptartmental			L160	74525	CIP Reliability and Efficiency - PI	4/15/16 SciEng and MTS driving (Chris Johnson). SHE - Project identified during SBP Review.	12/1/15 IMPACT retitled from Phosphoric Acid Reduction and determined is a duplicate of Placeholder CIP Improvements.	Individual	RTO	Improvements and Efficiencies	Reliability and Value		A study to see how we can reduce the phosphoric acid use in the CIP cycle and use WFI rinse only cycles for buffer tanks.	Idea	Jim Neeleman	TBD	Mel Davis	Pierre Luong (TBD)					0.07			$20k					$20k	$20k	#REF!

## 2016_Budget_by_FIN_CYCLE
				EXP
		BUDGET REPORTS					#REF!
		2016					$155,147,081.74	$9,774,257.46		$141,379,690.25	$20,061,867.77		$116,138,963.67	$11,946,567.78		$29,592,884.00	$5,655,500.00		$63,729,949.00	$2,127,960.00
				CURRENT ESTIMATE					T0					MO5					T3					T0
				2016			2017			2018			2019			2020			2021			2022					2016			2017			2018			2019			2020			2021	T0 2016			2016			2017			2018			2019			2020			2021	MO5 2016			2015			2016			2017			2018			2019			2020			2021	T3 2015			2016			2017			2018			2019			2020			2021	T0 2015
	Global Type	CA No.	Project Title	Status	SPPM Lead	Program		Credit Type	2014 Actuals	2015 Actuals		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total			Total	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total	Total
1
	FAE	6DM	GNE Oceanside Prod Ops					Global Bucket	$3,580,630	$786,250		$3,562,007	$50,850	$3,612,857	$3,523,427	$0	$3,325,311	$0	$0	$3,657,842	$0	$0	$4,023,627	$0	$0	$4,425,989	$1,385,000		$1,385,000			$1,385,000	$26,182,506		$2,554,107	$24,450	$2,578,556	$477,848	$0	$3,325,311	$0	$0	$3,657,842	$0	$0	$4,023,627	$0	$0	$4,425,989	$1,385,000		$1,385,000	$19,134,416	$3,149,795	$28,850	$3,178,645	$927,505	$0	$3,325,311	$0	$0	$3,657,842	$0	$0	$4,023,627	$0	$0	$4,425,989	$1,385,000		$1,385,000	$24,363,294	$880,407	$0	$880,407	$2,179,955	$0	$2,179,955	$1,270,000		$1,270,000	$1,305,000		$1,305,000	$1,345,000		$1,345,000	$1,385,000		$1,385,000				$8,738,102	$2,554,107	$24,450	$2,578,556	$477,848	$0	$3,325,311	$0	$0	$3,657,842	$0	$0	$4,023,627	$0	$0	$4,425,989	$1,385,000		$1,385,000	$19,134,416
	FAC	90024	NIMO Small Projects - Misc					Global Bucket	$14,427,220	$9,765,687		$2,308,740	$22,286	$2,331,026	$132,000	$0	$1,790,552	$132,000	$0	$1,969,607	$0	$0	$2,166,568	$484,000	$0	$2,383,225	$5,979,000		$5,979,000			$5,979,000	$46,791,886		$2,028,821	$22,286	$2,051,107	$0	$0	$1,790,552	$0	$0	$1,969,607	$0	$0	$2,166,568	$0	$0	$2,383,225	$5,979,000		$5,979,000	$13,866,135	$2,379,243	$22,791	$2,402,034	$3,432,000	$0	$1,790,552	$3,432,000	$0	$1,969,607	$3,300,000	$0	$2,166,568	$3,784,000	$0	$2,383,225	$5,979,000		$5,979,000	$40,883,894	$1,753,651	$245,995	$1,999,646	$1,170,172	$28,903	$1,199,075	$5,785,440		$5,785,440	$5,786,069		$5,786,069	$5,805,000		$5,805,000	$5,979,000		$5,979,000				$28,516,798	$2,028,821	$22,286	$2,051,107	$0	$0	$1,790,552	$0	$0	$1,969,607	$0	$0	$2,166,568	$0	$0	$2,383,225	$5,979,000		$5,979,000	$13,866,135
1					0
0	FAC	64899	Engineering Library TOP Storage Unit	Execute	Jim Neeleman	Reliable	Improvements and Efficiencies	Global	$0	$66,881		$4,011		$4,011			$0			$0			$0			$0			$0			$0	$70,892				$0			$0			$0			$0			$0			$0	$75,000	$4,011		$4,011			$0			$0			$0			$0			$0	$70,892	$75,000		$75,000			$0			$0			$0			$0			$0				$75,000			$0			$0			$0			$0			$0			$0	$75,000
1	FAC	64901	MCS Peripheral Asset Replacement - 2015	Execute	Scott Fields	Reliability and Value	Stay in Business	Global	$0	$223,217		$43,151		$43,151			$0			$0			$0			$0			$0			$0	$266,368		$100,000		$100,000			$0			$0			$0			$0			$0	$425,200	$99,984		$99,984			$0			$0			$0			$0			$0	$323,201	$225,000	$100,000	$325,000			$0			$0			$0			$0			$0				$325,000	$100,000		$100,000			$0			$0			$0			$0			$0	$425,200
1	FAE	64914	QC M9 TOC Analyzers	Execute	Jim Neeleman	Launch and Commercial Excellence	New Technologies	Global	$0	$87,070		$17,480		$17,480			$0			$0			$0			$0			$0			$0	$104,550		$106,000		$106,000			$0			$0			$0			$0			$0	$106,000	$18,930		$18,930			$0			$0			$0			$0			$0	$106,000	$106,000		$106,000			$0			$0			$0			$0			$0				$106,000	$106,000		$106,000			$0			$0			$0			$0			$0	$106,000
1	FAE	64923	QC Met-One Air Sampler Replacement 2015	Execute	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Global	$0	$44,115		$15,885		$15,885			$0			$0			$0			$0			$0			$0	$60,000		$60,000		$60,000			$0			$0			$0			$0			$0	$60,000	$15,885		$15,885			$0			$0			$0			$0			$0	$60,000			$0			$0			$0			$0			$0			$0				$0	$60,000		$60,000			$0			$0			$0			$0			$0	$60,000
0	FAE	64925	QC UV Vis Spectometer Replacement 2015	Execute	Jim Neeleman	Reliable	Stay in Business	Global	$0			$21,531		$21,531			$0			$0			$0			$0			$0			$0	$21,531				$0			$0			$0			$0			$0			$0	$28,350	$21,531		$21,531			$0			$0			$0			$0			$0	$21,531			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$28,350
1	FAE	64927	QC Gel Imager Replacement 2015	Execute	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Global	$0	$12,340		$987		$987			$0			$0			$0			$0			$0			$0	$13,327		$15,000		$15,000			$0			$0			$0			$0			$0	$15,000	$2,660		$2,660			$0			$0			$0			$0			$0	$15,000			$0			$0			$0			$0			$0			$0				$0	$15,000		$15,000			$0			$0			$0			$0			$0	$15,000
1		73356	Supplemental BDU Sampling	Execute 2	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Individual	$258,306	$1,420,589		$157,774		$157,774			$0			$0			$0			$0			$0			$0	$1,836,669		$200,000		$200,000			$0			$0			$0			$0			$0	$1,674,665	$157,774		$157,774			$0			$0			$0			$0			$0	$1,836,669	$1,864,000		$1,864,000	$200,000		$200,000			$0			$0			$0			$0				$2,064,000	$200,000		$200,000			$0			$0			$0			$0			$0	$1,674,665
1		73367	FS & DS Automation Integration	Execute 2	Zaymar Sedra	Fit for Purpose	Tech Transfers	Individual	$246,193	$476,778		$26,719		$26,719			$0			$0			$0			$0			$0			$0	$749,690		$10,000		$10,000			$0			$0			$0			$0			$0	$733,193	$26,719		$26,719			$0			$0			$0			$0			$0	$749,690	$602,000		$602,000			$0			$0			$0			$0			$0				$602,000	$10,000		$10,000			$0			$0			$0			$0			$0	$733,193
1	FAC	73384	Caustic Bath Upgrade	Execute	Melanie Yevilov	Highly Capable Workforce	Stay in Business	Global	$0	$1,421		$459		$459			$0			$0			$0			$0			$0			$0	$1,880		$9,000		$9,000			$0			$0			$0			$0			$0	$51,106	$11,541	$459	$12,000			$0			$0			$0			$0			$0	$13,421	$34,000		$34,000			$0			$0			$0			$0			$0				$51,106	$9,000		$9,000			$0			$0			$0			$0			$0	$51,106
1	FAC	73387	MCSBACKUP Phase 2 Tape Retrieval	Execute	Deidre Dunham	Reliability and Value	New Technologies	Global	$3,918	$41,874				$0			$0			$0			$0			$0			$0			$0	$45,791		$5,000		$5,000			$0			$0			$0			$0			$0	$52,000	$5,000		$5,000			$0			$0			$0			$0			$0	$50,791	$43,000	$5,000	$48,000			$0			$0			$0			$0			$0				$48,000	$5,000		$5,000			$0			$0			$0			$0			$0	$52,000
1	FAC	73388	SIMCA Online Real Time Process Monitoring System	Execute	Jim Neeleman	Launch and Commercial Excellence	New Technologies	Global	$0	$262,943				$0			$0			$0			$0			$0			$0			$0	$262,943		$58,000		$58,000			$0			$0			$0			$0			$0	$344,000			$0			$0			$0			$0			$0			$0	$262,943	$298,664	$22,495	$321,159			$0			$0			$0			$0			$0				$321,159	$58,000		$58,000			$0			$0			$0			$0			$0	$344,000
1	FAC	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Execute	Scott Fields	Reliability and Value	Stay in Business	Global	$0	$13,347		$215,828		$215,828			$0			$0			$0			$0			$0			$0	$229,175		$95,000		$95,000			$0			$0			$0			$0			$0	$211,000	$204,700		$204,700			$0			$0			$0			$0			$0	$218,047	$253,487		$253,487	$20,000		$20,000			$0			$0			$0			$0				$273,487	$95,000		$95,000			$0			$0			$0			$0			$0	$211,000
1	FAC	73399	Frit Handling and Storage	Execute	Melanie Yevilov	Highly Capable Workforce	Tech Transfers	Global	$0	$18,994		$153,215		$153,215			$0			$0			$0			$0			$0			$0	$172,209		$108,000	$15,000	$123,000			$0			$0			$0			$0			$0	$138,000	$191,950	$15,000	$206,950			$0			$0			$0			$0			$0	$225,944	$48,000		$48,000	$91,000	$15,000	$106,000			$0			$0			$0			$0				$154,000	$108,000	$15,000	$123,000			$0			$0			$0			$0			$0	$138,000
0	FAC	73406	Guided Wave Radar V-4045 & V-4055	Execute	Zaymar Sedra	Agile	New Technologies	Global	$0	$32,021		$17,477		$17,477			$0			$0			$0			$0			$0			$0	$49,498				$0			$0			$0			$0			$0			$0	$60,000	$17,477		$17,477			$0			$0			$0			$0			$0	$49,498	$20,000		$20,000			$0			$0			$0			$0			$0				$20,000			$0			$0			$0			$0			$0			$0	$60,000
1	FAC	73409	Solar Power Enabling Project	Execute	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$132,223		$307,216		$307,216			$0			$0			$0			$0			$0			$0	$439,439		$271,000		$271,000			$0			$0			$0			$0			$0	$455,000	$305,902		$305,902			$0			$0			$0			$0			$0	$438,125	$379,500	$61,500	$441,000			$0			$0			$0			$0			$0				$441,000	$271,000		$271,000			$0			$0			$0			$0			$0	$455,000
1		74119	Harvest Upgrade (New Centrifuge)	Execute 2	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$0	$3,555,499		$4,614,221	$21,631	$4,635,852	$7,236,886	$51,254	$7,288,140			$0			$0			$0			$0			$0	$15,479,491		$7,233,192	$28,727	$7,261,919	$1,057,804	$56,618	$1,114,422			$0			$0			$0			$0	$12,909,963	$7,001,377	$37,498	$7,038,875	$4,833,864	$51,254	$4,885,118			$0			$0			$0			$0	$15,479,491	$4,422,093	$111,529	$4,533,622	$9,645,276	$194,535	$9,839,811	$1,057,804	$56,618	$1,114,422			$0			$0			$0				$15,487,855	$7,233,192	$28,727	$7,261,919	$1,057,804	$56,618	$1,114,422			$0			$0			$0			$0	$12,909,963
1		74127	Harvest Modifications Start-up	Budgeted	Deidre Dunham	Launch Facility	Strategic	Start-up	$0	$0		$125,000		$125,000	$2,275,000		$2,275,000			$0			$0			$0			$0			$0	$2,400,000		$125,000		$125,000	$2,275,000		$2,275,000			$0			$0			$0			$0	$2,400,000	$125,000		$125,000	$2,275,000		$2,275,000			$0			$0			$0			$0	$2,400,000			$0	$800,000		$800,000	$1,600,000		$1,600,000			$0			$0			$0				$2,400,000	$125,000		$125,000	$2,275,000		$2,275,000			$0			$0			$0			$0	$2,400,000
1		74268	P2 Downstream Processing Expansion	Execute 2	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$6,699,119	$58,484,942		$91,862,606	$1,766,871	$93,629,477	$33,364,075	$916,060	$34,280,135			$0			$0			$0			$0			$0	$193,093,673		$104,650,502	$825,644	$105,476,146	$29,469,907	$2,950,438	$32,420,345			$0			$0			$0			$0	$187,356,818	$92,403,605	$1,248,192	$93,651,797	$33,364,075	$916,060	$34,280,135			$0			$0			$0			$0	$193,115,993	$46,838,234	$2,675,210	$49,513,444	$119,331,552	$2,898,925	$122,230,477	$14,062,863	$1,541,104	$15,603,967			$0			$0			$0				$187,347,889	$104,650,502	$825,644	$105,476,146	$29,469,907	$2,950,438	$32,420,345			$0			$0			$0			$0	$187,356,818
0		74277	P2 DPE Start-Up	Execute	Zaymar Sedra	Fit for Purpose	Strategic	Start-up	$0	$0		$4,461,207		$4,461,207	$40,280,925		$40,280,925	$6,754,868		$6,754,868			$0			$0			$0			$0	$51,497,000		$8,000,000		$8,000,000	$44,445,136		$44,445,136			$0			$0			$0			$0	$52,445,136	$4,461,207		$4,461,207	$40,280,925		$40,280,925	$6,754,868		$6,754,868			$0			$0			$0	$51,497,000			$0	$8,000,000		$8,000,000	$44,445,136		$44,445,136			$0			$0			$0				$52,445,136	$8,000,000		$8,000,000	$44,445,136		$44,445,136			$0			$0			$0			$0	$52,445,136
0		74278	K6 Program - Project 3 - Replace Cold Room Compressors	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	SHE and K-Directives	Individual	$0	$0				$0	$528,000	$75,000	$603,000	$4,828,000		$4,828,000	$4,828,000		$4,828,000	$500,000		$500,000			$0			$0	$10,759,000				$0	$528,000	$75,000	$603,000	$4,828,000		$4,828,000	$4,828,000		$4,828,000	$500,000		$500,000			$0	$10,759,000			$0	$528,000	$75,000	$603,000	$4,828,000		$4,828,000	$4,828,000		$4,828,000	$500,000		$500,000			$0	$10,759,000			$0	$528,000		$528,000	$4,828,000		$4,828,000	$4,828,000		$4,828,000	$500,000		$500,000			$0				$10,684,000			$0	$528,000	$75,000	$603,000	$4,828,000		$4,828,000	$4,828,000		$4,828,000	$500,000		$500,000			$0	$10,759,000
1		74279	New Media Technology - HTST / Adventitious	Execute 2	Scott Fields	Reliability and Value	New Technologies	Individual	$523,433	$1,984,354		$4,859,034	$88,096	$4,947,130	$1,553,492	$37,670	$1,591,162			$0			$0			$0			$0			$0	$9,046,079		$5,444,000		$5,444,000	$1,588,000		$1,588,000			$0			$0			$0			$0	$9,106,000	$4,810,886	$1,768	$4,812,654	$1,602,703		$1,602,703			$0			$0			$0			$0	$8,923,144	$3,259,000	$2,000	$3,261,000	$4,120,000		$4,120,000	$1,588,000		$1,588,000			$0			$0			$0				$8,969,000	$5,444,000		$5,444,000	$1,588,000		$1,588,000			$0			$0			$0			$0	$9,106,000
1		74302	Waterpooling Remediation	Execute 2	Jim Neeleman	Reliability and Value	Stay in Business	Individual	$1,194,816	$470,099		$369,680		$369,680	$50,426		$50,426			$0			$0			$0			$0			$0	$2,085,021		$435,000		$435,000			$0			$0			$0			$0			$0	$945,000	$369,680		$369,680	$51,636		$51,636			$0			$0			$0			$0	$2,086,231	$574,000		$574,000	$1,292,000		$1,292,000			$0			$0			$0			$0				$1,866,000	$435,000		$435,000			$0			$0			$0			$0			$0	$945,000
1		74368	Dev/Val Automation Capacity Expansion	Execute	Jim Neeleman	Launch and Commercial Excellence	Improvements and Efficiencies	Individual	$489,325	$56,153		$10,000		$10,000			$0			$0			$0			$0			$0			$0	$555,477		$10,000		$10,000			$0			$0			$0			$0			$0	$66,000	$10,000		$10,000			$0			$0			$0			$0			$0	$555,477	$69,000		$69,000			$0			$0			$0			$0			$0				$69,000	$10,000		$10,000			$0			$0			$0			$0			$0	$66,000
1		74371	Odor Treatment	FXNL LT Appr	Melanie Yevilov	TBD	SHE and K-Directives	Individual	$0	$0				$0			$0	$750,000		$750,000	$4,250,000	$500,000	$4,750,000			$0			$0			$0	$5,500,000				$0	$1,000,000		$1,000,000	$4,000,000	$500,000	$4,500,000			$0			$0			$0	$5,600,000			$0	$750,000		$750,000	$4,250,000	$500,000	$4,750,000			$0			$0			$0	$5,500,000	$100,000		$100,000	$1,000,000		$1,000,000	$4,000,000		$4,000,000			$0			$0			$0				$5,100,000			$0	$1,000,000		$1,000,000	$4,000,000	$500,000	$4,500,000			$0			$0			$0	$5,600,000
1		74373	WFI Generation and Storage System / CUB Expansion	Execute 2	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$1,738,974	$6,525,760		$5,512,468	$23,739	$5,536,207			$0			$0			$0			$0			$0			$0	$13,800,941		$5,342,000	$12,500	$5,354,500			$0			$0			$0			$0			$0	$11,609,722	$5,523,133	$13,075	$5,536,208			$0			$0			$0			$0			$0	$13,800,942	$8,959,000	$134,000	$9,093,000	$2,740,000	$2,000	$2,742,000			$0			$0			$0			$0				$11,835,000	$5,342,000	$12,500	$5,354,500			$0			$0			$0			$0			$0	$11,609,722
1		74382	Sci&Eng Lab Mods and Equipment	Execute 2	Jim Neeleman	Launch and Commercial Excellence	Strategic	Individual	$0	$6,008,632		$7,414,885	$195,338	$7,610,223	$390,885		$390,885			$0			$0			$0			$0			$0	$14,009,740		$7,008,000	$393,000	$7,401,000			$0			$0			$0			$0			$0	$12,673,000	$6,232,184	$458,027	$6,690,211	$488,779		$488,779			$0			$0			$0			$0	$13,187,622	$9,335,000	$300,000	$9,635,000	$2,914,000	$172,000	$3,086,000			$0			$0			$0			$0				$12,721,000	$7,008,000	$393,000	$7,401,000			$0			$0			$0			$0			$0	$12,673,000
0		74385	Media Prep Endotoxin/Bioburden Sampling	Hold	Melanie Yevilov	Reliability and Value	Stay in Business	Individual	$0	$0				$0			$0			$0			$0			$0			$0			$0	$0		$500,000		$500,000	$2,500,000		$2,500,000			$0			$0			$0			$0	$3,000,000	$250,000		$250,000	$2,750,000		$2,750,000			$0			$0			$0			$0	$3,000,000			$0			$0			$0			$0			$0			$0				$0	$500,000		$500,000	$2,500,000		$2,500,000			$0			$0			$0			$0	$3,000,000
1		74392	Water Reclaim System	Execute	Scott Fields	Reliability and Value	SHE and K-Directives	Individual	$0	$179,085		$143,846		$143,846			$0			$0			$0			$0			$0			$0	$322,931		$676,000		$676,000	$800,000		$800,000			$0			$0			$0			$0	$1,656,000	$162,102		$162,102			$0			$0			$0			$0			$0	$341,187	$1,166,000		$1,166,000	$514,000		$514,000			$0			$0			$0			$0				$1,680,000	$676,000		$676,000	$800,000		$800,000			$0			$0			$0			$0	$1,656,000
1		74404	Mezzanine Lift Media Prep: Phase 1B	Execute	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Individual	$17,731	$265,047		$270,440	-$431	$270,009			$0			$0			$0			$0			$0			$0	$552,787		$330,000		$330,000			$0			$0			$0			$0			$0	$592,000	$201,044	-$431	$200,613			$0			$0			$0			$0			$0	$483,391	$597,000	$20,000	$617,000			$0			$0			$0			$0			$0				$617,000	$330,000		$330,000			$0			$0			$0			$0			$0	$592,000
1		74406	Corrosive Chemical Compliance	Execute	Scott Fields	Reliability and Value	SHE and K-Directives	Individual	$0	$103,025		$1,724,239		$1,724,239	$83,733		$83,733			$0			$0			$0			$0			$0	$1,910,997		$1,812,000		$1,812,000			$0			$0			$0			$0			$0	$1,910,000	$1,596,303		$1,596,303	$83,733		$83,733			$0			$0			$0			$0	$1,783,061	$1,279,000		$1,279,000	$622,000	$52,000	$674,000			$0			$0			$0			$0				$1,953,000	$1,812,000		$1,812,000			$0			$0			$0			$0			$0	$1,910,000
1		74409	K6 Program - Project 1 - Replace DX HVAC Units	Execute	Zaymar Sedra	Fit for Purpose	SHE and K-Directives	Individual	$0	$0				$0	$310,000	$22,000	$332,000			$0			$0			$0			$0			$0	$332,000		$1,902,000	$22,000	$1,924,000			$0			$0			$0			$0			$0	$2,014,000			$0	$310,000	$22,000	$332,000	$1,592,000		$1,592,000			$0			$0			$0	$1,924,000	$415,000	$40,000	$455,000	$968,000	$50,000	$1,018,000			$0			$0			$0			$0				$1,473,000	$1,902,000	$22,000	$1,924,000			$0			$0			$0			$0			$0	$2,014,000
1		74416	Asphyxiant Gas Remediation	Execute 1	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Individual	$0	$36,659		$126,295		$126,295			$0			$0			$0			$0			$0			$0	$162,954		$99,000		$99,000			$0			$0			$0			$0			$0	$132,392	$142,115		$142,115	$400,000		$400,000			$0			$0			$0			$0	$578,774	$555,000		$555,000			$0			$0			$0			$0			$0				$555,000	$99,000		$99,000			$0			$0			$0			$0			$0	$132,392
1		74418	QC Lab Reconfiguration & Equipment	Execute 1	Jim Neeleman	Launch and Commercial Excellence	Tech Transfers	Individual	$0	$224,746		$3,160,674	$114,000	$3,274,674	$289,726		$289,726			$0			$0			$0			$0			$0	$3,789,146		$3,675,000		$3,675,000			$0			$0			$0			$0			$0	$3,888,000	$1,918,122	$113,000	$2,031,122	$1,568,006		$1,568,006			$0			$0			$0			$0	$3,823,874	$3,145,000		$3,145,000	$1,016,000		$1,016,000			$0			$0			$0			$0				$4,161,000	$3,675,000		$3,675,000			$0			$0			$0			$0			$0	$3,888,000
1		74426	Process VSD and SOV Replacement - 2015	Execute	Scott Fields	Reliability and Value	Stay in Business	Individual	$0	$194,621		$589,735		$589,735			$0			$0			$0			$0			$0			$0	$784,356		$489,000		$489,000			$0			$0			$0			$0			$0	$692,000	$495,036		$495,036			$0			$0			$0			$0			$0	$689,657	$707,000		$707,000			$0			$0			$0			$0			$0				$707,000	$489,000		$489,000			$0			$0			$0			$0			$0	$692,000
1		74427	MCS Network Infrastructure Asset Replacement - 2016	Execute	Scott Fields	Reliability and Value	Stay in Business	Individual	$0	$0		$1,466,000		$1,466,000			$0			$0			$0			$0	$2,340,000		$2,340,000			$0	$3,806,000		$1,944,000		$1,944,000			$0			$0			$0			$0			$0	$1,951,000	$1,944,000		$1,944,000			$0			$0			$0			$0	$2,340,000		$2,340,000	$4,284,000	$500,000		$500,000	$1,450,000		$1,450,000			$0			$0			$0			$0				$1,950,000	$1,944,000		$1,944,000			$0			$0			$0			$0			$0	$1,951,000
0		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	FXNL LT Appr	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Individual	$0	$0				$0		$200,000	$200,000	$900,000		$900,000	$900,000		$900,000	$935,000		$935,000			$0			$0	$2,935,000				$0	$950,000	$8,000	$958,000	$950,000	$8,000	$958,000	$935,000		$935,000			$0			$0	$2,851,000			$0		$200,000	$200,000	$900,000		$900,000	$900,000		$900,000	$935,000		$935,000			$0	$2,935,000			$0			$0	$950,000	$8,000	$958,000	$950,000	$8,000	$958,000	$935,000		$935,000			$0				$2,851,000			$0	$950,000	$8,000	$958,000	$950,000	$8,000	$958,000	$935,000		$935,000			$0			$0	$2,851,000
1		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Execute	Scott Fields	Reliability and Value	Stay in Business	Individual	$0	$242,656		$204,573		$204,573	$23,445		$23,445			$0			$0			$0			$0			$0	$470,674		$350,000		$350,000			$0			$0			$0			$0			$0	$661,000	$198,196		$198,196	$22,991		$22,991			$0			$0			$0			$0	$463,843	$416,000		$416,000	$246,000		$246,000			$0			$0			$0			$0				$662,000	$350,000		$350,000			$0			$0			$0			$0			$0	$661,000
1	FAC	74431	Buffer Prep Mezzanine Lift Construction	JPMT Appr	Scott Fields	Reliability and Value	SHE and K-Directives	Global	$0	$0		$442,000		$442,000			$0			$0			$0			$0			$0			$0	$442,000		$442,000		$442,000			$0			$0			$0			$0			$0	$442,000	$442,000		$442,000			$0			$0			$0			$0			$0	$442,000	$100,000		$100,000	$428,000	$30,000	$458,000			$0			$0			$0			$0				$558,000	$442,000		$442,000			$0			$0			$0			$0			$0	$442,000
1		74432	K6 Program - Project 4 - Replace Chillers	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	SHE and K-Directives	Individual	$0	$0				$0			$0	$2,650,000	$350,000	$3,000,000	$6,650,000		$6,650,000	$6,000,000		$6,000,000	$3,650,000		$3,650,000			$0	$19,300,000				$0	$2,650,000	$350,000	$3,000,000	$6,650,000		$6,650,000	$6,000,000		$6,000,000	$3,650,000		$3,650,000			$0	$19,300,000			$0	$2,650,000	$350,000	$3,000,000	$6,650,000		$6,650,000	$6,000,000		$6,000,000	$3,650,000		$3,650,000			$0	$19,300,000			$0			$0	$2,650,000		$2,650,000	$6,650,000		$6,650,000	$5,650,000		$5,650,000	$3,650,000		$3,650,000				$18,600,000			$0	$2,650,000	$350,000	$3,000,000	$6,650,000		$6,650,000	$6,000,000		$6,000,000	$3,650,000		$3,650,000			$0	$19,300,000
1		74435	Hastelloy Chromatography Column (160cm)	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	Improvements and Efficiencies	Individual	$0	$0		$400,000		$400,000	$1,149,000		$1,149,000			$0			$0			$0			$0			$0	$1,549,000		$1,549,000		$1,549,000			$0			$0			$0			$0			$0	$1,549,000			$0	$1,549,000		$1,549,000			$0			$0			$0			$0	$1,549,000			$0			$0	$378,000		$378,000	$776,102		$776,102			$0			$0				$1,154,102	$1,549,000		$1,549,000			$0			$0			$0			$0			$0	$1,549,000
1		74453	NPI Pool Tanks	PTAA	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$0	$581,240		$601,771	$2,484	$604,255	$37,505		$37,505			$0			$0			$0			$0			$0	$1,223,000		$452,919	$10,802	$463,721			$0			$0			$0			$0			$0	$1,009,121	$684,545	$2,883	$687,428	$3,878	$0	$3,878			$0			$0			$0			$0	$1,272,546	$545,400		$545,400	$649,000		$649,000			$0			$0			$0			$0				$1,194,400	$452,919	$10,802	$463,721			$0			$0			$0			$0			$0	$1,009,121
1		74454	Seed Lab (20L Bioreactor)	Execute	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$0	$1,387,337		$912,870	$97,323	$1,010,193	$438,751	$2,075	$440,826			$0			$0			$0			$0			$0	$2,838,356		$938,961	$10,802	$949,763	$177,848	$9,518	$187,366			$0			$0			$0			$0	$1,899,375	$954,867	$141,531	$1,096,398	$352,550	$2,075	$354,625			$0			$0			$0			$0	$2,838,360	$755,170	$7,076	$762,246	$1,621,678	$32,708	$1,654,386	$177,848	$9,518	$187,366			$0			$0			$0				$2,603,998	$938,961	$10,802	$949,763	$177,848	$9,518	$187,366			$0			$0			$0			$0	$1,899,375
1		74455	3rd HCCF Vessel	Execute	Zaymar Sedra	Fit for Purpose	Strategic	Individual	$0	$1,535,902		$1,669,681	$34,808	$1,704,489			$0			$0			$0			$0			$0			$0	$3,240,391		$2,328,891	$27,591	$2,356,482	$254,209	$13,607	$267,816			$0			$0			$0			$0	$3,713,805	$2,027,438	$43,784	$2,071,222	$113,412	$464	$113,876			$0			$0			$0			$0	$3,721,000	$1,079,394	$10,113	$1,089,507	$2,292,065	$72,611	$2,364,676	$254,209	$13,607	$267,816			$0			$0			$0				$3,721,999	$2,328,891	$27,591	$2,356,482	$254,209	$13,607	$267,816			$0			$0			$0			$0	$3,713,805
1		74486	PCS Controller Cabinet Asset Replacement	Execute	Melanie Yevilov	Highly Capable Workforce	Stay in Business	Individual	$0	$0		$2,294,000		$2,294,000	$110,000		$110,000			$0			$0			$0			$0			$0	$2,404,000		$2,404,000		$2,404,000	$1,546,000		$1,546,000	$2,092,000		$2,092,000			$0			$0			$0	$6,042,000	$2,294,000		$2,294,000	$110,000		$110,000			$0			$0			$0			$0	$2,404,000	$450,000		$450,000	$1,000,000		$1,000,000	$2,275,000		$2,275,000	$2,275,000		$2,275,000			$0			$0				$6,000,000	$2,404,000		$2,404,000	$1,546,000		$1,546,000	$2,092,000		$2,092,000			$0			$0			$0	$6,042,000
1		74487	Process VSD and SOV Asset Replacement	Execute	Melanie Yevilov	Highly Capable Workforce	Stay in Business	Individual	$0	$0		$3,599,797		$3,599,797	$2,925,031	$18,000	$2,943,031			$0			$0			$0			$0			$0	$6,542,828		$4,542,000	$7,000	$4,549,000	$7,408,000	$18,000	$7,426,000	$5,427,000	$20,000	$5,447,000			$0			$0			$0	$17,422,000	$3,599,318		$3,599,318	$2,925,031	$18,000	$2,943,031			$0			$0			$0			$0	$6,542,349	$500,000		$500,000	$3,294,314		$3,294,314	$3,749,999		$3,749,999			$0			$0			$0				$7,544,313	$4,542,000	$7,000	$4,549,000	$7,408,000	$18,000	$7,426,000	$5,427,000	$20,000	$5,447,000			$0			$0			$0	$17,422,000
1		74489	4040 Avenida Conference Center Acquisition	Execute	Deidre Dunham	Exceptional Culture	Strategic	Individual	$0	$2,701,000		$685,700		$685,700			$0			$0			$0			$0			$0			$0	$3,386,700		$688,000		$688,000			$0			$0			$0			$0			$0	$3,388,000	$686,850		$686,850			$0			$0			$0			$0			$0	$3,387,850	$2,700,000		$2,700,000			$0			$0			$0			$0			$0				$2,700,000	$688,000		$688,000			$0			$0			$0			$0			$0	$3,388,000
1		74490	Hyfish Material Screening Operation	Execute	Jim Neeleman	Reliability and Value	Improvements and Efficiencies	Individual	$0	$860,038		$601,445		$601,445			$0			$0			$0			$0			$0			$0	$1,461,483		$460,000		$460,000			$0			$0			$0			$0			$0	$1,242,000	$422,881		$422,881			$0			$0			$0			$0			$0	$1,282,919	$734,000		$734,000	$734,000		$734,000			$0			$0			$0			$0				$1,468,000	$460,000		$460,000			$0			$0			$0			$0			$0	$1,242,000
0		74491	Etro Tech Transfer	Hold	Deidre Dunham	Launch and Commercial Excellence	Tech Transfers	Start-up	$0	$0		$1,295,272	$69,004	$1,364,276	$9,065,569	$3,771,061	$12,836,630	$3,267,374	$80,000	$3,347,374	$487,190	$20,600	$507,790	$61,490	$4,800	$66,290			$0			$0	$18,122,360		$7,015,007	$200,000	$7,215,007	$11,618,688	$254,750	$11,873,438	$2,915,160	$82,980	$2,998,140	$232,200	$61,920	$294,120	$20,640	$47,520	$68,160			$0	$22,448,865	$6,094,794	$116,900	$6,211,694	$12,701,630	$135,000	$12,836,630	$3,267,374	$80,000	$3,347,374	$487,190	$20,600	$507,790	$61,490	$4,800	$66,290			$0	$22,969,778			$0	$8,400,000	$50,000	$8,450,000	$8,400,000	$50,000	$8,450,000			$0			$0			$0				$16,900,000	$7,015,007	$200,000	$7,215,007	$11,618,688	$254,750	$11,873,438	$2,915,160	$82,980	$2,998,140	$232,200	$61,920	$294,120	$20,640	$47,520	$68,160			$0	$22,448,865
1		74510	PCS Asset Replacement - 2016	Execute	Zaymar Sedra	Fit for Purpose	Stay in Business	Individual	$0	$0		$1,765,839	$219	$1,766,058	$149,000		$149,000			$0			$0			$0			$0			$0	$1,915,058		$1,869,000		$1,869,000			$0			$0			$0			$0			$0	$1,869,000	$1,745,958	$69	$1,746,027	$149,000		$149,000			$0			$0			$0			$0	$1,895,027			$0			$0			$0			$0			$0			$0				$0	$1,869,000		$1,869,000			$0			$0			$0			$0			$0	$1,869,000
0			PCS Asset Replacement Depreciation Write-Off				#N/A	Expense					$800,000	$800,000			$0			$0			$0			$0			$0			$0	$800,000					$800,000	$800,000			$0			$0			$0			$0			$0	$800,000
1		74511	QR018 Compliance Steam and Condensate Containment	Execute	Jim Neeleman	Reliability and Value	Stay in Business	Individual	$0	$0		$1,943,300		$1,943,300	$3,074,500		$3,074,500			$0			$0			$0			$0			$0	$5,017,800		$2,457,000	$45,000	$2,502,000	$2,471,000		$2,471,000			$0			$0			$0			$0	$4,973,000	$1,943,300		$1,943,300	$3,074,500		$3,074,500			$0			$0			$0			$0	$5,017,800			$0			$0			$0			$0			$0			$0				$0	$2,457,000	$45,000	$2,502,000	$2,471,000		$2,471,000			$0			$0			$0			$0	$4,973,000
1		74512	K6 Program - Project 2 - B381 Compliance	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	SHE and K-Directives	Individual	$0	$0				$0			$0	$333,333	$22,222	$355,556	$416,667	$27,778	$444,444			$0			$0			$0	$800,000				$0	$650,000	$50,000	$700,000			$0			$0			$0			$0	$700,000			$0	$333,333	$22,222	$355,556	$416,667	$27,778	$444,444			$0			$0			$0	$800,000			$0			$0			$0			$0			$0			$0				$0			$0	$650,000	$50,000	$700,000			$0			$0			$0			$0	$700,000
0		74513	Electric Vehicle Charging Stations	Hold	Deidre Dunham	Exceptional Culture	Improvements and Efficiencies	Individual	$0	$0				$0	$712,000	$18,000	$730,000			$0			$0			$0			$0			$0	$730,000				$0	$712,000	$18,000	$730,000			$0			$0			$0			$0	$730,000			$0	$712,000	$18,000	$730,000			$0			$0			$0			$0	$730,000			$0			$0			$0			$0			$0			$0				$0			$0	$712,000	$18,000	$730,000			$0			$0			$0			$0	$730,000
1	FAE	76643	Optimize Column Movement Device	Execute	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$126,474		$143,425		$143,425			$0			$0			$0			$0			$0			$0	$269,899		$128,000		$128,000			$0			$0			$0			$0			$0	$196,000	$143,425		$143,425			$0			$0			$0			$0			$0	$269,899	$167,000		$167,000	$186,000		$186,000			$0			$0			$0			$0				$353,000	$128,000		$128,000			$0			$0			$0			$0			$0	$196,000
0	FAE	96069	Warehouse Crown Forklift Asset Replacement	Hold	Zaymar Sedra	Fit for Purpose	Life Cycle Mgmt	Global	$0	$0				$0	$144,407		$144,407			$0			$0			$0			$0			$0	$144,407				$0	$144,407		$144,407			$0			$0			$0			$0	$144,407			$0	$144,407		$144,407			$0			$0			$0			$0	$144,407	$144,407		$144,407			$0			$0			$0			$0			$0				$144,407			$0	$144,407		$144,407			$0			$0			$0			$0	$144,407
0		96105	TMAC Tenderizer	Hold	Melanie Yevilov	Highly Capable Workforce	Stay in Business	Individual	$0	$0				$0	$0		$0			$0			$0			$0			$0			$0	$0				$0	$575,000		$575,000			$0			$0			$0			$0	$575,000			$0			$0			$0			$0			$0			$0	$0			$0			$0			$0	$575,000		$575,000			$0			$0				$575,000			$0	$575,000		$575,000			$0			$0			$0			$0	$575,000
0		96112	Maintenance Ops Shop Buildout	Budgeted	Zaymar Sedra	Fit for Purpose	Improvements and Efficiencies	Individual	$0	$0				$0			$0			$0	$500,000		$500,000	$2,500,000		$2,500,000			$0			$0	$3,000,000				$0	$1,000,000		$1,000,000	$2,000,000		$2,000,000			$0			$0			$0	$3,000,000			$0	$500,000		$500,000	$2,500,000		$2,500,000			$0			$0			$0	$3,000,000			$0			$0			$0			$0			$0			$0				$0			$0	$1,000,000		$1,000,000	$2,000,000		$2,000,000			$0			$0			$0	$3,000,000
0		96113	Bulk Product Storage -20/-40	Placeholder	Deidre Dunham	Launch Facility	Improvements and Efficiencies	Individual	$0	$0				$0			$0			$0			$0	$10,000,000		$10,000,000			$0			$0	$10,000,000				$0			$0			$0			$0	$10,000,000		$10,000,000			$0	$10,000,000			$0			$0			$0			$0	$10,000,000		$10,000,000			$0	$10,000,000			$0			$0			$0			$0			$0	$10,000,000		$10,000,000				$10,000,000			$0			$0			$0			$0	$10,000,000		$10,000,000			$0	$10,000,000
0		96116	PCS Process Support Equipment Integration	Idea	Deidre Dunham	TBD	Improvements and Efficiencies	Individual	$0	$0				$0			$0	$750,000	$750,000	$1,500,000	$750,000	$750,000	$1,500,000			$0			$0			$0	$3,000,000				$0	$750,000	$750,000	$1,500,000	$750,000	$750,000	$1,500,000			$0			$0			$0	$3,000,000			$0			$0	$750,000	$750,000	$1,500,000	$750,000	$750,000	$1,500,000			$0			$0	$3,000,000			$0			$0	$750,000	$750,000	$1,500,000	$750,000	$750,000	$1,500,000			$0			$0				$3,000,000			$0	$750,000	$750,000	$1,500,000	$750,000	$750,000	$1,500,000			$0			$0			$0	$3,000,000
0	FAC	96117	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2019	Idea	Deidre Dunham	Reliable	Life Cycle Mgmt	Global	$0	$0				$0			$0			$0			$0	$440,000		$440,000			$0			$0	$440,000				$0			$0			$0	$440,000		$440,000			$0			$0	$440,000			$0			$0			$0			$0	$440,000		$440,000			$0	$440,000			$0			$0			$0			$0	$440,000		$440,000			$0				$440,000			$0			$0			$0	$440,000		$440,000			$0			$0	$440,000
0		74527	Vessel 1020 Upgrade	Idea	Zaymar Sedra	Fit for Purpose	Stay in Business	Individual	$0	$0		$0		$0			$0	$3,700,000	$100,000	$3,800,000	$100,000		$100,000			$0			$0			$0	$3,900,000		$2,646,000		$2,646,000	$11,013,000		$11,013,000			$0			$0			$0			$0	$13,659,000			$0	$4,859,000		$4,859,000			$0			$0			$0			$0	$4,859,000			$0			$0			$0			$0			$0			$0				$0	$2,646,000		$2,646,000	$11,013,000		$11,013,000			$0			$0			$0			$0	$13,659,000
0		96124	Perjeta Tech Transfer	Idea	Jim Neeleman	Launch and Commercial Excellence	Tech Transfers	Start-up	$0	$0				$0	$8,793,594	$147,070	$8,940,664	$61,780,285	$16,999,060	$78,779,345	$1,376,100	$55,330	$1,431,430	$349,305	$19,800	$369,105	$38,280	$40,920	$79,200			$0	$89,599,744				$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0			$0			$0	$16,500,000			$0	$8,793,594	$147,070	$8,940,664	$78,610,055	$169,290	$78,779,345	$1,376,100	$55,330	$1,431,430	$349,305	$19,800	$369,105	$38,280	$40,920	$79,200	$89,599,744			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0			$0				$16,500,000			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0			$0			$0	$16,500,000
0		96125	Flu A Tech Transfer	Idea	Deidre Dunham	Launch and Commercial Excellence	Tech Transfers	Start-up	$0	$0				$0			$0			$0	$8,793,594	$147,070	$8,940,664	$24,767,312	$6,402,538	$31,169,850	$1,376,100	$55,330	$1,431,430			$0	$41,541,944				$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0			$0	$16,500,000			$0			$0			$0	$8,793,594	$147,070	$8,940,664	$31,000,560	$169,290	$31,169,850	$1,376,100	$55,330	$1,431,430	$41,541,944			$0			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0				$16,500,000			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0			$0	$16,500,000
0		96126	Flu B Tech Transfer	Idea	Deidre Dunham	Launch and Commercial Excellence	Tech Transfers	Start-up	$0	$0				$0			$0			$0			$0	$8,793,594	$147,070	$8,940,664	$22,558,264	$6,194,763	$28,753,027			$0	$37,693,691				$0			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0	$16,500,000			$0			$0			$0			$0	$8,793,594	$147,070	$8,940,664	$28,583,737	$169,290	$28,753,027	$37,693,691			$0			$0			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000				$16,500,000			$0			$0			$0	$8,000,000	$50,000	$8,050,000	$8,400,000	$50,000	$8,450,000			$0	$16,500,000
1		74546	Mezzanine Safety Shower/Eye Wash Station Install	IMPACT Appr	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Individual	$0	$0		$450,000		$450,000	$436,000		$436,000			$0			$0			$0			$0			$0	$886,000		$210,000		$210,000			$0			$0			$0			$0			$0	$210,000	$100,000		$100,000	$785,864		$785,864			$0			$0			$0			$0	$885,864			$0	$210,000		$210,000			$0			$0			$0			$0				$210,000	$210,000		$210,000			$0			$0			$0			$0			$0	$210,000
0	FAE	96133	QC Rapid Scan RDI System	Hold	Jim Neeleman	Launch and Commercial Excellence	New Technologies	Global	$0	$0				$0	$210,000		$210,000			$0			$0			$0			$0			$0	$210,000				$0	$210,000		$210,000			$0			$0			$0			$0	$210,000			$0	$210,000		$210,000			$0			$0			$0			$0	$210,000			$0			$0			$0			$0			$0			$0				$0			$0	$210,000		$210,000			$0			$0			$0			$0	$210,000
1	FAE	96135	QC Spectrophotometers	Hold	Deidre Dunham	Highly Capable Workforce	Global	$0	$0					$0			$0			$0			$0			$0			$0			$0	$0		$327,522		$327,522			$0			$0			$0			$0			$0	$327,522	$23,000		$23,000			$0			$0			$0			$0			$0	$23,000			$0			$0			$0			$0			$0			$0				$0	$327,522		$327,522			$0			$0			$0			$0			$0	$327,522
0	FAC	96136	V-3007 Replacement	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	Life Cycle Mgmt	Global	$0	$0				$0	$120,000		$120,000	$120,000		$120,000			$0			$0			$0			$0	$240,000				$0	$240,000		$240,000			$0			$0			$0			$0	$240,000			$0	$120,000		$120,000	$120,000		$120,000			$0			$0			$0	$240,000			$0	$240,000		$240,000			$0			$0			$0			$0				$240,000			$0	$240,000		$240,000			$0			$0			$0			$0	$240,000
1	FAC	96137	Security Systems Upgrade	JPMT Appr	Deidre Dunham	Exceptional Culture	SHE and K-Directives	Global	$0	$0		$200,000		$200,000			$0			$0			$0			$0			$0			$0	$200,000		$250,000		$250,000			$0			$0			$0			$0			$0	$250,000	$175,000		$175,000			$0			$0			$0			$0			$0	$175,000			$0			$0			$0			$0			$0			$0				$0	$250,000		$250,000			$0			$0			$0			$0			$0	$250,000
1	FAC	96139	Trash Bin Storm Water Mitigation	FXNL LT Appr	Deidre Dunham	Exceptional Culture	SHE and K-Directives	Global	$0	$0				$0	$200,000		$200,000			$0			$0			$0			$0			$0	$200,000		$200,000		$200,000			$0			$0			$0			$0			$0	$200,000			$0	$200,000		$200,000			$0			$0			$0			$0	$200,000			$0			$0			$0			$0			$0			$0				$0	$200,000		$200,000			$0			$0			$0			$0			$0	$200,000
1	FAE	65066	Appleton Tank Mover	Hold	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$0		$73,000		$73,000			$0			$0			$0			$0			$0			$0	$73,000				$0	$80,000		$80,000			$0			$0			$0			$0	$80,000	$73,000		$73,000			$0			$0			$0			$0			$0	$73,000			$0			$0			$0			$0			$0			$0				$0			$0	$80,000		$80,000			$0			$0			$0			$0	$80,000
1	FAE	65021	Hazardous Material Response Cart	Execute	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$0		$17,985		$17,985			$0			$0			$0			$0			$0			$0	$17,985				$0			$0			$0			$0			$0			$0	$18,000	$19,424		$19,424			$0			$0			$0			$0			$0	$19,424			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$18,000
0	FAC	96159	OCC Network Remediation	Idea	Zaymar Sedra	Fit for Purpose	Improvements and Efficiencies	Global	$0	$0		$150,000		$150,000			$0			$0			$0			$0			$0			$0	$150,000		$150,000		$150,000			$0			$0			$0			$0			$0	$150,000	$150,000		$150,000			$0			$0			$0			$0			$0	$150,000			$0			$0			$0			$0			$0			$0				$0	$150,000		$150,000			$0			$0			$0			$0			$0	$150,000
0		96165	WAN Link Redundancy	Hold	Scott Fields	Reliability and Value	Improvements and Efficiencies	Individual	$0	$0				$0			$0			$0			$0			$0			$0			$0	$0				$0	$2,000,000		$2,000,000			$0			$0			$0			$0	$2,000,000			$0	$2,000,000		$2,000,000			$0			$0			$0			$0	$2,000,000			$0			$0			$0			$0			$0			$0				$0			$0	$2,000,000		$2,000,000			$0			$0			$0			$0	$2,000,000
0	FAC	96163	MFG Depth Filter Housing	Idea	Zaymar Sedra	Reliability and Value	Stay in Business	Global	$0	$0				$0	$300,000	$100,000	$400,000			$0			$0			$0			$0			$0	$400,000				$0	$300,000	$100,000	$400,000			$0			$0			$0			$0	$400,000			$0	$300,000	$100,000	$400,000			$0			$0			$0			$0	$400,000			$0			$0			$0			$0			$0			$0				$0			$0	$300,000	$100,000	$400,000			$0			$0			$0			$0	$400,000
0	FAC	96164	Hazardous Materials Containers Washing Station	Hold	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$0				$0	$30,000		$30,000			$0			$0			$0			$0			$0	$30,000		$30,000		$30,000			$0			$0			$0			$0			$0	$30,000			$0	$30,000		$30,000			$0			$0			$0			$0	$30,000			$0			$0			$0			$0			$0			$0				$0	$30,000		$30,000			$0			$0			$0			$0			$0	$30,000
0	FAC	96167	Emergency Generator High Level Alarm	Idea	Melanie Yevilov	Reliability and Value	SHE and K-Directives	Global	$0	$0		$25,000		$25,000			$0			$0			$0			$0			$0			$0	$25,000		$25,000		$25,000			$0			$0			$0			$0			$0	$25,000	$25,000		$25,000			$0			$0			$0			$0			$0	$25,000			$0			$0			$0			$0			$0			$0				$0	$25,000		$25,000			$0			$0			$0			$0			$0	$25,000
0	FAC	96168	Replace Warehouse #321 Sprinkler Heads	Idea	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Global	$0	$0		$20,000		$20,000			$0			$0			$0			$0			$0			$0	$20,000		$20,000		$20,000			$0			$0			$0			$0			$0	$20,000	$20,000		$20,000			$0			$0			$0			$0			$0	$20,000			$0			$0			$0			$0			$0			$0				$0	$20,000		$20,000			$0			$0			$0			$0			$0	$20,000
1		74526	Utility and Process Safety System	FXNL LT Appr	Scott Fields	Reliability and Value	SHE and K-Directives	Individual	$0	$0		$1,882,404		$1,882,404	$57,596		$57,596			$0			$0			$0			$0			$0	$1,940,000		$1,700,000		$1,700,000			$0			$0			$0			$0			$0	$1,700,000	$1,190,000		$1,190,000	$510,000		$510,000			$0			$0			$0			$0	$1,700,000			$0			$0			$0			$0			$0			$0				$0	$1,700,000		$1,700,000			$0			$0			$0			$0			$0	$1,700,000
1		98026	Launch Capability Program (LCP)	Execute	Jim Neeleman	Launch and Commercial Excellence	Tech Transfers	N/A	$0	$0			$800,000	$800,000			$0			$0			$0			$0			$0			$0	$800,000			$800,000	$800,000			$0			$0			$0			$0			$0	$800,000		$800,000	$800,000			$0			$0			$0			$0			$0	$800,000			$0			$0			$0			$0			$0			$0				$0		$800,000	$800,000			$0			$0			$0			$0			$0	$800,000
1		74525	CIP Reliability and Efficiency - PI	Idea	#N/A	Reliability and Value	#N/A	Individual	$0	$0			$0	$0			$0			$0	$0		$0			$0			$0			$0	$0			$400,000	$400,000	$1,000,000		$1,000,000	$2,000,000		$2,000,000	$1,000,000		$1,000,000			$0			$0	$4,400,000			$0			$0			$0			$0			$0			$0	$0			$0			$0			$0	$1,000,000		$1,000,000	$2,000,000		$2,000,000	$1,000,000		$1,000,000				$4,000,000		$400,000	$400,000	$1,000,000		$1,000,000	$2,000,000		$2,000,000	$1,000,000		$1,000,000			$0			$0	$4,400,000
1	FAE	65005	Analytical Scale	Execute	Scott Fields	Reliability and Value	New Technologies	Global	$0	$0		$24,238		$24,238			$0			$0			$0			$0			$0			$0	$24,238					$24,238		$24,238			$0			$0			$0			$0			$0	$24,238			$0			$0			$0			$0			$0			$0				$0
1	FAE	65009	Drum Mover/Raw Material Tenderizer	Execute	Jim Neeleman	Highly Capable Workforce	SHE and K-Directives	Global	$0	$0		$30,000	$4,000	$34,000			$0			$0			$0			$0			$0			$0	$34,000			$25,000	$25,000			$0			$0			$0			$0			$0	$25,000	$30,000	$4,000	$34,000			$0			$0			$0			$0			$0	$34,000			$0			$0			$0			$0			$0			$0				$0		$25,000	$25,000			$0			$0			$0			$0			$0	$25,000
1	FAE	65020	QC Auto-Pipettor for Potency Assay	Execute	Melanie Yevilov	Reliability and Value	SHE and K-Directives	Global	$0	$0		$27,987		$27,987			$0			$0			$0			$0			$0			$0	$27,987					$27,987		$27,987			$0			$0			$0			$0			$0	$27,987			$0			$0			$0			$0			$0			$0				$0
1	FAE	65023	QC Plate Washer for Potency Assay	Execute	Jim Neeleman	Launch and Commercial Excellence	New Technologies	Global	$0	$0		$56,795		$56,795			$0			$0			$0			$0			$0			$0	$56,795					$56,795		$56,795			$0			$0			$0			$0			$0	$56,795			$0			$0			$0			$0			$0			$0				$0
1	FAE	65018	Spare Bowl for Hermetic Centrifuge	Execute	Zaymar Sedra	Fit for Purpose	Improvements and Efficiencies	Global	$0	$0		$320,000		$320,000			$0			$0			$0			$0			$0			$0	$320,000					$320,000		$320,000			$0			$0			$0			$0			$0	$320,000			$0			$0			$0			$0			$0			$0				$0
1	FAE	65015	Lower Solid Collector for Centrifuge	Execute	Scott Fields	Reliability and Value	Improvements and Efficiencies	Global	$0	$0		$142,000		$142,000			$0			$0			$0			$0			$0			$0	$142,000					$245,000		$245,000			$0			$0			$0			$0			$0	$245,000			$0			$0			$0			$0			$0			$0				$0
1	FAE	65024	Sci&Eng Lab Incubator and Freezer Asset Replacement	Execute	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Global	$0	$0		$129,028		$129,028			$0			$0			$0			$0			$0			$0	$129,028					$140,000		$140,000	$488,779		$488,779			$0			$0			$0			$0	$628,779			$0			$0			$0			$0			$0			$0				$0
0	FAE	96169	Level Indicator Transmitters	Idea	Zaymar Sedra	Fit for Purpose	New Technologies	Global	$0	$0		$70,000		$70,000			$0			$0			$0			$0			$0			$0	$70,000					$70,000		$70,000			$0			$0			$0			$0			$0	$70,000
1		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	Execute	Jim Neeleman	Reliability and Value	Stay in Business	Individual	$0	$0		$306,000		$306,000	$654,000		$654,000			$0			$0			$0			$0			$0	$960,000					$306,000		$306,000	$654,000		$654,000			$0			$0			$0			$0	$960,000
1	FAC	65044	Additional MCS Backup Storage	Execute	Scott Fields	Reliability and Value	Improvements and Efficiencies	Global	$0	$0		$62,000		$62,000			$0			$0			$0			$0			$0			$0	$62,000					$62,000		$62,000			$0			$0			$0			$0			$0	$62,000
1	FAE	65037	Analytical Scales (CAPA1150248)	Execute	Scott Fields	Reliability and Value	New Technologies	Global	$0	$0		$23,997		$23,997			$0			$0			$0			$0			$0			$0	$23,997					$23,914		$23,914			$0			$0			$0			$0			$0	$23,914
1	FAC	96174	Fall Protection Phase II	CA Routing	TBD	TBD	SHE and K-Directives	Global	$0	$0		$130,000		$130,000	$5,000		$5,000			$0			$0			$0			$0			$0	$135,000					$135,000		$135,000			$0			$0			$0			$0			$0	$135,000
1	FAE	65040	Sci&Eng Cryofreezer	Execute	Jim Neeleman	Launch and Commercial Excellence	Stay in Business	Global	$0	$0		$20,185		$20,185			$0			$0			$0			$0			$0			$0	$20,185					$20,185		$20,185			$0			$0			$0			$0			$0	$20,185
1	FAE	65048	Process Maintenance Boroscope	Execute	Jim Neeleman	Reliability and Value	Stay in Business	Global	$0	$0		$35,008		$35,008			$0			$0			$0			$0			$0			$0	$35,008					$37,000		$37,000			$0			$0			$0			$0			$0	$37,000
0		96177	Efficiency Projects	Placeholder	Scott Fields	Reliability and Value	Improvements and Efficiencies	Individual	$0	$0				$0	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000			$0	$15,000,000					$0	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000		$3,000,000	$15,000,000
0		96178	Process VSD and SOV Replacement - Phase 2				Stay in Business	Individual					$0			$0	$2,500,000		$2,500,000	$3,000,000		$3,000,000			$0			$0			$0	$5,500,000					$0			$0	$2,500,000		$2,500,000	$3,000,000		$3,000,000			$0			$0	$5,500,000
0		96179	Process VSD and SOV Replacement - Phase 3				Stay in Business	Individual					$0			$0			$0	$458,000		$458,000	$5,000,000		$5,000,000			$0			$0	$5,458,000					$0			$0			$0	$458,000		$458,000	$5,000,000		$5,000,000			$0	$5,458,000
0		96180	TMAC Waste System Improvements				Stay in Business	Individual					$0	$1,500,000		$1,500,000			$0			$0			$0			$0			$0	$1,500,000					$0	$1,500,000		$1,500,000			$0			$0			$0			$0	$1,500,000
0	FAC	96181	Fall Protection Phase III				SHE and K-Directives	Global					$0	$130,000	$20,000	$150,000			$0			$0			$0			$0			$0	$150,000					$0	$100,000		$100,000			$0			$0			$0			$0	$100,000
0	FAC	96183	Site Signage Upgrade				Stay in Business	Global					$0	$175,000	$25,000	$200,000			$0			$0			$0			$0			$0	$200,000					$0	$200,000		$200,000			$0			$0			$0			$0	$200,000			$0			$0			$0			$0			$0			$0
0		96191	Utility and Process Safety System Phase 2				Stay in Business	Individual					$0	$2,000,000		$2,000,000			$0			$0			$0			$0			$0	$2,000,000					$0	$2,000,000		$2,000,000			$0			$0			$0			$0	$2,000,000			$0			$0			$0			$0			$0			$0
0	FAC	96193	Column Packing Fall Hazard				SHE and K-Directives	Global					$0			$0			$0			$0			$0			$0			$0	$0					$0	$300,000		$300,000			$0			$0			$0			$0	$300,000
0	FAC	96201	Storm Water BMP for upper lot				Stay in Business	Global					$0	$200,000		$200,000			$0			$0			$0			$0			$0	$200,000					$0	$200,000		$200,000			$0			$0			$0			$0	$200,000
0		96204	322 MRO Racks				SHE and K-Directives	Individual					$0	$500,000		$500,000			$0			$0			$0			$0			$0	$500,000					$0	$500,000		$500,000			$0			$0			$0			$0	$500,000
1	FAC	96207	Weigh and Dispense Sink (CAPA1123109)				Stay in Business	Global				$150,000	$15,000	$165,000			$0			$0			$0			$0			$0			$0	$165,000					$25,000	$5,000	$30,000			$0			$0			$0			$0			$0	$30,000			$0			$0			$0			$0			$0			$0
1	FAE	65082	RF Sealer Generator				TBD	Global				$22,000		$22,000			$0			$0			$0			$0			$0			$0	$22,000					$17,250		$17,250			$0			$0			$0			$0			$0	$17,250
0	FAE	96209	Harvest Depth Filter Installation Tool					Global					$0	$100,000		$100,000			$0			$0			$0			$0			$0	$100,000
0		96210	P2 User Furnished Equipment Procurement					Individual				$950,000	$150,000	$1,100,000	$950,000	$150,000	$1,100,000			$0			$0			$0			$0			$0	$2,200,000
0		96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting					Individual					$0	$500,000	$500,000	$1,000,000			$0			$0			$0			$0			$0	$1,000,000
0		96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000					Individual					$0	$500,000	$50,000	$550,000			$0			$0			$0			$0			$0	$550,000
0		96213	Replacement of Obsolete Benchtop Horiba pH Meter					Individual					$0	$1,000,000	$200,000	$1,200,000			$0			$0			$0			$0			$0	$1,200,000
0	FAE	96215	20L Bioreactors and NovaFlex Analyzer					Global				$450,000		$450,000			$0			$0			$0			$0			$0			$0	$450,000
0	FAE	96216	Frit Handling and Storage Phase 2					Global				$50,000		$50,000			$0			$0			$0			$0			$0			$0	$50,000
0	FAE	96217	Pallet Wrapper					Global					$0	$50,000		$50,000			$0			$0			$0			$0			$0	$50,000
0	FAC	96218	Column Maintenance Platform Installation					Global				$75,000		$75,000	$100,000		$100,000			$0			$0			$0			$0			$0	$175,000
0		96219	Harvest Filter Housing A Removal/Installation Improvements	FXNL LT Appr		Highly Capable Workforce	Improvements and Efficiencies	Individual					$0	$400,000	$100,000	$500,000			$0			$0			$0			$0			$0	$500,000					$0			$0			$0			$0			$0			$0
0	FAE	96220	400L Mixing Vessel					Global				$320,000	$20,000	$340,000	$50,000	$12,000	$62,000			$0			$0			$0			$0			$0	$402,000
0		96221	Corrosive Chemical Compliance - CUB and Warehouse	FXNL LT Appr		Reliability and Value	SHE and K-Directives	Individual					$0	$2,900,000		$2,900,000	$20,000		$20,000			$0			$0			$0			$0	$2,920,000					$0			$0			$0			$0			$0			$0
0		96222	Pressure Safety Program - Mechanical	FXNL LT Appr		Highly Capable Workforce	SHE and K-Directives					$0	$2,000,000		$2,000,000			$0			$0			$0			$0			$0	$2,000,000					$0			$0			$0			$0			$0			$0
0		96223	Pressure Safety Program - Automation	FXNL LT Appr		Highly Capable Workforce	SHE and K-Directives					$0			$0	$2,500,000		$2,500,000			$0			$0			$0			$0	$2,500,000					$0			$0			$0			$0			$0			$0
0		96224	Tangential Flow Filtration Cassettes Management	#N/A	#N/A	#N/A	#N/A	#N/A	$0	$0				$0		$1,030,000	$1,030,000			$0			$0			$0			$0			$0	$1,030,000				$0		$491,216	$491,216			$0			$0			$0			$0	$491,216			$0		$550,000	$550,000			$0			$0			$0			$0	$550,000			$0			$0			$0			$0			$0			$0				$0			$0		$491,216	$491,216			$0			$0			$0			$0	$491,216
0					$0
0				#N/A		#N/A	#N/A					$0					$0			$0			$0			$0			$0			$0
0	FAE	96991	Asset Replacement 2016 - Engineering (cc642)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$987,350	$19,747	$1,007,097	$500,000	$5,000	$505,000			$0			$0			$0			$0			$0	$1,512,097		$987,350	$19,747	$1,007,097			$0			$0			$0			$0			$0	$1,007,097	$987,350	$19,747	$1,007,097			$0			$0			$0			$0			$0	$1,007,097					$987,350	$19,747	$1,007,097			$0			$0			$0			$0			$0	$1,007,097
0	FAE	96992	Asset Replacement 2016 - Material Ops (cc484)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$124,000	$2,480	$126,480	$1,167,829	$10,000	$1,177,829			$0			$0			$0			$0			$0	$1,304,309		$124,000	$2,480	$126,480			$0			$0			$0			$0			$0	$126,480	$124,000	$2,480	$126,480			$0			$0			$0			$0			$0	$126,480					$124,000	$2,480	$126,480			$0			$0			$0			$0			$0	$126,480
0	FAC	96993	Asset Replacement 2016 - Manufacturing (cc1359)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$50,375		$50,375	$365,000		$365,000			$0			$0			$0			$0			$0	$415,375		$50,375		$50,375			$0			$0			$0			$0			$0	$50,375	$50,375		$50,375			$0			$0			$0			$0			$0	$50,375					$50,375		$50,375			$0			$0			$0			$0			$0	$50,375
0	FAC	96994	Asset Replacement 2016 - Manufacturing (cc659)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$263,008	$5,260	$268,268	$157,778		$157,778			$0			$0			$0			$0			$0	$426,046		$263,008	$5,260	$268,268			$0			$0			$0			$0			$0	$268,268	$263,008	$5,260	$268,268			$0			$0			$0			$0			$0	$268,268			$0	$502,793		$502,793			$0			$0			$0			$0				$502,793	$263,008	$5,260	$268,268			$0			$0			$0			$0			$0	$268,268
0	FAE	96995	Asset Replacement 2016 - Quality (cc583)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$407,893		$407,893	$722,929		$722,929			$0			$0			$0			$0			$0	$1,130,822		$407,893		$407,893			$0			$0			$0			$0			$0	$668,893	$407,893		$407,893			$0			$0			$0			$0			$0	$407,893	$261,000		$261,000	$407,893		$407,893			$0			$0			$0			$0				$668,893	$407,893		$407,893			$0			$0			$0			$0			$0	$668,893
0	FAE	96997	Asset Replacement 2016 - Maintenance (cc1236)	FXNL LT Appr		Fit for Purpose	Stay in Business	Global				$31,233		$31,233	$56,049		$56,049			$0			$0			$0			$0			$0	$87,282		$31,233		$31,233			$0			$0			$0			$0			$0	$31,233	$31,233		$31,233			$0			$0			$0			$0			$0	$31,233			$0	$1,028,658	$10,075	$1,038,733			$0			$0			$0			$0				$1,038,733	$31,233		$31,233			$0			$0			$0			$0			$0	$31,233
0	FAE	96998	Asset Replacement 2016 - Sci&Eng (cc1198)	FXNL LT Appr		Reliable	Stay in Business	Global					$0	$201,901		$201,901			$0			$0			$0			$0			$0	$201,901				$0			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0	$0			$0	$359,226	$1,200	$360,426			$0			$0			$0			$0				$360,426			$0			$0			$0			$0			$0			$0	$0
0		96999	Site Management Adjustments (if any)				0	Individual	-$3,847,202	-$10,661,762				$0			$0			$0			$0			$0			$0			$0	-$14,508,965		-$8,348,298	$235,000	-$8,113,298			$0			$0			$0			$0			$0	-$22,622,263	-$1,487,180	-$197,487	-$1,684,667			$0			$0			$0			$0			$0	-$16,193,631	-$10,661,762		-$10,661,762	-$21,328,357		-$21,328,357			$0			$0			$0			$0				-$35,837,322	-$8,348,298	$235,000	-$8,113,298			$0			$0			$0			$0			$0	-$22,622,263
0		T	TOTAL					$25,332,463			$152,328,222	$4,229,569	$156,557,791	$134,225,032	$7,460,190	$141,685,222	$93,853,860	$18,301,282	$112,155,143	$35,509,551	$1,500,778	$37,010,328	$62,346,701	$6,574,208	$68,920,909	$32,962,644	$6,291,013	$39,253,657			$0	$580,915,512		$175,557,472	$3,085,553	$178,643,025	$140,163,999	$4,703,931	$144,867,930	$53,262,160	$1,460,980	$54,723,140	$31,735,200	$161,920	$31,897,120	$27,970,640	$97,520	$28,068,160				$516,038,841	$157,460,138	$3,639,273	$161,099,411	$149,174,690	$2,607,146	$151,781,836	$120,838,964	$1,527,068	$122,366,031	$31,492,884	$973,000	$32,465,884	$69,129,949	$340,960	$69,470,909	$35,338,117	$265,540	$35,603,657	$568,987,493	$95,955,862	$3,842,276	$99,798,138	$161,289,098	$3,644,779	$183,513,664	$103,595,053	$2,553,847	$106,148,900	$46,504,102	$858,000	$47,362,102	$31,575,000	$100,000	$31,675,000	$28,450,000	$50,000	$28,500,000				$497,714,305	$175,557,472	$3,085,553	$178,643,025	$140,163,999	$4,703,931	$144,867,930	$53,262,160	$1,460,980	$54,723,140	$31,735,200	$161,920	$31,897,120	$27,970,640	$97,520	$28,068,160				$516,038,841
0					$k
1	Expense	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Execute 1	Deidre Dunham	Reliability and Value	Stay in Business	Expense		$70,227			$866,058	$866,058		$574,661	$574,661			$0			$0			$0			$0			$0	$1,510,946			$1,180,000	$1,180,000			$0			$0			$0			$0			$0	$1,220,000		$933,708	$933,708		$781,722	$781,722			$0			$0			$0			$0	$1,785,657		$540,000	$540,000		$980,000	$980,000			$0			$0			$0			$0				$1,520,000		$1,180,000	$1,180,000			$0			$0			$0			$0			$0	$1,220,000
1	Expense	97001	Lunches	Execute	Scott Fields	Reliability and Value	Stay in Business	Expense					$4,000	$4,000		$4,000	$4,000			$0			$0			$0			$0			$0	$8,000			$5,000	$5,000			$0			$0			$0			$0			$0	$10,000		$4,000	$4,000					$0			$0			$0	$4,000		$5,000	$5,000		$5,000	$5,000					$0			$0				$10,000		$5,000	$5,000			$0			$0			$0			$0			$0	$10,000
1	Expense	97002	Office Supplies inc. Laptops	Execute	Scott Fields	Reliability and Value	Stay in Business	Expense					$45,000	$45,000		$45,000	$45,000			$0			$0			$0			$0			$0	$90,000			$50,000	$50,000			$0			$0			$0			$0			$0	$100,000		$45,000	$45,000					$0			$0			$0	$45,000		$50,000	$50,000		$50,000	$50,000					$0			$0				$100,000		$50,000	$50,000			$0			$0			$0			$0			$0	$100,000
1	Expense	97003	MFG Systems Integration Improvement Phase 1 - 2015	Execute 1	Deidre Dunham	Reliability and Value	Improvements and Efficiencies	Expense					$292,227	$292,227		$135,000	$135,000			$0			$0			$0			$0			$0	$427,227			$443,000	$443,000			$0			$0			$0			$0			$0	$458,000		$443,000	$443,000			$0			$0			$0			$0			$0	$443,000		$290,000	$290,000		$514,000	$514,000			$0			$0			$0			$0				$804,000		$443,000	$443,000			$0			$0			$0			$0			$0	$458,000
0	Expense	97005	MCS Peripheral Asset Replacement - 2018	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	Stay in Business	Expense					$0			$0		$312,000	$312,000			$0			$0			$0			$0	$312,000				$0		$312,000	$312,000			$0			$0			$0			$0	$312,000			$0		$312,000	$312,000			$0			$0			$0			$0	$312,000			$0			$0		$312,000	$312,000			$0			$0			$0				$312,000			$0		$312,000	$312,000			$0			$0			$0			$0	$312,000
0	Expense	97006	MCS Peripheral Asset Replacement - 2020	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0		$332,000	$332,000			$0			$0	$332,000				$0			$0			$0		$332,000	$332,000			$0			$0	$332,000			$0			$0			$0		$332,000	$332,000			$0			$0	$332,000			$0			$0			$0			$0		$332,000	$332,000			$0				$332,000			$0			$0			$0		$332,000	$332,000			$0			$0	$332,000
0	Expense	97063	MCS Peripheral Asset Replacement - 2022	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0			$0			$0		$351,000	$351,000	$351,000					$0			$0			$0			$0			$0	$351,000		$351,000	$351,000
1	Expense	97007	Automation System Lifecycle MCS Upgrade	Execute	Deidre Dunham	Reliability and Value	Improvements and Efficiencies	Expense					$295,781	$295,781			$0			$0			$0			$0			$0			$0	$295,781			$270,000	$270,000			$0			$0			$0			$0			$0	$270,000		$295,169	$295,169			$0			$0			$0			$0			$0	$295,169	$600,000	$300,000	$900,000	$200,000	$1,900,000	$2,100,000			$0			$0			$0			$0				$3,000,000		$270,000	$270,000			$0			$0			$0			$0			$0	$270,000
0	Expense	97008	PCS Asset Replacement - 2018	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0		$487,500	$487,500		$487,500	$487,500			$0			$0			$0	$975,000				$0			$0			$0		$975,000	$975,000		$975,000	$975,000			$0	$1,950,000			$0			$0		$487,500	$487,500		$487,500	$487,500			$0			$0	$975,000			$0			$0			$0		$975,000	$975,000		$975,000	$975,000			$0				$1,950,000			$0			$0			$0		$975,000	$975,000		$975,000	$975,000			$0	$1,950,000
0	Expense	97064	PCS Asset Replacement - 2021	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0			$0		$463,000	$463,000			$0	$463,000					$0			$0			$0			$0			$0		$463,000	$463,000	$463,000
0	Expense	97009	MES Asset Replacement - 2017	Idea	Zaymar Sedra	Fit for Purpose	Stay in Business	Expense					$0		$400,000	$400,000		$575,000	$575,000			$0			$0			$0			$0	$975,000				$0		$500,000	$500,000		$1,126,000	$1,126,000			$0			$0			$0	$1,626,000			$0		$400,000	$400,000		$575,000	$575,000			$0			$0			$0	$975,000			$0			$0			$0			$0			$0			$0				$0			$0		$500,000	$500,000		$1,126,000	$1,126,000			$0			$0			$0	$1,626,000
0	Expense	97010	MES Asset Replacement - 2020	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0		$500,000	$500,000		$525,000	$525,000			$0	$1,025,000				$0			$0			$0		$926,000	$926,000		$926,000	$926,000			$0	$1,852,000			$0			$0			$0			$0		$500,000	$500,000		$525,000	$525,000	$1,025,000			$0			$0			$0		$926,000	$926,000		$926,000	$926,000			$0				$1,852,000			$0			$0			$0		$926,000	$926,000		$926,000	$926,000			$0	$1,852,000
0	Expense	97012	Site Data Historian Asset Replacement - 2017	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	Stay in Business	Expense					$0		$366,000	$366,000			$0			$0			$0			$0			$0	$366,000				$0		$366,000	$366,000			$0			$0			$0			$0	$366,000			$0		$366,000	$366,000			$0			$0			$0			$0	$366,000			$0		$366,000	$366,000			$0			$0			$0			$0				$366,000			$0		$366,000	$366,000			$0			$0			$0			$0	$366,000
0	Expense	97013	Site Data Historian Asset Replacement - 2019	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0		$488,000	$488,000			$0			$0			$0	$488,000				$0			$0			$0		$488,000	$488,000			$0			$0	$488,000			$0			$0			$0		$488,000	$488,000			$0			$0	$488,000			$0			$0			$0		$488,000	$488,000			$0			$0				$488,000			$0			$0			$0		$488,000	$488,000			$0			$0	$488,000
0	Expense	97065	Site Data Historian Asset Replacement - 2021	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0			$0		$488,000	$488,000			$0	$488,000					$0			$0			$0			$0			$0		$488,000	$488,000	$488,000
0	Expense	97015	MCS Backup System Asset Replacement - 2017	FXNL LT Appr	Zaymar Sedra	Fit for Purpose	Stay in Business	Expense					$0		$390,000	$390,000			$0			$0			$0			$0			$0	$390,000				$0		$390,000	$390,000			$0			$0			$0			$0	$390,000			$0		$390,000	$390,000			$0			$0			$0			$0	$390,000			$0			$0		$390,000	$390,000			$0			$0			$0				$390,000			$0		$390,000	$390,000			$0			$0			$0			$0	$390,000
0	Expense	97016	MCS Backup System Asset Replacement - 2020	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0		$439,000	$439,000			$0			$0	$439,000				$0			$0			$0			$0		$439,000	$439,000			$0	$439,000			$0			$0			$0			$0		$439,000	$439,000			$0	$439,000			$0			$0			$0			$0			$0		$439,000	$439,000				$439,000			$0			$0			$0			$0		$439,000	$439,000			$0	$439,000
0	Expense	97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0		$488,000	$488,000			$0			$0			$0			$0	$488,000				$0		$488,000	$488,000			$0			$0			$0			$0	$488,000			$0			$0		$488,000	$488,000			$0			$0			$0	$488,000			$0			$0		$488,000	$488,000			$0			$0			$0				$488,000			$0		$488,000	$488,000			$0			$0			$0			$0	$488,000
0	Expense	97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020	FXNL LT Appr	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0		$488,000	$488,000			$0			$0	$488,000				$0			$0			$0			$0		$488,000	$488,000			$0	$488,000			$0			$0			$0			$0		$488,000	$488,000			$0	$488,000			$0			$0			$0			$0			$0		$488,000	$488,000				$488,000			$0			$0			$0			$0		$488,000	$488,000			$0	$488,000
0	Expense	97030	MFG Systems Integration Improvement Phase 3 - 2017	Canceled	Zaymar Sedra	Fit for Purpose	Improvements and Efficiencies	Expense					$0			$0			$0			$0			$0			$0			$0	$0				$0		$1,625,000	$1,625,000			$0			$0			$0			$0	$1,625,000			$0		$1,625,000	$1,625,000			$0			$0			$0			$0	$1,625,000			$0			$0		$1,625,000	$1,625,000			$0			$0			$0				$1,625,000			$0		$1,625,000	$1,625,000			$0			$0			$0			$0	$1,625,000
0	Expense	97031	MCS Data Analytics Asset Replacement - 2017	Idea	Zaymar Sedra	Fit for Purpose	Stay in Business	Expense					$0		$325,000	$325,000			$0			$0			$0			$0			$0	$325,000				$0		$325,000	$325,000			$0			$0			$0			$0	$325,000			$0		$325,000	$325,000			$0			$0			$0			$0	$325,000			$0			$0		$325,000	$325,000			$0			$0			$0				$325,000			$0		$325,000	$325,000			$0			$0			$0			$0	$325,000
0	Expense	97032	MCS Data Analytics Asset Replacement - 2020	Idea	Deidre Dunham	Reliable	Stay in Business	Expense					$0			$0			$0			$0		$360,000	$360,000			$0			$0	$360,000				$0			$0			$0			$0		$360,000	$360,000			$0	$360,000			$0			$0			$0			$0		$360,000	$360,000			$0	$360,000			$0			$0			$0			$0			$0		$360,000	$360,000				$360,000			$0			$0			$0			$0		$360,000	$360,000			$0	$360,000
0	Expense	97033	PCS Automated Documentation Asset Replacement	Idea	Deidre Dunham	Reliable	New Technologies	Expense					$0			$0		$325,000	$325,000			$0			$0			$0			$0	$325,000				$0			$0		$325,000	$325,000			$0			$0			$0	$325,000			$0			$0		$325,000	$325,000			$0			$0			$0	$325,000			$0			$0			$0		$325,000	$325,000			$0			$0				$325,000			$0			$0		$325,000	$325,000			$0			$0			$0	$325,000
0	Expense	97066	PCS Automated Documentation Asset Replacement - 2021	Idea	Deidre Dunham	Reliable	New Technologies	Expense					$0			$0			$0			$0			$0		$360,000	$360,000			$0	$360,000					$0			$0			$0			$0			$0		$360,000	$360,000	$360,000
0	Expense	97037	Recipe Reconfiguration Alignment for Operating Systems	FXNL LT Appr	Jim Neeleman	Launch and Commercial Excellence	Improvements and Efficiencies	Expense					$0		$250,000	$250,000		$1,500,000	$1,500,000		$1,750,000	$1,750,000			$0			$0			$0	$3,500,000				$0		$3,750,000	$3,750,000			$0			$0			$0			$0	$3,750,000			$0		$3,750,000	$3,750,000			$0			$0			$0			$0	$3,750,000			$0		$3,750,000	$3,750,000			$0			$0			$0			$0				$3,750,000			$0		$3,750,000	$3,750,000			$0			$0			$0			$0	$3,750,000
0	Expense	97038	PCS Functional Specification Development Project (CAPA 960297)	FXNL LT Appr	Deidre Dunham	Reliability and Value	Strategic	Expense					$0	$0		$500,000	$500,000		$2,250,000	$2,250,000		$2,250,000	$2,250,000		$3,000,000	$3,000,000			$0			$0	$8,000,000			$1,000,000	$1,000,000		$3,750,000	$3,750,000		$3,250,000	$3,250,000			$0			$0			$0	$8,000,000		$0	$0		$4,750,000	$4,750,000		$3,250,000	$3,250,000			$0			$0			$0	$8,000,000			$0		$2,000,000	$2,000,000		$3,000,000	$3,000,000		$3,000,000	$3,000,000			$0			$0				$8,000,000		$1,000,000	$1,000,000		$3,750,000	$3,750,000		$3,250,000	$3,250,000			$0			$0			$0	$8,000,000
0	Expense	97039	PCS Remediation for EBR Review by Exception - PI	Idea	Melanie Yevilov	Highly Capable Workforce	Improvements and Efficiencies	Expense					$0		$250,000	$250,000		$2,250,000	$2,250,000		$3,375,000	$3,375,000			$0			$0			$0	$5,875,000			$250,000	$250,000		$2,250,000	$2,250,000		$3,375,000	$3,375,000			$0			$0			$0	$5,875,000			$0		$250,000	$250,000		$2,250,000	$2,250,000		$3,375,000	$3,375,000			$0			$0	$5,875,000			$0		$500,000	$500,000		$2,250,000	$2,250,000		$3,375,000	$3,375,000			$0			$0				$6,125,000		$250,000	$250,000		$2,250,000	$2,250,000		$3,375,000	$3,375,000			$0			$0			$0	$5,875,000
0	Expense	97040	Tech Transfer: Master Data Management	FXNL LT Appr	Jim Neeleman	Launch and Commercial Excellence	Tech Transfers	Expense					$0	$0		$0	$0			$0			$0			$0			$0			$0	$0			$250,000	$250,000		$305,750	$305,750			$0			$0			$0			$0	$555,750		$0	$0			$0			$0			$0			$0			$0	$0			$0		$555,750	$555,750			$0			$0			$0			$0				$555,750		$250,000	$250,000		$305,750	$305,750			$0			$0			$0			$0	$555,750
1	Expense	97042	CRB Project Budget Estimating	Execute	Scott Fields	Reliability and Value	Improvements and Efficiencies	Expense					$250,400	$250,400		$250,400	$250,400			$0			$0			$0			$0			$0	$500,800			$360,000	$360,000			$0			$0			$0			$0			$0	$720,000		$250,400	$250,400			$0			$0			$0			$0			$0	$250,400		$360,000	$360,000		$360,000	$360,000			$0			$0			$0			$0				$720,000		$360,000	$360,000			$0			$0			$0			$0			$0	$720,000
1	Expense	97043	Travel Expenses	Execute	Scott Fields	Reliability and Value	Stay in Business	Expense					$10,000	$10,000		$10,000	$10,000			$0			$0			$0			$0			$0	$20,000			$200,000	$200,000			$0			$0			$0			$0			$0	$400,000		$10,000	$10,000			$0			$0			$0			$0			$0	$10,000		$200,000	$200,000		$200,000	$200,000			$0			$0			$0			$0				$400,000		$200,000	$200,000			$0			$0			$0			$0			$0	$400,000
1	Expense	97044	IMPACT Support	Execute	Scott Fields	Reliability and Value	Stay in Business	Expense					$8,000	$8,000		$8,000	$8,000			$0			$0			$0			$0			$0	$16,000			$12,000	$12,000			$0			$0			$0			$0			$0	$24,000		$8,000	$8,000			$0			$0			$0			$0			$0	$8,000		$12,000	$12,000		$12,000	$12,000			$0			$0			$0			$0				$24,000		$12,000	$12,000			$0			$0			$0			$0			$0	$24,000
0	Expense	97045	Site Exterior Lighting Upgrade - Title 24	FXNL LT Appr	Scott Fields	Reliability and Value	SHE and K-Directives	Expense					$100,000	$100,000		$100,000	$100,000			$0			$0			$0			$0			$0	$200,000			$200,000	$200,000			$0			$0			$0			$0			$0	$200,000		$100,000	$100,000		$100,000	$100,000			$0			$0			$0			$0	$200,000			$0			$0			$0			$0			$0			$0				$400,000		$200,000	$200,000			$0			$0			$0			$0			$0	$200,000
0	Expense	97046	Hazardous Waste Storage Bunker	Execute	Jim Neeleman	Reliable	SHE and K-Directives	Expense					$0			$0			$0			$0			$0			$0			$0	$0				$0			$0			$0			$0			$0			$0	$157,000			$0			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$157,000
0	Expense	97047	Flammable Storage Cabinets Upgrade	Execute	Jim Neeleman	Reliable	SHE and K-Directives	Expense					$0			$0			$0			$0			$0			$0			$0	$0				$0			$0			$0			$0			$0			$0	$90,000			$0			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$90,000
1	Expense	97048	Arc Flash Prevention	Execute	Melanie Yevilov	Highly Capable Workforce	SHE and K-Directives	Expense					$318,000	$318,000			$0			$0			$0			$0			$0			$0	$318,000			$318,000	$318,000			$0			$0			$0			$0			$0	$366,000		$319,456	$319,456			$0			$0			$0			$0			$0	$319,456			$0			$0			$0			$0			$0			$0				$0		$318,000	$318,000			$0			$0			$0			$0			$0	$366,000
0	Expense	97049	SIMCA Online - Downstream Application	Execute	Jim Neeleman	TBD	New Technologies	Expense					$0			$0			$0			$0			$0			$0			$0	$0				$0			$0			$0			$0			$0			$0	$327,000			$0			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$327,000
1	Expense	97053	Pressure Safety Program					Expense					$100,000	$100,000			$0			$0			$0			$0			$0			$0	$100,000					$100,000	$100,000			$0			$0			$0			$0			$0	$100,000					$100,000	$100,000			$0			$0			$0			$0			$0	$100,000
0	Expense	97054	HVAC Retro Commissioning	FXNL LT Appr	Scott Fields	Reliability and Value	Stay in Business	Expense					$0		$113,000	$113,000		$44,000	$44,000			$0			$0			$0			$0	$157,000				$0		$131,250	$131,250	$43,750		$43,750			$0			$0			$0	$175,000			$0		$113,000	$113,000		$44,000	$44,000			$0			$0			$0	$157,000			$0			$0			$0			$0			$0			$0				$0			$0		$131,250	$131,250	$43,750		$43,750			$0			$0			$0	$175,000
1	Expense	97057	Conference Room 315 Expansion	Idea	Deidre Dunham	Exceptional Culture	Improvements and Efficiencies	Expense					$150,000	$150,000			$0			$0			$0			$0			$0			$0	$150,000			$300,000	$300,000			$0			$0			$0			$0			$0	$300,000		$108,000	$108,000		$192,000	$192,000			$0			$0			$0			$0	$300,000			$0			$0			$0			$0			$0			$0				$0		$300,000	$300,000			$0			$0			$0			$0			$0	$300,000
1	Expense	97058	Parking Pavement Repair	Execute	Scott Fields	Reliability and Value	Stay in Business	Expense					$245,040	$245,040			$0			$0			$0			$0			$0			$0	$245,040			$80,000	$80,000			$0			$0			$0			$0			$0	$200,000		$245,040	$245,040			$0			$0			$0			$0			$0	$245,040			$0			$0			$0			$0			$0			$0				$0		$80,000	$80,000			$0			$0			$0			$0			$0	$200,000
1	Expense	97059	B311 & B321 Gowning Room Modifications	Execute	Zaymar Sedra	Reliability and Value	Stay in Business	Expense					$100,492	$100,492			$0			$0			$0			$0			$0			$0	$100,492				$0			$0			$0			$0			$0			$0	$0		$107,000	$107,000			$0			$0			$0			$0			$0	$107,000			$0			$0			$0			$0			$0			$0				$0			$0			$0			$0			$0			$0			$0	$0
0	Expense	97060	QC Gas Cabinet Removal	FXNL LT Appr	TBD		TBD	Expense					$75,000	$75,000			$0			$0			$0			$0			$0			$0	$75,000					$75,000	$75,000			$0			$0			$0			$0			$0	$75,000			$0			$0			$0			$0			$0			$0				$0
1	Expense	TBD	PAIR				Stay in Business	Expense					$3,102,350	$3,102,350		$4,788,348	$4,788,348			$0			$0			$0			$0			$0	$7,890,698					$3,091,211	$3,091,211		$3,000,000	$3,000,000		$3,000,000	$3,000,000			$0			$0			$0	$9,091,211
0	Expense	97062	PI- Ammonia RMP Study				TBD	Expense					$0			$0			$0			$0			$0			$0			$0	$0					$0			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0
1	Expense	97067	OCN Lean Implementation					Expense					$0		$85,000	$85,000		$40,000	$40,000			$0			$0			$0			$0	$125,000
1	Expense	97068	OCN Resource Planning and Management Tool					Expense					$0		$85,000	$85,000		$15,000	$15,000		$15,000	$15,000		$15,000	$15,000			$0			$0	$130,000
1	Expense	74524	Bioburden 2606 IPA Exhaust Improvement	Execute	Melanie Yevilov	Reliability and Value	SHE and K-Directives	Expense	$0	$0			$14,571	$14,571			$0			$0			$0			$0			$0			$0	$14,571		$12,000		$12,000	$550,000		$550,000	$550,000		$550,000			$0			$0			$0	$1,112,000		$8,519	$8,519		$550,000	$550,000			$0			$0			$0			$0	$558,519			$0			$0	$550,000		$550,000	$550,000		$550,000			$0			$0				$1,100,000	$12,000		$12,000	$550,000		$550,000	$550,000		$550,000			$0			$0			$0	$1,112,000
0	Expense	97069	Manufacturing Bullpen					$150,000	$150,000			$0			$0			$0			$0			$0			$0	$150,000
	Expense	97070	Pressure Safety Program Automation - PI					$0		$300,000	$300,000			$0			$0			$0			$0			$0	$300,000
0	Expense	97071	Pipe Labelling Improvement				Stay in Business	Expense					$0		$2,100,000	$2,100,000			$0			$0			$0			$0			$0	$2,100,000					$0	$100,000		$100,000			$0			$0			$0			$0	$100,000
0	Expense	97072	Tangential Flow Filtration Cassettes Management	FXNL LT Appr	Scott Fields	Reliability and Value	Improvements and Efficiencies	Individual	$0	$0				$0		$1,030,000	$1,030,000			$0			$0			$0			$0			$0	$1,030,000				$0		$491,216	$491,216			$0			$0			$0			$0	$491,216			$0		$550,000	$550,000			$0			$0			$0			$0	$550,000			$0			$0			$0			$0			$0			$0				$0			$0		$491,216	$491,216			$0			$0			$0			$0	$491,216
				$0			$0			$0			$0			$0			$0			$0	$0					$0			$0			$0			$0			$0			$0				$0
	Expense	97999	Site Management Adjustments (if any)					$0			$0			$0			$0			$0			$0	$0			-$2,125,000	-$2,125,000			$0			$0			$0			$0			$0	$0			$0			$0			$0			$0			$0			$0	$0			$0					$0			$0			$0			$0				$0		-$2,125,000				$0			$0			$0			$0			$0	$0
		E	TOTAL					#REF!			$0	$6,126,919	$6,126,919	$0	$12,109,409	$12,109,409	$0	$8,286,500	$8,286,500	$0	$8,365,500	$8,365,500	$0	$5,134,000	$5,134,000	$0	$1,836,000	$1,836,000			$351,000	$42,279,555		$0	$2,918,000	$5,043,000	$0	$14,684,216	$14,684,216	$43,750	$8,076,000	$8,119,750	$0	$2,721,000	$2,721,000	$0	$3,188,000	$3,188,000				$36,139,966	$0	$6,134,984	$6,134,984	$0	$16,904,722	$16,904,722	$0	$10,419,500	$10,419,500	$0	$4,682,500	$4,682,500	$0	$1,787,000	$1,787,000	$351,000	$1,836,000	$2,187,000	$42,185,933	$600,000	$2,362,000	$2,962,000	$200,000	$13,447,750	$13,647,750	$0	$8,390,000	$8,390,000	$0	$9,089,000	$9,089,000	$0	$2,233,000	$2,233,000	$0	$1,775,000	$1,775,000				$38,681,750	$0	$2,918,000	$5,043,000	$0	$14,684,216	$14,684,216	$43,750	$8,076,000	$8,119,750	$0	$2,721,000	$2,721,000	$0	$3,188,000	$3,188,000				$36,139,966

				158,198,969	4,302,704	162,501,674	137,880,458	7,460,190	146,801,086	93,985,860	18,301,282	117,782,592	35,509,551	1,500,778	43,200,523	62,830,701	6,574,208	75,730,123	40,326,644	6,291,013	46,617,657			7,364,000	713,577,374

				$23,574,540		162501673.6

## 2015_Budget_BY_YEAR
			BUDGET REPORTS BY YEAR
			2015
								2014					2015					2016					2017					2018					2019					2020
								T0			MO5			T3				T0			MO5			T3				T0			MO5			T3				T0			MO5			T3				T0			MO5			T3				T0			MO5			T3				T0			MO5			T3
		Global Type	CA No.	Project Title	Status	PMO Lead	SME	Credit Type	Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total		Capital	Expense	Total	Capital	Expense	Total	Capital	Expense	Total

		FAE	6DM	GNE Oceanside Prod Ops				Global Bucket	#REF!	#REF!	#REF!	$612,740	$0	$612,740	$372,740	$0	$372,740		#REF!	#REF!	#REF!	$1,195,000	$0	$1,195,000	$995,000	$0	$995,000		$3,562,007	$50,850	$3,612,857			$1,230,000			$1,230,000		$3,523,427	$0	$3,523,427			$1,270,000			$1,270,000		$0	$0	$0			$1,305,000			$1,305,000		$0	$0	$0			$1,345,000			$1,345,000		$0	$0	$0
		FAC	90024	NIMO Small Projects - Misc				Global Bucket	#REF!	#REF!	#REF!	$3,107,568	$624,000	$3,731,568	$1,762,568	$200,000	$1,962,568		#REF!	#REF!	#REF!	$5,405,933	$387,000	$5,792,933	$4,605,933	$387,000	$4,992,933		$2,308,740	$22,286	$2,331,026			$5,790,749			$5,790,749		$132,000	$0	$132,000			$5,785,440			$5,785,440		$132,000	$0	$132,000			$5,786,069			$5,786,069		$0	$0	$0			$5,805,000			$5,805,000		$484,000	$0	$484,000
								#REF!	#REF!	#REF!					0	0	0					0	0	0					0	0	0					0	0	0					0	0	0
		FAE	64643	Microscopic Visual Examination (MVE) Implemenmtation	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$13,000	$0	$13,000	$13,000	$0	$13,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73316	20L Bionet Cabinet	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$35,000	$0	$35,000	$35,000	$0	$35,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73323	Stainless Steel HMI Replacement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$55,000	$90,000	$145,000	$55,000	$90,000	$145,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73325	Agitator Seal Reliability	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$18,000	$0	$18,000	$17,000	$0	$17,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73328	Filter Integrity Testers	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$900,000	$50	$900,050	$1,106,000	$0	$1,106,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73337	Support Equipment to Delta V	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$760,000	$5,000	$765,000	$760,000	$5,000	$765,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73345	Autoclave Optimization	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$80,000	$0	$80,000	$87,000	$0	$87,000		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73350	BMS (MCS) Upgrades	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$493,000	$0	$493,000	$412,000	$0	$412,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73355	CAPA 732540 - Agitator Mechanical Seal Flush	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$169,438	$0	$169,438	$180,000	$0	$180,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73356	BDU Supplemental BDU Sampling	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Execute 2	Greg Crecely	Individual	#REF!	#REF!	#REF!	$2,721,431	$0	$2,721,431	$997,212	$0	$997,212		#REF!	#REF!	#REF!	$0	$0	$0	$1,937,957	$13,608	$1,951,565		$157,774	$0	$157,774			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73361	Demand Flow CW VSD Upgrades	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$877,749	$0	$877,749	$800,300	$0	$800,300		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73363	Bioreactor Piping Corrections (CAPA)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$167,000	$0	$167,000	$135,000	$6,000	$141,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73364	Fall Protection Improvement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$204,000	$0	$204,000	$169,000	$0	$169,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73366	MCS (PCS and MES) System Access and Account Management Enhancement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$190,000	$0	$190,000	$174,000	$0	$174,000		#REF!	#REF!	#REF!	$0	$0	$0	$46,000	$0	$46,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P56	OCN B300 PCS Automated Documentation (DeltaV)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$530,000	$0	$530,000	$0	$0	$0		#REF!	#REF!	#REF!	$120,000	$0	$120,000	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73368	Cooling Tower Water Filtration System	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$698,082	$0	$698,082	$590,000	$0	$590,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73348	Freeze Thaw Skids, Return HTF Filter	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$37,000	$37,000	$37,000	$0	$37,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74111	Debottlenecking	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$4,739,264	$100,495	$4,839,759	$3,882,816	$91,000	$3,973,816		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74119	Harvest Modifications (New Hermetic Centrifuge)	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Execute 2	N/A	Individual	#REF!	#REF!	#REF!	$500,000	$0	$500,000	$410,600	$19,483	$430,083		#REF!	#REF!	#REF!	$7,083,500	$137,500	$7,221,000	$5,884,293	$279,216	$6,163,509		$4,614,221	$21,631	$4,635,852			$7,221,000	$3,945,285	$187,208	$4,132,493		$7,236,886	$51,254	$7,288,140			$0	$195,988	$9,300	$205,288		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74126	Debottlenecking Start-up	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$8,237,336	$293,577	$8,530,913	$8,194,000	$127,000	$8,321,000		#REF!	#REF!	#REF!	$0	$0	$0	$55,000	$0	$55,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74127	Harvest Modifications Start-up		Budgeted	Rich Johnson	Start-up	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$125,000	$0	$125,000			$800,000			$800,000		$2,275,000	$0	$2,275,000			$1,600,000			$1,600,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74162	TDS Remediation	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$223,910	$0	$223,910		#REF!	#REF!	#REF!	$0	$0	$0	$4,254,284		$4,254,284		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74198	3k Solera	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$90,000	$0	$90,000	$72,000	$0	$72,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74241	Delta V PCS	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$95,000	$2,000	$97,000	$98,000	$2,000	$100,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74244	Cell Culture Sampling - NovaFlex	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$900,000	$0	$900,000	$425,358	$10,000	$435,358		#REF!	#REF!	#REF!	$600,000	$0	$600,000	$1,247,171	$65,000	$1,312,171		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74246	G6 Tech Transfer	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$2,354,000		$2,354,000	$1,591,502	$50,000	$1,641,502		#REF!	#REF!	#REF!	$7,750,000	$120,000	$7,870,000	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74255	Purification Spare Columns	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74265	Harvest Depth Filtration	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$800,000	$0	$800,000	$835,000	$0	$835,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	74268	P2 Downstream Processing Expansion	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Execute 2	Dirk Ellison	Individual	#REF!	#REF!	#REF!	$11,550,000	$550,000	$12,100,000	$9,639,330	$969,413	$10,608,743		#REF!	#REF!	#REF!	$63,700,000	$1,000,000	$64,700,000	$96,449,117	$4,201,821	$100,650,938		$91,862,606	$1,766,871	$93,629,477			$44,330,917	$75,911,683	$3,254,747	$79,166,430		$33,364,075	$916,060	$34,280,135			$234,619	$3,278,880	$365,709	$3,644,589		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74275	WFI Still Drive Upgrade	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$85,000	$0	$85,000	$85,000	$0	$85,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74277	P2 DPE Start-Up	Site support for the design, testing for the engineering runs, plant time for 12 runs, and materials that can be used for both engineering runs and qualification runs. The ISD is based on licensure of the potential product candidates for OCN according to the CMContinuum Designated Launch Facility Strategy.	Execute	Rich Johnson	Start-up	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$4,461,207	$0	$4,461,207			$8,000,000			$8,000,000		$40,280,925	$0	$40,280,925			$43,500,000			$43,500,000		$6,754,868	$0	$6,754,868			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74278	K6 Project Implementation - Phase 2 (-20 Freezer Compressors)	Complies with Roche K6 directive to reduce R-41A and R-22 refrigerants. Will reduce R-22 refrigerant in all cold rooms across the site by 2018 and R-404 refigerant in the main freezer by 2022. Free standing lab freezers are out fo scope.	FXNL LT Appr	TBD	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$528,000			$528,000		$528,000	$75,000	$603,000			$4,828,000			$4,828,000		$4,828,000	$0	$4,828,000			$4,828,000			$4,828,000		$4,828,000	$0	$4,828,000			$500,000			$500,000		$500,000	$0	$500,000
			74279	New Media Technology - HTST / Adventitious	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Execute 2	John Urban	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$1,080,000	$20,000	$1,100,000		#REF!	#REF!	#REF!	$0	$0	$0	$2,030,000	$120,000	$2,150,000		$4,859,034	$88,096	$4,947,130			$0	$6,015,000	$35,000	$6,050,000		$1,553,492	$37,670	$1,591,162			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74280	Hasstelloy Columns	Project reduces risk to 5 day PCO my mitigating operation risk at ProA step for both Actemra and Rituxan campaigns. To maintain run rate of 3.p rpw a 3rd column needs to be packed to support the ProA step. With this project the risk of not achieving 5 day PCO is minimized.	Execute	John Urban	Individual	#REF!	#REF!	#REF!	$800,000	$0	$800,000	$802,000	$0	$802,000		#REF!	#REF!	#REF!	$1,700,000	$10,000	$1,710,000	$1,697,000	$1,000	$1,698,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74281	Automation Lifecycle Projects	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$2,344,000	$0	$2,344,000	$2,344,000		$2,344,000		$0	$0	$0			$937,600			$937,600		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74302	Waterpooling Remediation	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Execute 2	John Urban	Individual	#REF!	#REF!	#REF!	$3,165,000	$25,000	$3,190,000	$3,165,000	$25,000	$3,190,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$369,680	$0	$369,680			$0			$0		$50,426	$0	$50,426			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74303	Mezzanine Lifts - MP BP Ferm	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P57	PCS Development and Validation Environments Capacity Expansion (DeltaV)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$625,000	$0	$625,000	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74369	PCS (Delta V) Upgrade (Lifecycle)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$800,000			$700,000		$0	$0	$0			$200,000			$300,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74370	New Media Technology -Adventitious ($1M 2014)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$1,000,000	$50,000	$1,050,000	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74371	Waste Water Recovery System and Odor Treatment	Strategic project to detoxify/purify the water and reuse it in the different processes as conservation plan.	FXNL LT Appr	Jim Koons	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$100,000	$0	$100,000	$100,000		$100,000		$0	$0	$0			$1,000,000			$1,000,000		$0	$0	$0			$4,000,000			$4,000,000		$750,000	$0	$750,000			$0			$0		$4,250,000	$500,000	$4,750,000			$0			$0		$0	$0	$0
			74372	Solar Power System	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$2,000,000	$0	$0	$2,000,000		$0	$0	$0			$8,000,000			$8,000,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74373	3rd RO/DI/WFI System	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Execute 2	Jim Koons	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$1,343,000		$1,343,000		#REF!	#REF!	#REF!	$0	$0	$0	$5,408,121		$5,408,121		$5,512,468	$23,739	$5,536,207			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$4,400,000			$0		$0	$0	$0			$6,600,000			$0		$0	$0	$0
			74374	Process Data Analytics	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$950,000	$0	$950,000	$950,000		$950,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74375	EBR Review By Exception Project - MES/EBR Remediation - 2016	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$675,000	$0	$675,000	$675,000		$675,000		$0	$0	$0			$675,000			$675,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74376	Paperless Sys Val Lifecycle Mgm	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$200,000			$200,000		$0	$0	$0			$1,800,000			$1,800,000		$0	$0	$0			$1,000,000			$1,000,000		$0	$0	$0
			74377	Maintenance and PCO Recipes	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$300,000			$300,000		$0	$0	$0			$200,000			$200,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74378	Automation Proximity Switch Additions to Manufacturing Areas	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$100,000			$100,000		$0	$0	$0			$200,000			$200,000		$0	$0	$0			$200,000			$200,000		$0	$0	$0			$0			$0		$0	$0	$0
			74379	New Media Technology -HTST	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$7,000,000	$75,000	$7,075,000	$0	$0	$0		$0	$0	$0			$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74380	MES (Syncade) Upgrade (Lifecycle)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$600,000			$600,000		$0	$0	$0			$150,000			$400,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74381	Dynamic BMO's	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$50,000			$50,000		$0	$0	$0			$300,000			$300,000		$0	$0	$0			$150,000			$150,000		$0	$0	$0			$0			$0		$0	$0	$0
			74382	Sci&Eng Lab Mods and Equipment	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Execute 2	Greg Crecely	Individual	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$3,400,000	$0	$3,400,000	$8,000,000		$8,000,000		$7,414,885	$195,338	$7,610,223			$10,200,000			$5,600,000		$390,885	$0	$390,885			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74383	Vent Housings (six) on Production Bioreactors	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$1,000,000	$0	$1,000,000			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74384	Replace V3025 with new vessel	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$300,000	$0	$300,000			$0		$0	$0	$0			$4,000,000					$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74385	Media Prep Endotoxin/Bioburden Sampling	Risk of microbial contamination exists in media prep operations for cell culture media. Contaminants can have a negative impact on product output, product quality and patient safety. facilities. Fail to comply with the committment could result in regulatory. The expected benefit of routine monitoring of bioburden and endotoxin is action. that cell culture media can be confirmed to be free of harmful levels of bacteria, exotoxins and endotoxins. This future state results in increased patient safety, improved undestanding and microbial control of open process.	Hold	Greg Crecely	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$1,500,000	$0	$1,500,000	$0	$0	$0		$0	$0	$0			$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74386	4040 Avenida Conference Center	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$5,000,000	$100,000	$5,100,000	$2,500,000	$100,000	$2,600,000		#REF!	#REF!	#REF!	$0	$250,000	$250,000	$2,500,000	$250,000	$2,750,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	76427	Actemra G6 Start-up	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		#REF!	#REF!	#REF!	$64,400,000	$0	$64,400,000	$0	$0	$0		$0	$0	$0			$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	76585	Fan Wall Implementation	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$359,730	$30,000	$389,730	$359,550	$30,000	$389,550		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P10	Artificial Turf	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$190,000	$190,000			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P11	CRB Project Budget Estimating	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$75,000	$75,000			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0		$178,000			$0	$0	$0			$0					$0	$0	$0
		FAC	P13	Travel Expenses	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$180,000	$180,000			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P14	IMPACT Support	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$12,000	$12,000			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0		$12,000			$0	$0	$0			$0					$0	$0	$0
		FAC	P22	WFI Pump Autostart	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0	$239,000		$239,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	74404	Mezzanine Lift Media Prep: Phase 1B	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Execute	Tucker Creighton	Individual	#REF!	#REF!	#REF!	$300,000	$0	$300,000	$657,000	$0	$657,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$270,440	-$431	$270,009			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73383	Actemra Freezer Installation	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$250,000		$250,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P25	TMAC Re-design	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0		$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P29	Microbial Risk Assessment CAPAs(500k)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$62,400	$0	$62,400			$0		#REF!	#REF!	#REF!	$0	$0	$0		$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P32	Automate Centrifuge Shot Volume	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$308,000	$10,000	$318,000			$0		#REF!	#REF!	#REF!	$0	$0	$0	$308,000	$10,000	$318,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P36	Functional Specification Development Project	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$246,000	$0	$246,000	$0	$0	$0		#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P38	Automation LifeCycle - PDFX Lab DeltaV Upgrade	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$160,000	$0	$160,000		$0	$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P39	Automation LifeCycle - (PI) Upgrade and Event Migration	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$210,000	$0	$210,000		$0	$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P40	GWR 1080/1090	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0	$170,000	$10,000	$180,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	76643	Optimize Column Movement Device	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Execute	John Urban	Global	#REF!	#REF!	#REF!	$320,000	$0	$320,000	$320,000	$0	$320,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$143,425	$0	$143,425			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	64645	Sievers TOC Analyzers	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$105,000	$0	$105,000	$105,000	$0	$105,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P45	Ion Chromatogram Replacement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$97,200	$0	$97,200	$250,000	$0	$250,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P46	Refrigerators for Microbiology	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$22,540	$0	$22,540	$22,540	$0	$22,540		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P47	Incubators for Microbiology	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$17,500	$0	$17,500	$17,500	$0	$17,500		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P48	Turbidmeter	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$5,000	$0	$5,000	$5,000	$0	$5,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P49	20c Freezers	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$32,500	$0	$32,500	$32,500	$0	$32,500		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P50	Parking Lot Lighting Upgrade	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P51	Site Specification Update	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			76642	AV System and Equipment Refresh	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$200,000		$200,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			73367	FS & DS Automation Integration	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Execute 2	John Urban	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$816,000	$0	$816,000		#REF!	#REF!	#REF!	$0	$0	$0	$115,000	$0	$115,000		$26,719	$0	$26,719			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74368	Dev/Val Automation Capacity Expansion	The DEL/VAL system expansion in order to increase the amount of project work, reduce delays in projects, allow MAR charges that correct current automation issues. Evaluation of system indicated we will fall short of required resources for MAR work with upcoming projects.	Execute	Greg Crecely	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$592,000	$0	$592,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$10,000	$0	$10,000			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P58	PDFX Lab DeltaV Upgrade and (PI) Upgrade and Event Migration	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$0		$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	64709	MES Load Balanceers (F5)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$44,000	$11,000	$55,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	73379	Electric Cart Replacement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$39,000	$0	$39,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P61	Tower Secondary Containment	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$120,000		$120,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	74392	Water Reclaim System	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Execute	Jim Koons	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$176,000	$0	$176,000		#REF!	#REF!	#REF!	$0	$0	$0	$3,335,304		$3,335,304		$143,846	$0	$143,846			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAC	P65	Ventilation Installation in QC Lab	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$150,000	$0	$150,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	74417	Fall Protection (Clean Space)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$500,000		$500,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	64777	Biosafety Hood & Laminar Flow Hood QC Asset Replac.	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$99,000		$99,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P68	Lab Office 2006 QC Asset Replac.	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$460,000		$460,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
		FAE	P69	Warehouse Left Asset Replac.	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$63,000		$63,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			64786	Cedex System for Sci&Eng Asset Replacement	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$177,000		$177,000		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74406	Corrosive Chemical Compliance	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Execute	Jim Koons	Individual	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0	$1,300,000		$1,300,000		$1,724,239	$0	$1,724,239			$0			$0		$83,733	$0	$83,733			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74413	OCN MES Enhacement Project	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$250,000	$0	$250,000	$250,000		$250,000		$0	$0	$0			$500,000			$500,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74407	CUB Expansion for New WFI Still and Storage Tank	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$317,000		$317,000		#REF!	#REF!	#REF!	$0	$0	$0	$2,849,723		$2,849,723		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74409	Replace DX Units	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Execute	John Urban	Individual	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$310,000	$22,000	$332,000			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74416	Asphyxiant Gas Engineering Improvements and Detection	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Execute 1	Marcus Espinoza	Individual	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0	$925,000		$925,000		$126,295	$0	$126,295			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74408	VSD Upgrade	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0			$0		#REF!	#REF!	#REF!	$0	$0	$0	$927,000		$927,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74418	QC Lab Reconfiguration & Equipment	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Execute 1	Greg Crecely	Individual	#REF!	#REF!	#REF!	$0	$0	$0	$232,000		$232,000		#REF!	#REF!	#REF!	$0	$0	$0	$4,403,574		$4,403,574		$3,160,674	$114,000	$3,274,674			$0			$0		$289,726	$0	$289,726			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P78	Add New 3rd HCCF Vessels	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$154,173	$7,316	$161,489		#REF!	#REF!	#REF!	$0	$0	$0	$2,226,349	$105,643	$2,331,992		$0	$0	$0			$0	$1,491,977	$70,796	$1,562,773		$0	$0	$0			$0	$74,116	$3,517	$77,633		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			P79	Seed Lab (Six 20L Bioreactors)	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!	$0	$0	$0	$173,642	$8,239	$181,881		#REF!	#REF!	#REF!	$0	$0	$0	$2,497,260	$118,498	$2,615,758		$0	$0	$0			$0	$1,673,971	$79,432	$1,753,403		$0	$0	$0			$0	$83,157	$3,946	$87,103		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
			74427	MCS Network Infrastructure Upgrade - 2016	The Network is the backbone of the Manufacturing Control System (MCS). The infrastructure must be kept up to date to avoid downtime. Lifecycle for equipment is 5 - 7 years. Last replacement was 2009. Project implementation requires shutdown.	Execute	John Urban	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$1,466,000	$0	$1,466,000					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P81	MCS Manufacturing Area Wireless Access Point Upgrade - 2015	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74426	Process VSD and SOV Replacement - 2015	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Execute	Tucker Creighton	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$589,735	$0	$589,735					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74428	PCS Process Support Equipment Automation (PLC) Upgrade - 2015	Per site prioritization, this project is necessary to support high run rates at OCN, Currently, the skids are in paper records and do not support release by exception.	FXNL LT Appr	Tucker Creighton	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!	$0	$0	$0			$0		$0	$0	$0			$0			$0		$0	$200,000	$200,000			$0			$0		$900,000	$0	$900,000			$0			$0		$900,000	$0	$900,000			$0			$0		$935,000	$0	$935,000
			74429	Mettler Toledo Weight Transmitter conversion to Hardy Weight Transmitter - 2015	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Execute	Tucker Creighton	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$204,573	$0	$204,573					$23,445	$0	$23,445					$0	$0	$0					$0	$0	$0					$0	$0	$0
			73377	Upstream Capacity Buildout	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					$2,378,222	$2,378,222		#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P85	HPLC Upgrade Kits	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			73384	Caustic Bath Upgrade	The increased run rates, and the column packing activities require a safer, more reliable method for out of place cleaning. A safety job hazard assessment was performed comparing a score of 60 (high risk priority) for the current operation, to a score of 16 (low risk priority) for the proposed solution. / It is the right thing to do for our employees.	Execute	N/A	Global	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$459	$0	$459					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P87	Frit Handling and Storage	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P89	Reduce Air Change Rates in Warehouse	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P90	Reduce Reheat Requirements	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			64765	QC UPLC Analyzers Asset Replacement 2014	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			64773	QC UPLC Analyzers Asset Replacement 2014	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74431	Buffer Prep Mezzanine Lift Construction	Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	JPMT Appr	Tucker Creighton	Global	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$442,000	$0	$442,000					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			73388	SIMCA Online Real Time Process Monitoring System	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Execute	John Urban	Global	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			73387	MCSBACKUP Phase 2 Tape Retrieval	Phase 2 for the MCSBACKUP deployment. Need to ensure data can be retrieved and stored per GMP requirement.	Execute	John Urban	Global	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P96	Fencing Solar Power Panel Area	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74430	Automation I&C Database Remediation Project (I&C Database Migration and DCA Integration) - 2015	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74432	K6 Project Implementation - Phase 3 (Chillers)	Four (4) existing chillers in B-341 Central Utilities are not K6 compliant due to R-134A refigerant.	FXNL LT Appr	TBD	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$2,650,000	$350,000	$3,000,000					$6,650,000	$0	$6,650,000					$6,000,000	$0	$6,000,000
			74435	Chromatography Column (160cm) Asset Replacement 2015	Only one chromatography column is needed per stage to run the process. The second column is a backup to replace expired resin on the column being used. If a third packed column is not vailable, there is the risk that the second column fails while the first one is being packed. Such an issue would incapacitate production to continue.	FXNL LT Appr	Jim Koons	Individual	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$400,000	$0	$400,000					$1,149,000	$0	$1,149,000					$0	$0	$0					$0	$0	$0					$0	$0	$0
			64843	QC Potency Centrifuges and Ice Maker	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			64844	QC Ice Maker	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			74449	TDS Remediation 2015	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			73392	Automated Cooling of V-2194	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
								#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
								#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P994	Asset Replacement 2015 - Manufacturing	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P995	Asset Replacement 2015 - Quality	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P996	Asset Replacement 2015 - Technology	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P997	Asset Replacement 2015 - Facilities Ops	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P998	Asset Replacement 2015 - BMSO	#N/A	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!					#REF!	#REF!	#REF!					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0					$0	$0	$0
			P999	Site Management Adjustments (if any)	Idea	#N/A	#N/A	#N/A	#REF!	#REF!	#REF!		$0	$0	-$2,143,645		-$2,143,645		#REF!	#REF!	#REF!	-$500,000	$0	-$500,000	-$10,176,700		-$10,176,700		$0	$0	$0			-$500,000	-$500,000		-$500,000		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0			$0			$0		$0	$0	$0
0			T	TOTAL					#REF!	#REF!	#REF!	$50,098,170	$1,750,122	$51,848,292	$42,160,505	$4,012,673	#REF!		#REF!	#REF!	#REF!	-$500,000	$0	$170,952,933			#REF!		$133,956,027	$2,282,379	$136,238,407			$88,563,266			$120,976,448		$91,191,020	$1,301,984	$92,493,004			$70,468,059			$74,598,053		$16,014,868	$350,000	$16,364,868			$18,469,069			$14,069,069		$16,628,000	$500,000	$17,128,000			$15,250,000			$8,650,000		$7,919,000	$0	$7,919,000

## 2014_Resource_Plan
			RESOURCE PLAN
			2015
								2014					2015
								Q1			Q2			Q3			Q4	2014			Q1			Q2			Q3			Q4	2015		Q4	2014
			CA No.	Project Title	Credit Type	Business Driver	Total Project Cost	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	Total Resource Demand	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	PTQ	PTB	Total Resource	Total Resource Demand		Total Resource	Total Resource Demand

#REF!		#REF!	73323	Stainless Steel HMI Replacement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73328	Filter Integrity Testers	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73337	Support Equipment to Delta V	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73355	CAPA 732540 - Agitator Mechanical Seal Flush	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73356	Supplemental BDU Sampling	CTT	Stay in Business	$157,774			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73361	Demand Flow CW VSD Upgrades	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73363	Bioreactor Piping Corrections (CAPA)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73364	Fall Protection Improvement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73366	MCS (PCS and MES) System Access and Account Management Enhancement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73368	Cooling Tower Water Filtration System	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74119	Harvest Modifications (New Hermetic Centrifuge)	QSP	Strategic	$11,923,993			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74126	Debottlenecking Start-up	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74127	Harvest Modifications Start-up	QSP	Strategic	$2,400,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74162	TDS Remediation	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74244	Cell Culture Sampling - NovaFlex	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74246	G6 Tech Transfer	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74265	Harvest Depth Filtration	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74268	P2 Downstream Processing Expansion	QSP	Strategic	$127,931,932			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74275	WFI Still Drive Upgrade	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74277	P2 DPE Start-Up	QSP	Strategic	$51,497,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74278	K6 Project Implementation	CTT	SHE and K-Directives	$10,759,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	$6,415,357			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74280	Spare Hasstelloy Columns	QSP	Stay in Business				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74281	Automation Lifecycle Projects	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74302	Waterpooling Remediation	RTO	Stay in Business	$421,316			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74369	PCS (Delta V) Upgrade (Lifecycle)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74371	Waste Water Recovery System	CTT	SHE and K-Directives	$5,500,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74372	Solar Power System	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74373	New HWFI and RO-DI System	QSP	Strategic	$5,536,208			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74374	Process Data Analytics	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74375	Review By Exception Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74376	Paperless Sys Val Lifecycle Mgm	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74377	Maintenance and PCO Recipes	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74378	Automation Proximity Switch Additions to Manufacturing Areas	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74380	MES (Syncade) Upgrade (Lifecycle)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74381	MES Dynamic BOM Enhancement Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	$7,178,990			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74386	4040 Avenida Conference Center	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P22	WFI Pump Autostart	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	$200,613			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P24	Warehouse Actemra Freezer Installation	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P32	Automate Centrifuge Shot Volume	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P40	GWR 1080/1090	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P42	Optimize Column Packing Safety and Process Improvements	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P45	Ion Chromatogram Replacement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P46	Refrigerators for Microbiology	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P47	Incubators for Microbiology	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P48	Turbidmeter	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P49	20c Freezers	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P52	AV Refresh	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73367	FS & DS Automation Integration	CTT	Tech Transfers	$26,719			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	$10,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	64709	MES Load Balancers (F5)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P59	Electric Cart Replacement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74392	Water Reclaim System	CTT	SHE and K-Directives	$162,102			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	$542,115			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P65	Ventilation Installation in QC Lab	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74417	Fall Protection (Clean Space)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P67	Biosafety Hood & Laminar Flow Hood QC Asset Replac.	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P68	Lab Office 2006 QC Asset Replac.	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P69	Warehouse Lift Asset Replac.	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P70	Nova 400 for Sci&Eng Asset Replac.	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74406	Caustic Compliance	RTO	SHE and K-Directives	$1,680,036			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74413	MES Enhacement Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74407	CUB Expansion for New WFI Still and Storage Tank	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74409	Replace DX Units	CTT	SHE and K-Directives	$1,924,000			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74408	VSD Upgrade	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	$3,599,128			0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P78	Add 3rd HCCF Vessels	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P79	Seed Lab (Six 20L Bioreactors)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P80	Automation I&C Remediation Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P81	PCS Controller Cabinet UL Compliance Retrofit Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P82	MES Integration with SAP for Manufacturing Scheduling	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P83	PCS Web-Server Addition	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P84	Automation Server Virtualization Readiness Project	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P85	MCS Manufacturing Area Wireless Access Points	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P86	MCS Peripheral Upgrade	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P87	MCS Active Directory	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	73377	Upstream Buildout (PI)	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P89	Reduce Air Change Rates in Warehouse	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P90	Reduce Reheat Requirements	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P91	QC UPLC analyzers Asset Replacement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P92	GelDoc Imaging System - Asset Replacement	#N/A	#N/A				0			0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0		#REF!	#REF!
#REF!		#REF!	P93	UV-vis Spectrophtometer - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P94	Trace Oxygen Analyzer - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P95	Met One Particle Counter - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P96	LAL Reader- Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P97	Refrigerators for Microbiology Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P98	80c Freezers Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P99	Incubators - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P100	Centrifuge - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P101	LAF - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P102	HPLC Ready for Empower 3 - Asset Replacement 2015	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!	P103	Buffer Prep Mezzanine Lift Construction	#N/A	#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
		#REF!						#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!			0			0			0			0	0
#REF!		1	T	TOTAL				$0	$0	$0	$0	$0	$0	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0	$0		#REF!	#REF!

## Monthly_Cashflow_2016
	MASTER PORTFOLIO
	Monthly Cashflow - 2016
						2016
	Project No.	Project Title	Credit Type	Status	PMO Lead	SME	Estm/ / Budg?	Type of Expend.		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	2016 Current Forecast	Budget 2016
1	64901	MCS Peripheral Asset Replacement - 2015		Execute			Estm	Capital		$1k	$2k					$40k					$43k	$43k	0.0
						Estm	Expense					$k	$k	0.0
1	64914	QC M9 TOC Analyzers					Estm	Capital			$17k					$17k	$17k	0.0
						Estm	Expense					$k	$k	0.0
1	64923	QC Met-One Air Sampler Replacement 2015					Estm	Capital					$16k					$16k	$16k	0.0
						Estm	Expense					$k	$k	0.0
1	64927	QC Gel Imager Replacement 2015					Estm	Capital				$1k					$1k	$1k	0.0
						Estm	Expense					$k	$k	0.0
0	73356	Supplemental BDU Sampling	Individual	Execute 2	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Jim Neeleman	Estm	Capital		$30k	$82k	$45k					$158k	$158k	0.0
						Estm	Expense					$k	$k	0.0
0	73367	FS & DS Automation Integration	Individual	Execute 2	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Zaymar Sedra	Estm	Capital		$18k	$8k	$1k					$27k	$27k	0.0
						Estm	Expense					$k	$k	0.0
1	73384	Caustic Bath Upgrade		Execute			Estm	Capital				$k					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
1	73387	MCSBACKUP Phase 2 Tape Retrieval		Execute			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	73388	SIMCA Online Real Time Process Monitoring System	Global	Execute	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Jim Neeleman	Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
1	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Global	Execute	Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Scott Fields	Estm	Capital		$12k	$4k	$12k	$64k	$39k	$65k	$20k					$216k	$216k	0.0
						Estm	Expense					$k	$k	0.0
1	73399	Frit Handling and Storage	Global	Execute	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Melanie Yevilov	Estm	Capital		$1k		$4k		$k	$1k	$1k	$55k	$11k	$45k	$44k	$22k	$186k	$153k	33105.0
						Estm	Expense					$k	$k	0.0
1	73409	Solar Power Enabling Project		Execute			Estm	Capital		-$9k	$97k	$79k	$94k	$46k					$307k	$307k	0.0
						Estm	Expense					$k	$k	0.0
1	74119	Harvest Upgrade (New Centrifuge)	Individual	Execute 2	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Zaymar Sedra	Estm	Capital		-$1,074k	$1,175k	$716k	$232k	-$219k	$285k	$611k	$574k	$645k	$548k	$677k	$444k	$4,614k	$4,614k	0.0
						Estm	Expense		$1k	$1k	$1k	$1k	-$5k	$4k	$5k	$4k	$3k	$2k	$3k	$1k	$22k	$22k	0.0
1	74127	Harvest Modifications Start-up		Budgeted			Estm	Capital					$10k	$15k	$28k	$22k	$50k	$125k	$125k	0.0
						Estm	Expense					$k	$k	0.0
1	74268	P2 Downstream Processing Expansion	Individual	Execute 2	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Zaymar Sedra	Estm	Capital		-$3,393k	$10,209k	$4,758k	$15,251k	$6,224k	$10,521k	$10,089k	$8,566k	$9,152k	$6,675k	$8,179k	$5,633k	$91,863k	$91,863k	0.0
						Estm	Expense		$97k	$111k	$132k	$151k	$394k	$347k	$127k	$106k	$84k	$68k	$85k	$64k	$1,767k	$1,767k	0.0
0	74277	P2 DPE Start-Up		Execute			Estm	Capital				$289k	$171k	$140k	$188k	$241k	$539k	$527k	$661k	$687k	$1,018k	$4,461k	$4,461k	-1.0
						Estm	Expense					$k	$k	0.0
1	74279	New Media Technology - HTST / Adventitious	Individual	Execute 2	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Scott Fields	Estm	Capital		$166k	$136k	$111k	$654k	$440k	$393k	$530k	$386k	$337k	$596k	$573k	$537k	$4,859k	$4,859k	0.0
						Estm	Expense		$1k		$1k	$11k	$k					$38k	$38k	$88k	$88k	0.0
1	74302	Waterpooling Remediation	Individual	Execute 2	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Jim Neeleman	Estm	Capital		$8k	$19k	$k	$k	$2k	$1k	$k		$102k	$83k	$77k	$77k	$370k	$370k	-92.0
						Estm	Expense					$k	$k	0.0
1	74368	Dev/Val Automation Capacity Expansion		Execute			Estm	Capital					$5k	$5k					$10k	$10k	0.0
						Estm	Expense					$k	$k	0.0
1	74373	WFI Generation and Storage System / CUB Expansion	Individual	Execute 2	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Zaymar Sedra	Estm	Capital		$198k	$710k	$1,034k	$629k	$370k	$300k	$750k	$550k	$400k	$250k	$150k	$173k	$5,512k	$5,512k	0.0
						Estm	Expense				$1k	$k	$23k					$24k	$24k	0.0
1	74382	Sci&Eng Lab Mods and Equipment	Individual	Execute 2	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Jim Neeleman	Estm	Capital		$391k	$832k	$373k	$987k	$542k	$51k	$1,289k	$1,648k	$202k	$135k	$136k	$831k	$7,415k	$7,415k	0.0
						Estm	Expense		$1k	$20k	$3k	$2k	$5k	$47k	$67k	$30k	$10k	$10k			$195k	$195k	0.0
1	74392	Water Reclaim System	Individual	Execute	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Scott Fields	Estm	Capital		$k		$2k			$8k	$32k	$44k	$32k	$26k			$144k	$144k	0.0
						Estm	Expense					$k	$k	0.0
1	74404	Mezzanine Lift Media Prep: Phase 1B	Individual	Execute	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Melanie Yevilov	Estm	Capital		-$4k	$85k	$6k	$7k	$43k	$5k	$45k	$21k	$10k	$30k	$15k	$7k	$270k	$270k	-1.0
						Estm	Expense		-$1k		$k					$k	$k	0.0
1	74406	Corrosive Chemical Compliance	Individual	Execute	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Scott Fields	Estm	Capital		$5k					$258k	$344k	$430k	$344k	$258k	$86k	$1,724k	$1,724k	0.0
						Estm	Expense					$k	$k	0.0
1	74416	Asphyxiant Gas Remediation	Individual	Execute 1	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Melanie Yevilov	Estm	Capital		$k	$k		$1k	$2k	$2k	$9k	$9k		$15k	$26k	$62k	$126k	$126k	0.0
						Estm	Expense					$k	$k	0.0
1	74418	QC Lab Reconfiguration & Equipment	Individual	Execute 1	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Jim Neeleman	Estm	Capital		$1k		$k	$1k	$27k	$39k	$375k	$515k	$566k	$874k	$392k	$370k	$3,161k	$3,161k	1.0
						Estm	Expense					$2k	$1k	$96k	$1k		$13k	$114k	$114k	-1.0
1	74426	Process VSD and SOV Replacement - 2015	Individual	Execute	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Scott Fields	Estm	Capital		$114k	$19k	$23k	$28k	$71k	$38k	$94k	$154k	$34k	$15k			$590k	$590k	-1.0
						Estm	Expense					$k	$k	0.0
1	74427	MCS Network Infrastructure Asset Replacement - 2016		Execute			Estm	Capital					$448k	$15k	$52k	$248k	$404k	$111k	$137k	$51k		$1,466k	$1,466k	0.0
						Estm	Expense					$k	$k	0.0
1	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Individual	Execute	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Scott Fields	Estm	Capital		$5k	$51k	$22k	$10k	$14k	$8k	$14k	$13k	$12k	$12k	$21k	$21k	$205k	$205k	0.0
						Estm	Expense					$k	$k	0.0
1	74453	NPI Pool Tanks		PTAA			Estm	Capital			$321k	$101k	$3k	$164k	-$163k	$45k	$36k	$27k	$18k	$27k	$23k	$602k	$602k	0.0
						Estm	Expense					$k	$19k	-$19k	$k	$k	$k	$k	$k	$k	$2k	$2k	0.0
1	74454	Seed Lab (20L Bioreactor)		Execute			Estm	Capital		-$110k			$110k	-$90k	$200k	$148k	$129k	$123k	$100k	$131k	$171k	$913k	$913k	0.0
						Estm	Expense		$1k	$2k	$2k	$1k	-$9k	$19k	$23k	$19k	$14k	$9k	$14k	$2k	$97k	$97k	0.0
1	74455	3rd HCCF Vessel		Execute			Estm	Capital		-$141k	$4k	$40k	$180k	-$110k	$253k	$332k	$267k	$228k	$160k	$314k	$142k	$1,670k	$1,670k	0.0
						Estm	Expense		$3k	$6k	$6k	$3k	-$23k	$24k	$5k	$4k	$3k	$2k	$3k	$k	$35k	$35k	0.0
1	74486	PCS Controller Cabinet Asset Replacement		Execute			Estm	Capital					$407k	$520k	$481k	$267k	$349k	$270k	$2,294k	$2,294k	0.0
						Estm	Expense					$k	$k	0.0
1	74487	Process VSD and SOV Asset Replacement		Execute			Estm	Capital					$k	$3k	$415k	$611k	$623k	$652k	$530k	$764k	$3,600k	$3,600k	0.0
						Estm	Expense					$k	$k	0.0
1	74489	4040 Avenida Conference Center Acquisition		Execute			Estm	Capital				-$1k					$229k	$229k	$229k	$686k	$686k	0.0
						Estm	Expense					$k	$k	0.0
1	74490	Hyfish Material Screening Operation		Execute			Estm	Capital		$194k	$18k	$90k	$60k	$75k	$11k	$141k	$5k	$5k	$3k			$601k	$601k	1.0
						Estm	Expense					$k	$k	0.0
0	74491	Etro Tech Transfer		Hold			Estm	Capital					$1,507k	$745k	$2,131k	$175k	$1,536k	$6,095k	$1,295k	4799522.0
						Estm	Expense					$37k	$9k	$10k	$53k	$9k	$117k	$69k	47896.0
1	74510	PCS Asset Replacement - 2016		Execute			Estm	Capital				$25k	-$23k	$38k	$21k	$642k	$389k	$233k	$147k	$147k	$147k	$1,766k	$1,766k	0.0
						Estm	Expense			$k		$k					$k	$k	0.0
1	74511	QR018 Compliance Steam and Condensate Containment		Execute			Estm	Capital					$44k	$71k	$163k	$161k	$344k	$512k	$650k	$1,943k	$1,943k	0.0
						Estm	Expense					$k	$k	0.0
1	74524	Bioburden 2606 IPA Exhaust Improvement		Execute			Estm	Capital					$k	$k	0.0
						Estm	Expense			$7k	$1k	$5k				$2k					$15k	$15k	0.0
1	74526	Utility and Process Safety System		FXNL LT Appr			Estm	Capital					$7k	$76k	$333k	$408k	$236k	$412k	$412k	$1,882k	$1,882k	0.0
						Estm	Expense					$k	$k	0.0
0	76643	Optimize Column Movement Device	Global	Execute	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Melanie Yevilov	Estm	Capital		$16k	$30k	$k			$1k	$11k	$73k		$12k			$143k	$143k	0.0
						Estm	Expense					$k	$k	0.0
1	65005	Analytical Scale					Estm	Capital		$24k	$k					$24k	$24k	0.0
						Estm	Expense					$k	$k	0.0
1	65009	Drum Mover/Raw Material Tenderizer					Estm	Capital					$15k	$15k				$30k	$30k	0.0
						Estm	Expense					$4k					$4k	$4k	0.0
1	65018	Spare Bowl for Hermetic Centrifuge		Execute			Estm	Capital					$320k				$320k	$320k	0.0
						Estm	Expense					$k	$k	0.0
1	65015	Lower Solid Collector for Centrifuge		Execute			Estm	Capital					$46k		$86k	$10k			$142k	$142k	0.0
						Estm	Expense					$k	$k	0.0
0	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital					$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$494k	$494k	-3.0
						Estm	Expense					$k	$k	0.0
0	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital					$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$62k	$62k	1.0
						Estm	Expense					$k	$k	0.0
0	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital					$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$25k	$25k	1.5
						Estm	Expense					$k	$k	0.0
0	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital					$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$132k	$132k	-1.0
						Estm	Expense					$k	$k	0.0
0	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital					$13k	$13k	$13k	$13k	$13k	$13k	$13k	$13k	$13k	$114k	$204k	-89997.5
						Estm	Expense					$k	$k	0.0
0	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital					$8k	$8k				$16k	$16k	0.5
						Estm	Expense					$k	$k	0.0
1	65020	QC Auto-Pipettor for Potency Assay		Execute			Estm	Capital					$27k		$1k					$28k	$28k	0.0
						Estm	Expense					$k	$k	0.0
1	65023	QC Plate Washer for Potency Assay		Execute			Estm	Capital				$57k					$57k	$57k	0.0
						Estm	Expense					$k	$k	0.0
1	65021	Hazardous Material Response Cart		Execute			Estm	Capital					$18k					$18k	$18k	0.0
						Estm	Expense					$k	$k	0.0
1	65024	Sci and Eng Lab Incubator and Freezer Asset Replacement		Execute			Estm	Capital				$1k	$124k			$4k					$129k	$129k	0.0
						Estm	Expense					$k	$k	0.0
1	96174	Fall Protection Phase II		CA Routing			Estm	Capital					$20k	$35k	$50k	$25k	$130k	$130k	0.0
						Estm	Expense					$k	$k	0.0
1	65040	Sci&Eng Cryofreezer		Execute			Estm	Capital					$20k					$20k	$20k	0.0
						Estm	Expense					$k	$k	0.0
1	65037	Analytical Scales (CAPA 1150248)					Estm	Capital					$24k					$24k	$24k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	65048	Process Maintenance Boroscope					Estm	Capital					$35k					$35k	$35k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)					Estm	Capital					$8k	$46k	$116k	$136k	$306k	$306k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	65044	Additional MCS Backup Storage					Estm	Capital					$41k	$5k	$5k	$5k	$5k			$62k	$62k	2.0
				#N/A			Estm	Expense					$k	$k	0.0
1	74431	Buffer Prep Mezzanine Lift Construction	Global	JPMT Appr	Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	Scott Fields	Estm	Capital					$41k	$48k	$56k	$59k	$238k		$442k	$442k	0.0
						Estm	Expense					$k	$k	0.0
1	96137	Security Systems Upgrade		JPMT Appr			Estm	Capital					$200k	$200k	$200k	0.0
						Estm	Expense					$k	$k	0.0
1	65066	Appleton Tank Mover		Hold			Estm	Capital					$68k		$5k					$73k	$73k	0.0
						Estm	Expense					$k	$k	0.0
1	96207	Weigh and Dispense Sink (CAPA1123109)		FXNL LT Appr			Estm	Capital					$25k	$25k	$150k	-125000.0
						Estm	Expense					$5k	$5k	$15k	-10000.0
1	74546	Mezzanine Safety Shower/Eye Wash Station Install		IMPACT Appr			Estm	Capital					$65k			$35k	$100k	$450k	-350000.0
						Estm	Expense					$k	$k	0.0
0	96205	Pressure Safety		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$20k	$20k	$20k	$20k				$20k	$100k	$k	100000.0
1	65082	RF Sealer Generator					Estm	Capital					$22k		$22k	$22k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
						$k	$k
0	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital					$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$494k	$494k	0.0
						Estm	Expense					$10k	$10k					$20k	$20k	0.0
0	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital					$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$62k	$62k	0.0
						Estm	Expense					$1k	$1k					$2k	$2k	0.0
0	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital					$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$25k	$25k	0.0
						Estm	Expense					$k	$k	0.0
0	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital					$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$132k	$132k	0.0
						Estm	Expense					$1k	$2k	$2k			$5k	$5k	0.2
0	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital					$23k	$23k	$23k	$23k	$23k	$23k	$23k	$23k	$23k	$204k	$204k	0.0
						Estm	Expense					$k	$k	0.0
0	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital					$k	$k	$k	$k	$8k	$8k	$k	$k	$k	$16k	$16k	0.0
						Estm	Expense					$k	$k	0.0
0	96159	OCC Network Remediation		Idea			Estm	Capital					$50k	$50k	$50k			$150k	$150k	0.0
						Estm	Expense					$k	$k	0.0
0	74435	Hastelloy Chromatography Column (160cm)		FXNL LT Appr			Estm	Capital					$k	$400k	-400000.0
						Estm	Expense					$k	$k	0.0
0	96135	QC Spectrophotmeters		Canceled			Estm	Capital					$23k					$23k	$k	23000.0
						Estm	Expense					$k	$k	0.0
1	74409	K6 Program - Project 1 - Replace DX HVAC Units	Individual	Execute	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Zaymar Sedra	Estm	Capital					$10k	$100k	$100k	$100k	$310k	$k	310000.0
						Estm	Expense					$11k	$11k		$22k	$k	22000.0
0	74527	Vessel 1020 Upgrade		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96134	QC Liquid Handler		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74385	Media Prep Endotoxin/Bioburden Sampling		Hold			Estm	Capital					$83k	$83k	$83k	$250k	$k	250000.0
						Estm	Expense					$k	$k	0.0
0	96164	Hazardous Materials Containers Washing Station		Hold			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96167	Emergency Generator High Level Alarm		Idea			Estm	Capital					$25k					$25k	$25k	0.0
						Estm	Expense					$k	$k	0.0
0	96168	Replace Warehouse #321 Sprinkler Heads		Idea			Estm	Capital					$20k				$20k	$20k	0.0
						Estm	Expense					$k	$k	0.0
0	74525	CIP Reliability and Efficiency - PI					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96169	Level Indicator Transmitters					Estm	Capital					$70k			$70k	$70k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	96139	Trash Bin Storm Water Mitigation		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96136	V-3007 Replacement		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74432	K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74278	K6 Program - Project 3 - Replace Cold Room Compressors		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74512	K6 Program - Project 2 - B381 Compliance		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96133	QC Rapid Scan RDI System		Hold			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96165	WAN Link Redundancy		Hold			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74371	Odor Treatment		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74513	Electric Vehicle Charging Stations					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96163	MFG Depth Filter Housing		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96069	Warehouse Crown Forklift Asset Replacement					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96105	TMAC Tenderizer					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96112	Maintenance Ops Shop Buildout					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96116	PCS Process Support Equipment Integration					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96124	Perjeta Tech Transfer		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96177	Efficiency Projects					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0		Contingency					Estm	Capital		$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96999	Site Adjustment		TBD			Estm	Capital		$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0.0
						Estm	Expense		$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0.0
		TOTAL Capex				TOTAL				-$3,444k	$13,967k	$7,936k	$19,452k	$8,496k	$13,141k	$17,530k	$18,431k	$16,707k	$15,540k	$15,145k	$14,623k	$157,525k	$152,914k

1	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		Execute 1			Estm	Expense		$23k	$26k	$72k	$106k	$54k	$98k	$97k	$82k	$82k	$62k	$84k	$80k	$866k	$866k	0.0
1	97003	MFG Systems Integration Improvement Phase 1 - 2015		Execute 1			Estm	Expense					$2k	$20k	$45k	$45k	$45k	$45k	$45k	$45k	$292k	$292k	0.0
1	97007	Automation System Lifecycle MCS Upgrade		Execute			Estm	Expense				$45k	$1k	$57k	$41k	$96k	$57k					$296k	$296k	0.0
1	97048	Arc Flash Prevention		Execute			Estm	Expense					$55k	$4k	$3k	$17k	$18k	$19k	$25k	$178k		$318k	$318k	0.0
1	97053	Pressure Safety Program - PI Phase		Execute			Estm	Expense					$20k	$20k	$20k	$20k		$20k	$100k	$100k	0.0
1	97058	Parking Pavement Repair		Execute			Estm	Expense		$140k		$105k					$245k	$245k	0.0
1	98026	Launch Capability Program (LCP)					Estm	Expense		$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$800k	$800k	4.0
1	97059	B311 & B321 Gowning Room Modifications		Execute			Estm	Expense				$4k	$8k	$84k	$5k					$100k	$100k	0.0
1	N/A	CRB, travel, ofc supplies, trailer, others					Estm	Expense		$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$317k	$317k	0.0
1	97057	Conference Room 315 Expansion		Idea			Estm	Expense					$108k		$108k	$150k	-42000.0
1		PCS Asset Replacement Depreciation Write-Off					Estm	Expense		$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$800k	$800k	4.0
1		Piping Corrosion					Estm	Expense		$224k	$23k	$335k	$355k	$194k	$227k	$271k	$480k	$105k	$166k	$259k	$463k	$3,102k	$3,102k	0.0

0	97040	Tech Transfer: Master Data Management		FXNL LT Appr			Estm	Expense					$k	$k	0.0
0	97038	PCS Functional Specification Development Project (CAPA 960297)		FXNL LT Appr			Estm	Expense					$k	$k	0.0
0	97039	PCS Remediation for EBR Review by Exception - PI		Idea			Estm	Expense					$k	$k	0.0
0	97045	Site Exterior Lighting Upgrade - Title 24		FXNL LT Appr			Estm	Expense					$33k	$33k	$33k	$100k	$100k	-1.0
0	97054	HVAC Retro Commissioning		FXNL LT Appr			Estm	Expense	#REF!					$k	$k	0.0
0	97061	Tangential Flow Filtration Cassettes Management		#REF!			Estm	Expense	#REF!					$k	$k	0.0
0	97005	MCS Peripheral Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97009	MES Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97012	Site Data Historian Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97015	MCS Backup System Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97030	MFG Systems Integration Improvement Phase 3 - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97031	MCS Data Analytics Asset Replacement - 2017					Estm	Expense					$k	$k	0.0
0	97037	Recipe Reconfiguration Alignment for Operating Systems					Estm	Expense	#REF!					$k	$k	0.0
0	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!					$30k	$45k					$75k	$75k	0.0
0	97999	Site Adjustment					Estm	Expense					$k	$k	0.0
		TOTAL Expense Projects				TOTAL				$547k	$208k	$721k	$684k	$585k	$598k	$705k	$862k	$430k	$511k	$868k	$802k	$7,520k	$7,562k
		Total Capital				TOTAL		Capital		-$3,548k	$13,820k	$7,790k	$19,278k	$8,071k	$12,688k	$17,270k	$18,201k	$16,485k	$15,425k	$14,938k	$14,472k	$154,891k	$150,440k
		Total Expense					Expense		$651k	$355k	$867k	$859k	$1,010k	$1,051k	$965k	$1,092k	$652k	$626k	$1,075k	$953k	$10,154k	$10,036k
		Cashflow Variance					Capital	#DIV/0!					$-	$-
						Expense
						467,206.74

						10%	12%	9%	10%	10%	10%	8%	7%	7%	6%	6%	5%
						5%	8%	6%	5%	6%	8%	9%	8%	11%	21%	7%	7%

	BELOW THE LINE
0	96162	Pressure Safety Improvements		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64922	QC Mettler Toledo Balances Replacement 2015		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64924	QC Biotek LAL Reader Replacement 2015		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64926	QC SpeedVac Replacement 2015		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96160	B331 HVAC Fire Code Compliance		#N/A			Estm	Capital					$1,000k					$1,000k	$k	1000000.0
						Estm	Expense					$k	$k	0.0

1	97049	SIMCA Online - Downstream Application					Estm	Expense					$k	$k	0.0
0	97029	Study for K6 Program - Project 4 - Replace Chillers		#N/A			Estm	Expense	#REF!					$k	$k	0.0
1	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!					$30k	$45k					$75k	$75k	0.0

## Monthly_Cashflow_2017
				105,951,624.00
	MASTER PORTFOLIO					5,702,276.48
	Monthly Cashflow - 2016
				2015					2017
	Project No.	Project Title	Credit Type	Status	PMO Lead	SME	Estm/ / Budg?	Type of Expend.	Budget 2015		Current Forecast	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	2017 Current Forecast	Budget 2017
	64901	MCS Peripheral Asset Replacement - 2015		Execute			Estm	Capital	#REF!		$225k					$171k	$36k	$7k	$k	$6k	$5k					$k	$k	0
				Estm	Expense	#REF!		$100k					$40k	$30k	$10k	$10k	$10k					$k	$k	0
1	64914	QC M9 TOC Analyzers					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	64923	QC Met-One Air Sampler Replacement 2015					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	64927	QC Gel Imager Replacement 2015					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
	73356	Supplemental BDU Sampling	Individual	Execute 2	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$1,475k	$81k	$100k	-$3k	$296k	$157k	$141k	$144k	$111k	$115k	$123k	$115k	$95k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	73367	FS & DS Automation Integration	Individual	Execute 2	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$467k		$212k	-$16k	$103k	$28k	$25k	$28k	$26k	$16k	$29k	$16k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	73384	Caustic Bath Upgrade		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	73387	MCSBACKUP Phase 2 Tape Retrieval		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	73388	SIMCA Online Real Time Process Monitoring System	Global	Execute	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$264k	$258k					$1k	$5k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$22k					$1k	$3k	$3k	$3k	$3k	$3k	$3k	$3k					$k	$k	0
1	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Global	Execute	Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Scott Fields	Estm	Capital	#REF!	#REF!	$116k					$5k	$11k	$60k	$40k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	73399	Frit Handling and Storage	Global	Execute	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$15k					$15k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	73409	Solar Power Enabling Project		Execute			Estm	Capital	#REF!	#REF!	$184k					$26k	$49k	$109k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74119	Harvest Upgrade (New Centrifuge)	Individual	Execute 2	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$4,492k					$2,049k	$448k	$389k	$501k	$528k	$577k	$849k	$869k	$781k	$750k	$745k	$714k	$651k	$650k	$476k	$470k	$242k	$39k	$7,237k	$7,237k	0
				Estm	Expense	#REF!	#REF!	$42k					$3k	$3k	$3k	$3k	$3k	$27k	$48k	$1k	$1k	$1k	$1k					$51k	$51k	0
1	74127	Harvest Modifications Start-up		Budgeted			Estm	Capital	#REF!		$k					$k	$2,275k	-2275000
				Estm	Expense	#REF!		$k					$k	$k	0
1	74268	P2 Downstream Processing Expansion	Individual	Execute 2	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$46,114k	-$761k	$1,384k	$1,731k	$2,455k	$5,656k	$3,566k	$5,313k	$3,897k	$5,141k	$6,318k	$6,234k	$5,181k	$6,312k	$5,696k	$4,805k	$4,001k	$3,578k	$2,924k	$2,804k	$2,279k	$390k	$144k	$144k	$288k	$33,364k	$33,364k	0
				Estm	Expense	#REF!	#REF!	$3,346k	$9k	$11k	$16k	$90k	$54k	$34k	$47k	-$84k	$50k	$51k	$54k	$3,011k	$146k	$144k	$142k	$116k	$115k	$110k	$107k	$37k					$916k	$916k	0
	74277	P2 DPE Start-Up		Execute			Estm	Capital	#REF!		$k					$2,181k	$2,184k	$6,857k	$6,491k	$6,255k	$6,157k	$6,052k	$1,118k	$899k	$957k	$608k	$524k	$40,281k	$40,281k	-1
				Estm	Expense	#REF!		$k					$k	$k	0
	74279	New Media Technology - HTST / Adventitious	Individual	Execute 2	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Scott Fields	Estm	Capital	#REF!	#REF!	$2,072k	$9k	$97k	$7k	$116k	$82k	$110k	$69k	$78k	$561k	$354k	$310k	$279k	$518k	$414k	$379k	$171k	$66k	$5k					$1,553k	$1,553k	0
				Estm	Expense	#REF!	#REF!	$2k				$3k	-$1k					$38k					$38k	$38k	0
1	74302	Waterpooling Remediation	Individual	Execute 2	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$510k		$139k		$134k	$75k	$41k	$25k	$18k	$24k	$8k	$1k	$45k	$50k					$50k	$50k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	74368	Dev/Val Automation Capacity Expansion		Execute			Estm	Capital	#REF!	#REF!	$56k	$68k	-$12k			$3k	-$3k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	74373	WFI Generation and Storage System / CUB Expansion	Individual	Execute 2	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$6,162k	$31k	$376k	$759k	$303k	$590k	$176k	$160k	$400k	$815k	$551k	$900k	$1,100k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$93k		$3k	$2k	$2k	$7k	$2k	$8k	$26k	$33k	$4k	$4k	$3k					$k	$k	0
1	74382	Sci&Eng Lab Mods and Equipment	Individual	Execute 2	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$5,270k				$1,056k	$203k	$168k	$185k	$609k	$128k	$1,282k	$1,100k	$539k	-	$32k	$107k	$93k	$74k	$79k	$6k					$391k	$391k	0
				Estm	Expense	#REF!	#REF!	$2k				$3k	-$1k					$k	$k	0
	74392	Water Reclaim System	Individual	Execute	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Scott Fields	Estm	Capital	#REF!	#REF!	$180k				$8k	$26k	$23k	$37k	$30k	$48k	$2k	$4k	$2k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74404	Mezzanine Lift Media Prep: Phase 1B	Individual	Execute	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$262k		$10k		$10k	$34k	$101k	$21k	$12k	$17k	$17k	$20k	$20k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74406	Corrosive Chemical Compliance	Individual	Execute	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Scott Fields	Estm	Capital	#REF!	#REF!	$98k				$6k	$12k	$25k	$22k	$2k	$5k	$5k	$19k	$2k	$84k					$84k	$84k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74416	Asphyxiant Gas Remediation	Individual	Execute 1	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$33k					$2k	$1k	$8k	$22k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74418	QC Lab Reconfiguration & Equipment	Individual	Execute 1	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$213k					$1k	$15k	$45k	$26k	$59k	$39k	$28k		$144k	$146k					$290k	$290k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	74426	Process VSD and SOV Replacement - 2015	Individual	Execute	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Scott Fields	Estm	Capital	#REF!	#REF!	$203k					$6k	$47k	$100k	$50k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	74427	MCS Network Infrastructure Asset Replacement - 2016		Execute			Estm	Capital	#REF!		$7k					$7k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Individual	Execute	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Scott Fields	Estm	Capital	#REF!	#REF!	$311k					$2k	$4k	$210k	$55k	$40k	$21k	$2k					$23k	$23k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74453	NPI Pool Tanks		PTAA			Estm	Capital	#REF!	#REF!	$545k					$273k			$273k				$22k	$15k	$1k	$k					$38k	$38k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74454	Seed Lab (20L Bioreactor)		Execute			Estm	Capital	#REF!	#REF!	$755k					$345k	$75k	$65k	$84k	$89k	$97k	$204k	$141k	$41k	$36k	$7k	$1k	$1k	$1k	$1k	$1k	$1k	$2k	$439k	$439k	0
				Estm	Expense	#REF!	#REF!	$7k					$k	$k	$1k	$1k	$1k	$4k	$1k	$1k	$k	$k					$2k	$2k	0
1	74455	3rd HCCF Vessel		Execute			Estm	Capital	#REF!	#REF!	$1,079k					$492k	$108k	$94k	$120k	$127k	$139k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$10k					$1k	$1k	$1k	$1k	$1k	$6k					$k	$k	0
1	74486	PCS Controller Cabinet Asset Replacement		Execute			Estm	Capital	#REF!		$450k					$100k	$100k	$250k	$110k					$110k	$110k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74487	Process VSD and SOV Asset Replacement		Execute			Estm	Capital	#REF!		$k					$877k	$1,530k	$519k					$2,925k	$2,925k	0
				Estm	Expense	#REF!		$k					$18k					$18k	$18k	0
	74489	4040 Avenida Conference Center Acquisition		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74490	Hyfish Material Screening Operation		Execute			Estm	Capital	#REF!		$782k					$36k	$173k	$573k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74491	Etro Tech Transfer		Hold			Estm	Capital	#REF!		$k					$817k	$191k	$1,645k	$436k	$360k	$1,856k	$484k	$484k	$1,932k	$479k	$445k	$3,575k	$12,702k	$9,066k	3636061
				Estm	Expense	#REF!		$k					$13k	$4k	$9k	$23k	$9k	$24k	$14k	$9k	$9k	$9k	$9k	$4k	$135k	$3,771k	-3636061
1	74510	PCS Asset Replacement - 2016		Execute			Estm	Capital	#REF!		$k					$149k					$149k	$149k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74511	QR018 Compliance Steam and Condensate Containment		Execute			Estm	Capital	#REF!		$k					$488k	$449k	$365k	$245k	$185k	$113k	$125k	$245k	$245k	$245k	$245k	$125k	$3,075k	$3,075k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74524	Bioburden 2606 IPA Exhaust Improvement		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$138k	$138k	$138k	$138k					$550k	$k	550000
1	74526	Utility Process Safety System		FXNL LT Appr			Estm	Capital	#REF!		$k					$58k					$58k	$58k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	76643	Optimize Column Movement Device	Global	Execute	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$68k	$25k					$35k				$8k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	65005	Analytical Scale					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	65009	Drum Mover/Raw Material Tenderizer					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
	65018	Spare Bowl for Hermetic Centrifuge		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65015	Lower Solid Collector for Centrifuge		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$500k	-500000
				Estm	Expense	#REF!		$k					$k	$5k	-5000
	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$1,168k	-1167829
				Estm	Expense	#REF!		$k					$k	$10k	-10000
	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$365k	-365000
				Estm	Expense	#REF!		$k					$k	$k	0
	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$158k	-157778
				Estm	Expense	#REF!		$k					$k	$k	0
	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$723k	-722929
				Estm	Expense	#REF!		$k					$k	$k	0
	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$56k	-56049
				Estm	Expense	#REF!		$k					$k	$k	0
1	65020	QC Auto-Pipettor for Potency Assay		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65023	QC Plate Washer for Potency Assay		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	73442	V-2170 Agitator Drain Valve		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65021	Hazardous Material Response Cart		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65024	Sci and Eng Lab Incubator and Freezer Asset Replacement		Execute			Estm	Capital	#REF!		$18k					$18k	$101k	$76k	$74k	$77k	$74k	$81k	$6k					$489k	$k	488779
				Estm	Expense	#REF!		$k					$k	$k	0
1	96174	Fall Protection Phase II		CA Routing			Estm	Capital	#REF!		$18k					$18k	$5k					$5k	$5k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65040	Sci&Eng Cryofreezer		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65037	Analytical Scales (CAPA 1150248)		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	64898	Terumo Sterile BCT SCDIIB Welders		#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65048	Process Maintenance Boroscope					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)					Estm	Capital					$138k	$80k	$229k	$207k					$654k	$654k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	65044	Additional MCS Backup Storage					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74431	Buffer Prep Mezzanine Lift Construction	Global	JPMT Appr	Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	Scott Fields	Estm	Capital	#REF!	#REF!	$k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	96139	Trash Bin Storm Water Mitigation		FXNL LT Appr			Estm	Capital	#REF!		$k					$20k	$40k	$60k	$80k					$200k	$200k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				$k	$k
	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$500k	-500000
				Estm	Expense	#REF!		$k					$k	$5k	-5000
	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$1,168k	-1167829
				Estm	Expense	#REF!		$k					$k	$10k	-10000
	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$365k	-365000
				Estm	Expense	#REF!		$k					$k	$k	0
	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$158k	-157778
				Estm	Expense	#REF!		$k					$k	$k	0
	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$723k	-722929
				Estm	Expense	#REF!		$k					$k	$k	0
	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$56k	-56049
				Estm	Expense	#REF!		$k					$k	$k	0
	96159	OCC Network Remediation		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74435	Hastelloy Chromatography Column (160cm)		FXNL LT Appr			Estm	Capital	#REF!		$k					$9k	$526k	$89k	$9k	$81k	$k	$580k	$k	$k	$25k	$22k	$207k	$1,549k	$1,149k	399958
				Estm	Expense	#REF!		$k					$k	$k	0
	96135	QC Spectrophotmeters		Canceled			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74527	Vessel 1020 Upgrade		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	96134	QC Liquid Handler		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96137	Security Systems Upgrade		JPMT Appr			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74385	Media Prep Endotoxin/Bioburden Sampling		Hold			Estm	Capital	#REF!		$k					$83k	$83k	$83k					$250k	$k	250000
				Estm	Expense	#REF!		$k					$k	$k	0
1	74546	Mezzanine Safety Shower/Eye Wash Station Install		IMPACT Appr			Estm	Capital	#REF!		$k					$233k	$233k	$233k					$700k	$436k	263999
				Estm	Expense	#REF!		$k					$k	$k	0
	96164	Hazardous Materials Containers Washing Station		Hold			Estm	Capital	#REF!		$k					$30k					$30k	$30k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	96167	Emergency Generator High Level Alarm		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	96168	Replace Warehouse #321 Sprinkler Heads		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
	74525	CIP Reliability and Efficiency - PI					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	65066	Appleton Tank Mover					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	74513	Electric Vehicle Charging Stations					Estm	Capital					$k	$712k	-712000
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$18k	-18000
	96112	Maintenance Ops Shop Buildout					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	96999	Site Adjustment		TBD			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
		TOTAL Capex				TOTAL			#REF!	#REF!	$75,640k	-$306k	$2,320k	$2,496k	$4,585k	$6,928k	$4,700k	$9,003k	$5,794k	$7,857k	$9,949k	$10,116k	$12,197k	$13,872k	$12,994k	$16,558k	$12,875k	$11,549k	$12,064k	$10,859k	$4,823k	$3,951k	$2,331k	$1,715k	$4,764k	$108,354k	$115,376k

1	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		Execute 1			Estm	Expense	#REF!		$38k					$k	$5k	$k	$32k		$108k	$101k	$80k	$221k	$66k					$575k	$575k	0
1	97003	MFG Systems Integration Improvement Phase 1 - 2015		Execute 1			Estm	Expense	#REF!	#REF!	$15k					$15k	$45k	$45k	$45k					$135k	$135k	0
	97007	Automation System Lifecycle MCS Upgrade		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	97048	Arc Flash Prevention		Execute			Estm	Expense	#REF!		$k					$k	$k	0
1	97058	Parking Pavement Repair		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	98026	Launch Capability Program (LCP)					Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	97059	B311 & B321 Gowning Room Modifications		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	N/A	CRB, travel, ofc supplies, trailer, others					Estm	Expense	$925k	$k	$925k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$317k	$317k	0
1		PCS Asset Replacement Depreciation Write-Off					Estm	Expense					$k	$k	0
1		Piping Corrosion					Estm	Expense	#REF!	#REF!	$k					$455k	$322k	$272k	$332k	$420k	$467k	$500k	$471k	$461k	$430k	$319k	$339k	$4,788k	$4,788k	0
1	97057	Conference Room 315 Expansion		Idea			Estm	Expense					$192k					$192k	$k	192000

	97040	Tech Transfer: Master Data Management		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
	97038	PCS Functional Specification Development Project (CAPA 960297)		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$500k	-500000
	97039	PCS Remediation for EBR Review by Exception - PI		Idea			Estm	Expense	#REF!	#REF!	$k					$k	$250k	-250000
	97045	Site Exterior Lighting Upgrade - Title 24		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$33k	$33k	$33k					$100k	$100k	-1
	97999	Site Adjustment					Estm	Expense	#REF!	#REF!	$k					$k	$k
		TOTAL Expense Projects				TOTAL			#REF!	#REF!	$978k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$82k	$77k	$109k	$92k	$860k	$527k	$456k	$579k	$512k	$494k	$526k	$498k	$488k	$457k	$345k	$366k	$6,107k	$6,665k
		Total Capital				TOTAL		Capital	#REF!		$73,240k	-$229k	$2,397k	$2,573k	$4,662k	$7,005k	$4,777k	$9,080k	$5,872k	$7,939k	$10,027k	$10,225k	$12,289k	$13,471k	$12,707k	$16,268k	$12,597k	$11,425k	$11,930k	$10,738k	$4,777k	$3,943k	$2,322k	$1,706k	$4,760k	$106,644k	$110,532k
		Total Expense					Expense	#REF!		$4,502k					$1,260k	$814k	$747k	$857k	$636k	$628k	$647k	$543k	$497k	$466k	$354k	$370k	$7,817k	$11,510k
		Cashflow Variance					Capital	#REF!	#DIV/0!
				Expense	#REF!	#DIV/0!
				(47,779,192.94)

				10%	12%	9%	10%	10%	10%	8%	7%	7%	6%	6%	5%
				5%	8%	6%	5%	6%	8%	9%	8%	11%	21%	7%	7%

	BELOW THE LINE
0	96162	Pressure Safety Improvements		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64922	QC Mettler Toledo Balances Replacement 2015		#N/A			Estm	Capital	#REF!		$60k					$40k	-$23k	$43k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64924	QC Biotek LAL Reader Replacement 2015		#N/A			Estm	Capital	#REF!		$19k					$17k		$2k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64926	QC SpeedVac Replacement 2015		#N/A			Estm	Capital	#REF!		$12k					$12k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74371	Odor Treatment		FXNL LT Appr			Estm	Capital	#REF!		$100k					$50k	$50k					$125k	$125k	$125k	$125k	$125k	$125k	$750k	$k	750000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96136	V-3007 Replacement		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$120k	-120000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96165	WAN Link Redundancy		Hold			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74409	K6 Program - Project 1 - Replace DX HVAC Units	Individual	Execute	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$90k					$50k	$40k					$10k	$100k	$100k	$100k	$310k	$310k	0
				Estm	Expense	#REF!	#REF!	$k					$11k	$11k		$22k	$22k	0
1	74512	K6 Program - Project 2 - B381 Compliance		FXNL LT Appr			Estm	Capital	#REF!		$k					$83k	$83k	$83k	$83k	$333k	$k	333333
				Estm	Expense	#REF!		$k					$6k	$6k	$6k	$6k	$22k	$k	22222
0	74278	K6 Program - Project 3 - Replace Cold Room Compressors		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$528k	-528000
				Estm	Expense	#REF!		$k					$k	$75k	-75000
0	74432	K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96160	B331 HVAC Fire Code Compliance		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96133	QC Rapid Scan RDI System		Hold			Estm	Capital	#REF!		$k					$210k					$210k	$210k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96163	MFG Depth Filter Housing		Idea			Estm	Capital	#REF!		$k					$k	$300k	-300000
				Estm	Expense	#REF!		$k					$k	$100k	-100000
0	96124	Perjeta Tech Transfer		Idea			Estm	Capital	#REF!		$k					$k	$8,794k	-8793594
				Estm	Expense	#REF!		$k					$k	$147k	-147070
0	96183	Site Signage Upgrade		Idea			Estm	Capital	#REF!		$k					$67k	$67k	$67k					$200k	$175k	25000
				Estm	Expense	#REF!		$k					$k	$25k	-25000
0	96189	Pipe Labelling		#N/A			Estm	Capital	#REF!		$k					$33k	$33k	$33k					$100k	$k	100000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96198	Crane & Hoist Mitigation		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96192	Pressure Safety Facility Mitigations		#N/A			Estm	Capital	#REF!		$k					$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$2,500k	$k	2500000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96191	Utility and Process Safety System Phase 2		Idea			Estm	Capital	#REF!		$k					$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$2,000k	$2,000k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96193	Column Packing Fall Hazard		Canceled			Estm	Capital	#REF!		$k					$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$300k	$k	300000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96195	K6- All Design		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96204	322 MRO Racks		Hold			Estm	Capital	#REF!		$k					$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$500k	$500k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0

0	97061	Tangential Flow Filtration Cassettes Management		#REF!			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	97049	SIMCA Online - Downstream Application					Estm	Expense					$k	$k	0
0	97029	Study for K6 Program - Project 4 - Replace Chillers		#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	97054	HVAC Retro Commissioning		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$25k	$11k	$11k	$11k	$11k	$11k	$11k	$11k	$11k	$113k	$113k	0
0	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$k	0

## Chart_Data
				PROJECT STATUS
				Column1	2014	2015	2016	2017	2018	2019		Nro. Projects
				BMLT Appr	$0	#REF!	$0	$0	$0	$0		0
				Budgeted	#REF!	#REF!	$250	$5,050	$2,500	$500		2
				CA Routing	$0	#REF!	$265	$5	$0	$0		1
				CA Submitted	$0	#REF!	$0	$0	$0	$0		0
				Canceled	#REF!	#REF!	#VALUE!	#VALUE!	#VALUE!	#VALUE!		4
				Complete	$0	#REF!	$0	$0	$0	$0		0
				Execute	#REF!	#REF!	$53,073	$101,487	$15,102	$0		50
				Execute 1	#REF!	#REF!	$5,574	$2,258	$0	$0		2
				Execute 2	#REF!	#REF!	$235,197	$84,909	$0	$0		8
				Expense	$0	#REF!	$0	$0	$0	$0		0
				Financial Closed	$0	#REF!	$0	$0	$0	$0		0
				FXNL LT Appr	#REF!	#REF!	$9,415	$22,616	$30,166	$29,300		33
				Hold	#REF!	#REF!	$7,972	$36,652	$6,695	$1,016		14
				Idea	#REF!	#REF!	$530	$28,340	$169,359	$30,760		17
				JPMT Appr	#REF!	#REF!	$1,259	$0	$0	$0		2
				IMPACT Appr	#REF!	#REF!	$550	$1,222	$0	$0		1
				Placeholder	#REF!	#REF!	$0	$6,000	$6,000	$6,000		2
				PTAA	#REF!	#REF!	$1,292	$41	$0	$0		1
				TBD	$0	#REF!	$0	$0	$0	$0		0
					#REF!	#REF!	#VALUE!	#VALUE!	#VALUE!	#VALUE!		137	119

Financial R	Total
T0 - Year 2015	#REF!			BUDGET	2014	2015	2016	2017	2018	2019		ESTIMATE	2015	2016	2017	2018	2019	2020
MO5 - Year 2015	$170,953			RTO	$0	#REF!	$11,508	$7,698	$0	$0		RTO	$2,721	$13,020	$11,233	$2,520	$0	$0
T3 - Year 2015	#REF!			QSP	$0	#REF!	$144,217	$122,550	$96,402	$16,738		QSP	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!
				CTT	$0	#REF!	$465	$7,271	$18,264	$10,828		CTT	$2,076	$1,547	$4,265	$8,934	$16,672	$6,500
				TBD	$0	#REF!	$1,162	$5,919	$3,000	$3,000		TBD	$0	$4,144	$8,223	$3,000	$3,000	$3,000
					$0	#REF!	$157,352	$143,437	$117,666	$30,566			#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!

				Column1	2014	2015	2016	2017	2018	2019
				Department	$0	#REF!	$0	$0	$0	$0
				Global	$0	#REF!	$5,098	$5,393	$3,120	$3,000
				Individual	$0	#REF!	$141,457	$73,710	$25,664	$16,686
				Start-up	$0	#REF!	$10,798	$64,333	$88,882	$10,880
				TBD	$0	#REF!	$0	$0	$0	$0
				Expense	$0	#REF!	$0	$0	$0	$0
					$0	#REF!	$157,352	$143,437	$117,666	$30,566

						<$0.5M
				500,001.00	2,000,000.00	$0.5M-$2M
				2,000,001.00	10,000,000.00	$2M-$10M
						>$10M

			Column1	Column2	2014	2015	2016	2017	2018	2019
			74268	P2	$0	#REF!	$93,652	$0	$0	$0
			74246	G6	$0	#REF!	$0	$0	$0	$0
			74111	DBX CA1	$0	#REF!	$0	$0	$0	$0
			74126	DBX CA2	$0	#REF!	$0	$0	$0	$0

			Categories - All Inclusive
			Category	2014	2015	2016	2017	2018	2019	2020
			Capacity	0	#REF!	0	0	0	0	0
			Compliance	0	#REF!	0	0	0	0	0
			Efficiency	0	#REF!	0	0	0	0	0
			Life Cycle Mgmt	0	#REF!	0	264,407	120,000	0	440,000
			Other	0	#REF!	0	0	0	0	0
			Safety	0	#REF!	0	0	0	0	0
			Sustainability	0	#REF!	0	0	0	0	0
			Utility	0	#REF!	0	0	0	0	0
				0	#REF!	0	264,407	120,000	0	440,000

			Categories Excluding P2, G2, DBX1, 2
			Category	2014	2015	2016	2017	2018	2019	2020
			Capacity	0	#REF!	-98,113,004	-74,561,060	0	0	0
			Compliance	0	#REF!	0	0	0	0	0
			Efficiency	0	#REF!	0	0	0	0	0
			Life Cycle Mgmt	0	#REF!	0	264,407	120,000	0	440,000
			Other	0	#REF!	0	0	0	0	0
			Safety	0	#REF!	0	0	0	0	0
			Sustainability	0	#REF!	0	0	0	0	0
			Utility	0	#REF!	0	0	0	0	0
				0	#REF!	-98,113,004	-74,296,653	120,000	0	440,000

	Number	Project	Category	2014	2015	2016	2017	2018	2019	2020
	74111	Debottlenecking	Capacity	0	#REF!	0	0	0	0	0
	74126	Debottlenecking Start-up	Capacity	0	#REF!	0	0	0	0	0
	74246	G6 Tech Transfer	Efficiency	0	#REF!	0	0	0	0	0
	74268	P2 Downstream Processing Expansion	Capacity	0	#REF!	93,651,797	34,280,135	0	0	0
	74277	P2 DPE Start-Up	Capacity	0	#REF!	4,461,207	40,280,925	6,754,868	0	0
				0	#REF!	98,113,004	74,561,060	6,754,868	0	0

			Programs	TOTAL T0
			Agile	29,458,134
			ACCR	0
			Launch Facility	348,015,907
			Multi Product	0
			Reliable	141,549,576

			Programs	Current Estimate		Programs	Estimate Year 2015
			Agile	4,981,000		Agile	11,247,482
			ACCR	0		ACCR	0
			Launch Facility	0		Launch Facility	65,938,837
			Multi Product	0		Multi Product	0
			Reliable	25,629,894		Reliable	30,011,285

			Programs	Total RR Demand Year 2015		Programs	Number of Projects
			Agile	0.32		Agile	25
			ACCR	-		ACCR	0
			Launch Facility	79.97		Launch Facility	14
			Multi Product	1.58		Multi Product	8
			Reliable	58.69		Reliable	89

			Category	Total	2014	2015	2016	2017	2018	2019	2020
			RTO	#REF!	0	#REF!	11,507,601	7,697,936	0	0	0
			QSP	#REF!	0	#REF!	144,217,160	122,549,565	96,401,587	16,737,884	56,920,909
			CTT	#REF!	0	#REF!	465,377	7,270,556	18,264,444	10,828,000	4,150,000
			TBD	#REF!	0	#REF!	1,162,185	5,918,779	3,000,000	3,000,000	3,000,000
				#REF!	0	#REF!	157,352,323	143,436,836	117,666,031	30,565,884	64,070,909

			Category	2014	2015	2016	2017	2018	2019	2020
			RTO	0	#REF!	11,507,601	7,697,936	0	0	0
			QSP	0	#REF!	144,217,160	122,549,565	96,401,587	16,737,884	56,920,909
			CTT	0	#REF!	465,377	7,270,556	18,264,444	10,828,000	4,150,000
			TBD	0	#REF!	1,162,185	5,918,779	3,000,000	3,000,000	3,000,000
				0	#REF!	157,352,323	143,436,836	117,666,031	30,565,884	64,070,909
			Expenditure Trend	26,780,000	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!

			Excluding (P2,DBX,G6)
			Category	2014	2015	2016	2017	2018	2019	2020
			RTO	0	#REF!	11,507,601	7,697,936	0	0	0
			QSP	0	#REF!	46,104,156	47,988,505	96,401,587	16,737,884	56,920,909
			CTT	0	#REF!	465,377	7,270,556	18,264,444	10,828,000	4,150,000
			TBD	0	#REF!	1,162,185	5,918,779	3,000,000	3,000,000	3,000,000
				0	#REF!	59,239,319	68,875,776	117,666,031	30,565,884	64,070,909
		Exc P2, DBX, G6	Expenditure Trend					17,000,000	18,000,000	19,000,000

			Status	Label	Agile	ACCR	Launch Facility	Multi Product	Reliable
			BMLT Appr	2011	2012	2013	2014	2015	2016		2018	2019	2020
			Budgeted	27201282	22,626,000	70,027,575	26,780,000	#REF!	#REF!		#REF!	#REF!	#REF!
		Exc P2, DBX, G6	CA Routing	27201282	22,626,000	70,027,575	10,654,000	#REF!	#REF!		#REF!	#REF!	#REF!
			CA Submitted
			BMLT Appr	Approvals	0	0	0	0	0
			Budgeted	Budgeted	0	0	1	0	0
			CA Routing	Approvals	0	0	0	0	0
			CA Submitted	Approvals	0	0	0	0	0
			Complete	Complete	0	0	1	0	3
			Execute	Execution	6	7	0	7	17
			Execute 1	Execution	0	0	0	0	0
			Execute 2	Execution	0	0	0	0	0
			Financial Closed	Complete	0	0	0	0	0
			FXNL LT Appr	Initiation	0	0	1	0	11
			Hold	Hold	1	1	0	1	0
			Idea	Initiation	1	0	1	0	5
			JPMT Appr	Approvals	0	0	0	0	0
			IMPACT Appr	Approvals	0	0	0	0	0
			Placeholder	Initiation	0	0	1	0	0
			PTAA	PTAA	0	0	0	0	0
			TBD	TBD	0	0	0	0	0
			Canceled		0	0	0	1	0
				TOTAL	8	8	5	7	36

			Program	Nro. Projects	2015 Total Cost (Cap+Expense)	Resources	Rate / FTE	Total Resource Cost	Fully Loaded Cost	Variance
			Agile	8	#REF!	-	$264,000	$0	#REF!	#REF!
			ACCR	8	$0k	-	$264,000	$0	$0	#DIV/0!
			Launch Facility	5	$22,400k	-	$264,000	$0	$22,400,000	0%
			Multi Product	7	$0k	-	$264,000	$0	$0	#DIV/0!
			Reliable	36	$906k	0.1	$264,000	$13,200	$918,742	1%

			Waterfall
				10
			New	1
			Estimate Increased	3
			Removed	-1
			Delayed	-2

## MO5_Monthly_Cashflow_2016
	MASTER PORTFOLIO
	Monthly Cashflow - 2016
						2016
	Project No.	Project Title	Credit Type	Status	PMO Lead	SME	Estm/ / Budg?	Type of Expend.		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	2016 Current Forecast	Budget 2016
1	64901	MCS Peripheral Asset Replacement - 2015		Execute			Estm	Capital		$1k	$2k			$25k	$30k	$15k	$16k	$11k				$100k	$100k	0.0
						Estm	Expense					$k	$k	0.0
1	64914	QC M9 TOC Analyzers					Estm	Capital			$17k			$1k					$19k	$19k	0.0
						Estm	Expense					$k	$k	0.0
1	64923	QC Met-One Air Sampler Replacement 2015					Estm	Capital					$16k					$16k	$16k	0.0
						Estm	Expense					$k	$k	0.0
1	64927	QC Gel Imager Replacement 2015					Estm	Capital				$1k		$2k					$3k	$3k	0.0
						Estm	Expense					$k	$k	0.0
1	73356	Supplemental BDU Sampling	Individual	Execute 2	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Jim Neeleman	Estm	Capital		$30k	$82k	$45k					$158k	$158k	0.0
						Estm	Expense					$k	$k	0.0
1	73367	FS & DS Automation Integration	Individual	Execute 2	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Zaymar Sedra	Estm	Capital		$18k	$8k	$1k					$27k	$27k	0.0
						Estm	Expense					$k	$k	0.0
1	73384	Caustic Bath Upgrade		Execute			Estm	Capital					$3k	$9k					$12k	$12k	0.0
						Estm	Expense				$k					$k	$k	0.0
1	73387	MCSBACKUP Phase 2 Tape Retrieval		Execute			Estm	Capital					$5k					$5k	$5k	0.0
						Estm	Expense					$k	$k	0.0
1	73388	SIMCA Online Real Time Process Monitoring System	Global	Execute	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Jim Neeleman	Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
1	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Global	Execute	Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Scott Fields	Estm	Capital		$12k	$4k	$12k	$64k	$74k	$39k					$205k	$205k	0.0
						Estm	Expense					$k	$k	0.0
1	73399	Frit Handling and Storage	Global	Execute	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Melanie Yevilov	Estm	Capital		$1k		$4k	$41k	$2k	-$8k	$49k	$94k	$10k				$192k	$192k	0.0
						Estm	Expense					$15k					$15k	$15k	0.0
1	73409	Solar Power Enabling Project		Execute			Estm	Capital		-$9k	$97k	$79k	$100k	$30k	$8k					$306k	$306k	0.0
						Estm	Expense					$k	$k	0.0
1	74119	Harvest Upgrade (New Centrifuge)	Individual	Execute 2	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Zaymar Sedra	Estm	Capital		-$1,074k	$1,175k	$716k	$660k	$627k	$649k	$811k	$724k	$745k	$648k	$777k	$544k	$7,001k	$7,001k	0.4
						Estm	Expense		$1k	$1k	$1k	$8k	$4k	$4k	$5k	$4k	$3k	$2k	$3k	$1k	$37k	$37k	1.0
1	74127	Harvest Modifications Start-up		Budgeted			Estm	Capital					$10k	$15k	$28k	$22k	$50k	$125k	$125k	0.0
						Estm	Expense					$k	$k	0.0
1	74268	P2 Downstream Processing Expansion	Individual	Execute 2	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Zaymar Sedra	Estm	Capital		-$3,393k	$10,209k	$4,758k	$13,745k	$9,268k	$8,501k	$10,189k	$8,666k	$8,573k	$7,176k	$8,629k	$6,082k	$92,404k	$92,404k	-0.5
						Estm	Expense		$97k	$111k	$132k	$112k	$144k	$118k	$127k	$106k	$84k	$68k	$85k	$64k	$1,248k	$1,248k	0.0
1	74277	P2 DPE Start-Up		Execute			Estm	Capital				$289k	$171k	$140k	$188k	$241k	$539k	$527k	$661k	$687k	$1,018k	$4,461k	$4,461k	-1.0
						Estm	Expense					$k	$k	0.0
1	74279	New Media Technology - HTST / Adventitious	Individual	Execute 2	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Scott Fields	Estm	Capital		$166k	$136k	$111k	$632k	$919k	$477k	$337k	$262k	$267k	$520k	$513k	$472k	$4,811k	$4,811k	0.0
						Estm	Expense		$1k		$1k					$2k	$2k	0.0
1	74302	Waterpooling Remediation	Individual	Execute 2	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Scott Fields	Estm	Capital		$8k	$19k	$k	$k	$1k	$1k	$1k		$103k	$83k	$77k	$77k	$370k	$370k	0.0
						Estm	Expense					$k	$k	0.0
1	74368	Dev/Val Automation Capacity Expansion		Execute			Estm	Capital					$5k	$5k					$10k	$10k	0.0
						Estm	Expense					$k	$k	0.0
1	74373	WFI Generation and Storage System / CUB Expansion	Individual	Execute 2	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Zaymar Sedra	Estm	Capital		$198k	$710k	$1,034k	$675k	$763k	$750k	$650k	$300k	$100k	$75k	$135k	$135k	$5,523k	$5,523k	0.0
						Estm	Expense				$1k		$13k					$13k	$13k	0.0
1	74382	Sci&Eng Lab Mods and Equipment	Individual	Execute 2	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Jim Neeleman	Estm	Capital		$391k	$832k	$373k	$985k	$382k	$371k	$887k	$701k	$362k	$342k	$250k	$356k	$6,232k	$6,232k	0.0
						Estm	Expense		$1k	$20k	$3k			$217k	$217k					$458k	$458k	0.0
1	74392	Water Reclaim System	Individual	Execute	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Scott Fields	Estm	Capital		$k		$2k					$72k	$40k	$28k	$20k	$162k	$162k	0.0
						Estm	Expense					$k	$k	0.0
1	74404	Mezzanine Lift Media Prep: Phase 1B	Individual	Execute	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Melanie Yevilov	Estm	Capital		-$4k	$85k	$6k	$7k	$65k	$18k	$18k			$6k			$201k	$201k	0.0
						Estm	Expense		-$1k		$k					$k	$k	0.0
1	74406	Corrosive Chemical Compliance	Individual	Execute	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Scott Fields	Estm	Capital		$5k					$50k	$201k	$335k	$419k	$335k	$251k	$1,596k	$1,596k	-1.0
						Estm	Expense					$k	$k	0.0
1	74416	Asphyxiant Gas Remediation	Individual	Execute 1	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Melanie Yevilov	Estm	Capital		$k	$k		$7k	$8k	$8k	$8k	$8k		$15k	$26k	$62k	$142k	$142k	0.0
						Estm	Expense					$k	$k	0.0
1	74418	QC Lab Reconfiguration & Equipment	Individual	Execute 1	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Jim Neeleman	Estm	Capital		$1k		$k	$k		-$57k	-$57k		$17k	$385k	$908k	$719k	$1,918k	$1,918k	0.0
						Estm	Expense					$57k	$57k					$113k	$113k	0.0
1	74426	Process VSD and SOV Replacement - 2015	Individual	Execute	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Scott Fields	Estm	Capital		$114k	$19k	$23k	$28k	$18k	$38k	$115k	$140k					$495k	$495k	-1.0
						Estm	Expense					$k	$k	0.0
1	74427	MCS Network Infrastructure Asset Replacement - 2016		Execute			Estm	Capital					$448k	$416k	$48k	$578k	$221k	$114k	$119k			$1,944k	$1,944k	0.0
						Estm	Expense					$k	$k	0.0
1	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Individual	Execute	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Scott Fields	Estm	Capital		$5k	$51k	$22k	$10k	$19k	$19k	$13k	$13k	$2k	$2k	$21k	$21k	$198k	$198k	0.0
						Estm	Expense					$k	$k	0.0
1	74453	NPI Pool Tanks		PTAA			Estm	Capital		$k	$321k	$101k	$33k	$36k	$37k	$45k	$36k	$27k	$18k	$27k	$3k	$685k	$685k	0.0
						Estm	Expense		$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$3k	$3k	0.0
1	74454	Seed Lab (20L Bioreactor)		Execute			Estm	Capital		-$110k	$k	$k	$134k	$112k	$117k	$148k	$129k	$123k	$100k	$131k	$71k	$955k	$955k	0.0
						Estm	Expense		$1k	$2k	$2k	$18k	$19k	$19k	$23k	$19k	$14k	$9k	$14k	$2k	$142k	$142k	0.0
1	74455	3rd HCCF Vessel		Execute			Estm	Capital		-$141k	$4k	$40k	$291k	$241k	$250k	$332k	$267k	$228k	$160k	$314k	$42k	$2,027k	$2,027k	0.0
						Estm	Expense		$3k	$6k	$6k	$5k	$4k	$4k	$5k	$4k	$3k	$2k	$3k	$k	$44k	$44k	0.0
1	74486	PCS Controller Cabinet Asset Replacement		Execute			Estm	Capital					$184k	$407k	$520k	$481k	$267k	$259k	$176k	$2,294k	$2,294k	0.0
						Estm	Expense					$k	$k	0.0
1	74487	Process VSD and SOV Asset Replacement		Execute			Estm	Capital					$3k	$415k	$611k	$623k	$652k	$530k	$764k	$3,599k	$3,599k	0.0
						Estm	Expense					$k	$k	0.0
1	74489	4040 Avenida Conference Center Acquisition		Execute			Estm	Capital				-$1k				$50k	$50k	$100k	$100k	$200k	$188k	$687k	$687k	0.0
						Estm	Expense					$k	$k	0.0
1	74490	Hyfish Material Screening Operation		Execute			Estm	Capital		$194k	$18k	$90k	$63k	$26k	$23k	$9k					$423k	$423k	0.0
						Estm	Expense					$k	$k	0.0
1	74491	Etro Tech Transfer		Idea			Estm	Capital					$1,507k	$745k	$2,131k	$175k	$1,536k	$6,095k	$6,095k	0.0
						Estm	Expense					$37k	$9k	$10k	$53k	$9k	$117k	$117k	0.0
1	74510	PCS Asset Replacement - 2016		Execute			Estm	Capital				$25k	$1k		$680k	$389k	$105k	$105k	$147k	$147k	$147k	$1,746k	$1,746k	0.0
						Estm	Expense			$k					$k	$k	0.0
1	74511	QR018 Compliance Steam and Condensate Containment		Execute			Estm	Capital					$44k	$71k	$163k	$161k	$344k	$512k	$650k	$1,943k	$1,943k	0.0
						Estm	Expense					$k	$k	0.0
1	74524	Bioburden 2606 IPA Exhaust Improvement		Execute			Estm	Capital					$k	$k	0.0
						Estm	Expense					$2k	$1k	$6k					$9k	$9k	0.0
1	74526	Utility and Process Safety System		FXNL LT Appr			Estm	Capital					$255k	$255k	$255k	$255k	$170k	$1,190k	$1,190k	0.0
						Estm	Expense					$k	$k	0.0
1	76643	Optimize Column Movement Device	Global	Execute	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Melanie Yevilov	Estm	Capital		$16k	$30k	$k		$12k	$73k				$12k			$143k	$143k	0.0
						Estm	Expense					$k	$k	0.0
1	65005	Analytical Scale					Estm	Capital		$24k	$k					$24k	$24k	0.0
						Estm	Expense					$k	$k	0.0
1	65009	Drum Mover/Raw Material Tenderizer					Estm	Capital					$15k	$15k				$30k	$30k	0.0
						Estm	Expense					$4k					$4k	$4k	0.0
1	65018	Spare Bowl for Hermetic Centrifuge		Execute			Estm	Capital					$320k					$320k	$320k	0.0
						Estm	Expense					$k	$k	0.0
1	65015	Lower Solid Collector for Centrifuge		Execute			Estm	Capital					$245k					$245k	$245k	0.0
						Estm	Expense					$k	$k	0.0
1	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital					$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$494k	$494k	-3.0
						Estm	Expense					$k	$k	0.0
1	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital					$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$62k	$62k	1.0
						Estm	Expense					$k	$k	0.0
1	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital					$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$25k	$25k	1.5
						Estm	Expense					$k	$k	0.0
1	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital					$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$132k	$132k	-1.0
						Estm	Expense					$k	$k	0.0
1	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital					$13k	$13k	$13k	$13k	$13k	$13k	$13k	$13k	$13k	$114k	$204k	-89997.5
						Estm	Expense					$k	$k	0.0
1	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital					$8k	$8k				$16k	$16k	0.5
						Estm	Expense					$k	$k	0.0
1	65020	QC Auto-Pipettor for Potency Assay		Execute			Estm	Capital					$28k					$28k	$28k	0.0
						Estm	Expense					$k	$k	0.0
1	65023	QC Plate Washer for Potency Assay		Execute			Estm	Capital				$57k					$57k	$57k	0.0
						Estm	Expense					$k	$k	0.0
1	65021	Hazardous Material Response Cart		Execute			Estm	Capital					$19k					$19k	$19k	0.0
						Estm	Expense					$k	$k	0.0
1	65024	Sci and Eng Lab Incubator and Freezer Asset Replacement		Execute			Estm	Capital					$140k					$140k	$140k	0.0
						Estm	Expense					$k	$k	0.0
1	96174	Fall Protection Phase II		Idea			Estm	Capital					$5k	$10k	$25k	$35k	$35k	$25k	$135k	$135k	0.0
						Estm	Expense					$k	$k	0.0
1	65040	Sci&Eng Cryofreezer		Execute			Estm	Capital					$20k					$20k	$20k	0.0
						Estm	Expense					$k	$k	0.0
1	65037	Analytical Scales (CAPA 1150248)					Estm	Capital					$24k					$24k	$24k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	65048	Process Maintenance Boroscope					Estm	Capital					$37k					$37k	$37k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)					Estm	Capital					$8k	$46k	$116k	$136k	$306k	$306k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	65044	Additional MCS Backup Storage					Estm	Capital					$12k	$12k	$12k	$12k	$12k				$62k	$62k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
1	74431	Buffer Prep Mezzanine Lift Construction	Global	JPMT Appr	Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	Scott Fields	Estm	Capital					$41k	$48k	$56k	$59k	$238k				$442k	$442k	0.0
						Estm	Expense					$k	$k	0.0
0	96137	Security Systems Upgrade		Hold			Estm	Capital					$175k					$175k	$175k	0.0
						Estm	Expense					$k	$k	0.0
0	96152	Appleton Tank Mover		Hold			Estm	Capital					$73k					$73k	$73k	0.0
						Estm	Expense					$k	$k	0.0
0	96207	Weigh and Dispense Sink (CAPA1123109)		FXNL LT Appr			Estm	Capital					$25k					$25k	$25k	0.0
						Estm	Expense					$5k					$5k	$5k	0.0
0	96132	Mezzanine Safety Shower/Eye Wash Station Install		IMPACT Appr			Estm	Capital					$100k	$100k	$100k	0.0
						Estm	Expense					$k	$k	0.0
0				#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
						$k	$k	0.0
1	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital					$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$55k	$494k	$494k	0.0
						Estm	Expense					$10k	$10k					$20k	$20k	0.0
1	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital					$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$7k	$62k	$62k	0.0
						Estm	Expense					$1k	$1k					$2k	$2k	0.0
1	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital					$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$3k	$25k	$25k	0.0
						Estm	Expense					$k	$k	0.0
1	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital					$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$15k	$132k	$132k	0.0
						Estm	Expense					$1k	$2k	$2k			$5k	$5k	0.2
1	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital					$23k	$23k	$23k	$23k	$23k	$23k	$23k	$23k	$23k	$204k	$204k	0.0
						Estm	Expense					$k	$k	0.0
1	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital					$k	$k	$k	$k	$8k	$8k	$k	$k	$k	$16k	$16k	0.0
						Estm	Expense					$k	$k	0.0
1	96159	OCC Network Remediation		Idea			Estm	Capital					$50k	$50k	$50k			$150k	$150k	0.0
						Estm	Expense					$k	$k	0.0
1	74435	Hastelloy Chromatography Column (160cm)		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
1	96135	QC Spectrophotmeters		Hold			Estm	Capital					$23k					$23k	$23k	0.0
						Estm	Expense					$k	$k	0.0
1	74409	K6 Program - Project 1 - Replace DX HVAC Units	Individual	Execute	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Zaymar Sedra	Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74527	Vessel 1020 Upgrade		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96134	QC Liquid Handler		Canceled			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
1	74385	Media Prep Endotoxin/Bioburden Sampling		Idea			Estm	Capital					$83k	$83k	$83k	$250k	$250k	0.0
						Estm	Expense					$k	$k	0.0
1	96164	Hazardous Materials Containers Washing Station		Placeholder			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96167	Emergency Generator High Level Alarm		Idea			Estm	Capital					$25k					$25k	$25k	0.0
						Estm	Expense					$k	$k	0.0
0	96168	Replace Warehouse #321 Sprinkler Heads		Idea			Estm	Capital					$20k				$20k	$20k	0.0
						Estm	Expense					$k	$k	0.0
0	74525	CIP Reliability and Efficiency - PI					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96114	QC Testing Equipment for Launch Capability and Storage Requirements					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96169	Level Indicator Transmitters					Estm	Capital					$70k			$70k	$70k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96208	RF Sealer Generator					Estm	Capital					$22k			$17k	$17k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96139	Trash Bin Storm Water Mitigation		Hold			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96136	V-3007 Replacement		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74432	K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74278	K6 Program - Project 3 - Replace Cold Room Compressors		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74512	K6 Program - Project 2 - B381 Compliance		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96133	QC Rapid Scan RDI System		Hold			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96165	WAN Link Redundancy		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74371	Odor Treatment		FXNL LT Appr			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74513	Electric Vehicle Charging Stations					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96163	MFG Depth Filter Housing		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96069	Warehouse Crown Forklift Asset Replacement					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96105	TMAC Tenderizer					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96109	Sci&Eng Lab Equipment for NPI and Launch Capability					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96112	Maintenance Ops Shop Buildout					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96116	PCS Process Support Equipment Integration					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96124	Perjeta Tech Transfer		Idea			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96177	Efficiency Projects					Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0						Estm	Capital					$k	$k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0		Contingecy					Estm	Capital		$357k	$435k	$342k	$349k	$362k	$357k	$305k	$265k	$252k	$216k	$219k	$180k	$3,639k	$3,639k	0.0
				#N/A			Estm	Expense					$k	$k	0.0
0	96999	Site Adjustment		TBD			Estm	Capital		-$146k	-$178k	-$140k	-$143k	-$148k	-$146k	-$125k	-$108k	-$103k	-$88k	-$90k	-$73k	-$1,487k	-$1,487k	0.0
						Estm	Expense		$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0.0
		TOTAL Capex				TOTAL				-$3,233k	$14,216k	$8,137k	$18,842k	$13,942k	$14,149k	$16,738k	$16,298k	$14,943k	$15,427k	$15,675k	$14,273k	$159,403k	$159,493k

1	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		Execute 1			Estm	Expense		$23k	$26k	$73k	$28k	$75k	$99k	$99k	$99k	$84k	$64k	$81k	$183k	$934k	$934k	0.0
1	97003	MFG Systems Integration Improvement Phase 1 - 2015		Execute 1			Estm	Expense					$55k	$58k	$50k	$50k	$50k	$110k	$70k		$443k	$443k	0.0
1	97007	Automation System Lifecycle MCS Upgrade		Execute			Estm	Expense				$45k		$193k			$57k					$295k	$295k	0.0
1	97048	Arc Flash Prevention		Execute			Estm	Expense					$59k	$10k	$11k	$18k	$19k	$25k	$178k		$319k	$319k	0.0
1	97058	Parking Pavement Repair		Execute			Estm	Expense		$140k		$105k					$245k	$245k	0.0
1	98026	Launch Capability Program (LCP)					Estm	Expense		$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$800k	$800k	4.0
1	97059	B311 & B321 Gowning Room Modifications		Execute			Estm	Expense					$107k					$107k	$107k	0.0
1	97053	Pressure Safety Program - PI Phase					Estm	Expense					$20k	$20k	$20k	$20k				$20k	$100k	$100k	0.0
1	N/A	CRB, travel, ofc supplies, trailer, others					Estm	Expense		$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$26k	$317k	$317k	0.0
0	97057	Conference Room 315 Expansion		Idea			Estm	Expense					$108k	$108k	$108k	0.0
1		PCS Asset Replacement Depreciation Write-Off					Estm	Expense		$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$67k	$800k	$800k	4.0
1		Piping Corrosion					Estm	Expense		$115k	$23k	$307k	$335k	$583k	$349k	$173k	$259k	$207k	$199k	$187k	$356k	$3,091k	$3,091k	0.0

1	97040	Tech Transfer: Master Data Management		FXNL LT Appr			Estm	Expense					$k	$k	0.0
1	97038	PCS Functional Specification Development Project (CAPA 960297)		FXNL LT Appr			Estm	Expense					$k	$k	0.0
1	97039	PCS Remediation for EBR Review by Exception - PI		Idea			Estm	Expense					$k	$k	0.0
0	97045	Site Exterior Lighting Upgrade - Title 24		FXNL LT Appr			Estm	Expense					$33k	$33k	$33k	$100k	$100k	-1.0
1	97054	HVAC Retro Commissioning		FXNL LT Appr			Estm	Expense	#REF!					$k	$k	0.0
0	97061	Tangential Flow Filtration Cassettes Management		#REF!			Estm	Expense	#REF!					$k	$k	0.0
0	97005	MCS Peripheral Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97009	MES Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97012	Site Data Historian Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97015	MCS Backup System Asset Replacement - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97030	MFG Systems Integration Improvement Phase 3 - 2017					Estm	Expense	#REF!					$k	$k	0.0
0	97031	MCS Data Analytics Asset Replacement - 2017					Estm	Expense					$k	$k	0.0
0	97037	Recipe Reconfiguration Alignment for Operating Systems					Estm	Expense	#REF!					$k	$k	0.0
0	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!					$30k	$45k					$75k	$75k	0.0
	97999	Site Adjustment					Estm	Expense					$k	$k	0.0
		TOTAL Expense Projects				TOTAL				$437k	$208k	$690k	$523k	$1,282k	$741k	$512k	$662k	$519k	$591k	$709k	$860k	$7,735k	$7,735k
		Total Capital				TOTAL		Capital		-$3,336k	$14,077k	$7,991k	$18,699k	$13,756k	$13,719k	$16,268k	$16,121k	$14,828k	$15,334k	$15,517k	$14,198k	$157,166k	$157,256k
		Total Expense					Expense		$541k	$348k	$836k	$666k	$1,468k	$1,171k	$983k	$838k	$634k	$685k	$868k	$935k	$9,972k	$9,972k
		Cashflow Variance					Capital	#DIV/0!					$3,800,236	$3,800,236
						Expense
						(10,927,625.80)

						10%	12%	9%	10%	10%	10%	8%	7%	7%	6%	6%	5%
						5%	8%	6%	5%	6%	8%	9%	8%	11%	21%	7%	7%

	BELOW THE LINE
0	96162	Pressure Safety Improvements		#N/A			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64922	QC Mettler Toledo Balances Replacement 2015		Execute			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64924	QC Biotek LAL Reader Replacement 2015		Execute			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	64926	QC SpeedVac Replacement 2015		Complete			Estm	Capital					$k	$k	0.0
						Estm	Expense					$k	$k	0.0
0	96160	B331 HVAC Fire Code Compliance		Canceled			Estm	Capital					$1,000k					$1,000k	$k	1000000.0
						Estm	Expense					$k	$k	0.0

1	97049	SIMCA Online - Downstream Application					Estm	Expense					$k	$k	0.0
0	97029	Study for K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Expense	#REF!					$k	$k	0.0
1	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!					$30k	$45k					$75k	$75k	0.0

## MO5_Monthly_Cashflow_2017
				105,951,624.00
	MASTER PORTFOLIO					5,702,276.48
	Monthly Cashflow - 2016
				2015					2017
	Project No.	Project Title	Credit Type	Status	PMO Lead	SME	Estm/ / Budg?	Type of Expend.	Budget 2015		Current Forecast	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	2017 Current Forecast	Budget 2017
1	64901	MCS Peripheral Asset Replacement - 2015		Execute			Estm	Capital	#REF!		$225k					$171k	$36k	$7k	$k	$6k	$5k					$k	$k	0
				Estm	Expense	#REF!		$100k					$40k	$30k	$10k	$10k	$10k					$k	$k	0
1	64914	QC M9 TOC Analyzers					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	64923	QC Met-One Air Sampler Replacement 2015					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	64927	QC Gel Imager Replacement 2015					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	73356	Supplemental BDU Sampling	Individual	Execute 2	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$1,475k	$81k	$100k	-$3k	$296k	$157k	$141k	$144k	$111k	$115k	$123k	$115k	$95k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	73367	FS & DS Automation Integration	Individual	Execute 2	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$467k		$212k	-$16k	$103k	$28k	$25k	$28k	$26k	$16k	$29k	$16k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	73384	Caustic Bath Upgrade		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	73387	MCSBACKUP Phase 2 Tape Retrieval		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	73388	SIMCA Online Real Time Process Monitoring System	Global	Execute	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$264k	$258k					$1k	$5k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$22k					$1k	$3k	$3k	$3k	$3k	$3k	$3k	$3k					$k	$k	0
1	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Global	Execute	Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Scott Fields	Estm	Capital	#REF!	#REF!	$116k					$5k	$11k	$60k	$40k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	73399	Frit Handling and Storage	Global	Execute	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$15k					$15k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	73409	Solar Power Enabling Project		Execute			Estm	Capital	#REF!	#REF!	$184k					$26k	$49k	$109k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74119	Harvest Upgrade (New Centrifuge)	Individual	Execute 2	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$4,492k					$2,049k	$448k	$389k	$501k	$528k	$577k	$599k	$619k	$611k	$600k	$575k	$554k	$491k	$470k	$176k	$79k	$20k	$39k	$4,834k	$4,834k	-2
				Estm	Expense	#REF!	#REF!	$42k					$3k	$3k	$3k	$3k	$3k	$27k	$48k	$1k	$1k	$1k	$1k					$51k	$51k	0
1	74127	Harvest Modifications Start-up		Budgeted			Estm	Capital	#REF!		$k					$k	$2,275k	-2275000
				Estm	Expense	#REF!		$k					$k	$k	0
1	74268	P2 Downstream Processing Expansion	Individual	Execute 2	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$46,114k	-$761k	$1,384k	$1,731k	$2,455k	$5,656k	$3,566k	$5,313k	$3,897k	$5,141k	$6,318k	$6,234k	$5,181k	$6,312k	$5,696k	$4,805k	$4,001k	$3,578k	$2,924k	$2,804k	$2,279k	$390k	$144k	$144k	$288k	$33,364k	$33,364k	0
				Estm	Expense	#REF!	#REF!	$3,346k	$9k	$11k	$16k	$90k	$54k	$34k	$47k	-$84k	$50k	$51k	$54k	$3,011k	$146k	$144k	$142k	$116k	$115k	$110k	$107k	$37k					$916k	$916k	0
1	74277	P2 DPE Start-Up		Execute			Estm	Capital	#REF!		$k					$2,181k	$2,184k	$6,857k	$6,491k	$6,255k	$6,157k	$6,052k	$1,118k	$899k	$957k	$608k	$524k	$40,281k	$40,281k	-1
				Estm	Expense	#REF!		$k					$k	$k	0
1	74279	New Media Technology - HTST / Adventitious	Individual	Execute 2	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Scott Fields	Estm	Capital	#REF!	#REF!	$2,072k	$9k	$97k	$7k	$116k	$82k	$110k	$69k	$78k	$561k	$354k	$310k	$279k	$614k	$423k	$370k	$140k	$48k	$8k					$1,603k	$1,603k	-1
				Estm	Expense	#REF!	#REF!	$2k				$3k	-$1k					$k	$k	0
1	74302	Waterpooling Remediation	Individual	Execute 2	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Scott Fields	Estm	Capital	#REF!	#REF!	$510k		$139k		$134k	$75k	$41k	$25k	$18k	$24k	$8k	$1k	$45k	$52k					$52k	$52k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74368	Dev/Val Automation Capacity Expansion		Execute			Estm	Capital	#REF!	#REF!	$56k	$68k	-$12k			$3k	-$3k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74373	WFI Generation and Storage System / CUB Expansion	Individual	Execute 2	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$6,162k	$31k	$376k	$759k	$303k	$590k	$176k	$160k	$400k	$815k	$551k	$900k	$1,100k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$93k		$3k	$2k	$2k	$7k	$2k	$8k	$26k	$33k	$4k	$4k	$3k					$k	$k	0
1	74382	Sci&Eng Lab Mods and Equipment	Individual	Execute 2	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$5,270k				$1,056k	$203k	$168k	$185k	$609k	$128k	$1,282k	$1,100k	$539k	$101k	$76k	$74k	$77k	$74k	$81k	$6k					$489k	$489k	0
				Estm	Expense	#REF!	#REF!	$2k				$3k	-$1k					$k	$k	0
1	74392	Water Reclaim System	Individual	Execute	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Scott Fields	Estm	Capital	#REF!	#REF!	$180k				$8k	$26k	$23k	$37k	$30k	$48k	$2k	$4k	$2k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74404	Mezzanine Lift Media Prep: Phase 1B	Individual	Execute	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$262k		$10k		$10k	$34k	$101k	$21k	$12k	$17k	$17k	$20k	$20k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74406	Corrosive Chemical Compliance	Individual	Execute	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Scott Fields	Estm	Capital	#REF!	#REF!	$98k				$6k	$12k	$25k	$22k	$2k	$5k	$5k	$19k	$2k	$84k					$84k	$84k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74416	Asphyxiant Gas Remediation	Individual	Execute 1	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$33k					$2k	$1k	$8k	$22k		$5k	$50k	$75k	$100k	$90k	$80k					$400k	$400k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74418	QC Lab Reconfiguration & Equipment	Individual	Execute 1	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Jim Neeleman	Estm	Capital	#REF!	#REF!	$213k					$1k	$15k	$45k	$26k	$59k	$39k	$28k		$540k	$514k	$343k	$171k					$1,568k	$1,568k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74426	Process VSD and SOV Replacement - 2015	Individual	Execute	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Scott Fields	Estm	Capital	#REF!	#REF!	$203k					$6k	$47k	$100k	$50k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74427	MCS Network Infrastructure Asset Replacement - 2016		Execute			Estm	Capital	#REF!		$7k					$7k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Individual	Execute	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Scott Fields	Estm	Capital	#REF!	#REF!	$311k					$2k	$4k	$210k	$55k	$40k	$21k	$2k					$23k	$23k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74453	NPI Pool Tanks		PTAA			Estm	Capital	#REF!	#REF!	$545k					$273k			$273k				$2k	$1k	$1k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$4k	$4k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0
1	74454	Seed Lab (20L Bioreactor)		Execute			Estm	Capital	#REF!	#REF!	$755k					$345k	$75k	$65k	$84k	$89k	$97k	$154k	$71k	$66k	$44k	$7k	$1k	$1k	$1k	$1k	$1k	$1k	$2k	$353k	$353k	0
				Estm	Expense	#REF!	#REF!	$7k					$k	$k	$1k	$1k	$1k	$4k	$1k	$1k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$2k	$2k	0
1	74455	3rd HCCF Vessel		Execute			Estm	Capital	#REF!	#REF!	$1,079k					$492k	$108k	$94k	$120k	$127k	$139k	$30k	$21k	$16k	$11k	$6k	$4k	$4k	$4k	$4k	$3k	$3k	$6k	$113k	$113k	0
				Estm	Expense	#REF!	#REF!	$10k					$1k	$1k	$1k	$1k	$1k	$6k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	$k	0
1	74486	PCS Controller Cabinet Asset Replacement		Execute			Estm	Capital	#REF!		$450k					$100k	$100k	$250k	$110k					$110k	$110k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74487	Process VSD and SOV Asset Replacement		Execute			Estm	Capital	#REF!		$k					$877k	$1,530k	$519k					$2,925k	$2,925k	0
				Estm	Expense	#REF!		$k					$18k					$18k	$18k	0
1	74489	4040 Avenida Conference Center Acquisition		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74490	Hyfish Material Screening Operation		Execute			Estm	Capital	#REF!		$782k					$36k	$173k	$573k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74491	Etro Tech Transfer		Idea			Estm	Capital	#REF!		$k					$817k	$191k	$1,645k	$436k	$360k	$1,856k	$484k	$484k	$1,932k	$479k	$445k	$3,575k	$12,702k	$12,702k	0
				Estm	Expense	#REF!		$k					$13k	$4k	$9k	$23k	$9k	$24k	$14k	$9k	$9k	$9k	$9k	$4k	$135k	$135k	0
1	74510	PCS Asset Replacement - 2016		Execute			Estm	Capital	#REF!		$k					$149k					$149k	$149k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74511	QR018 Compliance Steam and Condensate Containment		Execute			Estm	Capital	#REF!		$k					$488k	$449k	$365k	$245k	$185k	$113k	$125k	$245k	$245k	$245k	$245k	$125k	$3,075k	$3,075k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74524	Bioburden 2606 IPA Exhaust Improvement		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$138k	$138k	$138k	$138k					$550k	$550k	0
1	74526	Utility Process Safety System		FXNL LT Appr			Estm	Capital	#REF!		$k					$170k	$128k	$128k	$85k					$510k	$510k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	76643	Optimize Column Movement Device	Global	Execute	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Melanie Yevilov	Estm	Capital	#REF!	#REF!	$68k	$25k					$35k				$8k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	65005	Analytical Scale					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	65009	Drum Mover/Raw Material Tenderizer					Estm	Capital					$k	$k	0
				Estm	Expense					$k	$k	0
1	65018	Spare Bowl for Hermetic Centrifuge		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65015	Lower Solid Collector for Centrifuge		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65020	QC Auto-Pipettor for Potency Assay		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65023	QC Plate Washer for Potency Assay		Execute			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	73442	V-2170 Agitator Drain Valve		Canceled			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65021	Hazardous Material Response Cart		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65024	Sci and Eng Lab Incubator and Freezer Asset Replacement		Execute			Estm	Capital	#REF!		$18k					$18k	$101k	$76k	$74k	$77k	$74k	$81k	$6k					$489k	$489k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96174	Fall Protection Phase II		Idea			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65040	Sci&Eng Cryofreezer		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65037	Analytical Scales (CAPA 1150248)		Execute			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	64898	Terumo Sterile BCT SCDIIB Welders		Complete			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	65048	Process Maintenance Boroscope					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)					Estm	Capital					$138k	$80k	$229k	$207k					$654k	$654k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	65044	Additional MCS Backup Storage					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	74431	Buffer Prep Mezzanine Lift Construction	Global	JPMT Appr	Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	Scott Fields	Estm	Capital	#REF!	#REF!	$k					$k	$k	0
				Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	96139	Trash Bin Storm Water Mitigation		Hold			Estm	Capital	#REF!		$k					$k	$200k	-200000
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$18k					$18k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
				$k	$k
1	96991	Asset Replacement 2016 - Engineering (cc642)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96992	Asset Replacement 2016 - Material Ops (cc484)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96993	Asset Replacement 2016 - Manufacturing (cc1359)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96994	Asset Replacement 2016 - Manufacturing (cc659)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96995	Asset Replacement 2016 - Quality (cc583)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96997	Asset Replacement 2016 - Maintenance (cc1236)		FXNL LT Appr			Estm	Capital	#REF!		$73k					$2k	$71k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96159	OCC Network Remediation		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74435	Hastelloy Chromatography Column (160cm)		FXNL LT Appr			Estm	Capital	#REF!		$k					$9k	$526k	$89k	$9k	$81k	$k	$580k	$k	$k	$25k	$22k	$207k	$1,549k	$1,549k	-42
				Estm	Expense	#REF!		$k					$k	$k	0
0	96135	QC Spectrophotmeters		Hold			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	74527	Vessel 1020 Upgrade		Idea			Estm	Capital	#REF!		$k					$k	$4,859k	-4859000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96134	QC Liquid Handler		Canceled			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96137	Security Systems Upgrade		Hold			Estm	Capital	#REF!		$k					$115k					$115k	$k	115000
				Estm	Expense	#REF!		$k					$k	$k	0
1	74385	Media Prep Endotoxin/Bioburden Sampling		Idea			Estm	Capital	#REF!		$k					$83k	$83k	$83k					$250k	$2,750k	-2500000
				Estm	Expense	#REF!		$k					$k	$k	0
1	96132	Mezzanine Safety Shower/Eye Wash Station Install		IMPACT Appr			Estm	Capital	#REF!		$k					$262k	$262k	$262k					$786k	$786k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	96164	Hazardous Materials Containers Washing Station		Placeholder			Estm	Capital	#REF!		$k					$30k					$30k	$30k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96167	Emergency Generator High Level Alarm		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96168	Replace Warehouse #321 Sprinkler Heads		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	74525	CIP Reliability and Efficiency - PI					Estm	Capital					$k	$k	0
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	96152	Appleton Tank Mover					Estm	Capital					$64k					$64k	$k	63694
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	96109	Sci&Eng Lab Equipment for NPI and Launch Capability					Estm	Capital					$k	$600k	-600000
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	96114	QC Testing Equipment for Launch Capability and Storage Requirements					Estm	Capital					$k	$600k	-600000
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	74513	Electric Vehicle Charging Stations					Estm	Capital					$k	$712k	-712000
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$18k	-18000
0	96112	Maintenance Ops Shop Buildout					Estm	Capital					$k	$500k	-500000
				#N/A			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	96999	Site Adjustment		TBD			Estm	Capital	#REF!		$k					$k	-$1,487k	1487180
				Estm	Expense	#REF!		$k					$k	$k	0
		TOTAL Capex				TOTAL			#REF!	#REF!	$75,640k	-$306k	$2,320k	$2,496k	$4,585k	$6,928k	$4,700k	$9,003k	$5,794k	$7,857k	$9,949k	$10,116k	$12,197k	$14,259k	$13,269k	$16,901k	$12,974k	$11,458k	$11,992k	$10,882k	$4,647k	$3,655k	$1,943k	$1,496k	$4,770k	$108,246k	$118,844k

1	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		Execute 1			Estm	Expense	#REF!		$38k					$k	$5k	$k	$32k		$162k	$160k	$327k	$133k					$782k	$782k	-1
1	97003	MFG Systems Integration Improvement Phase 1 - 2015		Execute 1			Estm	Expense	#REF!	#REF!	$15k					$15k					$k	$k	0
1	97007	Automation System Lifecycle MCS Upgrade		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	97048	Arc Flash Prevention		Execute			Estm	Expense	#REF!		$k					$k	$k	0
1	97058	Parking Pavement Repair		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	98026	Launch Capability Program (LCP)					Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	97059	B311 & B321 Gowning Room Modifications		Execute			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	97053	Pressure Safety Program - PI Phase					Estm	Expense					$k	$k	0
1	N/A	CRB, travel, ofc supplies, trailer, others					Estm	Expense	$925k	$k	$925k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k					$k	$k	0
1		PCS Asset Replacement Depreciation Write-Off					Estm	Expense					$k	$k	0
1		Piping Corrosion					Estm	Expense	#REF!	#REF!	$k					$k	$k	0

0	97040	Tech Transfer: Master Data Management		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
0	97038	PCS Functional Specification Development Project (CAPA 960297)		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$4,750k	-4750000
0	97039	PCS Remediation for EBR Review by Exception - PI		Idea			Estm	Expense	#REF!	#REF!	$k					$k	$250k	-250000
0	97045	Site Exterior Lighting Upgrade - Title 24		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$33k	$33k	$33k					$100k	$100k	-1
0	97057	Conference Room 315 Expansion		Idea			Estm	Expense					$192k					$192k	$192k	0
	97999	Site Adjustment					Estm	Expense	#REF!	#REF!	$k					$k	$k
		TOTAL Expense Projects				TOTAL			#REF!	#REF!	$978k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$77k	$82k	$77k	$109k	$92k	$387k	$193k	$361k	$133k	$k	$k	$k	$k	$k	$k	$k	$k	$1,074k	$6,074k
		Total Capital				TOTAL		Capital	#REF!		$73,240k	-$229k	$2,397k	$2,573k	$4,662k	$7,005k	$4,777k	$9,080k	$5,872k	$7,939k	$10,027k	$10,225k	$12,289k	$13,895k	$12,983k	$16,611k	$12,696k	$11,334k	$11,858k	$10,761k	$4,602k	$3,647k	$1,934k	$1,487k	$4,766k	$106,573k	$117,153k
		Total Expense					Expense	#REF!		$4,502k					$751k	$480k	$651k	$410k	$125k	$134k	$121k	$45k	$9k	$9k	$9k	$4k	$2,747k	$7,765k
		Cashflow Variance					Capital	#REF!	#DIV/0!
				Expense	#REF!	#DIV/0!
				(60,196,253.10)

				10%	12%	9%	10%	10%	10%	8%	7%	7%	6%	6%	5%
				5%	8%	6%	5%	6%	8%	9%	8%	11%	21%	7%	7%

	BELOW THE LINE
0	96162	Pressure Safety Improvements		#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64922	QC Mettler Toledo Balances Replacement 2015		Execute			Estm	Capital	#REF!		$60k					$40k	-$23k	$43k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64924	QC Biotek LAL Reader Replacement 2015		Execute			Estm	Capital	#REF!		$19k					$17k		$2k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	64926	QC SpeedVac Replacement 2015		Complete			Estm	Capital	#REF!		$12k					$12k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
1	74371	Odor Treatment		FXNL LT Appr			Estm	Capital	#REF!		$100k					$50k	$50k					$125k	$125k	$125k	$125k	$125k	$125k	$750k	$750k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96136	V-3007 Replacement		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$120k	-120000
				Estm	Expense	#REF!		$k					$k	$k	0
0	96165	WAN Link Redundancy		Idea			Estm	Capital	#REF!		$k					$k	$2,000k	-2000000
				Estm	Expense	#REF!		$k					$k	$k	0
1	74409	K6 Program - Project 1 - Replace DX HVAC Units	Individual	Execute	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Zaymar Sedra	Estm	Capital	#REF!	#REF!	$90k					$50k	$40k					$10k	$100k	$100k	$100k	$310k	$310k	0
				Estm	Expense	#REF!	#REF!	$k					$11k	$11k		$22k	$22k	0
1	74512	K6 Program - Project 2 - B381 Compliance		FXNL LT Appr			Estm	Capital	#REF!		$k					$83k	$83k	$83k	$83k	$333k	$333k	0
				Estm	Expense	#REF!		$k					$6k	$6k	$6k	$6k	$22k	$22k	0
0	74278	K6 Program - Project 3 - Replace Cold Room Compressors		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$528k	-528000
				Estm	Expense	#REF!		$k					$k	$75k	-75000
0	74432	K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Capital	#REF!		$k					$k	$2,650k	-2650000
				Estm	Expense	#REF!		$k					$k	$350k	-350000
0	96160	B331 HVAC Fire Code Compliance		Canceled			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96133	QC Rapid Scan RDI System		Hold			Estm	Capital	#REF!		$k					$210k					$210k	$210k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96163	MFG Depth Filter Housing		Idea			Estm	Capital	#REF!		$k					$k	$300k	-300000
				Estm	Expense	#REF!		$k					$k	$100k	-100000
0	96124	Perjeta Tech Transfer		Idea			Estm	Capital	#REF!		$k					$k	$8,794k	-8793594
				Estm	Expense	#REF!		$k					$k	$147k	-147070
0	96183	Site Signage Upgrade		Idea			Estm	Capital	#REF!		$k					$67k	$67k	$67k					$200k	$200k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96189	Pipe Labelling		Idea			Estm	Capital	#REF!		$k					$33k	$33k	$33k					$100k	$100k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96198	Crane & Hoist Mitigation		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96192	Pressure Safety Facility Mitigations		Idea			Estm	Capital	#REF!		$k					$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$208k	$2,500k	$2,500k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96191	UPSS Phase 2		Idea			Estm	Capital	#REF!		$k					$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$167k	$2,000k	$2,000k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96193	Column Packing Fall Hazard		Idea			Estm	Capital	#REF!		$k					$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$25k	$300k	$300k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96195	K6- All Design		Idea			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0	96204	322 MRO Racks		Idea			Estm	Capital	#REF!		$k					$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$42k	$500k	$500k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0
0				#N/A			Estm	Capital	#REF!		$k					$k	$k	0
				Estm	Expense	#REF!		$k					$k	$k	0

0	97061	Tangential Flow Filtration Cassettes Management		#REF!			Estm	Expense	#REF!	#REF!	$k					$k	$550k	-550000
0	97049	SIMCA Online - Downstream Application					Estm	Expense					$k	$k	0
0	97029	Study for K6 Program - Project 4 - Replace Chillers		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$k	0
1	97054	HVAC Retro Commissioning		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$25k	$11k	$11k	$11k	$11k	$11k	$11k	$11k	$11k	$113k	$113k	0
0	97060	QC Gas Cabinet Removal		FXNL LT Appr			Estm	Expense	#REF!	#REF!	$k					$k	$k	0

## ppms
	Bio Drug Substance - Oceanside			E
	Average Resource Demand			E
	In FTEs
	FTE =	147						T3					Current Estimate					T3
								2014		2015			2016					2016
	Location (Site) Name	Project Indicator	Project number	Project Name	Score	Program	Current Estimate	Roche	External	Roche	External		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Roche	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	External	Total		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Roche	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	External
0	Site Project	Global	64901	MCS Peripheral Asset Replacement - 2015	0	Reliability and Value	$43,151					0.00	0.00	0.00	0.00	0.05	0.05	0.10	0.10	0.10	0.10	0.10	0.12	0.06	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.06		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			65044	Additional MCS Backup Storage	0	Reliability and Value	$62,000					0.00					0.00	0.00	0.00	0.25	0.25	0.25	0.25	0.25	0.25	0.00	0.00	0.00	0.13	0.00	0.00	0.00	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.05
0	Site Project	Individual Project	73356	Supplement BDU Sampling	19.5	Launch and Commercial Excellence	$157,774	0.32	2.70	0.75	6.14		3.84	3.23	1.53	0.00	0.00	2.14	2.48	1.97	1.97	1.56	1.36	0.00	1.68	12.97	12.97	10.72	0.00	0.00	1.81	7.53	11.51	10.35	5.69	4.86	0.95	6.61	8.29		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	73367	FS & DS Automation Integration	24.4	Fit for Purpose	$26,719	2.25	1.17	0.50	0.42		0.20	0.41	0.54	0.60	0.56	0.26	0.00	0.00	0.00	0.00	0.00	0.00	0.21	0.00	2.52	2.52	2.24	1.50	0.82	0.00	0.00	0.00	0.00	0.00	0.00	0.80	1.01		0.36	0.36	0.36	0.36	0.28	0.28	0.29	0.29	0.29	0.29	0.29	0.21	0.31	0.20	0.20	0.20	0.20	0.12	0.12	0.13	0.13	0.13	0.13	0.13	0.09	0.15
0	Site Project	Global	73398	MCS Manufacturing Area Wireless Access Point Upgrade - 2015	10.5	Reliability and Value	$273,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.34	0.00	0.00	0.00	0.00	0.03	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.29	1.29	1.29	1.29	0.43	0.46		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Global	73399	Frit Handling and Storage	11.3	Highly Capable Workforce	$153,215					0.00	0.01	0.03	0.00	0.00	0.00	0.00	0.00	0.02	0.00	0.00	0.00	0.01	0.02	0.09	0.09	0.02	0.00	0.00	0.00	0.00	0.00	0.01	0.00	0.00	0.02	0.02		0.07	0.07	0.58	0.07	0.07	0.14	0.34	0.00	0.00	0.00	0.00	0.00	0.11	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			73406	Guided Wave Radar V-4045 & V-4055	12	Agile	$17,477					0.00	0.00	0.00	0.00	0.00	0.00	0.27	1.63	1.54	0.54	0.41	0.56	0.41					0.27	0.31	0.60	0.16	0.61	0.41	0.39	0.81					0.00					0.00
0			73409	Solar Power Enabling Project	5.1	Highly Capable Workforce	$307,216					0.00	0.00	0.00	0.00	0.00	0.00	0.60	0.63	0.52	0.35	0.41	0.41	0.24	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.24		0.26	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74119	Harvest Upgrade (New Centrifuge)	60	Fit for Purpose	$4,635,852	1.30	1.70	2.50	8.20		0.00	0.00	0.00	0.00	0.60	0.60	0.60	0.59	0.59	0.59	0.59	0.59	0.40	0.00	0.00	0.00	0.00	1.27	1.30	1.30	1.30	1.39	1.06	1.06	1.06	0.81	1.21		2.47	2.47	2.55	2.49	2.43	2.41	2.18	2.18	2.18	2.18	2.18	1.85	2.30	2.25	2.25	2.36	2.36	3.03	3.06	3.10	3.10	3.00	2.67	2.67	2.67	2.71
0			74127	Harvest Modifications Start-up	60	Launch Facility	$125,000					0.00					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.04	0.14	0.14	0.14	1.30	1.44	0.53
1	Site Project	Individual Project	74268	P2 Downstream Processing Expan	60	Fit for Purpose	$93,629,477	10.00	1.60	13.10	3.50		0.00	0.00	0.00	0.00	5.63	5.63	5.63	5.49	5.49	5.49	5.49	5.49	3.70	0.00	0.00	0.00	0.00	11.88	12.15	12.15	12.15	13.05	9.90	9.90	9.90	7.59	11.29		22.73	22.73	23.27	22.73	22.19	22.01	20.30	20.30	20.30	20.30	20.30	17.33	21.21	21.06	21.06	22.14	22.14	28.44	28.71	29.07	29.07	28.17	25.02	25.02	25.02	25.41
0	Site Project	Individual Project	74279	New Media Technology - HTST / Adventitious	19.2	Reliability and Value	$4,947,130	0.76	1.55	1.99	5.02		2.68	2.68	2.68	2.68	2.41	2.48	4.11	5.13	6.19	5.99	6.27	5.78	4.09	3.31	3.31	3.31	3.31	6.61	8.93	10.03	10.03	11.13	11.54	11.16	11.97	7.88	11.97		4.79	3.77	3.87	5.50	5.16	3.71	7.04	7.89	6.19	5.33	4.96	3.60	5.15	13.59	15.05	14.99	13.76	13.11	12.19	12.32	11.34	13.11	15.01	12.72	9.05	13.02
0	Site Project	Individual Project	74302	Water Pooling Remediation	23	Reliability and Value	$369,680	0.83	7.10				1.73	1.99	0.17	0.17	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.34	7.88	0.66	0.66	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.77	1.11		0.00	0.00	0.00	1.36	2.04	2.36	2.02	1.87	0.35	0.00	0.00	0.00	0.83	0.00	0.00	0.00	8.52	8.52	8.52	8.52	8.52	1.27	0.00	0.00	0.00	3.66
0	Site Project	Individual Project	74373	WFI Generation and Storage System / CUB Expansion	11.1	Fit for Purpose	$5,536,207	0.67	0.35	1.00	0.53		1.95	2.75	3.55	4.00	4.60	5.06	5.06	5.06	5.06	5.16	5.21	5.76	4.44	11.92	13.45	13.75	12.51	12.92	8.32	8.04	8.78	9.14	9.78	11.76	12.27	11.05	15.49		6.88	6.78	5.93	3.58	2.93	5.45	5.45	0.00	0.00	0.00	0.00	0.00	3.08	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74382	SciEng Lab Mods and Equiment	7.6	Launch and Commercial Excellence	$7,610,223	0.25	0.25	0.25	0.25		3.62	3.62	3.62	5.87	5.87	5.87	3.56	3.56	3.56	2.75	2.75	2.75	3.95	0.30	0.30	0.30	6.54	6.54	6.54	0.19	0.19	0.19	0.00	0.00	0.00	1.76	5.71		3.40	3.40	3.40	3.40	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.13	1.31	1.31	1.31	1.22	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.43
0	Site Project	Individual Project	74392	Water Reclaim System	6.1	Reliability and Value	$143,846	0.21	0.00	1.42	1.21		0.27	0.27	0.27	0.07	0.01	0.01	0.01	0.88	0.07	1.09	0.09	0.09	0.26					0.00	0.26		1.84	1.84	1.70	0.27	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.47	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74404	Mezzanine Lift Media Prep: Phase 1B	10.7	Highly Capable Workforce	$270,009	0.35	0.05				0.49	0.44	0.38	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.11					0.00	0.11		0.03	0.03	0.03	0.02	0.02	0.01	0.00	0.00	0.00	0.00	0.00	0.00	0.01	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74406	Corrosive Chemical Compliance	34	Reliability and Value	$1,724,239			0.34	0.34		0.51	0.71	0.71	0.65	0.65	0.00	0.00	0.00	0.00	0.00	0.00	0.17	0.28					0.00	0.28		0.23	0.22	0.24	0.21	0.18	0.15	0.03	0.02	0.02	0.02	0.00	0.00	0.11	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74409	K6 Program - Project 1 - Replace DX HVAC Units	11.3	Fit for Purpose	$1,900,000					0.00	0.00	0.00	0.00	0.00	0.00	0.79	0.52	0.14	0.06	0.06	0.06	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.41	0.41	1.10	5.48	5.48	5.48	1.53	1.67		0.10	0.27	0.31	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.06	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74416	Asphyxiant Gas Remediation	11.1	Highly Capable Workforce	$126,295			0.17	0.17		0.00	0.00	0.00	0.00	0.00	0.08	0.14	0.13	0.12	0.06	0.12	0.18	0.07	0.00	0.00	0.00	0.00	0.00	0.31	0.61	0.73	0.87	0.94	0.94	0.28	0.39	0.46		0.14	0.13	0.12	0.06	0.12	0.18	0.00	0.00	0.00	0.00	0.00	0.00	0.06	0.61	0.73	0.87	0.94	0.94	0.28	0.00	0.00	0.00	0.00	0.00	0.00	0.36
0	Site Project	Individual Project	74418	QC Lab Reconfiguration & Equipment	15.8	Launch and Commercial Excellence	$3,274,674	0.50	1.50	2.00	3.00		0.37	0.44	0.61	0.61	0.58	0.51	5.71	9.32	1.05	1.67	0.34	0.27	1.79	1.29	2.59	5.84	6.03	1.26	1.02	2.23	2.23	8.01	5.99	3.61	3.37	3.62	5.41		1.67	0.88	0.58	0.17	0.07	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.28	6.09	3.16	3.16	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.03
0	Site Project	Individual Project	74426	Process VSD and SOV Replacement - 2015	N/A	Reliability and Value	$589,735					0.00	0.00	0.00	0.00	0.00	0.00	0.07	0.07	0.12	0.80	0.07	0.07	0.10	0.00	0.00	0.00	0.00	0.61	0.61	0.61	0.61	1.67	2.43	1.43	0.61	0.72	0.82		0.61	0.61	0.61	0.61	0.14	0.14	0.14	0.14	0.14	0.14	0.14	0.14	0.30	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			74427	MCS Network Infrastructure Asset Replacement - 2016	N/A	Reliability and Value	$1,466,000					0.00					0.31	0.37	0.51	0.31	0.31	0.31	0.44	0.51	0.44	0.00	0.00	0.00	0.29	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74429	Mettler Toledo Weight Transmitter conversion to Hardy Weight Transmitter Asset Replacement- - 2015	7.7	Reliability and Value	$204,573					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.48	0.48	0.48	0.48	0.16	0.00	0.00	0.00	0.00	0.00	0.00	1.59	1.59	1.59	1.59	1.59	1.59	0.79	0.95		0.52	0.52	0.52	0.48	0.48	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.21	1.31	1.31	1.29	1.29	1.29	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.54
0	Site Project	Gllobal	74431	Buffer Prep Mezzanine Lift Construction	10.7	Reliability and Value	$442,000					0.00	0.00	0.00	0.00	0.00	0.00	0.68	0.67	0.26	0.13	0.12	0.12	0.16					0.00	0.16		0.23	0.56	0.34	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.09	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			74435	Hastelloy Chromatography Column	17.1	Fit for Purpose	$400,000					0.00					2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	2.39	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48	3.48
1	Site Project	Individual Project	74454	Seed Lab (20L Bioreactor)	60	Fit for Purpose	$1,010,193					0.00	0.00	0.00	0.00	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.00	0.00	0.00	0.00	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01		0.03	0.03	0.03	0.03	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03
1	Site Project	Individual Project	74455	3rd HCCF	60	Fit for Purpose	$1,704,489					0.00	0.00	0.00	0.00	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.01	0.00	0.00	0.00	0.00	0.04	0.04	0.04	0.04	0.04	0.03	0.03	0.03	0.02	0.04		0.08	0.08	0.08	0.08	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.06	0.07	0.07	0.07	0.07	0.07	0.09	0.10	0.10	0.10	0.09	0.08	0.08	0.08	0.08
0			74486	PCS Controller Cabinet Asset Replacement	N/A	Highly Capable Workforce	$2,294,000					0.00					0.17	0.17	0.20	0.20	0.53	0.53	0.53	0.53	0.53	0.53	0.53	0.53	0.42	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38	0.38
0			74487	Process VSD and SOV Replacement Project	N/A	Highly Capable Workforce	$3,599,797					0.00					0.27	0.27	0.27	0.27	0.27	0.27	0.41	0.54	0.54	0.44	0.23	0.23	0.33	0.00	0.00	0.00	0.00	0.00	0.00	30.54	30.54	30.54	30.57	0.00	0.00	10.18
0			74489	4040 Avenida Conference Center Acquisition	3.1	Exceptional Culture	$685,700					0.00					0.00					0.00
0	Site Project	Individual Project	74490	Hyfish Material Screening Operation	16.3	Reliability and Value	$601,445					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	2.00	2.00	2.00	6.00	6.00	6.00	2.00	2.00		0.59	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74491	Etro Tech Transfer	60	Launch and Commercial Excellence	$1,364,276					0.00					0.00				15.49	22.99	22.99	22.99	26.49	26.49	26.49	31.92	31.92	31.92	25.97	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Global	74511	QR018 Compliance Steam and Condensate Containment	13.3	Reliability and Value	$1,943,300					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.03	0.05	0.00	0.00	0.00	0.00	0.01	0.01		1.31	1.34	1.41	1.27	1.27	1.27	2.44	2.30	2.30	2.30	2.30	2.30	1.82	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74512	K6 Program - Project 2 - B381 Compliance	0	Fit for Purpose	$800,000					0.00	0.00	0.00	0.00	0.00	0.00	0.79	0.52	0.14	0.06	0.06	0.06	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.41	0.41	1.10	5.48	5.48	5.48	1.53	1.67		0.10	0.10	0.10	0.10	0.10	0.10	0.50	0.50	0.50	0.00	0.00	0.00	0.18					0.00
0	Site Project	Individual Project	74524	Bioburden 2606 IPA Exhaust Improvement	18	Reliability and Value	$14,571					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00	0.00		0.12	0.41	0.44	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.08	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			74526	Utility and Process Safety System	13.3	Reliability and Value	$1,882,404					0.00					1.00	1.00					0.00					0.00
0			74535	Draining of Top Mounted Agitator Well	0	Reliability and Value	$306,000					0.00	0.00	0.91	0.97	0.71	0.27	0.06	0.06	0.10	0.88	0.80	0.24	0.42	0.00	0.00	2.31	2.04	2.55	1.87	0.20	0.20	0.95	2.31	2.08	0.78	2.00	2.42		0.91	0.91	0.91	1.94	1.94	1.94	0.22	0.22	0.22	1.93	1.93	1.93	1.25	1.90	1.90	1.90	5.78	5.78	5.78	1.36	1.36	1.36	5.01	5.01	5.01	3.51
0	Site Project	Individual Project	76643	Optimize Column Movement Device	18.6	Highly Capable Workforce	$143,425					0.00	0.32	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.04	0.14	0.14	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.07		0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	3.4	Reliability and Value	$866,058					0.00	0.00	0.00	1.36	1.36	1.36	0.00	0.00	0.00	0.00	0.00	0.00	0.34	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.34		0.70	0.70	0.70	1.00	1.00	1.00	1.00	1.00	1.00	0.00	0.00	0.00	0.68	4.00	4.00	4.00	4.00	4.00	4.00	3.50	3.50	3.50	0.00	0.00	0.00	2.88
0	Site Project	Global	96121	Supplemental Terumo Sterile Connecting Device (SCD IIB) for Upstream	#N/A	#N/A	$32,000					0.00	0.00	0.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25	0.00	0.00	0.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25	0.50					0.00					0.00
0	Site Project	Global	96135	QC Spectrophotmeters	14.4	Highly Capable Workforce	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00		0.50	0.50	0.50	0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.18					0.00
0			96159	OCC Network Remediation	22.8	Fit for Purpose	$150,000					0.00					0.00					0.00
0	Site Project	Expense	97003	MFG Systems Integration Improvement Phase 1 - 2015	15.3	Reliability and Value	$606,000					0.00	0.00	0.00	0.00	0.00	0.00	2.26	2.26	2.26	2.26	2.26	2.26	1.13	0.14	0.14	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.04	1.17		2.26	2.26	2.26	2.26	2.26	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.94	2.67	2.67	2.67	2.67	1.59	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.02
0	Site Project	Expense	97007	Automation System Lifecycle MCS Upgrade	27.6	Reliability and Value	$813,000					0.25	0.25	0.25	0.25	0.25	0.25	1.00	1.00	1.00	1.00	1.00	1.00	0.63	0.00	0.00	0.00	0.10	0.10	0.10	1.99	1.99	1.99	3.97	3.97	3.97	1.51	2.14		2.04	2.04	2.04	2.04	2.04	2.04	2.38	2.38	2.38	0.68	0.68	0.68	1.79					0.00
0			97059	B311 and B321 Gowning Room Modifications	0	Reliability and Value	$100,492					0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05
1			96174	Fall Protection Phase II	3.6	TBD	$130,000					0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.11	0.03	0.03	0.05	0.07	0.04					0.00					0.00
0			96215	20L Bioreactors and NovaFlex Analyzer	20	Fit for Purpose	$450,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.00	1.00	1.00	0.25					0.00					0.00
0	Site Project	Global	64777	Biosafety & Laminar Flow Hood Asset Replacement	#N/A	#N/A	$0					0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05		0.14	0.14	0.14	0.13	0.11	0.10	0.07	0.07	0.07	0.07	0.07	0.07	0.10	0.11	0.11	0.11	0.11	0.10	0.09	0.08	0.08	0.08	0.08	0.08	0.08	0.09
0	Site Project	Global	64786	Cedex System for Sci&Eng Asset Replacement	#N/A	#N/A	$0					0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05					0.00	0.05					0.00					0.00
0	Site Project	Individual Project	73328	Filter Integrity Testers	#N/A	#N/A	$0					0.15	0.15	0.15	0.15	0.15	0.15	0.15	0.10	0.00	0.00	0.00	0.00	0.10					0.00					0.00
0	Site Project	Individual Project	73368	Cooling Tower Water Filtration System	#N/A	#N/A	$0					0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.02					0.00					0.00
0	Site Project	Individual Project	73377	Upstream Buildout (PI)	#N/A	#N/A	$0	0.63	0.78				2.40	2.50	2.40	2.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.78					0.00	0.78					0.00					0.00
0	Site Project	Global	73383	Actemra Freezer Installation	#N/A	#N/A	$0					0.45	0.31	0.18	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.08	1.22	0.93	0.20	0.03	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.28		0.15	0.15	0.17	0.17	0.17	0.17	0.13	0.13	0.13	0.13	0.11	0.08	0.14	0.11	0.11	0.11	0.11	0.11	0.11	0.11	0.11	0.11	0.11	0.11	0.08	0.11
0	Site Project	Global	73387	MCSBACKUP Phase 2 Tape Retrieval	N/A	Reliability and Value	$0					0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05					0.00	0.05		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.00	1.00	1.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.50
0	Site Project	Individual Project	73388	SIMCA Online Real Time Process Monitoring System	7.8	Launch and Commercial Excellence	$0					0.03	0.17	0.19	0.16	0.17	0.10	0.24	0.24	0.24	0.22	0.22	0.17	0.18	0.00	0.00	0.00	0.12	0.12	0.12	0.12	0.12	0.12	1.99	1.99	1.99	0.56	0.74					0.00					0.00
0	Site Project	Individual Project	74244	Cell Culture Sampling	#N/A	#N/A	$0	0.56	2.79	0.34	2.55		0.80	0.86	0.81	0.72	0.72	0.12	0.00	0.00	0.00	0.00	0.00	0.00	0.34	6.91	6.50	6.03	5.59	2.49	1.81	1.20	0.00	0.00	0.00	0.00	0.00	2.54	2.88		0.47	0.47	0.46	0.46	0.44	0.46	0.40	0.40	0.40	0.40	0.40	0.29	0.42	0.26	0.26	0.26	0.30	0.30	0.30	0.30	0.30	0.30	0.30	0.30	0.23	0.28
0			74278	K6 Program - Project 3 - Replace Cold Room Compressors	16.5	Fit for Purpose	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.64	0.93	0.91	0.21					0.61	0.37	0.32	0.32	0.31	0.32	0.36	0.72	0.94	0.00	0.00	0.00	0.36	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74280	OCN B311 Hastelloy Columns	11.6	Agile	$0	0.40	0.30	0.49	0.41		0.26	0.02	0.02	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.20	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.02	0.05		0.02	0.02	0.02	0.02	0.02	0.02	0.01	0.01	0.01	0.01	0.01	0.01	0.02	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.01
0	Site Project	Individual Project	74371	Waste Water Recovery System and Odor Treatment - PI Phase	6.8	TBD	$0			0.25	0.25		0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.10					0.20	0.20	0.20	0.20	0.20					0.30	0.30	0.30	0.30	0.30
0	Site Project	Global	96046	Refrigerators for Microbiology	#N/A	#N/A	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.20	0.20	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00
0	Site Project	Global	96047	Incubators for Microbiology	#N/A	#N/A	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.20	0.20	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00
0	Site Project	Global	96069	Warehouse Crown Forklift	N/A	Fit for Purpose	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.03	0.05	0.00	0.00	0.00	0.00	0.01	0.01					0.00					0.00
0			96107	CIP Reliability and Efficiency	#N/A	#N/A	$0					0.00					0.00	0.00	2.00	2.00	2.00	2.00	2.00	0.00	0.00	0.00	0.00	0.00	0.83					0.00
1			96132	Mezzanine Safety Shower/Eye Wash Station Install	#N/A	#N/A	$0					0.44	0.31	0.18	0.04	0.04	0.04	0.33	0.42	0.44	0.56	0.37	0.01	0.27					0.44	0.31	0.18	0.04	0.04	0.04	0.04	0.14	0.43	0.56	0.37	0.01	0.22	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Global	96133	QC Rapid Scan RDI System	15.3	Launch and Commercial Excellence	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00		0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75	0.75					0.00
0	Site Project	Global	96134	QC Liquid Handler	#N/A	#N/A	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00		0.50	0.50	0.50	0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.18					0.00
0	Site Project	Global	96136	V-3007 Replacement	N/A	Fit for Purpose	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00		0.00	0.00	0.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	0.75					0.00
0			96139	Storm Water Management Mitigation	9.6	Exceptional Culture	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.54	0.54	0.54	0.54	0.54	0.54	0.27	0.00	0.00	0.00	0.00	0.00	0.00	1.70	1.70	1.70	1.70	1.70	1.70	0.85	1.12					0.00					0.00
0			96165	WAN Link Redundancy	14.1	Reliability and Value	$0					0.00					0.00					0.00
0			97012	Site Data Historian Upgrade - 2016	N/A	Fit for Purpose	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00		0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54	0.54					0.00
0			97036	Locker Room Floor Replacement	#N/A	#N/A	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.03	0.00	0.01	0.01	0.01					0.01	0.01	0.34	0.34	0.05	0.04	0.37	0.36	0.00	0.00	0.00	0.00	0.13	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			97040	Tech Transfer: Master Data Management	24.3	Launch and Commercial Excellence	$0					2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00
0			97054	HVAC Retro Commissioning	15.6	Reliability and Value	$0					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10					0.00
0			98022	MFG Systems Integration Improvement Phase 2 - 2016	0	ACCR	$0					0.00	0.00	0.00	0.41	0.41	0.41	0.41	0.41	0.41	0.41	0.41	0.41	0.31					0.00
0			98029	Study for K6 Project Implementation - Phase 3 (Chillers)	0	ACCR	$0					0.00	0.09	0.09	0.09	0.09	0.09	0.09	0.00	0.00	0.00	0.00	0.00	0.05					0.00
0			98039	PCS Remediation for EBR Review by Exception	0	Reliable	$0					0.00	0.00	0.00	0.61	0.61	0.61	0.61	0.61	0.61	0.61	0.61	0.61	0.46					0.00
0			74385	Media Prep Endotoxin/Bioburden Sampling	6.5	Reliability and Value	$0					0.00					0.00	0.00	0.00	3.04	3.04	3.04	3.04	3.04	3.04	3.04	3.04	3.04	2.28					0.00
0	Site Project	Individual Project	74386	4040 Avenida Conference Center	#N/A	#N/A	$0	0.10	0.00	0.05	0.00		0.25	0.25	0.25	0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.11					0.00	0.11		0.44	0.44	0.37	0.37	0.37	0.37	0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0	Site Project	Individual Project	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement - 2015	N/A	Launch and Commercial Excellence	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	4.00	4.00	4.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	8.00	8.00	8.00	2.00	3.00					0.00					0.00
0			74432	K6 Program - Project 4 - Replace Chillers	16.5	Fit for Purpose	$0					0.00					0.05	0.05	0.05	0.05					0.00
0	Site Project	Individual Project	74449	TDS Remediation	#N/A	#N/A	$0	0.06	0.20	0.06	0.20		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.19	0.39	0.50	0.09	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.09					0.00					0.00
0			74485	4040 Avenida Conference Center - Phase 2	#N/A	#N/A	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.14	0.14	0.14	0.14	0.21	0.21	0.08					0.00	0.08					0.05	0.05	0.05	0.10	0.10	0.10	0.10	0.10	0.10	0.08					0.00
0	Site Project	Individual Project	74488	Etro Molecule	#N/A	#N/A	$0					7.27	7.27	7.27	9.77	9.77	9.77	11.93	11.93	11.93	15.06	15.07	15.07	11.01					0.00	11.01		0.36	0.36	0.36	0.36	0.36	0.36	0.36	0.36	0.36	0.36	0.37	0.34	0.36	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
0			74527	Vessel 1020 Upgrade	13.5	Fit for Purpose	$0					0.00					0.00	0.00		5.27	3.84	3.87	4.35	4.48	6.16	0.00	0.00	0.00	0.00	0.00	0.00	2.33					0.00
1			96216	Frit Handling and Storage Phase 2	20.2		$50,000					0.00	0.00	0.00	0.00	0.00	0.00	0.34	0.34	0.34	0.00	0.00	0.00	0.09					0.00	0.09					0.00					0.00
1			96210	P2 User Furnished Equipment Procurement	9		$1,100,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	2.00	2.00	2.00	2.00	2.00	2.00	1.00	1.00					0.00					0.00
1			96218	Column Maintenance Platform Installation			$75,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.00	1.00	1.00	0.25					0.00	0.25					0.00					0.00
1			96207	Weigh and Dispense Sink (CAPA1123109)			$165,000					0.00	0.00	0.00	0.25	0.25	0.25	0.10	0.10	0.10	0.10	0.10	0.10	0.11	0.00	0.00	0.00	0.00	0.00	0.00	0.25	0.25	0.25	0.25	0.25	0.25	0.13	0.24					0.00					0.00
0			65082	RF Sealer Generator			$22,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	1.00	1.00	1.00	0.25					0.00	0.25					0.00					0.00
0							$0					0.00					0.00	0.00					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0							$0					0.00					0.00
0	Site Project	Individual Project		Asset Replacement Bucket (All Dptms)	0	#N/A	$1,366,760					2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	2.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	3.00					0.00					0.00

				TOTAL SITE PROJECTS			$150,711,402	19.19	22.04	25.21	32.18		30.79	31.78	29.56	33.78	37.70	38.32	50.03	56.45	47.11	58.06	55.02	53.19	43.48	47.30	44.60	47.00	40.53	49.90	47.81	55.95	59.68	71.53	88.61	86.20	80.38	61.87	104.49		70.02	66.42	84.07	94.11	89.01	89.16	87.33	80.65	77.71	78.89	78.09	72.81	80.69	62.63	61.28	62.53	70.46	74.42	70.26	95.17	94.29	88.10	85.32	53.62	49.95	72.34
	Site Project	Individual Project	74408	VSD Upgrade	#N/A	#N/A	$0			0.77	0.77		0.00	0.00	0.00	0.00	0.50	0.50	0.50	0.50	0.50	0.50	0.50	0.50	0.33					0.00	0.33					0.00					0.00
	Site Project	Gllobal	96040	GWR 1080/1090	1.3	Agile	$0					0.00	0.00	0.00	0.00	0.00	0.38	0.48	0.48	0.48	1.30	1.30	1.30	0.48	0.00	0.00	0.00	0.00	0.00	0.24	0.65	0.65	0.65	0.52	0.52	0.52	0.31	0.79					0.00					0.00
	Site Project	Gllobal	74413	MES Enhancement Project - 2015	#N/A	#N/A	$0	#REF!	E	$0	#REF!		1.00	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.16	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	0.99	1.15					0.00					0.00
	Tech Transfer	Individual Project		CMContinuum	#N/A	#N/A	$0					0.30	0.30	0.30	0.30	0.30	0.30	0.00	0.00	0.00	0.00	0.00	0.00	0.15					0.00	0.15					0.00					0.00
			96124	TT Per Tec Transfer
				TOTAL TECH TRANSFER					1.30	0.38	0.38	0.38	0.88	1.26	1.06	1.06	1.06	1.88	1.88	1.88	1.12	0.99	0.99	0.99	0.99	0.99	1.24	1.65	1.65	1.65	1.51	1.51	1.51	1.31	2.42		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
									0.00
1			98001	CMC Continuum					0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98005	Empower 3 Rollout					0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.04	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98006	GMP Document Lifecycle - 2014/2015					0.19	0.19	0.19	0.12	0.12	0.12	0.01	0.01	0.01	0.01	0.01	0.01	0.08	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98009	PTB-006 Material of Construction (MOC) Program (GSP100 Implementation)					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98010	PTB-011 Microbial Task Force (GASP085 Implementation) Project				#REF!		1.07			1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07					0.00	1.07		1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	1.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98014	PTB-003 Analysis of Global Tank Management Process and System Improvements					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1	Network		98016	PTB-009 Investigation Free Lots		#N/A		#REF!		0.13			0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13					0.00	0.13			0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98017	PTQ-005 Coremap					0.40	0.40	0.40	0.30	0.30	0.30	0.30	0.30	0.30	0.10	0.10	0.10	0.28	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98019	PTQ-017 GMP Livelink to Condor					0.25	0.25	0.25	0.30	0.30	0.30	0.20	0.20	0.20	0.20	0.20	0.20	0.24	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98022	PTQ-002 ALEX LES (Lab Execution System) Project					4.34	4.34	4.34	3.84	3.84	3.84	3.84	3.84	3.84	3.59	3.59	3.59	3.90	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98026	Launch Capability Project (LCP)		Launch and Commercial Excellence					2.27	2.27	2.27	4.44	4.44	4.44	5.06	5.06	5.06	3.39	3.39	3.39	3.79					0.00	3.79		2.22	2.22	2.22	1.47	1.47	1.47	0.56	0.56	0.56	0.56	0.56	0.56	1.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98027	PCR Based Adventitious Agents					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98028	CalMan Replacement					0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.08	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98029	PTA-008 Business Continuity Management					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98031	PTB-016 PDM DS Phase II Project Resource Collection (TL)					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98032	PTQ-035: Automating Non-Routine Sample Management in LIMS					0.20	0.20	0.20	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98034	PTS201416-Global Warehouse Capacity Management					1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98035	Biologics Commercial DS Investigation Reduction Project					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98036	REMIS Pilot		Launch Facility					0.00	0.00	0.00	4.00	4.00	4.00	4.00	4.00	4.00	4.00	4.00	4.00	3.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98037	PTB-023: Rapid Bioburden Method for Pre-Filtration Media		Multi Product					2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	2.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98038	PTB-025: Warehouse Business Continuity Management		ACCR					0.50	0.50	0.50	0.50	0.50	0.50	0.50	0.50	0.50	0.00	0.00	0.00	0.38	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay					0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.00	0.00	0.00	0.19	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98040	PTQ-038: Quality Compliance Scorecard (QCS) Phase 2					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98041	PTQ-041: Simply Core for PT					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98042	PTQ-046: Quality and Compliance Risk roll up					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98043	PTQ-050: QC Network Capacity Model					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
1			98044	PTQ-051: FileNet Replacement Assessment					0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00

	Network			PTB-016 PDM DS Phase II Project Resource Collection (TL)		#N/A		#REF!		0.27			0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27					0.00	0.27					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
	Network			PTQ-032: Knowledge Manangement Strategy		#N/A		#REF!		0.07			0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07					0.00	0.07					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
	Network			PTQ-035: Automating Non-Routine Sample Management in LIMS		#N/A		#REF!		0.03			0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03					0.00	0.03					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
				TOTAL NETWORK				#REF!	0.00	1.47	0		3.82	3.82	3.82	5.98	5.98	5.98	6.60	6.60	6.60	4.93	4.93	4.93	5.33					0.00	5.33		13.25	13.25	13.25	15.68	15.68	15.68	14.56	14.56	14.56	13.36	13.36	13.36	14.21					0.00

				OCN TOTAL RESOURCE DEMAND				#REF!	22.04	26.68	32.18		35.91	35.98	33.76	40.14	44.56	45.56	57.69	64.11	54.77	64.87	61.83	60.00	49.93	48.29	45.60	47.99	41.53	50.90	49.05	57.59	61.33	73.18	90.12	87.71	81.89	63.18	112.24		83.27	79.67	97.32	109.79	104.69	104.84	101.89	95.21	92.27	92.25	91.45	86.17	94.90	62.63	61.28	62.53	70.46	74.42	70.26	95.17	94.29	88.10	85.32	53.62	49.95	72.34
				OCN TOTAL CAPACITY					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.75		49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75

									Roche	Ext	Count					Roche	Ext	Count
							Projects above the line					9.46	8.75	36					9.46	8.75	36
							Projects below the line					39.02	53.13	103					39.02	53.13	103

									Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average					Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average
							External					48.29	45.60	47.99	41.53	50.90	49.05	57.59	61.33	73.18	90.12	87.71	81.89	61.26					62.63	61.28	62.53	70.46	74.42	70.26	95.17	94.29	88.10	85.32	53.62	49.95	72.34
							Roche					35.91	35.98	33.76	40.14	44.56	45.56	57.69	64.11	54.77	64.87	61.83	60.00	49.93					83.27	79.67	97.32	109.79	104.69	104.84	101.89	95.21	92.27	92.25	91.45	86.17	94.90
							Capacity (Only Roche)					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75
							Variance (Cap. vs Roche)					13.25	6.09	8.31	1.93	-2.48	1.51	-3.61	-10.03	1.31	-8.79	-5.75	-3.93	-0.18					-34.11	-37.59	-55.24	-67.71	-62.61	-57.77	-47.82	-41.14	-36.20	-36.18	-35.38	-30.10	-45.15

							Excluding Projects below the line
									Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average					Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average
							External					0.00	0.00	0.00	0.00	11.93	12.20	14.45	14.45	15.35	12.19	12.19	12.19	8.75					21.15	21.15	22.23	22.23	28.56	28.84	29.20	29.20	28.29	25.13	25.13	25.13	25.52
							Roche					3.92	3.79	3.66	5.93	11.59	11.59	12.89	12.75	12.69	11.80	11.63	11.29	9.46					36.53	36.40	36.81	38.56	38.00	37.82	34.99	35.09	35.38	34.31	34.12	30.78	35.73
							Capacity (Only Roche)					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75
							Variance (Cap. vs Roche)					45.24	38.29	38.42	36.15	30.49	35.49	41.19	41.33	43.39	44.28	44.45	44.79	40.29					12.63	5.68	5.26	3.52	4.08	9.26	19.09	18.99	20.70	21.77	21.96	25.30	14.02

## Constraint_Analysis_ZS
		Bio Drug Substance - Oceanside					This version is in the portfolio
		Constraint Analysis					as of 2/22/16
		2016 T0					2015				2016

	2016	Project Indicator	Status	Project number	Project Name	Category	Score	Score A,B,C, E	Program	PMO Lead	Capital	Expense	Avg. Roche Resources		Avg. Roche Resources	Capital	Expense				Total		Project Total
1	1	Individual Project	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	74268	P2 Downstream Processing Expansion	Capacity	60	E	Launch Facility	Execute 2	$46,114,483	$3,345,844	29.71		21.21	$104,650,502	$825,644				$105,476,146		$194,047,008
2	1	Individual Project		74455	3rd HCCF Vessel	Capacity	60	E	Reliable	Execute	$1,079,394	$10,113	0.50		0.07	$2,328,891	$27,591				$2,356,482		$3,713,805
3	1	Individual Project		74454	Seed Lab (20L Bioreactor)	Capacity	60	E	Reliable	Execute	$755,170	$7,076	0.33		0.02	$938,961	$10,802				$949,763		$1,899,375
4	1	Individual Project		74453	NPI Pool Tanks	Capacity	60	E	Launch Facility	PTAA	$545,400	$0	0.00		0	$452,919	$10,802				$463,721		$1,009,121
5	1	Individual Project	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	74382	Sci&Eng Lab Mods and Equipment	New Product Intro	7.6	E	Launch Facility	Execute 2	$5,270,000	$2,000	3.95		1.13	$7,008,000	$393,000				$7,401,000		$12,673,000
6	1	Individual Project	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	74119	Harvest Upgrade (New Centrifuge)	Capacity	60	E	Launch Facility	Execute 2	$4,491,546	$42,076	2.47		2.30	$7,233,192	$28,727				$7,261,919		$12,909,963
7		Startup		74277	P2 DPE Start-Up	Capacity	60	A	Launch Facility	Execute	$0	$0	0.00		0	$8,000,000	$0				$8,000,000		$52,445,136
8		Expense		98026	Launch Capability Program (LCP)	New Product Intro	60	D	Launch Facility	Execute	$0	$0	3.79		12.00	$0	$800,000				$800,000		$800,000
9	1	Individual Project	FXNL LT Appr	74426	Process VSD and SOV Replacement - 2015	Efficiency	N/A	E	Reliable	Execute	$203,000	$0	0.00		0.30	$489,000	$0				$489,000		$692,000
10		Global		64901	MCS Peripheral Asset Replacement - 2015	Utility	N/A	E	Reliable	Execute	$225,200	$100,000	4.44		0	$100,000	$0				$100,000		$425,200
11		Individual Project		74368	Dev/Val Automation Capacity Expansion	Life Cycle Mgmt	N/A	E	Agile	Execute	$56,000	$0	0.16		0	$10,000	$0				$10,000		$625,000
12	1	Global		73387	MCSBACKUP Phase 2 Tape Retrieval	Other	N/A	E	Agile	Execute	$42,000	$5,000	0.00		0	$5,000	$0				$5,000		$52,000
13	1	Individual Project	Bldg. 311 is exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	74406	Corrosive Chemical Compliance	Life Cycle Mgmt	34	E	Reliable	Execute	$98,000	$0	0.09		0.11	$1,812,000	$0				$1,812,000		$1,910,000
14	1	Individual Project	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	73367	FS & DS Automation Integration	Sustainability	24.4	E	Reliable	Execute 2	$477,000	$0	0.26		0.31	$10,000	$0				$10,000		$733,193
15	1	Individual Project	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	74302	Waterpooling Remediation	Life Cycle Mgmt	23	E	Reliable	Execute 2	$510,000	$0	0.21		0.83	$435,000	$0				$435,000		$945,000
16	1	Individual Project	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	73356	Supplemental BDU Sampling	Compliance	19.5	E	ACCR	Execute 2	$1,474,665	$0	0.34		0	$200,000	$0				$200,000		$1,674,665
17	1	Individual Project	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	74279	New Media Technology - HTST / Adventitious	Life Cycle Mgmt	19.2	E	Reliable	Execute 2	$2,072,000	$2,000	0.00		5.15	$5,444,000	$0				$5,444,000		$9,106,000
18	1	Global	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	76643	Optimize Column Movement Device	Compliance	18.6	E	Reliable	Execute	$68,000	$0	1.68		0.02	$128,000	$0				$128,000		$196,000
19	1	Individual Project		74524	Bioburden 2606 IPA Exhaust Improvement	Efficiency	18	A	Reliable	FXNL LT Appr	$0	$0	0.36		0.08	$12,000	$0				$12,000		$1,112,000
20	#REF!	Global		73384	Caustic Bath Upgrade	Utility	16.5	E	Reliable	Execute	$25,000	$0	0.24		0	$9,000	$0				$9,000		$51,106
21	1	Individual Project		74490	Hyfish Material Screening Operation	Efficiency	16.3	A	Reliable	Execute	$782,000	$0	0.00		0.05	$460,000	$0				$460,000		$1,242,000
22	1	Individual Project	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	74418	QC Lab Reconfiguration & Equipment	Compliance	15.8	E	Reliable	Execute 1	$213,000	$0	0.28		0.28	$3,675,000	$0				$3,675,000		$3,888,000
24		Global		73399	Frit Handling and Storage	Efficiency	11.3	A	Agile	Execute	$15,000	$0	0.01		0.11	$108,000	$15,000				$123,000		$138,000				2016		Total (*)	Incl. 10% Adjustment		Total	Incl. 10% Adjustment
25	1	Individual Project	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	74373	WFI Generation and Storage System / CUB Expansion	Life Cycle Mgmt	11.1	E	Reliable	Execute 2	$6,162,014	$93,208	0.10		3.08	$5,342,000	$12,500				$5,354,500		$11,609,722				Global Credit	Capital	$1,461,200	$1,315,080		#REF!	#REF!
26	#REF!	Individual Project	FXNL LT Appr	74416	Asphyxiant Gas Remediation	Safety	11.1	A	Reliable	Execute 1	$33,392	$0	0.00		0.06	$99,000	$0				$99,000		$132,392					Expense	$127,000	-		#REF!	-
27	#REF!	Individual Project	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	74404	Mezzanine Lift Media Prep: Phase 1B	Capacity	10.7	E	Reliable	Execute	$262,000	$0	1.79		0.01	$330,000	$0				$330,000		$592,000					Total Cap + Exp	$1,588,200	$1,315,080		#REF!	#REF!
28		Global		73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Safety	10.5	R	Reliable	Execute	$116,000	$0	0.07		0	$95,000	$0				$95,000		$211,000
29	1	Global	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	73388	SIMCA Online Real Time Process Monitoring System	Life Cycle Mgmt	7.8	E	Reliable	Execute	$264,000	$22,000	0.03		0	$58,000	$0				$58,000		$344,000				Line Item / Projects	Capital	$73,887,064	$66,498,357		#REF!	#REF!
30	#REF!	Individual Project		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Compliance	7.7	R	Reliable	Execute	$311,000	$0	0.05		0.21	$350,000	$0				$350,000		$661,000					Expense	$3,502,317	-		#REF!	-
31	#REF!	Individual Project	CA Submitted	74392	Water Reclaim System	Compliance	6.1	E	ACCR	Execute	$180,000	$0	4.09		0.47	$676,000	$0				$676,000		$1,656,000					Total Cap + Exp	$77,389,381	$66,498,357		#REF!	#REF!
32		Global		73409	Solar Power Enabling Project	Compliance	5.1	R	Reliable	Execute	$184,000	$0	0.14		0.02	$271,000	$0				$271,000		$455,000
33	1	Individual Project		74489	4040 Avenida Conference Center Acquisition	TBD	3.1	A	Agile	Execute	$2,700,000	$0	0.00		0	$688,000	$0				$688,000		$3,388,000				Non-Automation	Expense	$201,000
34		Global		64914	QC M9 TOC Analyzers		N/A		Reliable	Execute	$0	$0	0.00		0	$106,000	$0				$106,000		$106,000				Automation	Expense	$245,000	YEAR 2015 / TOTAL BUDGET
35	1	Global		64923	QC Met-One Air Sampler Replacement 2015		N/A		Reliable	Execute	$0	$0	0.00		0	$60,000	$0				$60,000		$60,000
36	1	Global		64927	QC Gel Imager Replacement 2015		N/A		Reliable	Execute	$0	$0	0.00		0	$15,000	$0				$15,000		$15,000				GRAND TOTAL	Capital (Line Item + Global)	$75,348,264	$67,813,437		$71,888,754
37	#REF!	Expense			Piping Corrosion	#N/A	N/A		#N/A	#N/A	$0	$0	0.00		TBD	$0	$3,100,000				$3,100,000		$3,100,000					Expense (All)	$4,075,317	-	This total includes Above the line Auto. Expense Projects
38		Expense		97058	Parking Pavement Repair	Safety	0	A	TBD	Execute	$0	$120,000	0.11		0.00	$0	$80,000				$80,000		$200,000
39	1	Expense		97007	Automation System Lifecycle MCS Upgrade - PI	Compliance	27.6		Reliable	Execute	$0	$0	0.63		1.79	$0	$270,000				$270,000		$270,000
40	1	Expense	#N/A	97003	MFG Systems Integration Improvement Phase 1 - 2015	Efficiency	15.3	A	Agile	Execute 1	$0	$15,000	1.13		0.94	$0	$443,000				$443,000		$458,000
41		Expense		97048	Arc Flash Prevention	Efficiency	5.9		Reliable	JPMT Appr	$0	$48,000	0.00		0	$0	$318,000				$318,000		$366,000
42		Expense	#N/A	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Life Cycle Mgmt	3.4	A	Agile	Execute 1	$0	$40,000	0.34		0.68	$0	$1,180,000				$1,180,000		$1,220,000				2016		Total (*)	Incl. Adjustment		Total	Incl. Adjustment
43		Expense		N/A	CRB, travel, ofc supplies, trailer, others	#N/A	N/A	E			$0	$0	0.00		0	$0	$627,000				$627,000		$627,000				Global Credit	Capital	$3,776,859	$3,021,487		$891,126	$712,900
44		Global		65005	Analytical Scale					$24,000	$0				$24,000					Expense	$46,487	-		$27,487	-
45		Global		65009	Drum Mover/Raw Material Tenderizer					$30,000	$4,000				$34,000					Total Cap + Exp	$3,823,346	$3,021,487		$918,613	$712,900
46		Global		65013	Spare Bowl for Hermetic Centrifuge					$320,000	$0				$320,000
47		Global		65015	Lower Solid Collector for Centrifuge					$245,000	$0				$245,000
48		Global		96174	V-2170 Agitator Drain Valve					$31,000	$0				$31,000					Line Item / Projects	Capital	$174,249,472	$167,588,475		$33,378,305	$26,702,644
49					Expense	$1,561,066	-		$9,601,487	-
50					Total Cap + Exp	$175,810,538	$167,588,475		$42,979,792	$26,702,644
51					Everything above this line is currently in Execution
52		Startup		74127	Harvest Modifications Start-up	Capacity	60	A	Launch Facility	Budgeted	$0	$0	0.00		2.40	$125,000	$0				$125,000		$2,400,000
53		Individual Project		74491	Etro Tech Transfer	New Product Intro	60	A	Launch Facility	Idea	$0	$0	0.00		28.30	$7,015,007	$200,000				$7,215,007		$22,025,135				Non-Automation	Expense	$7,618,000
54	1	Individual Project	Upgrade PCS hardware and software for Development, Validation and Production environments. Coordinate with P2 Project Team to deploy during the 2016 Plant Shutdown.	74510	PCS Asset Replacement - 2016	Life Cycle Mgmt	N/A	B	Reliable	JPMT Appr	$0	$0	0.00		0.18	$1,869,000					$1,869,000		$1,869,000				Automation	Expense	$0	YEAR 2016 / TOTAL BUDGET
55	#REF!	Expense			PCS Asset Replacement Depreciation Write-Off					$800,000				$800,000		$800,000
56	#REF!	Individual Project		74486	PCS Controller Cabinet Asset Replacement	Life Cycle Mgmt	5.4	B	Reliable	IMPACT Appr	$0	$0	0.00		0.42	$2,404,000	$0				$2,404,000		$6,042,000
57		Individual Project		74487	Process VSD and SOV Asset Replacement	Life Cycle Mgmt	N/A	R	Reliable	IMPACT Appr	$0	$0	0.00		0.33	$4,542,000	$7,000				$4,549,000		$17,422,000				GRAND TOTAL	Capital (Line Item + Global)	$178,026,331	$170,609,963		$179,835,516
58		Individual Project		74427	MCS Network Infrastructure Asset Replacement - 2016	Life Cycle Mgmt	N/A	R	Reliable	JPMT Appr	$7,000	$0	0.00		0.29	$1,944,000	$0				$1,944,000		$1,951,000					Expense (All)	$9,225,553	- / This total includes Above the line Auto. Expense Projects
59	1	Individual Project		74511	Steaming Remediation - QR018 Compliance	Life Cycle Mgmt	13.3		Reliable	BMLT Appr	$0	$0	0.00		1.82	$2,457,000	$45,000				$2,502,000		$4,973,000				(**) Excludes Network projects "D".
60		Individual Project		74526	Utility and Process Safety System	Compliance	12.4	C	Reliable	FXNL LT Appr	$0	$0	0.00		0	$1,700,000	$0				$1,700,000		$1,700,000				(*) Includes Asset Replacement.
61		Global		96991	Asset Replacement 2016 - Engineering (cc642)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$493,675	$0				$1,007,097		$1,007,097
62	#REF!	Global		96995	Asset Replacement 2016 - Quality (cc583)		N/A	R	Reliable	FXNL LT Appr	$261,000	$0	0.00		0	$113,946.50	$0				$407,893		$668,893
63		Global		96994	Asset Replacement 2016 - Manufacturing (cc659)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$131,504	$0				$268,268		$268,268
64	1	Global	Asset Replacment	96992	Asset Replacement 2016 - Material Ops (cc484)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$62,000	$0				$126,480		$126,480
65	1	Global		96993	Asset Replacement 2016 - Manufacturing (cc1359)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$25,188	$0				$50,375		$50,375
66	#REF!	Global		96997	Asset Replacement 2016 - Maintenance (cc1236)		N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$15,617	$0				$31,233		$31,233
67		Global		96155	Hazardous Response Cart					0	$18,000	$0				$18,000
68		Global		96171	QC Auto-Pipettor					0	$30,000	$0				$30,000
69		Global		96172	QC Plate Washer					0	$60,000	$0				$60,000
70		Global		96175	Sci&Eng Lab Incubator and Freezer Asset Replacement					0	$140,000	$0				$140,000
71
72
73
74
75
76					Execution Target Line
77		Individual Project	Existing DX HVAC units use R-41A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 241, 361, and 371.	74409	K6 Program - Project 1 - Replace DX HVAC Units	Efficiency	11.3	A	ACCR	Execute	$90,000	$0	0.04
78		Global		96991	Asset Replacement 2016 - Engineering (cc642)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$493,675	$19,747				$1,007,097		$1,007,097
79	#REF!	Global		96995	Asset Replacement 2016 - Quality (cc583)		N/A	R	Reliable	FXNL LT Appr	$261,000	$0	0.00		0	$203,947	$0				$407,893		$668,893
80		Global		96994	Asset Replacement 2016 - Manufacturing (cc659)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$131,504	$5,260				$268,268		$268,268
81	1	Global	Asset Replacment	96992	Asset Replacement 2016 - Material Ops (cc484)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$62,000	$2,480				$126,480		$126,480
82	1	Global		96993	Asset Replacement 2016 - Manufacturing (cc1359)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$25,188	$0				$50,375		$50,375
83	#REF!	Global		96997	Asset Replacement 2016 - Maintenance (cc1236)		N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$15,617	$0				$31,233		$31,233
84	1	Global		96159	OCC Network Remediation	Efficiency	22.8		TBD	Idea	$0	$0	0.00		0	$150,000	$0				$150,000		$150,000
85	1	Individual Project		74435	Hastelloy Chromatography Column (160cm)	TBD	16.2		Reliable	FXNL LT Appr	$0	$0	0.00		2.39	$1,549,000	$0				$1,549,000		$1,549,000
86		Global		96135	QC Spectrophotmeters	Compliance	14.4	C	Reliable	Hold	$0	$0	0.00		0.18	$327,522	$0				$327,522		$327,522
87		Individual Project		74527	Vessel 1020 Upgrade	TBD	13.5	B	Reliable	Idea	$0	$0	0.00		3.75	$2,646,000	$0				$2,646,000		$13,659,000
88	#REF!	Global		96134	QC Liquid Handler	Efficiency	13.2	C	Reliable	Hold	$0	$0	0.00		0.18	$134,917	$0				$134,917		$134,917
89	1	Global		74431	Buffer Prep Mezzanine Lift Construction	Safety	10.7	A	Reliable	JPMT Appr	$0	$0	0.00		0.09	$442,000	$0				$442,000		$442,000
90		Global		96137	Security Cameras Improvement on Parking Lot	Efficiency	6.7	C	Reliable	Hold	$0	$0	0.00		0	$250,000	$0				$250,000		$250,000
91		Individual Project		74385	Media Prep Endotoxin/Bioburden Sampling	Efficiency	6.5	B	Reliable	Idea	$0	$0	0.00		2.28	$500,000	$0				$500,000		$3,000,000
92		Global		96139	Trash Bin Storm Water Mitigation	TBD	6.3		Reliable	Hold	$0	$0	0.16		0	$200,000	$0				$200,000		$200,000
93		Global		96132	Mezzanine Safety Shower/Eye Wash Station Install		2.9		Reliable	IMPACT Appr	$0	$0	0.00		0	$210,000	$0				$210,000		$210,000
94		Global		96164	Hazardous Materials Containers Washing Station		0		TBD	Placeholder	$0	$0	0.00		0	$30,000	$0				$30,000		$30,000
95		Global		96167	Emergency Generator High Level Alarm		0		TBD	Idea	$0	$0	0.27		0	$25,000	$0				$25,000		$25,000
96		Global		96168	Replace Warehouse #321 Sprinkler Heads		0		TBD	Idea	$0	$0	0.03		0	$20,000	$0				$20,000		$20,000
97	#REF!	Expense		97040	Tech Transfer: Master Data Management	Compliance	24.3	B	Reliable	FXNL LT Appr	$0	$0	0.00		2.00	$0	$250,000				$250,000		$555,750
98		Expense		97038	PCS Functional Specification Development Project (CAPA 960297)	Safety	13.5	B	Reliable	FXNL LT Appr	$0	$0	0.00		0	$0	$1,000,000				$1,000,000		$8,000,000
99	#REF!	Expense		97039	PCS Remediation for EBR Review by Exception - PI	Efficiency	13.0	B	Agile	Idea	$0	$0	0.00		0	$0	$250,000				$250,000		$5,875,000
100		Expense		97053	Pressure Safety Program - PI Phase		8.8		TBD	Idea	$0	$0	0.00		0	$0	$100,000				$100,000		$100,000
101		Expense		97045	Site Exterior Lighting Upgrade - Title 24	Compliance	0	C	ACCR	FXNL LT Appr	$0	$0	0.00		0	$0	$200,000				$200,000		$200,000
103		Individual Project		74525	CIP Reliability and Efficiency - PI	Life Cycle Mgmt	0	C	Reliable	Idea	$0	$0	0.00		0.83	$0	$400,000				$400,000		$4,400,000
104		Expense		97057	Conference Room 315 Expansion		0		TBD	Idea	$0	$0	0.00		0.00	$0	$300,000				$300,000		$300,000
105	#REF!	Expense		97054	HVAC Retro Commissioning	TBD	15.6		ACCR	FXNL LT Appr	$0	$0	0.00		0.10	$0	$0				$0		$175,000
106	1	Global		96136	V-3007 Replacement	Sustainability	N/A	B	Reliable	FXNL LT Appr	$0	$0	0.00		0.75	$0	$0				$0		$240,000
107	1	Individual Project		74432	K6 Program - Project 4 - Replace Chillers	#REF!	16.5		ACCR	FXNL LT Appr	$0	$0	0.00		0.05	$0	$0				$0		$19,300,000
108		Individual Project		74278	K6 Program - Project 3 - Replace Cold Room Compressors	Other	16.5	A	ACCR	FXNL LT Appr	$0	$0	0.21		0.36	$0	$0				$0		$10,759,000
109		Individual Project		74512	K6 Program - Project 2 - B381 Compliance	Efficiency	16.5		ACCR	FXNL LT Appr	$0	$0	0.14		0.18	$0	$0				$0		$700,000
110	#REF!	Global		96133	QC Rapid Scan RDI System	Efficiency	15.3	C	Reliable	Hold	$0	$0	0.00		0.75	$0	$0				$0		$210,000
111	1	Individual Project		96165	WAN Link Redundancy	#REF!	14.1		TBD	Idea	$0	$0	0.00		0	$0	$0				$0		$2,000,000
112	#REF!	Individual Project		96160	B331 Fire Code Compliance	TBD	10.8		TBD	FXNL LT Appr	$0	$0	0.00		0	$0	$0				$0		$1,000,000
113	1	Individual Project		74371	Odor Treatment	TBD	6.8	A	ACCR	FXNL LT Appr	$100,000	$0	0.10		0.20	$0	$0				$0		$5,600,000
114		Individual Project		74513	Electric Vehicle Charging Stations	Compliance	2.2		Agile	Hold	$0	$0	0.00		0	$0	$0				$0		$730,000
115		Global		96163	MFG Depth Filter Housing		0		TBD	Idea	$0	$0	0.00		0	$0	$0				$0		$400,000
116		Network		98001	CMC Continuum	Capacity		D	Launch Facility	#N/A			0.15		0	$0	$0				$0
117		Network		98005	PTB-016: Empower 3 Rollout	0		D	0.00	#N/A			1.15		0.13	$0	$0				$0
118		Network		98019	PTQ-017 GMP Livelink to Condor	0		D	Multi Product	#N/A			1.32		0.20	$0	$0				$0
119		Network		98010	PTB-011: NTWK Microbial Control Task Force (GSP085 Implementation)	0		D	0.00	#N/A			0.07		1.10	$0	$0				$0
120		Network		98011	PTQ-xxx PQS: GSP085 - Microbiological Testing of Non-Sterile Material	0		D	Multi Product	#N/A			1.07		0	$0	$0				$0
121		Network		98006	GMP Document Lifecycle - 2014/2015	Compliance		D	Reliable	#N/A			0.96		0	$0	$0				$0
122		Network		98022	PTQ-002 ALEX LES (Lab Execution System) Project	0		D	ACCR	#N/A			0.60		3.30	$0	$0				$0
123		Network		98028	PT-IPC1: Calman Replacement	0		D	Reliable	#N/A			0.25		0.28	$0	$0				$0
124		Network		98029	PTA-008 Business Continuity Management	0		D	ACCR	#N/A			1.08		0.15	$0	$0				$0
125		Network		98013	PTB-002 Gentamicin Removal Strategy for Commercial Processes	0		D	Multi Product	#N/A			0.90		0	$0	$0				$0
126		Network		98018	PTQ-xxx PQS: GSP034 - Biologics Cleaning Initiative	0		D	Multi Product	#N/A			0.27		0	$0	$0				$0
127		Network		98014	PTB-003 Analysis of Global Tank Management Process and System Improvements	0		D	Multi Product	#N/A			0.21		0	$0	$0				$0
128		Network		98017	PTQ-005 Coremap	0		D	Multi Product	#N/A			0.20		0	$0	$0				$0
129		Network		98034	PTS201416-Global Warehouse Capacity Management	0		D	Multi Product	#N/A			0.10		0.20	$0	$0				$0
130		Network		98037	PTB-023: Rapid Bioburden Method for Pre-filtration Media	Efficiency					2.10	$0	$0				$0
131		Network		98038	PTB-025: Warehouse Business Continuity Mgt	Life Cycle Mgmt					0.92	$0	$0				$0
132		Network		98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay	Compliance					1.06	$0	$0				$0
133		Network		98040	PTQ-038: Quality Compliance Scorecard (QCS) Phase 2	Compliance					0	$0	$0				$0
134		Network		98041	PTQ-041: Simply Core for PT	Efficiency					0.04	$0	$0				$0
135		Network		98042	PTQ-046: Quality and Compliance Risk Roll Up	Efficiency					0.03	$0	$0				$0
136		Network		98043	PTQ-050: QC Network Capacity Model	Capacity					0.03	$0	$0				$0
137		Network		98044	PTQ-051: FileNet Replacement Assessment	Efficiency					0.20	$0	$0				$0
138		Network		98009	PTB-006 Material of Construction (MOC) Program (GSP100 Implementation)	0		D	Multi Product	#N/A			0.06		0	$0	$0				$0
				Contingency					0.06	$2,362,071	$43,000
				Site Judgedown					-$10,661,762					-$7,416,369	-$1,890,000	$0	$0		-$9,306,369		-$9,306,369
				TOTAL					$64,425,501	$3,852,317	57.3		96.7	$177,757,472	$9,878,553	$195,674,323	$195,674,323		$187,636,025		$430,560,356
102					OCN TOTAL CAPACITY					49.75		94.0
				$177,757,472	$9,878,553

				$177,757,472	$9,878,553

				Capital	Expense	Resourc.		Resource	Capital	Expense				Total		Protect Total
				P2/CMC Projects					$58,255,993	$3,407,109	37.0		67.43	$137,752,472	$2,296,566	$0	$0	$0	$140,049,038		$303,922,543
				Non P2/CMC Proposed Projects in execution					11.15	$21,637,000	$27,500	$0	$0	$0	$21,664,500	0	$48,261,278
				Expense Only Projects in Execution					3.40	$0	$6,018,000	$0	$0	$0	$6,018,000		$0
				Shutdown Critical Projects not in execution					$3,743,000	$223,000	7.4		3.04	$14,916,000	$852,000	$0	$0	$0	$15,768,000		$34,757,000
				Non P2/CMC Proposed Projects not in execution					#REF!	#REF!	#REF!		8.86	$8,506,298	$27,487	$0	$0	$0	$8,533,785		$24,302,131
				Expense Only Projects not in Execution					2.00	$0	$1,800,000	$0	$0	$0	$1,800,000		$14,730,750
				IMPACT Recommended Deferral					0.83	$0	$700,000	$0	$0	$0	$700,000		$4,700,000
				Contingency					0.00	$2,362,071	$43,000				$2,405,071		$0
				Site Judgedown					-$10,661,762	$0				-$7,416,369	-$1,890,000	$0	$0	$0	-$9,306,369		-$9,306,369
				TOTAL					#REF!	#REF!	#REF!		97	$177,757,472	$9,874,553	$0	$0	$0	$187,636,025		$430,560,356

		Assumptions:
		Site Capital judge down is based on costs below 2016 Execution Targets.
		Total Expense budget is $9.9M
		Resource Capacity: Historical 50 FTE + 10 FTE TT, 2015 20 hired for P2, 2016 14 hired for TT = 94 FTE.
		Resource Demand to support network projects is 10 FTE
		OLT Decision: Focusing on projects already in execution, Tech Transfer and shutdown critical.

		12/8/15: AW to check w/ Susan & JimN on 74416 - Asphyxiant Gas Remediation.
		12/8/15: AW to check w/ Susan & Sumner on 74371, 96139, 96140 if defer.
		12/8/15: AW to check w/ Sumner 74512 for 2016 w/ project 74409.
		12/8/15: SS to review SHE projects w/ Melanie.

## Resource_2017
	Bio Drug Substance - Oceanside				E
	Average Resource Demand				E
	In FTEs
	FTE =	147								T3					T3					Current Estimate
										2014		2015			2015					2017
	Location (Site) Name	Project Indicator	Status	Project number	Project Name	Comment	PD	PMO Lead	Score	Score A,B,C, E	Program	Current Estimate	Roche	External	Roche	External		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Roche	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	External	Total		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Roche	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	External
0				74119	Harvest Upgrade (New Centrifuge)	Missing	#REF!	#REF!	N/A	A	Fit for Purpose	$7,288,140					0.00					0.00
0	Site Project	Individual Project	0	74127	Harvest Modifications Start-up				N/A		Launch Facility	$2,275,000	0.56	2.79	0.34	2.55		0.80	0.86	0.81	0.72	0.72	0.12	0.00	0.00	0.00	0.00	0.00	0.00	0.34	6.91	6.50	6.03	5.59	2.49	1.81	1.20	0.00	0.00	0.00	0.00	0.00	2.54	2.88					0.00					0.00
0				74268	P2 Downstream Processing Expan	Mark / Melanie	#REF!	#REF!	N/A	E	Fit for Purpose	$34,280,135					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.64	0.93	0.91	0.21					0.00					0.00
0	Site Project	Individual Project	Complies with Roche K6 directive to reduce R-41A and R-22 refrigerants. Will reduce R-22 refrigerant in all cold rooms across the site by 2018 and R-404 refigerant in the main freezer by 2022. Free standing lab freezers are out fo scope.	74278	K6 Program - Project 3 - Replace Cold Room Compressors				4.4		Fit for Purpose	$603,000	0.76	1.55	1.99	5.02		2.68	2.68	2.68	2.68	2.41	2.48	4.11	5.13	6.19	5.99	6.27	5.78	4.09	3.31	3.31	3.31	3.31	6.61	8.93	10.03	10.03	11.13	11.54	11.16	11.97	7.88	11.97					0.00					0.00
0	Site Project	Individual Project	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	74279	New Media Technology - HTST / Adventitious	OK	#REF!	#REF!	3.7	E	Reliability and Value	$1,591,162	0.40	0.30	0.49	0.41		0.26	0.02	0.02	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.20	0.02	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.02	0.05					0.00					0.00
0	Site Project	Individual Project	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	74302	Water Pooling Remediation	OK	#REF!	#REF!	3.4	E	Reliability and Value	$50,426			0.25	0.25		0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.10	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.10					0.00					0.00
0				74382	SciEng Lab Mods and Equiment	OK	#REF!	#REF!	2	E	Launch and Commercial Excellence	$390,885					0.00					0.00					0.00
0	Site Project	Individual Project	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	74406	Corrosive Chemical Compliance	OK	#REF!	#REF!	6.6	A	Reliability and Value	$83,733					0.00	0.00	0.00	0.00	0.00	0.00	0.79	0.52	0.14	0.06	0.06	0.06	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.41	0.41	1.10	5.48	5.48	5.48	1.53	1.67					0.00					0.00
0	Site Project	Individual Project	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	74409	K6 Program - Project 1 - Replace DX HVAC Units	OK	#REF!	#REF!	1.8	A	Fit for Purpose	$332,000			0.17	0.17		0.00	0.00	0.00	0.00	0.00	0.08	0.14	0.13	0.12	0.06	0.12	0.18	0.07	0.00	0.00	0.00	0.00	0.00	0.31	0.61	0.73	0.87	0.94	0.94	0.28	0.39	0.46					0.00					0.00
0	Site Project	Individual Project	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	74418	QC Lab Reconfiguration & Equipment	OK	#REF!	#REF!	3.4	A	Launch and Commercial Excellence	$289,726					0.00	0.00	0.00	0.00	0.00	0.00	0.07	0.07	0.12	0.80	0.07	0.07	0.10	0.00	0.00	0.00	0.00	0.61	0.61	0.61	0.61	1.67	2.43	1.43	0.61	0.72	0.82					0.00					0.00
0	Site Project	Individual Project	Per site prioritization, this project is necessary to support high run rates at OCN, Currently, the skids are in paper records and do not support release by exception.	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement - 2015	OK	#REF!	#REF!	N/A	C	Launch and Commercial Excellence	$200,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.48	0.48	0.48	0.48	0.16	0.00	0.00	0.00	0.00	0.00	0.00	1.59	1.59	1.59	1.59	1.59	1.59	0.79	0.95					0.00					0.00
0	Site Project	Gllobal	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	74429	Mettler Toledo Weight Transmitter conversion to Hardy Weight Transmitter Asset Replacement- - 2015	OK	#REF!	#REF!	1.5	C	Reliability and Value	$23,445					0.00	0.00	0.00	0.00	0.00	0.00	0.68	0.67	0.26	0.13	0.12	0.12	0.16					0.00	0.16					0.00					0.00
0	Site Project	Individual Project	Only one chromatography column is needed per stage to run the process. The second column is a backup to replace expired resin on the column being used. If a third packed column is not vailable, there is the risk that the second column fails while the first one is being packed. Such an issue would incapacitate production to continue.	74435	Hastelloy Chromatography Column				2.9		Fit for Purpose	$1,149,000	0.06	0.20	0.06	0.20		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.19	0.39	0.50	0.09	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.09					0.00					0.00
0	Site Project	Individual Project		74454	Seed Lab (20L Bioreactor)		#REF!	#REF!	N/A		Fit for Purpose	$440,826					0.49	0.49	0.49	0.50	0.50	0.50	0.49	0.49	0.49	0.49	0.49	0.53	0.50	0.44	0.46	0.48	0.50	0.67	0.72	0.72	0.72	0.98	1.15	1.20	1.24	0.77	1.27					0.00					0.00
0				74486	PCS Controller Cabinet Asset Replacement				0		Highly Capable Workforce	$110,000					0.00					0.00					0.00
0	Site Project	Individual Project		74487	Process VSD and SOV Replacement Project				N/A		Highly Capable Workforce	$2,943,031					7.27	7.27	7.27	9.77	9.77	9.77	11.93	11.93	11.93	15.06	15.07	15.07	11.01					11.01					0.00					0.00
0	Site Project	Global	6/14/16 Change to On Hold due to the uncertatnty with this project.	74491	Etro Tech Transfer				N/A		Launch and Commercial Excellence	$12,836,630					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.03	0.05	0.00	0.00	0.00	0.00	0.01	0.01					0.00					0.00
0	Site Project	Individual Project	Compliance with QR018, meeting CAPA 939326 requirements, and to mitigate equipment degradation due to splashing, pooling and vapor condensation. Mitigation of slipping hazards for personell from condensate pooling and drain splashing. Scope includes both P1 and P2.	74511	QR018 Compliance Steam and Condensate Containment		#REF!	#REF!	2.6		Reliability and Value	$3,074,500					0.00	0.00	0.00	0.00	0.00	0.00	0.79	0.52	0.14	0.06	0.06	0.06	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.41	0.41	1.10	5.48	5.48	5.48	1.53	1.67					0.00					0.00
0				74524	Bioburden 2606 IPA Exhaust Improvement				2.3	A	Reliability and Value	$0					0.00					0.00
0				74526	Utility and Process Safety System				2.6		Reliability and Value	$57,596					0.00					0.00					0.00
0	Site Project	Individual Project	The media is being made in a hastelloy tank in buffer prep and then needs to be packed out to be used in the upstream. Technically, we are crossing the US/DS barrier - this is a bad practice and will get more complex when we are mfg concurrent products. The pack out line in buffer prep is also stainless and is currently pitted due to the upstream solution. Replacement of the V1020 will replace the entire piping and media filter with the higher alloy metal.	74527	Vessel 1020 Upgrade				2.3		Fit for Purpose	$0					0.00	0.32	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.04	0.14	0.14	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.03	0.07					0.02					0.00
0	Site Project	Individual Project	To align with network commitment per the Multi-Site Assessment #1105078.	74535	Draining of Top Mounted Agitator Well				0		Reliability and Value	$654,000					0.00	0.00	0.00	1.36	1.36	1.36	0.00	0.00	0.00	0.00	0.00	0.00	0.34	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.34					0.00					0.00
0	Site Project	Global		82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	OK	#REF!	#REF!	0.6	C	Reliability and Value	$574,661					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.20	0.20	0.20	0.00	0.00	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05					0.00					0.00
0	Site Project	Global		96069	Warehouse Crown Forklift		#REF!	#REF!	N/A	R	Fit for Purpose	$144,407					0.00	0.00	0.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25	0.00	0.00	0.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25	0.50					0.00					0.00
0	Site Project	Global		96133	QC Rapid Scan RDI System				2.3		Launch and Commercial Excellence	$210,000					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00					0.00					0.00
0	Site Project	Expense	TMAC vessel has been determined to have corrosion and needs to be replaced. Upsizing the pumps and piping for offloading is required to shorten the TMAC waste transfer period. This project is needed to maintain out TMAC system in a reliable and efficient operational state. TMAC vessel is needed for Rituxan. P2 tie-in associated with this vessel.	96136	V-3007 Replacement				N/A		Fit for Purpose	$120,000					0.00	0.00	0.00	0.00	0.00	0.00	2.26	2.26	2.26	2.26	2.26	2.26	1.13	0.14	0.14	0.14	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.04	1.17					0.00					0.00
0	Site Project	Expense	Regional Water Board and City of OCN regulation states the need for an approved SWMP. Genentech OCN does not have a documented plan in place. This project will Identify plan requirements. Subsequent activity to include detailed design and construction to implement site changes.Regulatory requirement.	96139	Storm Water Management Mitigation				1.2		Exceptional Culture	$200,000					0.25	0.25	0.25	0.25	0.25	0.25	1.00	1.00	1.00	1.00	1.00	1.00	0.63	0.00	0.00	0.00	0.10	0.10	0.10	1.99	1.99	1.99	3.97	3.97	3.97	1.51	2.14					0.00					0.00
0				96165	WAN Link Redundancy				2.1		Reliability and Value	$0					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.05	0.03	0.00	0.01	0.01	0.01					0.00					0.00
0				97003	MFG Systems Integration Improvement Phase 1 - 2015		#REF!	#REF!	2.3	B	Reliability and Value	$135,000					0.00					0.00
0				97012	Site Data Historian Upgrade - 2016				0		Fit for Purpose	$366,000					0.00					0.00
0				97054	HVAC Retro Commissioning				2		Reliability and Value	$113,000					0.00					0.00					0.00
1				96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting				1.8		Reliability and Value	$1,000,000					0.00					2.00	2.00	2.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.75	2.00	2.00	2.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.75
1				96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000				2.7		Reliability and Value	$550,000					0.00					3.00	3.00	3.00	3.00	3.00	3.00	1.00	1.00	1.00	0.00	0.00	0.00	1.75	4.00	4.00	4.00	4.00	4.00	4.00	1.00	1.00	1.00	0.00	0.00	0.00	2.25
1				96213	Replacement of Obsolete Benchtop Horiba pH Meter				1.7		Fit for Purpose	$1,200,000					0.00					0.00	0.00	0.00	0.00	0.00	0.00	3.00	3.00	3.00	3.00	3.00	3.00	1.50	0.00	0.00	0.00	0.00	0.00	0.00	3.00	3.00	3.00	3.00	3.00	3.00	1.50
1				96221	Corrosive Chemical Compliance - CUB and Warehouse				6.6		Reliability and Value	$2,900,000					0.00					0.50	0.50	0.50	0.50	0.50	0.50	0.25	0.25	0.25	0.25	0.25	0.25	0.38					0.00
1				96210	P2 User Furnished Equipment Procurement				1.4		TBD	$1,100,000					0.00					0.00	0.50	0.50	0.50	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.13
1				96209	Harvest Depth Filter Installation Tool				1.8		Highly Capable Workforce	$100,000					0.00					0.00	1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25					0.00
0				96219	Harvest Filter Housing A Removal/Installation Improvements				1.8		Highly Capable Workforce	$500,000					0.00					0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.00	0.00	0.00	0.19					0.00
0				96222	Pressure Safety Program - Mechanical				3.8		Highly Capable Workforce	$2,000,000					0.00					1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50	1.50					0.00
0				97071	Pipe Labelling Improvement				1.8		Highly Capable Workforce	$2,100,000					0.00					0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25					0.00
0				96139	Trash Bin Storm Water Mitigation				1.2		Exceptional Culture	$200,000					0.00					0.25	0.25	0.25	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.06					0.00
0				96217	Pallet Wrapper				1.4		Highly Capable Workforce	$50,000					0.00					0.25	0.25	0.25	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.06					0.00
0				96181	Fall Protection Phase III				1.8		Highly Capable Workforce	$150,000					0.00					0.25	0.25	0.25	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.06					0.00
0				97070	Pressure Safety Program - Automation PI				2.7		Highly Capable Workforce	$300,000					0.00					0.00	0.00	0.00	0.00	0.00	0.00	3.00	3.00	3.00	3.00	3.00	3.00	1.50					0.00
0				96183	Site Signage Upgrade				1.8		TBD	$200,000					0.00					1.00	1.00	1.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.25					0.00
0				97045	Site Exterior Lighting Upgrade - Title 24				0.3		Reliability and Value	$100,000					0.00					0.10	0.10	0.10	0.05	0.05	0.05	0.00	0.00	0.00	0.00	0.00	0.00	0.04					0.00
0				97038	PCS Functional Specification Development Project (CAPA 960297)				2.3		Reliability and Value	$500,000					0.00					10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	10.00	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50	9.50
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00
0									#N/A		#N/A	#N/A					0.00					0.00					0.00

					TOTAL SITE PROJECTS					$52,050,528	#N/A	88.15	103.91	#N/A		11.60	11.42	11.37	13.79	13.50	13.05	18.31	19.04	19.83	24.00	24.09	23.80	16.98	10.42	9.83	9.33	8.89	9.71	11.65	14.45	13.38	16.35	21.97	20.59	19.93	13.88	19.14					0.00					0.00
				96124	TT Per Tec Transfer					Launch and Commercial Excellence	$8,940,664
					TOTAL TECH TRANSFER			#N/A					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!					0.00					0.00
								#N/A					0.00					0.00					0.00
1				98005	Empower 3 Rollout					0					0.00
	Network			98006	PTB-005 GMP Document Lifecycle Project			#REF!		A	Reliable		#REF!		0.96			0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96	0.96					0.00	0.96					0.00					0.00
	Network			98009	PTB-006 Materials of Construction Implementation Project Resource Collection			#N/A		C	Multi Product		#REF!		0.06			0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06	0.06					0.00	0.06					0.00					0.00
1	Network			98010	PTB-011 Microbial Task Force (GASP085 Implementation) Project			#N/A		A	0		#REF!		1.07			1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07	1.07					0.00	1.07					0.00					0.00
	Network			98014	PTB-003 Analysis of Global Tank Management Process and System Improv.			#N/A		B	Multi Product		#REF!		0.21			0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21	0.21					0.00	0.21					0.00					0.00
	Network			98016	PTB-009 Investigation Free Lots			#N/A		B	#N/A		#REF!		0.13			0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13	0.13					0.00	0.13					0.00					0.00
	Network			98017	PTQ-005:COREMAP			#N/A		C	Multi Product		#REF!		0.2			0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20	0.20					0.00	0.20					0.00					0.00
1	Network			98019	PTQ-017:GMP LiveLink to condor			#REF!			Multi Product		0.11		0.6			0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60					0.00	0.60					0.00					0.00
1	Network			98022	PTQ-002: Lab Execution System (LES) Pilot/Continuation ALEX LES			#REF!		A	ACCR		0.11		0.6			0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60	0.60					0.00	0.60					0.00					0.00
1	Network			98026	Launch Capability Project (LCP)			#N/A		A	Launch and Commercial Excellence					2.27	2.27	2.27	4.44	4.44	4.44	5.06	5.06	5.06	3.39	3.39	3.39	3.79					0.00	3.79					0.00					0.00
	Network			98027	PCR Based Adventitious Agents			#N/A		B	0		#REF!					0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90	0.90					0.00	0.90					0.00					0.00
1	Network			98028	CalMan Replacement			#N/A		A	Reliable		#REF!					0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25					0.00	0.25					0.00					0.00
1	Network			98029	PTA-008 Business Continuity Management			#N/A		B	ACCR		#REF!		0.2			1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08	1.08					0.00	1.08					0.00					0.00
1				98034	PTS201416-Global Warehouse Capacity Management					Multi Product					0.00
				98036	REMIS Pilot					Launch Facility					0.00
1				98037	PTB-023: Rapid Bioburden Method for Pre-Filtration Media					Multi Product					0.00
1				98038	PTB-025: Warehouse Business Continuity Management					ACCR					0.00
1				98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay					Reliable					0.00
1				98041	PTQ-041: Simply Core for PT					ACCR					0.00
1				98042	PTQ-046: Quality and Compliance Risk Roll Up					Agile					0.00
1				98043	PTQ-050: QC Network Capacity Model					ACCR					0.00
1				98044	PTQ-051: FileNet Replacement Assessment					ACCR					0.00
	Network				PTB-016 PDM DS Phase II Project Resource Collection (TL)			#N/A		B	#N/A		#REF!		0.27			0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27	0.27					0.00	0.27					0.00					0.00
	Network				PTQ-032: Knowledge Manangement Strategy			#N/A		C	#N/A		#REF!		0.07			0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07	0.07					0.00	0.07					0.00					0.00
	Network				PTQ-035: Automating Non-Routine Sample Management in LIMS			#N/A		C	#N/A		#REF!		0.03			0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03	0.03					0.00	0.03					0.00					0.00
					TOTAL NETWORK					#REF!	0.00	4.30	0		8.68	8.68	8.68	10.84	10.84	10.84	11.46	11.46	11.46	9.79	9.79	9.79	10.19					0.00	10.19		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					0.00

					OCN TOTAL RESOURCE DEMAND					#REF!	88.15	109.10	#N/A		#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	10.42	9.83	9.33	8.89	9.71	11.65	14.45	13.38	16.35	21.97	20.59	19.93	13.88	29.33		0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
					OCN TOTAL CAPACITY					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.75		49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75

										Roche	Ext	Count					Roche	Ext	Count
										Projects above the line					7.39	0.00	21					7.39	0.00	21
										Projects below the line					19.56	18.02	53					`			19.56	18.02	53

										Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average					Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average
										External					10.42	9.83	9.33	8.89	9.71	11.65	14.45	13.38	16.35	21.97	20.59	19.93	13.88					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
										Roche					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00
										Capacity (Only Roche)					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75
										Variance (Cap. vs Roche)					#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75

										Excluding Projects below the line
										Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average					Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Average
										External					0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00					6.50	6.50	6.50	5.00	5.00	5.00	4.00	4.00	4.00	3.00	3.00	3.00	4.63
										Roche					5.87	5.87	5.87	8.04	8.04	8.04	8.66	8.66	8.66	6.99	6.99	6.99	7.39					5.50	6.50	6.50	5.50	4.50	4.50	4.25	4.25	4.25	3.25	3.25	3.25	4.63
										Capacity (Only Roche)					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75					49.16	42.08	42.08	42.08	42.08	47.08	54.08	54.08	56.08	56.08	56.08	56.08	49.75
										Variance (Cap. vs Roche)					43.29	36.20	36.20	34.04	34.04	39.04	45.42	45.42	47.42	49.09	49.09	49.09	42.36					43.66	35.58	35.58	36.58	37.58	42.58	49.83	49.83	51.83	52.83	52.83	52.83	45.12

## VG
				MO5 - 2016				T0 - 2016				DELTA (T0 - MO5)

	2016	Project Indicator	Status	Project number	Project Name		Capital	Expense	Total		Capital	Expense	Total		Capital	Expense	Total
1	1	Individual Project	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	74268	P2 Downstream Processing Expansion		$91,862,606	$1,766,871	$93,629,477		$104,650,502	$825,644	$105,476,146		#N/A	#N/A	#N/A
2	1	Individual Project	The 3rd HCCF vessel is required to provide a buffer for manufacturing to stabilize the current operation; The requirement gets accentuated with P2 due to the need	74455	3rd HCCF Vessel		$1,669,681	$34,808	$1,704,489		$2,328,891	$27,591	$2,356,482		#N/A	#N/A	#N/A
3	1	Individual Project	The additional six 20l bioreactors are due to: (a) the site and network practice of having backups to the seed labs to reduce operationnal risk;. and (b) we use multiple thaws for product launch; this reduces risk to, and duration of, the qual campaign, and therefore provides a stronger package to submit to the regulatory authorities. And, qual campaigns would take longer without this capability. It is established practice in the network to run multiple thaws.	74454	Seed Lab (20L Bioreactor)		$912,870	$97,323	$1,010,193		$938,961	$10,802	$949,763		#N/A	#N/A	#N/A
4	1	Individual Project	Purchase and set three additional pool tanks into the P2 now together with the P2 project. Additional pool tank capacity is a known requirement for a significant portion of the PTD pipeline currently under development. This will minimize overall cost by 60% and eliminate the need for future shut down to set these tanks.	74453	NPI Pool Tanks		$601,771	$2,484	$604,255		$452,919	$10,802	$463,721		#N/A	#N/A	#N/A
5	1	Individual Project	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	74382	Sci&Eng Lab Mods and Equipment		$7,414,885	$195,338	$7,610,223		$7,008,000	$393,000	$7,401,000		#N/A	#N/A	#N/A
6	1	Individual Project	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	74119	Harvest Upgrade (New Centrifuge)		$4,614,221	$21,631	$4,635,852		$7,233,192	$28,727	$7,261,919		#N/A	#N/A	#N/A
7	1	Startup	Site support for the design, testing for the engineering runs, plant time for 12 runs, and materials that can be used for both engineering runs and qualification runs. The ISD is based on licensure of the potential product candidates for OCN according to the CMContinuum Designated Launch Facility Strategy.	74277	P2 DPE Start-Up		$4,461,207	$0	$4,461,207		$8,000,000	$0	$8,000,000		#N/A	#N/A	#N/A
8	1	Expense	#N/A	98026	Launch Capability Program (LCP)		$0	$800,000	$800,000		$0	$800,000	$800,000		#N/A	#N/A	#N/A
9	1	Individual Project	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	74426	Process VSD and SOV Replacement - 2015		$589,735	$0	$589,735		$489,000	$0	$489,000		#N/A	#N/A	#N/A
10	1	Global	Resolves OSHA Regulatory Agency finding which required OCN to cease use of HMIs. The improvement of the HMI platform will also give operators access to Syncade, Doclink, and DeltaV on four windows displayed on two screens.	64901	MCS Peripheral Asset Replacement - 2015		$43,151	$0	$43,151		$100,000	$0	$100,000		#N/A	#N/A	#N/A
11	1	Individual Project	The DEL/VAL system expansion in order to increase the amount of project work, reduce delays in projects, allow MAR charges that correct current automation issues. Evaluation of system indicated we will fall short of required resources for MAR work with upcoming projects.	74368	Dev/Val Automation Capacity Expansion		$10,000	$0	$10,000		$10,000	$0	$10,000		#N/A	#N/A	#N/A
12		Global	Phase 2 for the MCSBACKUP deployment. Need to ensure data can be retrieved and stored per GMP requirement.	73387	MCSBACKUP Phase 2 Tape Retrieval		$0	$0	$0		$5,000	$0	$5,000		#N/A	#N/A	#N/A
13	1	Individual Project	Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	74406	Corrosive Chemical Compliance		$1,724,239	$0	$1,724,239		$1,812,000	$0	$1,812,000		#N/A	#N/A	#N/A
14	1	Individual Project	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	73367	FS & DS Automation Integration		$26,719	$0	$26,719		$10,000	$0	$10,000		#N/A	#N/A	#N/A
15	1	Individual Project	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	74302	Waterpooling Remediation		$369,680	$0	$369,680		$435,000	$0	$435,000		#N/A	#N/A	#N/A
16	1	Individual Project	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	73356	Supplemental BDU Sampling		$157,774	$0	$157,774		$200,000	$0	$200,000		#N/A	#N/A	#N/A
17	1	Individual Project	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	74279	New Media Technology - HTST / Adventitious		$4,859,034	$88,096	$4,947,130		$5,444,000	$0	$5,444,000		#N/A	#N/A	#N/A
18	1	Global	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	76643	Optimize Column Movement Device		$143,425	$0	$143,425		$128,000	$0	$128,000		#N/A	#N/A	#N/A
19	1	Individual Project	Over exposure to IPA can lead to major health complications. Currently Roche and OSHA "Alert" and "Action" levels of exposure have been exceeded.	74524	Bioburden 2606 IPA Exhaust Improvement		$0	$14,571	$14,571		$12,000	$0	$12,000		#N/A	#N/A	#N/A
20	1	Global	The increased run rates, and the column packing activities require a safer, more reliable method for out of place cleaning. A safety job hazard assessment was performed comparing a score of 60 (high risk priority) for the current operation, to a score of 16 (low risk priority) for the proposed solution. / It is the right thing to do for our employees.	73384	Caustic Bath Upgrade		$459	$0	$459		$9,000	$0	$9,000		#N/A	#N/A	#N/A
21	1	Individual Project	Actemra runs have experienced a reduction in yields starting in Q4/2013. An 8% reduction in yield represents a loss of $20 million per 100 runs and potentially impact on site commercial schedule.	74490	Hyfish Material Screening Operation		$601,445	$0	$601,445		$460,000	$0	$460,000		#N/A	#N/A	#N/A
22	1	Individual Project	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	74418	QC Lab Reconfiguration & Equipment		$3,160,674	$114,000	$3,274,674		$3,675,000	$0	$3,675,000		#N/A	#N/A	#N/A
23	1	Global	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	73399	Frit Handling and Storage		$153,215	$0	$153,215		$108,000	$15,000	$123,000		#N/A	#N/A	#N/A
24	1	Individual Project	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	74373	WFI Generation and Storage System / CUB Expansion		$5,512,468	$23,739	$5,536,207		$5,342,000	$12,500	$5,354,500		#N/A	#N/A	#N/A
25	1	Individual Project	OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	74416	Asphyxiant Gas Remediation		$126,295	$0	$126,295		$99,000	$0	$99,000		#N/A	#N/A	#N/A
26	1	Individual Project	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	74404	Mezzanine Lift Media Prep: Phase 1B		$270,440	-$431	$270,009		$330,000	$0	$330,000		#N/A	#N/A	#N/A
27	1	Global	Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015		$215,828	$0	$215,828		$95,000	$0	$95,000		#N/A	#N/A	#N/A
28		Global	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	73388	SIMCA Online Real Time Process Monitoring System		$0	$0	$0		$58,000	$0	$58,000		#N/A	#N/A	#N/A
29	1	Individual Project	Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement		$204,573	$0	$204,573		$350,000	$0	$350,000		#N/A	#N/A	#N/A
30	1	Individual Project	There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	74392	Water Reclaim System		$143,846	$0	$143,846		$676,000	$0	$676,000		#N/A	#N/A	#N/A
31	1	Global	OCN has made the decision to do a Solar Lease Agreement (SPPA). This project facilitates the installation of solar panels and associated infrastructure as required by the lease agreement. The solar project supports the Roche Eco-Balance network initiative for sustainability. Projected energy savings over the life of the lease are estimated at $10 million (or higher as energy rates continue to increase).	73409	Solar Power Enabling Project		$307,216	$0	$307,216		$271,000	$0	$271,000		#N/A	#N/A	#N/A
32	1	Individual Project	0	74489	4040 Avenida Conference Center Acquisition		$685,700	$0	$685,700		$688,000	$0	$688,000		#N/A	#N/A	#N/A
33	1	Global	There is a global effort to harmonize all GNE/Roche sites to use the same GE model for the TOC assay testing.The intent of this project is to replace the existing TOC analyzers in the lab which are at the end of their lifecycle and purchase the recommended GNE/Roche model. Scope of work includes: Purchase two TOC analyzers, qualification, GMP release and turnover package for each.	64914	QC M9 TOC Analyzers		$17,480	$0	$17,480		$106,000	$0	$106,000		$88,520	$0	$88,520
34	1	Global	QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	64923	QC Met-One Air Sampler Replacement 2015		$15,885	$0	$15,885		$60,000	$0	$60,000		$44,115	$0	$44,115
35	1	Global	QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	64927	QC Gel Imager Replacement 2015		$987	$0	$987		$15,000	$0	$15,000		$14,013	$0	$14,013
36	1	Global	This project will eliminate the unsafe work environment for employees because they will no longer need to lift drums or use the current raw material tenderizer which has been deemed unsafe. This machine can also be a solution for other sites across the network who are looking for the same solution.	65009	Drum Mover/Raw Material Tenderizer		$30,000	$4,000	$34,000		$0	$25,000	$25,000		-$30,000	$21,000	-$9,000
37	1	Global	Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	65005	Analytical Scale		$24,238	$0	$24,238		$0	$0	$0		-$24,238	$0	-$24,238
38		Global		65015	Lower Solid Collector for Centrifuge		$142,000	$0	$142,000		$0	$0	$0		-$142,000	$0	-$142,000
39	1	Global	0	65018	Spare Bowl for Hermetic Centrifuge		$320,000	$0	$320,000		$0	$0	$0		-$320,000	$0	-$320,000
40		Global		65021	Hazardous Material Response Cart		$17,985	$0	$17,985		$0	$0	$0		-$17,985	$0	-$17,985
41		Global		73442	V-2170 Agitator Drain Valve		$0	$0	$0		$0	$0	$0		$0	$0	$0
42		Global		65020	QC Auto-Pipettor for Potency Assay		$27,987	$0	$27,987		$0	$0	$0		-$27,987	$0	-$27,987
43		Global		65023	QC Plate Washer for Potency Assay		$56,795	$0	$56,795		$0	$0	$0		-$56,795	$0	-$56,795
44		Global		65024	Sci&Eng Lab Incubator and Freezer Asset Replacement		$129,028	$0	$129,028		$0	$0	$0		-$129,028	$0	-$129,028
45		Global	Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	65037	Analytical Scales (CAPA 1150248)		$23,997	$0	$23,997		$0	$0	$0		-$23,997	$0	-$23,997
46		Global		65040	Sci&Eng Cryofreezer		$20,185	$0	$20,185		$0	$0	$0		-$20,185	$0	-$20,185
47		Global		64898	Terumo Sterile BCT SCDIIB Welders		$0	$0	$0		$0	$0	$0		$0	$0	$0
77		Global		65048	Process Maintenance Boroscope		$35,008	$0	$35,008		$0	$0	$0		-$35,008	$0	-$35,008
73		Global		65044	Additional MCS Backup Storage		$62,000	$0	$62,000		$0	$0	$0		-$62,000	$0	-$62,000
48		Expense		97059	B311 & B321 Gowning Room Modifications		$0	$100,492	$100,492		$0	$0	$0		$0	-$100,492	-$100,492
49	1	Expense	0	TBD	Piping Corrosion		$0	$3,100,000	$3,100,000		$0	$3,100,000	$3,100,000		$0	$0	$0
50	1	Expense	0	97058	Parking Pavement Repair		$0	$245,040	$245,040		$0	$80,000	$80,000		$0	-$165,040	-$165,040
51	1	Expense	0	97007	Automation System Lifecycle MCS Upgrade - PI		$0	$295,781	$295,781		$0	$270,000	$270,000		$0	-$25,781	-$25,781
52	1	Expense	Process Waste: Currently no ability to waste process materials that don’t exist in Syncade. When material cannot be wasted, it must be scrapped which requires justification and labor intensive forms.QC Sample Plan:Sample Plans have no user-viewable format specific to material and type that can be stored and managed in the DCA. Precludes that ability to use the DCA workflow for document approval. Order Locator: Inability to filter EBR review based on batch information creates inefficient process. The system is flooded with batch reports each day which makes targeting reports ready for review extremely difficult.	97003	MFG Systems Integration Improvement Phase 1 - 2015		$0	$292,227	$292,227		$0	$443,000	$443,000		$0	$150,773	$150,773
53	1	Expense	Multiple device settings, ciurcuit breakers and cable feeds were identified as being undersized operating above 95% of their operating capacity rate.	97048	Arc Flash Prevention		$0	$318,000	$318,000		$0	$318,000	$318,000		$0	$0	$0
54	1	Expense	With parallel project execution a browser I&C database allows concurrent queries and updates to be made. If nothing is done there is added overhead to maintain and outdated system.	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		$0	$866,058	$866,058		$0	$1,180,000	$1,180,000		$0	$313,942	$313,942
55	1	Expense	#N/A	N/A	CRB, travel, ofc supplies, trailer, others		$0	$627,000	$627,000		$0	$627,000	$627,000		$0	$0	$0
56	1	Individual Project	Upgrade PCS hardware and software for Development, Validation and Production environments. Coordinate with P2 Project Team to deploy during the 2016 Plant Shutdown.	74510	PCS Asset Replacement - 2016		$1,765,839		$1,765,839		$1,869,000		$1,869,000		$103,161	$0	$103,161
57	1	Expense	#N/A		PCS Asset Replacement Depreciation Write-Off			$800,000	$800,000			$800,000	$800,000			$0	$0
58	1	Individual Project	Genentech standards require that all controller cabinets shall be fully UL508 listed. CAPA 7046 was generated. PCS Delta Controller Cabinet legacy design represents a safety concern to personnel my means of electrocution, and to equipment resulting in critical failure.	74486	PCS Controller Cabinet Asset Replacement		$2,294,000	$0	$2,294,000		$2,404,000	$0	$2,404,000		$110,000	$0	$110,000
59	1	Individual Project	Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	74487	Process VSD and SOV Asset Replacement		$3,599,797	$0	$3,599,797		$4,542,000	$7,000	$4,549,000		$942,203	$7,000	$949,203
60	1	Individual Project	The Network is the backbone of the Manufacturing Control System (MCS). The infrastructure must be kept up to date to avoid downtime. Lifecycle for equipment is 5 - 7 years. Last replacement was 2009. Project implementation requires shutdown.	74427	MCS Network Infrastructure Asset Replacement - 2016		$1,466,000	$0	$1,466,000		$1,944,000	$0	$1,944,000		$478,000	$0	$478,000
				$140,892,368	$9,807,028	$150,699,396		$162,358,465	$8,974,066	$171,332,531		$21,466,097	-$832,962	$20,633,135
61					Everything above this line is currently in Execution
62	1	Startup	0	74127	Harvest Modifications Start-up		$125,000	$0	$125,000		$125,000	$0	$125,000		$0	$0	$0
63	1	Startup	6/14/16 Change to On Hold due to the uncertatnty with this project.	74491	Etro Tech Transfer		$1,295,272	$69,004	$1,364,276		$7,015,007	$200,000	$7,215,007		$5,719,735	$130,996	$5,850,731
64	1	Individual Project	Compliance with QR018, meeting CAPA 939326 requirements, and to mitigate equipment degradation due to splashing, pooling and vapor condensation. Mitigation of slipping hazards for personell from condensate pooling and drain splashing. Scope includes both P1 and P2.	74511	QR018 Compliance Steam and Condensate Containment		$1,943,300	$0	$1,943,300		$2,457,000	$45,000	$2,502,000		$513,700	$45,000	$558,700
65	1	Individual Project	The OCN site lacks a dedicated Safety Instrumented System to avoid issues with code compliance, avoid accidental trips, maintain and test instruments.	74526	Utility and Process Safety System		$1,882,404	$0	$1,882,404		$1,700,000	$0	$1,700,000		-$182,404	$0	-$182,404
66		Global	Asset Replacment	96991	Asset Replacement 2016 - Engineering (cc642)		$267,639	$0	$267,639		$0	$0	$0		-$267,639	$0	-$267,639
67		Global	Asset Replacment - The total comes from ARR minus the $393k that were tried to pull-in in 2014 (Project P68) + the new assets that need to be repalced for $396k + 45% escalation	96995	Asset Replacement 2016 - Quality (cc583)		$98,979.50	$0	$98,980		$0	$0	$0		-$98,980	$0	-$98,980
68		Global	Asset Replacment	96994	Asset Replacement 2016 - Manufacturing (cc659)		$131,504	$0	$131,504		$0	$0	$0		-$131,504	$0	-$131,504
69		Global	Asset Replacment	96992	Asset Replacement 2016 - Material Ops (cc484)		-$220	$0	-$220		$0	$0	$0		$220	$0	$220
70		Global	Asset Replacment	96993	Asset Replacement 2016 - Manufacturing (cc1359)		$25,188	$0	$25,188		$0	$0	$0		-$25,188	$0	-$25,188
71		Global	Asset Replacment	96997	Asset Replacement 2016 - Maintenance (cc1236)		$15,617	$0	$15,617		$0	$0	$0		-$15,617	$0	-$15,617
72		Individual Project		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)		$306,000	$0	$306,000		$0	$0	$0		-$306,000	$0	-$306,000
74	1	Global		74431	Buffer Prep Mezzanine Lift Construction		$442,000	$0	$442,000		$442,000	$0	$442,000		$0	$0	$0
75		Global		96174	Fall Protection Phase II		$130,000	$0	$130,000		$0	$0	$0		-$130,000	$0	-$130,000
76		Global		96139	Trash Bin Storm Water Mitigation		$0	$0	$0		$200,000	$0	$200,000		$200,000	$0	$200,000
78	1	Expense		97053	Pressure Safety Program - PI Phase		$0	$100,000	$100,000		$0	$100,000	$100,000		$0	$0	$0
				$6,662,683	$169,004	$6,831,687		$11,939,007	$345,000	$12,284,007		$5,276,325	$175,996	$5,452,321
79					Execution Target Line
80	1	Global		96991	Asset Replacement 2016 - Engineering (cc642)		$493,675	$19,747	$513,422		$987,350	$19,747	$1,007,097		$493,675	$0	$493,675
81	1	Global		96995	Asset Replacement 2016 - Quality (cc583)		$203,947	$0	$203,947		$407,893	$0	$407,893		$203,947	$0	$203,947
82	1	Global		96994	Asset Replacement 2016 - Manufacturing (cc659)		$131,504	$5,260	$136,764		$263,008	$5,260	$268,268		$131,504	$0	$131,504
83	1	Global	Asset Replacment	96992	Asset Replacement 2016 - Material Ops (cc484)		$58,000	$2,480	$60,480		$124,000	$2,480	$126,480		$66,000	$0	$66,000
84	1	Global		96993	Asset Replacement 2016 - Manufacturing (cc1359)		$25,188	$0	$25,188		$50,375	$0	$50,375		$25,188	$0	$25,188
85	1	Global		96997	Asset Replacement 2016 - Maintenance (cc1236)		$15,617	$0	$15,617		$31,233	$0	$31,233		$15,617	$0	$15,617
86		Global		96169	Level Indicator Transmitters		$70,000	$0	$70,000		$0	$0	$0		-$70,000	$0	-$70,000
87	1	Global		96159	OCC Network Remediation		$150,000	$0	$150,000		$150,000	$0	$150,000		$0	$0	$0
88	1	Individual Project		74435	Hastelloy Chromatography Column (160cm)		$400,000	$0	$400,000		$1,549,000	$0	$1,549,000		$1,149,000	$0	$1,149,000
89		Global		96135	QC Spectrophotmeters		$0	$0	$0		$327,522	$0	$327,522		$327,522	$0	$327,522
90		Individual Project		74527	Vessel 1020 Upgrade		$0	$0	$0		$2,646,000	$0	$2,646,000		$2,646,000	$0	$2,646,000
91		Global		96134	QC Liquid Handler		$0	$0	$0		$134,917	$0	$134,917		$134,917	$0	$134,917
92		Individual Project	Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	74409	K6 Program - Project 1 - Replace DX HVAC Units		$0	$0	$0		$1,902,000	$22,000	$1,924,000		$1,902,000	$22,000	$1,924,000
93	1	Global		96137	Security Cameras Improvement on Parking Lot		$200,000	$0	$200,000		$250,000	$0	$250,000		$50,000	$0	$50,000
94		Individual Project		74385	Media Prep Endotoxin/Bioburden Sampling		$0	$0	$0		$500,000	$0	$500,000		$500,000	$0	$500,000
95		Global		96132	Mezzanine Safety Shower/Eye Wash Station Install		$0	$0	$0		$210,000	$0	$210,000		$210,000	$0	$210,000
96		Global		96164	Hazardous Materials Containers Washing Station		$0	$0	$0		$30,000	$0	$30,000		$30,000	$0	$30,000
97	1	Global		96167	Emergency Generator High Level Alarm		$25,000	$0	$25,000		$25,000	$0	$25,000		$0	$0	$0
98	1	Global		96168	Replace Warehouse #321 Sprinkler Heads		$20,000	$0	$20,000		$20,000	$0	$20,000		$0	$0	$0
99		Expense		97040	Tech Transfer: Master Data Management		$0	$0	$0		$0	$250,000	$250,000		$0	$250,000	$250,000
100		Expense		97038	PCS Functional Specification Development Project (CAPA 960297)		$0	$0	$0		$0	$1,000,000	$1,000,000		$0	$1,000,000	$1,000,000
101		Expense		97039	PCS Remediation for EBR Review by Exception - PI		$0	$0	$0		$0	$250,000	$250,000		$0	$250,000	$250,000
102	1	Expense		97045	Site Exterior Lighting Upgrade - Title 24		$0	$100,000	$100,000		$0	$200,000	$200,000		$0	$100,000	$100,000
103		Individual Project		74525	CIP Reliability and Efficiency - PI		$0	$0	$0		$0	$400,000	$400,000		$0	$400,000	$400,000
104	1	Expense		97057	Conference Room 315 Expansion		$0	$150,000	$150,000		$0	$300,000	$300,000		$0	$150,000	$150,000
105		Expense		97054	HVAC Retro Commissioning		$0	$0	$0		$0	$0	$0		$0	$0	$0
106		Global		96136	V-3007 Replacement		$0	$0	$0		$0	$0	$0		$0	$0	$0
107		Individual Project		74432	K6 Program - Project 4 - Replace Chillers		$0	$0	$0		$0	$0	$0		$0	$0	$0
108		Individual Project		74278	K6 Program - Project 3 - Replace Cold Room Compressors		$0	$0	$0		$0	$0	$0		$0	$0	$0
109		Individual Project		74512	K6 Program - Project 2 - B381 Compliance		$0	$0	$0		$0	$0	$0		$0	$0	$0
110		Global		96133	QC Rapid Scan RDI System		$0	$0	$0		$0	$0	$0		$0	$0	$0
111		Individual Project		96165	WAN Link Redundancy		$0	$0	$0		$0	$0	$0		$0	$0	$0
112		Individual Project		96160	B331 Fire Code Compliance		$0	$0	$0		$0	$0	$0		$0	$0	$0
113		Individual Project		74371	Odor Treatment		$0	$0	$0		$0	$0	$0		$0	$0	$0
114		Individual Project		74513	Electric Vehicle Charging Stations		$0	$0	$0		$0	$0	$0		$0	$0	$0
115		Global		96163	MFG Depth Filter Housing		$0	$0	$0		$0	$0	$0		$0	$0	$0
116		Individual Project		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement		$0	$0	$0		$0	$0	$0		$0	$0	$0
117		Global		96069	Warehouse Crown Forklift Asset Replacement		$0	$0	$0		$0	$0	$0		$0	$0	$0
118		Individual Project		96105	TMAC Tenderizer		$0	$0	$0		$0	$0	$0		$0	$0	$0
119		Individual Project		96109	Sci&Eng Lab Equipment for NPI and Launch Capability		$0	$0	$0		$0	$0	$0		$0	$0	$0
120		Individual Project		96112	Maintenance Ops Shop Buildout		$0	$0	$0		$0	$0	$0		$0	$0	$0
121		Individual Project		96114	QC Testing Equipment for Launch Capability and Storage Requirements		$0	$0	$0		$0	$0	$0		$0	$0	$0
122		Individual Project		96116	PCS Process Support Equipment Integration		$0	$0	$0		$0	$0	$0		$0	$0	$0
123		Individual Project		96124	TT Per Tech Transfer		$0	$0	$0		$0	$0	$0		$0	$0	$0
124		Global		96152	Appleton Tank Mover		$0	$0	$0		$0	$0	$0		$0	$0	$0
125		Expense		97061	Tangential Flow Filtration Cassettes Management		$0	$0	$0		$0	$0	$0		$0	$0	$0
126		Expense		97005	MCS Peripheral Asset Replacement - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
127		Expense		97009	MES Asset Replacement - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
128		Expense		97012	Site Data Historian Asset Replacement - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
129		Expense		97015	MCS Backup System Asset Replacement - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
130		Expense		97030	MFG Systems Integration Improvement Phase 3 - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
131		Expense		97031	MCS Data Analytics Asset Replacement - 2017		$0	$0	$0		$0	$0	$0		$0	$0	$0
132		Expense		97037	Recipe Reconfiguration Alignment for Operating Systems		$0	$0	$0		$0	$0	$0		$0	$0	$0
133		Expense		97060	QC Gas Cabinet Removal		$0	$75,000	$75,000		$0	$0	$0		$0	-$75,000	-$75,000
134		Individual Project		96177	Efficiency Projects		$0	$0	$0		$0	$0	$0		$0	$0	$0
				$1,792,930	$352,487	$2,145,417		$9,608,298	$2,449,487	$12,057,785		$7,815,369	$2,097,000	$9,912,369
				Execution + Not Started		$149,347,980	$10,328,519	$159,676,499		$183,905,770	$11,768,553	$195,674,323		$34,557,790	$1,440,034	$35,997,824
160					IMPACT Controllable Delta		$3,061,379	$410,995	$3,472,374		N/A	N/A	N/A
				IMPACT Non-Controllable Delta (P2/CMC Projects/TT)		$24,794,959	-$690,893	$24,104,066		N/A	N/A	N/A
161					Site Judgedown		-$1,792,930	-$352,487	-$2,145,417		-$6,148,298	-$1,890,000	-$8,038,298
162					TOTAL*		$175,411,388	$9,696,134	$185,107,522		$177,757,472	$9,878,553	$187,636,025

				*MO5 Total will be finalized by 4/26/16, due to Controllable/Non-Controllable.

## Constraint_Analysis_2016_(Live)
		Bio Drug Substance - Oceanside					Updated: 6/28/16
		Constraint Analysis - T3 vs MO5
		2016 T3					T3				MO5				Delta T3 - MO5

	2016	Project Indicator	Project number	Project Name	SPgM	Program	Tag	Score	PMO Lead		Avg. Roche Resources	Capital	Expense	Total		Capital	Expense	Total		Delta Capital	Delta Expense	Delta Total		Project Total
1	1	Individual Project	74268	P2 Downstream Processing Expansion (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	Execute 2		21.21	$91,862,606	$1,766,871	$93,629,477		$92,403,605	$1,248,192	$93,651,797		-$540,999	$518,679	-$22,320		$193,915,669
2	1	Individual Project	74455	3rd HCCF Vessel (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	Execute		0.07	$1,669,681	$34,808	$1,704,489		$2,027,438	$43,784	$2,071,222		-$357,757	-$8,976	-$366,733		$3,240,391
3	1	Individual Project	74454	Seed Lab (20L Bioreactor) (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	Execute		0.02	$912,870	$97,323	$1,010,193		$954,867	$141,531	$1,096,398		-$41,997	-$44,208	-$86,205		$2,838,356
4	1	Individual Project	74453	NPI Pool Tanks (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	PTAA		0	$601,771	$2,484	$604,255		$684,545	$2,883	$687,428		-$82,774	-$399	-$83,173		$1,223,000
5	1	Individual Project	74382	Sci&Eng Lab Mods and Equipment	Jim Neeleman	Launch and Commercial Excellence	P2	7.6	Execute 2		1.13	$7,414,885	$195,338	$7,610,223		$6,232,184	$458,027	$6,690,211		$1,182,701	-$262,689	$920,012		$14,009,740
6	1	Individual Project	74119	Harvest Upgrade (New Centrifuge) (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	Execute 2		2.30	$4,614,221	$21,631	$4,635,852		$7,001,377	$37,498	$7,038,875		-$2,387,156	-$15,867	-$2,403,023		$15,479,491
7	1	Startup	74277	P2 DPE Start-Up	Zaymar Sedra	Fit for Purpose	P2	60	Execute		0	$4,461,207	$0	$4,461,207		$4,461,207	$0	$4,461,207		$0	$0	$0		$51,497,000
8	1	Expense	98026	Launch Capability Program (LCP)	Jim Neeleman	Launch and Commercial Excellence	P2	0	Execute		12.00	$0	$800,000	$800,000		$0	$800,000	$800,000		$0	$0	$0		$800,000
9	1	Individual Project	74426	Process VSD and SOV Replacement - 2015	Scott Fields	Reliability and Value	E	N/A	Execute		0.30	$589,735	$0	$589,735		$495,036	$0	$495,036		$94,699	$0	$94,699		$784,356
10	1	Global	64901	MCS Peripheral Asset Replacement - 2015	Scott Fields	Reliability and Value	E	0	Execute		0	$43,151	$0	$43,151		$99,984	$0	$99,984		-$56,833	$0	-$56,833		$266,368
11	1	Individual Project	74368	Dev/Val Automation Capacity Expansion	Jim Neeleman	Launch and Commercial Excellence	E	N/A	Execute		0	$10,000	$0	$10,000		$10,000	$0	$10,000		$0	$0	$0		$555,477
12		Global	73387	MCSBACKUP Phase 2 Tape Retrieval	Deidre Dunham	Reliability and Value	E	N/A	Execute		0.5	$0	$0	$0		$5,000	$0	$5,000		-$5,000	$0	-$5,000		$45,791
13	1	Individual Project	74406	Corrosive Chemical Compliance	Scott Fields	Reliability and Value	E	34	Execute		0.11	$1,724,239	$0	$1,724,239		$1,596,303	$0	$1,596,303		$127,936	$0	$127,936		$1,910,997
14	1	Individual Project	73367	FS & DS Automation Integration	Zaymar Sedra	Fit for Purpose	E	24.4	Execute 2		0.31	$26,719	$0	$26,719		$26,719	$0	$26,719		$0	$0	$0		$749,690
15	1	Individual Project	74302	Waterpooling Remediation	Jim Neeleman	Reliability and Value	E	23	Execute 2		0.83	$369,680	$0	$369,680		$369,680	$0	$369,680		$0	$0	$0		$2,085,021
16	1	Individual Project	73356	Supplemental BDU Sampling	Jim Neeleman	Launch and Commercial Excellence	E	19.5	Execute 2		0	$157,774	$0	$157,774		$157,774	$0	$157,774		$0	$0	$0		$1,836,669
17	1	Individual Project	74279	New Media Technology - HTST / Adventitious	Scott Fields	Reliability and Value	E	19.2	Execute 2		5.15	$4,859,034	$88,096	$4,947,130		$4,810,886	$1,768	$4,812,654		$48,148	$86,328	$134,476		$9,046,079
18	1	Global	76643	Optimize Column Movement Device	Melanie Yevilov	Highly Capable Workforce	E	18.6	Execute		0.02	$143,425	$0	$143,425		$143,425	$0	$143,425		$0	$0	$0		$269,899
19	1	Global	73384	Caustic Bath Upgrade	Melanie Yevilov	Highly Capable Workforce	E	16.5	Execute		0	$459	$0	$459		$11,541	$459	$12,000		-$11,082	-$459	-$11,541		$1,880
20	1	Individual Project	74490	Hyfish Material Screening Operation	Jim Neeleman	Reliability and Value	E	16.3	Execute		0.05	$601,445	$0	$601,445		$422,881	$0	$422,881		$178,564	$0	$178,564		$1,461,483
21	1	Individual Project	74418	QC Lab Reconfiguration & Equipment	Jim Neeleman	Launch and Commercial Excellence	E	15.8	Execute 1		0.28	$3,160,674	$114,000	$3,274,674		$1,918,122	$113,000	$2,031,122		$1,242,552	$1,000	$1,243,552		$3,789,146
22	1	Global	73399	Frit Handling and Storage	Melanie Yevilov	Highly Capable Workforce	E	11.3	Execute		0.11	$153,215	$0	$153,215		$191,950	$15,000	$206,950		-$38,735	-$15,000	-$53,735		$172,209
23	1	Individual Project	74373	WFI Generation and Storage System / CUB Expansion	Zaymar Sedra	Fit for Purpose	E	11.1	Execute 2		3.08	$5,512,468	$23,739	$5,536,207		$5,523,133	$13,075	$5,536,208		-$10,665	$10,664	-$1		$13,800,941
24	1	Individual Project	74416	Asphyxiant Gas Remediation	Melanie Yevilov	Highly Capable Workforce	E	11.1	Execute 1		0.06	$126,295	$0	$126,295		$142,115	$0	$142,115		-$15,820	$0	-$15,820		$162,954
25	1	Individual Project	74404	Mezzanine Lift Media Prep: Phase 1B	Melanie Yevilov	Highly Capable Workforce	E	10.7	Execute		0.01	$270,440	-$431	$270,009		$201,044	-$431	$200,613		$69,396	$0	$69,396		$552,787
26	1	Global	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Scott Fields	Reliability and Value	E	10.5	Execute		0	$215,828	$0	$215,828		$204,700	$0	$204,700		$11,128	$0	$11,128		$229,175
27	1	Individual Project	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Scott Fields	Reliability and Value	E	7.7	Execute		0.21	$204,573	$0	$204,573		$198,196	$0	$198,196		$6,377	$0	$6,377		$470,674
28	1	Individual Project	74392	Water Reclaim System	Scott Fields	Reliability and Value	E	6.1	Execute		0.47	$143,846	$0	$143,846		$162,102	$0	$162,102		-$18,256	$0	-$18,256		$322,931
29	1	Global	73409	Solar Power Enabling Project	Melanie Yevilov	Highly Capable Workforce	E	5.1	Execute		0.02	$307,216	$0	$307,216		$305,902	$0	$305,902		$1,314	$0	$1,314		$439,439
30	1	Individual Project	74489	4040 Avenida Conference Center Acquisition	Deidre Dunham	Exceptional Culture	E	3.1	Execute		0	$685,700	$0	$685,700		$686,850	$0	$686,850		-$1,150	$0	-$1,150		$3,386,700
31	1	Global	64914	QC M9 TOC Analyzers	Jim Neeleman	Launch and Commercial Excellence	E	N/A	Execute		0	$17,480	$0	$17,480		$18,930	$0	$18,930		-$1,450	$0	-$1,450		$104,550
32	1	Global	64923	QC Met-One Air Sampler Replacement 2015	Jim Neeleman	Launch and Commercial Excellence	E	N/A	Execute		0	$15,885	$0	$15,885		$15,885	$0	$15,885		$0	$0	$0		$60,000
33	1	Global	64927	QC Gel Imager Replacement 2015	Jim Neeleman	Launch and Commercial Excellence	E	N/A	Execute		0	$987	$0	$987		$2,660	$0	$2,660		-$1,673	$0	-$1,673		$13,327
34	1	Global	65009	Drum Mover/Raw Material Tenderizer	Jim Neeleman	Highly Capable Workforce	E	0	Execute		0	$30,000	$4,000	$34,000		$30,000	$4,000	$34,000		$0	$0	$0		$34,000
35	1	Global	65005	Analytical Scale	Scott Fields	Reliability and Value	E	0	Execute		0	$24,238	$0	$24,238		$24,238	$0	$24,238		$0	$0	$0		$24,238
36		Global	65015	Lower Solid Collector for Centrifuge	Scott Fields	Reliability and Value	E	0	Execute		0	$142,000	$0	$142,000		$245,000	$0	$245,000		-$103,000	$0	-$103,000		$142,000
37	1	Global	65018	Spare Bowl for Hermetic Centrifuge	Zaymar Sedra	Fit for Purpose	E	0	Execute		0	$320,000	$0	$320,000		$320,000	$0	$320,000		$0	$0	$0		$320,000
38		Global	65021	Hazardous Material Response Cart	Melanie Yevilov	Highly Capable Workforce	E	3.9	Execute		0	$17,985	$0	$17,985		$19,424	$0	$19,424		-$1,439	$0	-$1,439		$17,985
39		Global	65020	QC Auto-Pipettor for Potency Assay	Melanie Yevilov	Reliability and Value	E	0	Execute		0	$27,987	$0	$27,987		$27,987	$0	$27,987		$0	$0	$0		$27,987
40		Global	65023	QC Plate Washer for Potency Assay	Jim Neeleman	Launch and Commercial Excellence	E	0	Execute		0	$56,795	$0	$56,795		$56,795	$0	$56,795		$0	$0	$0		$56,795
41		Global	65024	Sci&Eng Lab Incubator and Freezer Asset Replacement	Jim Neeleman	Launch and Commercial Excellence	E	0	Execute		0	$129,028	$0	$129,028		$140,000	$0	$140,000		-$10,972	$0	-$10,972		$129,028
42		Global	65037	Analytical Scales (CAPA 1150248)	Scott Fields	Reliability and Value	E	0	Execute		0	$23,997	$0	$23,997		$23,914	$0	$23,914		$83	$0	$83		$23,997
43		Global	65040	Sci&Eng Cryofreezer	Jim Neeleman	Launch and Commercial Excellence	E	0	Execute		0	$20,185	$0	$20,185		$20,185	$0	$20,185		$0	$0	$0		$20,185
44		Global	65048	Process Maintenance Boroscope	Jim Neeleman	Reliability and Value	E	0	Execute		0	$35,008	$0	$35,008		$37,000	$0	$37,000		-$1,992	$0	-$1,992		$35,008
45		Global	65044	Additional MCS Backup Storage	Scott Fields	Reliability and Value	E	0	Execute		0	$62,000	$0	$62,000		$62,000	$0	$62,000		$0	$0	$0		$62,000
46		Individual Project	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	Jim Neeleman	Reliability and Value	E	0	Execute		0.42	$306,000	$0	$306,000		$306,000	$0	$306,000		$0	$0	$0		$960,000
47		Global	65066	Appleton Tank Mover	Melanie Yevilov	Highly Capable Workforce	E	8.9	Hold		0	$73,000	$0	$73,000		$73,000	$0	$73,000		$0	$0	$0		$73,000
48		Global	65082	RF Sealer Generator	Scott Fields	Reliability and Value	E	0			0.25	$22,000	$0	$22,000		$17,250	$0	$17,250		$4,750	$0	$4,750		$22,000
49	1	Individual Project	74546	Mezzanine Safety Shower/Eye Wash Station Install	Melanie Yevilov	Highly Capable Workforce	E	2.9	IMPACT Appr		0.27	$450,000	$0	$450,000		$100,000	$0	$100,000		$350,000	$0	$350,000		$886,000
50		Expense	74524	Bioburden 2606 IPA Exhaust Improvement	Melanie Yevilov	Reliability and Value	Ex	18	Execute		0.00	$0	$14,571	$14,571		$0	$8,519	$8,519		$0	$6,052	$6,052		$14,571
51		Expense	97053	Pressure Safety Program - PI Phase	Melanie Yevilov	Highly Capable Workforce	Ex	18.8	Execute		0.00	$0	$100,000	$100,000		$0	$100,000	$100,000		$0	$0	$0		$100,000
52		Expense	97059	B311 & B321 Gowning Room Modifications	Zaymar Sedra	Reliability and Value	Ex	0	Execute		0.05	$0	$100,492	$100,492		$0	$107,000	$107,000		$0	-$6,508	-$6,508		$100,492
53	1	Expense	TBD	PAIR	Scott Fields	Reliability and Value	Ex	0	Execute		TBD	$0	$3,102,350	$3,102,350		$0	$3,091,211	$3,091,211		$0	$11,139	$11,139		$7,890,698
54	1	Expense	97058	Parking Pavement Repair	Scott Fields	Reliability and Value	Ex	0	Execute		0.00	$0	$245,040	$245,040		$0	$245,040	$245,040		$0	$0	$0		$245,040
55	1	Expense	97007	Automation System Lifecycle MCS Upgrade - PI	Deidre Dunham	Reliability and Value	Ex	27.6	Execute		1.79	$0	$295,781	$295,781		$0	$295,169	$295,169		$0	$612	$612		$295,781
56	1	Expense	97003	MFG Systems Integration Improvement Phase 1 - 2015	Deidre Dunham	Reliability and Value	Ex	15.3	Execute 1		0.94	$0	$292,227	$292,227		$0	$443,000	$443,000		$0	-$150,773	-$150,773		$427,227
57	1	Expense	97048	Arc Flash Prevention	Melanie Yevilov	Highly Capable Workforce	Ex	5.9	Execute		0	$0	$318,000	$318,000		$0	$319,456	$319,456		$0	-$1,456	-$1,456		$318,000
58	1	Expense	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Deidre Dunham	Reliability and Value	Ex	3.4	Execute 1		0.68	$0	$866,058	$866,058		$0	$933,708	$933,708		$0	-$67,650	-$67,650		$1,510,946
59	1	Expense	N/A	CRB, travel, ofc supplies, others	Scott Fields	Reliability and Value	Ex	N/A			0	$0	$317,400	$317,400		$0	$317,400	$317,400		$0	$0	$0		$634,800
60	1	Individual Project	74510	PCS Asset Replacement - 2016	Zaymar Sedra	Fit for Purpose	SD	N/A	Execute		0.18	$1,765,839	$219	$1,766,058		$1,745,958	$69	$1,746,027		$19,881	$150	$20,031		$1,915,058
61	1	Expense		PCS Asset Replacement Depreciation Write-Off			SD					$800,000	$800,000		$0	$800,000	$800,000		$0	$0	$0		$800,000
62	1	Individual Project	74486	PCS Controller Cabinet Asset Replacement	Melanie Yevilov	Highly Capable Workforce	SD	N/A	Execute		0.42	$2,294,000	$0	$2,294,000		$2,294,000	$0	$2,294,000		$0	$0	$0		$2,404,000
63	1	Individual Project	74487	Process VSD and SOV Asset Replacement	Melanie Yevilov	Highly Capable Workforce	SD	N/A	Execute		0.33	$3,599,797	$0	$3,599,797		$3,599,318	$0	$3,599,318		$479	$0	$479		$6,542,828
64	1	Individual Project	74427	MCS Network Infrastructure Asset Replacement - 2016	Scott Fields	Reliability and Value	SD	N/A	Execute		0.29	$1,466,000	$0	$1,466,000		$1,944,000	$0	$1,944,000		-$478,000	$0	-$478,000		$3,806,000
65	1	Individual Project	74526	Utility and Process Safety System	Scott Fields	Reliability and Value	SD	13.3	FXNL LT Appr		0	$1,882,404	$0	$1,882,404		$1,190,000	$0	$1,190,000		$692,404	$0	$692,404		$1,940,000
66	1	Individual Project	74511	QR018 Compliance Steam and Condensate Containment	Jim Neeleman	Reliability and Value	SD	13.3	Execute		1.82	$1,943,300	$0	$1,943,300		$1,943,300	$0	$1,943,300		$0	$0	$0		$5,017,800
67				Everything above this line is currently in Execution
68	1	Startup	74127	Harvest Modifications Start-up	Deidre Dunham	Launch Facility	P2	60	Budgeted		2.40	$125,000	$0	$125,000		$125,000	$0	$125,000		$0	$0	$0		$2,400,000
69	1	Startup	74491	Etro Tech Transfer (NIC)	Deidre Dunham	Launch and Commercial Excellence	P2	60	Hold		28.30	$1,295,272	$69,004	$1,364,276		$6,094,794	$116,900	$6,211,694		-$4,799,522	-$47,896	-$4,847,418		$18,122,360
70		Global	96216	Frit Handling and Storage Phase 2	TBD	Highly Capable Workforce	AL	20.2	FXNL LT Appr		0.09	$50,000	$0	$50,000		$0	$0	$0		$50,000	$0	$50,000		$50,000
71	1	Individual Project	74435	Hastelloy Chromatography Column (160cm)	Zaymar Sedra	Fit for Purpose	AL	17.1	FXNL LT Appr		2.39	$400,000	$0	$400,000		$0	$0	$0		$400,000	$0	$400,000		$1,549,000
72	1	Global	74431	Buffer Prep Mezzanine Lift Construction	Scott Fields	Reliability and Value	AL	10.7	JPMT Appr		0.09	$442,000	$0	$442,000		$442,000	$0	$442,000		$0	$0	$0		$442,000
73	1	Global	96137	Security Systems Upgrade	Deidre Dunham	Exceptional Culture	AL	6.7	JPMT Appr		0	$200,000	$0	$200,000		$175,000	$0	$175,000		$25,000	$0	$25,000		$200,000
74		Global	96174	Fall Protection Phase II	TBD	TBD	AL	3.6	CA Routing		0.04	$130,000	$0	$130,000		$135,000	$0	$135,000		-$5,000	$0	-$5,000		$135,000
75		Global	96991	Asset Replacement 2016 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$95,639	-$10,000	$85,639		$229,675	$0	$229,675		-$134,036	-$10,000	-$144,036		$1,512,097
76		Global	96995	Asset Replacement 2016 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$98,980	$0	$98,980		$98,980	$0	$98,980		$0	$0	$0		$1,130,822
77		Global	96994	Asset Replacement 2016 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$131,504	$0	$131,504		$131,504	$0	$131,504		$0	$0	$0		$426,046
78		Global	96992	Asset Replacement 2016 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$13,765	$0	$13,765		$13,848	$0	$13,848		-$83	$0	-$83		$1,304,309
79		Global	96993	Asset Replacement 2016 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$25,188	$0	$25,188		$25,188	$0	$25,188		$0	$0	$0		$415,375
80		Global	96997	Asset Replacement 2016 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	AL	N/A	FXNL LT Appr		0	$15,617	$0	$15,617		$15,617	$0	$15,617		$0	$0	$0		$87,282
81		Global	96207	Weigh and Dispense Sink (CAPA1123109)	Scott Fields	Reliability and Value	AL	0			0.11	$150,000	$15,000	$165,000		$25,000	$5,000	$30,000		$125,000	$10,000	$135,000		$165,000
82	1	Expense	97057	Conference Room 315 Expansion	Deidre Dunham	Exceptional Culture	AL	0	Idea		0	$0	$150,000	$150,000		$0	$108,000	$108,000		$0	$42,000	$42,000		$150,000
87		Global	96220	400L Mixing Vessel	Jim Neeleman	Launch and Commercial Excellence	AL	17.3	FXNL LT Appr		0	$320,000	$20,000	$340,000		$0	$0	$0		$320,000	$20,000	$340,000		$402,000
88		Global	96218	Column Maintenance Platform Installation	Melanie Yevilov	Highly Capable Workforce	AL	13.3	FXNL LT Appr		0.25	$75,000	$0	$75,000		$0	$0	$0		$75,000	$0	$75,000		$175,000
89		Individual Project	96210	P2 User Furnished Equipment Procurement	TBD	TBD	AL	9	FXNL LT Appr		0	$950,000	$150,000	$1,100,000		$0	$0	$0		$950,000	$150,000	$1,100,000		$2,200,000
83	1	Expense	97069	Manufacturing Bullpen	TBD	TBD	AL	0	Idea		0	$0	$150,000	$150,000		$0	$0	$0		$0	$150,000	$150,000		$150,000
84				Execution Target Line
86		Global	96215	20L Bioreactors and NovaFlex Analyzer	Zaymar Sedra	Fit for Purpose	BL	20	FXNL LT Appr		0.25	$450,000	$0	$450,000		$0	$0	$0		$450,000	$0	$450,000		$450,000
85	1	Global	96159	OCC Network Remediation	Zaymar Sedra	Fit for Purpose	BL	22.8	Idea		0	$150,000	$0	$150,000		$150,000	$0	$150,000		$0	$0	$0		$150,000
90		Global	96135	QC Spectrophotometers	Melanie Yevilov	Highly Capable Workforce	BL	14.4	Canceled		0	$0	$0	$0		$23,000	$0	$23,000		-$23,000	$0	-$23,000		$0
91		Individual Project	74385	Media Prep Endotoxin/Bioburden Sampling	Melanie Yevilov	Reliability and Value	BL	6.5	Hold		2.28	$0	$0	$0		$250,000	$0	$250,000		-$250,000	$0	-$250,000		$0
92	1	Expense	97045	Site Exterior Lighting Upgrade - Title 24	Scott Fields	Reliability and Value	BL	2.4	FXNL LT Appr		0	$0	$100,000	$100,000		$0	$100,000	$100,000		$0	$0	$0		$200,000
93	1	Global	96991	Asset Replacement 2016 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$493,675	$14,747	$508,422		$493,675	$14,747	$508,422		$0	$0	$0		$1,512,097
94	1	Global	96995	Asset Replacement 2016 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$203,947	$0	$203,947		$203,947	$0	$203,947		$0	$0	$0		$1,130,822
95	1	Global	96994	Asset Replacement 2016 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$131,504	$5,260	$136,764		$131,504	$5,260	$136,764		$0	$0	$0		$426,046
96	1	Global	96992	Asset Replacement 2016 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$62,000	$2,480	$64,480		$62,000	$2,480	$64,480		$0	$0	$0		$1,304,309
97	1	Global	96993	Asset Replacement 2016 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$25,188	$0	$25,188		$25,188	$0	$25,188		$0	$0	$0		$415,375
98	1	Global	96997	Asset Replacement 2016 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	BL	N/A	FXNL LT Appr		0	$15,617	$0	$15,617		$15,617	$0	$15,617		$0	$0	$0		$87,282
99		Expense	97060	QC Gas Cabinet Removal	TBD	TBD	BL	0	FXNL LT Appr		0	$0	$75,000	$75,000		$0	$75,000	$75,000		$0	$0	$0		$75,000
101		Global	96169	Level Indicator Transmitters	Zaymar Sedra	Fit for Purpose	BL	0	Idea		0	$70,000	$0	$70,000		$70,000	$0	$70,000		$0	$0	$0		$70,000
102	1	Global	96167	Emergency Generator High Level Alarm	Melanie Yevilov	Reliability and Value	BL	0	Idea		0	$25,000	$0	$25,000		$25,000	$0	$25,000		$0	$0	$0		$25,000
103	1	Global	96168	Replace Warehouse #321 Sprinkler Heads	Melanie Yevilov	Highly Capable Workforce	BL	0	Idea		0	$20,000	$0	$20,000		$20,000	$0	$20,000		$0	$0	$0		$20,000
104				Contigency					$0	$0	$0		$3,800,236	$0	$3,800,236		-$3,800,236	$0	-$3,800,236		-$3,800,236
105				Site Judgedown					$0	$0	$0		-$1,487,180	-$197,487	-$1,684,667		$1,487,180	$197,487	$1,684,667		$1,684,667
106				TOTAL					91.9	$150,087,036	$10,144,001	$160,231,036		$157,000,000	$9,769,257	$166,769,257		-$5,266,035	$572,230	-$4,693,805		$397,086,308
107				OCN TOTAL CAPACITY					94.0

				T3				MO5				Delta T3 - MO5
				Resource	Capital	Expense	Total		Capital	Expense	Total		Capital	Expense	Delta Total		Lifetime Total
				P2/CMC Projects			P2				67.4	$112,957,513	$2,987,459	$115,944,972		$119,985,017	$2,848,814	$122,833,831		-$7,027,504	$138,644	-$6,888,859		$303,526,006
				Non P2/CMC Proposed in execution			E				12.4	$21,080,491	$229,404	$21,309,895		$19,033,361	$155,390	$19,188,751		$2,047,130	$74,014	$2,121,144		$45,352,767
				Expense Only Projects in Execution			Ex				3.5	$0	$5,651,919	$5,651,919		$0	$5,851,984	$5,851,984		$0	-$200,065	-$200,065		$11,537,555
				Shutdown Critical Projects			SD				3.0	$12,951,340	$800,219	$13,751,559		$12,716,576	$800,069	$13,516,645		$234,764	$150	$234,914		$22,425,686
				Non P2/CMC Endorsed Projects			AL				0.4	$3,097,692	$475,000	$3,572,692		$1,464,811	$113,000	$1,577,811		$1,632,881	$362,000	$1,994,881		$10,493,931
				Below Line (including Expense Only)					0.0	$0	$0	$0		$1,487,180	$197,487	$1,684,667		-$1,487,180	-$197,487	-$1,684,667		$5,415,931
				Contingency					$0	$0	$0		$3,800,236	$0	$3,800,236		-$3,800,236	$0	-$3,800,236		-$3,800,236
				Site Judgedown					$0	$0	$0		-$1,487,180	-$197,487	-$1,684,667		$1,487,180	$197,487	$1,684,667		$1,684,667
				TOTAL					86.7	$150,087,036	$10,144,001	$160,231,036		$157,000,000	$9,769,257	$166,769,257		-$6,912,964	$374,743	-$6,538,221		$396,636,308
				Deferred or Need Scope Defined					#REF!	#REF!	#REF!	#REF!					#REF!
				Deferred					0	$1,046,930	$97,487	$1,144,417					$0	$5,065,931

		Assumptions:
		Site Capital judge down is based on costs below 2016 Execution Targets.
		Total Expense budget is $9.9M
		Resource Capacity: Historical 50 FTE + 10 FTE TT, 2015 20 hired for P2, 2016 14 hired for TT = 94 FTE.
		Resource Demand to support network projects is 10 FTE
		OLT Decision: Focusing on projects already in execution, Tech Transfer and shutdown critical.
		Site judgedown applies in MO5 for all projects below the line as we did in T0.

				Target < $25M					$24,178,183	TRUE

				$0

				Total (*)	Incl. 10% Adjustment		Total	Incl. 10% Adjustment
				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Expense	#REF!
				Expense	#REF!	YEAR 2015 / TOTAL BUDGET

				Capital (Line Item + Global)	#REF!	#REF!		#REF!

				Expense	#REF!

				Expense (All)	#REF!	-	This total includes Above the line Auto. Expense Projects

				Total (*)	Incl. Adjustment		Total	Incl. Adjustment
				Capital	$4,229,561	$3,383,648		#REF!	#REF!

				Capital	$146,457,475	$147,303,387		$22,232,143	$17,785,714
				Expense	$2,563,082	-		$7,197,629	-
				Total Cap + Exp	$149,020,557	$147,303,387		$29,429,772	$17,785,714

				Expense	$29,000	-		#REF!	-
				Total Cap + Exp	$302,299,674	$297,990,423		#REF!	#REF!

				Expense	#REF!
				YEAR 2016 / TOTAL BUDGET

				Capital (Line Item + Global)	$150,687,036	$150,687,036		#REF!

				Expense (All)	#REF!	- / This total includes Above the line Auto. Expense Projects

## OLT
Project number	Project Name	Business Driver / (NPV)	Priority Score	2015 Total Cost	Execution Timeframe	Business Case	SME		Project Number	Project Name	Business Driver / (NPV)	Priority Score	Total Project Cost	Execution Timeframe	Driver	Business Case	SME
P995	Asset Replacement 2015 - Quality	#N/A	#N/A		2016	Asset Replacements as determined by Reliability Eng and documented in the ARR.	Alister Huffton		P106	Upstream Capacity Buildout (BD/CC)	#N/A	N/A	$0	2018-20	Capacity/Output	Additional BioRx Capacity	#N/A	#N/A		Capacity	$M
P68	#N/A	#N/A	#N/A		2015	Provides increased analytical ability for Mfg Staff. Asset Replacements as determined by Reliability Eng and documented in the ARR	#N/A		74268	P2 Downstream Processing Expansion	QSP	N/A	$193,093,673	2014-17	P2	Enables new product launch and concurrent manufacturing capability	Christian Kaempfen	Strategic		Compliance	$M
74413	#N/A	#N/A	#N/A		2015	Implement MES enhancements per new user requirements to simplify business process and reduce system complexity.	#N/A		74277	P2 DPE Start-up	QSP	N/A	$51,497,000	2016-17	P2	P2 start up phase	Alister Hufton	Strategic		Efficiency	$M
76643	Optimize Column Movement Device	RTO	2.4		2014-2015	Ongoing; Create safe way to move columns throughout mfg.	John Urban		74432	K6 Project Implementation - Phase 3 (Chillers)	CTT	5.2	$19,300,000	2017-2020	Environmental Steward / Compliance	Chillers Replacement. Eco-Balance	Mel Davis	SHE and K-Directives		Life Cycle Mgmt	$M
P81	#N/A	#N/A	#N/A		2015	Mitigates ongoing performance gaps.	#N/A		74119	Harvest Upgrade (New Centrifuge)	QSP	N/A	$15,479,491	2015-17	Launch / / Protein Reduction	Hermetic centrifuge technology is required for Roche / GNE pipeline products	Christian Kaempfen	Strategic		Other	$M
P69	#N/A	#N/A	#N/A		2015	Asset Replacements as determined by Reliability Eng and documented in the ARR.	#N/A		74373	WFI Generation and Storage System / CUB Expansion	QSP	5.1	$13,800,941	2014-16	Risk to Production / / Shutdown Avoidance	Reduces risk to 3.0 rpw operations by increasing wifi capacity	Alister Hufton	Strategic		Safety	$M
P40	#N/A	#N/A	#N/A		2015	Replaces existing tank level measurement and increases ability to properly mfg RFT through increased accuracy.	#N/A		74382	Sci & Eng Lab Mods and Equipment	QSP	5.1	$14,009,740	2015-16	CM Continuum	Transfers of new molecules from development (PIII) to commercial manufacturing	Alister Hufton	New Product Intro		Sustainability	$M
P996	#N/A	#N/A	#N/A		2015	Asset Replacements as determined by Reliability Eng and documented in the ARR.	Alister Huffton		74278	K6 Project Implementation - Phase 2 (-20 Freezer Compressors)	CTT	5.2	$10,759,000	2016-19	Environmental Steward / Compliance	Beginning Design for Compressor Replacement. Eco-Balance	Mel Davis	SHE and K-Directives		Utility	$M
P96	#N/A	#N/A	#N/A		2015	Create fence barrier around leased solar panels.	#N/A		P113	Bulk Product Storage -20/-40	#N/A	TBD	$0	2020	Launch	Provides NPI stability sample storage capacity	#N/A	#N/A		New Product Intro	$14M
73383	#N/A	#N/A	#N/A		2014-2015	Ongoing; project to add freezer space for MRA storage.	#N/A		74279	New Media Technology - HTST / Adventitious	RTO	3.8	$9,046,079	2014-17	CAPA Requirements	Fulfills commitment to FDA	Alister Hufton	New Technologies
P997	#N/A	#N/A	#N/A		2015	Asset Replacements as determined by Reliability Eng and documented in the ARR.	Mel Davis		74426	Process VSD and SOV Replacement - 2015	QSP	N/A	$784,356	2015	Asset Replacement	Variable Speed Drives (VSD) and Valves Solenoid Panels (SOV) are obsolete and failing	Alister Hufton	Stay in Business
73366	#N/A	#N/A	#N/A		2014-2015	Ongoing; project streamlines user access groups for increased operator group capability.	#N/A		P97	Process VSD and SOV Replacement - 2016	#N/A	N/A	$0	2016	Asset Replacement	Variable Speed Drives (VSD) and Valves Solenoid Panels (SOV) are obsolete and failing	#N/A	#N/A
P87	#N/A	#N/A	#N/A		2015	Provides Frit Storage rack to provide frit protection and ease of access.	#N/A		P98	Process VSD and SOV Replacement - 2017	#N/A	N/A	$0	2017	Asset Replacement	Variable Speed Drives (VSD) and Valves Solenoid Panels (SOV) are obsolete and failing	#N/A	#N/A
73323	Stainless Steel HMI Replacement	#N/A	#N/A		2016	Ongoing Project	#N/A		P99	Process VSD and SOV Replacement - 2018	#N/A	N/A	$0	2018	Asset Replacement	Variable Speed Drives (VSD) and Valves Solenoid Panels (SOV) are obsolete and failing	#N/A	#N/A
P89	#N/A	#N/A	#N/A		2015	K-18 energy improvement for warehouse HVAC	#N/A		P100	Process VSD and SOV Replacement - 2019	#N/A	N/A	$0	2019	Asset Replacement	Variable Speed Drives (VSD) and Valves Solenoid Panels (SOV) are obsolete and failing	#N/A	#N/A
64777	Biosafety & Laminar Flow Hood	#N/A	#N/A		2017	Asset Replacements as determined by Reliability Eng and documented in the ARR.	#N/A		P111	PCS Functional Specification Remediation Project (CAPA 960297)	#N/A	TBD	$0	2016-18	Compliance	Creates required documentation per GSP	#N/A	#N/A
P94	#N/A	#N/A	#N/A		2014-15	Ongoing; Provides increased analytical ability for Mfg Staff.	#N/A		P114	QC Testing Equipment for Launch Capability and Storage Requirements	#N/A	TBD	$0	2017-20	New Product Intro	Product specific testing and storage equipment for NPI	#N/A	New Product Intro
73387	MCSBACKUP Phase 2 Tape Retrieval	QSP	N/A		2014-15	Ongoing; Provides required ability to backup and restore MCS.	John Urban		P109	Sci&Eng Lab Equipment for NPI and Launch Capability	#N/A	TBD	$0	2017-20	New Product Intro	Product specific scale up equipment for NPI	#N/A	New Product Intro
64786	Cedex System for Sci&Eng Asset Replacement	#N/A	#N/A		2018	Asset Replacements as determined by Reliability Eng and documented in the ARR.	#N/A		P110	PCS Controller Cabinet Retrofit for UL Compliance	#N/A	TBD	$0	2017-19	Asset Replacement	Extends the life cycle of existing cabinets	#N/A	#N/A
P90	#N/A	#N/A	#N/A		2015	K-18 energy improvement for warehouse HVAC	#N/A		74371	Waste Water Recovery System and Odor Treatment	CTT	6.6	$5,500,000	2016-18	Environmental Steward / Compliance	Reduces water consumption by processing industrial waste water for reuse (SHEP 12). Eco-Balance	Mel Davis	SHE and K-Directives
				$0					P123	Vessel 1020 Asset Replacement	#N/A	N/A	$0	2015-16	Asset Replacement	Adds operational efficiency.	#N/A	#N/A
			Column1	Column2					74449	TDS Remediation 2016	#N/A	#N/A	$0	2016-17	Environmental Steward / Compliance	Meets local regulation/ code to meet waste / water discharge requirements	#N/A	#N/A
			QSP	$ 0					74418	QC Lab Reconfiguration & Equipment	QSP	4.4	$3,789,146	2015-16	PCR / P2 / CM Continuum	Provides capability to perform QC test assays required to support execution of P2 Processing Expansion	Mel Davis	Tech Transfers
			CTT	$ 0					74386	4040 Avenida Conference Center	#N/A	#N/A	$0	2014-15	P2	Continues holding larger events. Existing facility will be used for the Purification Suite (P2) project	#N/A	#N/A
			RTO	$ 0					73377	Upstream Capacity Buildout (PI/CD)	#N/A	#N/A	$0	2014-15	Capacity/Output	Additional BioRx Capacity	#N/A	#N/A
			TBD	$ 0					P107	Phosphoric Acid Remediation	#N/A	TBD	$0	2018-20	Environmental Steward / Compliance	Roche Eco-Balance tracks and requires phosphorous reduction	#N/A	#N/A
			TOTAL	$ 0					P108	PCS Remediation for EBR Review by Exception	#N/A	TBD	$0	2017-18	Efficiency	Creates automated work flow for review of batch report	#N/A	#N/A
				$0					P120	Etro Tech Transfer Start-Up	#N/A	TBD	$0	2016-18	New Product Intro	Etrolizumab Tech Transfer Start-Up	#N/A	New Product Intro
									74455	3rd HCCF Vessel	QSP	N/A	$3,240,391	2015-16	Launch	Adding flexibility to hold in process and avoid disposal of lots	Christian Kaempfen	Strategic
									74302	Water Pooling Remediation	RTO	2.3	$2,085,021	2014-15	Compliance	Removes water that remains in tank after completion of cleaning/steaming to comply with Global CAPA	Alister Hufton	Stay in Business
									74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	N/A	$2,935,000	2016-17	Asset Replacement	Replaces PLC controllers that are at end of life; support connection of equipment to remove paper batch records	Alister Hufton	Stay in Business
									73356	Supplemental BDU Sampling	CTT	3	$1,836,669	2014-15	Compliance	CAPA 746996. Investigation determined dilution occurs in Actemra SC. Additional controls requested by the EMA. Chugai requires a separate sample	Mel Davis	Stay in Business
									P112	Maintenance Ops Shop Buildout	#N/A	TBD	$0	2016-17	Capacity/Output	Allows increased maintenance capability to meet production demand	#N/A	#N/A
									P116	PCS Process Support Equipment Integration Project Phase 2	#N/A	TBD	$0	2016-17	Efficiency	Creates electronic batch reports and integrates the Process Support Equiment PLCs to the PCS	#N/A	#N/A
									74280	Spare Hastelloy Columns	QSP	2.4	$0	2014-15	Risk to Production	Reduction of risk to 5 day PCO for both Actemra and Rituxan campaigns. 3rd column needs to be packed to support the ProA step	Mel Davis	Stay in Business
									74127	Harvest Modifications Start-up	QSP	TBD	$2,400,000	2016-17	Launch / / Protein Reduction	Harvest Upgrade start up phase	Alister Hufton	Strategic
									74454	Seed Lab (20L Bioreactor)	QSP	N/A	$2,838,356	2015-16	Launch	Creates required 20L Bioreactor capacity to allow concurrent multi-product production.	Christian Kaempfen	Strategic
									P119	Etro Tech Transfer	#N/A	TBD	$0	2016	New Product Intro	Etrolizumab Tech Transfer	Semsi Ensari	New Product Intro

												Executed by
												PTAA	$266,148,910					PROGRAMS		# PROJECTS	TOTAL COST	RESOURCES (2015)
												Site	$86,245,952								(2013-2020)
																		Launch Facility	Launch Facility	2	#REF!	0.0
																		Multiple Product	Multi Product	0	$0k	0.0
																		Reliable Supplier	Reliable	6	#REF!	0.1
																		Agile Response	Agile	3	#REF!	0.0
																		Competitive Cost	Competitive	0	$0k	0.0
												Column1	Column2
												QSP	$ 303,868,093
												CTT	$ 37,395,669
												RTO	$ 11,131,101					PROGRAMS	Programs	2014	2015	2016	2017
												TBD	$ 0
												TOTAL	$ 352,394,862					Launch Facility	Launch Facility	#REF!	-	125,000	2,275,000
																		Multiple Product	Multi Product	-	-	-	-
													$352,394,862					Reliable Supplier	Reliable	#REF!	66,881	25,542	201,901
Column1	2015	Count	Column1	2016	Count													Agile Response	Agile	#REF!	32,021	17,477	-
RTO	$2,720,611	10	RTO	$13,019,729	5													Competitive Cost	Competitive	-	-	-	-
QSP	#VALUE!	36	QSP	#VALUE!	12															#REF!	98,902	168,019	2,476,901
CTT	$2,076,452	8	CTT	$1,547,121	4
	#VALUE!	54		#VALUE!	21

	2015	Count		2016
Capacity	$0	7	Capacity	$0										5 / 12 / 4 / # Projects
Compliance	$0	7	Compliance	$0
Efficiency	$0	11	Efficiency	$0
Life Cycle Mgmt	$0	19	Life Cycle Mgmt	$0
Other	$0	1	Safety	$0
Safety	$0	2	Sustainability	$0
Sustainability	$0	2	Utility	$0
Utility	$0	5										# Projects
	$0	54		$0								10 / 37 / 8

																		Constraint		Current Portfolio	Threshold	Variance
																		Resouce Demand (FTEs)		60.81	39.28	(21.53)
																		Expense ($MM)		$7.6	$3.0	($4.6)
																		Capital Expenditure ($MM)		$134	$114	($20)

									Portfolio By Business Driver

			2015	2016	2017	2018	2019	2020
		RTO	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!
		QSP	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!
		CTT	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!

		Excluding (P2, DBX2)
			2015	2016	2017	2018	2019	2020
		RTO	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!
		QSP	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!
		CTT	#REF!	#REF!	#REF!	#REF!	#REF!	#REF!

	Portfolio By Business Driver (Excl. P2, DBX2)

## Program
Status	(Multiple Items)

Programs	TOTAL MO5	Current Estimate	Total RR Demand Year 2015	Estimate Year 2015	Number of Projects	Sum of 2015
Agile	$29,458,134	$4,981,000	0.32	1,217,000	25	$11,247,482	5%					Programs	TOTAL MO5	Current Estimate	Total RR Demand Year 2015	Estimate Year 2015	Number of Projects
Launch Facility	$348,015,907	$0	79.97	0	14	$65,938,837	63%					Agile	29458134	$4,981,000	0.317133677	1217000	25
Reliable	$141,549,576	$25,629,894	58.69	1,838,894	89	$30,011,285	25%					Launch Facility	348015907	$0	79.97499055	0	14
(blank)	$29,000	$29,000	0.00	29,000	10	29000	0%					Reliable	141549575.8	$25,629,894	58.69131384	1838894	89
Multi Product	$0	$0	1.58	0	8	$0					(blank)	29000	$29,000	0	29000	10
ACCR	$36,469,126	$190,000	10.13	0	12	$3,744,000	7%					Multi Product	0	$0	1.58	0	8
Grand Total	$555,521,743	$30,829,894	150.70	3,084,894	158	$110,970,604

	2015		2016
	Capital	Expense	Capital	Expense
Launch Facility	#REF!	#REF!	#REF!	#REF!
Reliable	#REF!	#REF!	#REF!	#REF!
Agile	#REF!	#REF!	#REF!	#REF!
ACCR	#REF!	#REF!	#REF!	#REF!
Capital					Expense

Capital

## Global_Breakdown
Increase in Global Credit due to : / - New projects. / - Several projects expected to have accruals in 2015 have been rolled-over to 2016.

GLOBAL BUCKET BREAKDOWN BY YEAR
T3 2015

		2015			2016
Number	Project	Capital	Expense	Total	Capital	Expense	Total
73323	Stainless Steel HMI Replacement	#REF!	#REF!	#REF!	$0	$0	$0
73366	MCS (PCS and MES) System Access and Account Management Enhancement	#REF!	#REF!	#REF!	$0	$0	$0
73383	Actemra Freezer Installation	#REF!	#REF!	#REF!	$0	$0	$0
76643	Optimize Column Movement Device	#REF!	#REF!	#REF!	$143,425	$0	$143,425
64882	QC Microbiology Incubators	#REF!	#REF!	#REF!	$0	$0	$0
76642	AV System and Equipment Refresh	#REF!	#REF!	#REF!	$0	$0	$0
64777	Biosafety & Laminar Flow Hood	#REF!	#REF!	#REF!	$0	$0	$0
96069	Warehouse Crown Forklift	#REF!	#REF!	#REF!	$0	$0	$0
64786	Cedex System for Sci&Eng Asset Replacement	#REF!	#REF!	#REF!	$0	$0	$0
73398	MCS Manufacturing Area Wireless Access Point Upgrade - 2015	#REF!	#REF!	#REF!	$215,828	$0	$215,828
73384	Caustic Bath Upgrade	#REF!	#REF!	#REF!	$459	$0	$459
73399	Frit Handling and Storage	#REF!	#REF!	#REF!	$153,215	$0	$153,215
73388	SIMCA Online Real Time Process Monitoring System	#REF!	#REF!	#REF!	$0	$0	$0
73387	MCSBACKUP Phase 2 Tape Retrieval	#REF!	#REF!	#REF!	$0	$0	$0
96096	Fencing Solar Power Panel Area	#REF!	#REF!	#REF!	$0	$0	$0
64843	QC Potency Centrifuges - Asset Replacement	#REF!	#REF!	#REF!	$0	$0	$0
64844	QC Ice Maker Asset Replacement	#REF!	#REF!	#REF!	$0	$0	$0
73392	Automated Cooling of V-2194	#REF!	#REF!	#REF!	$0	$0	$0
64899	Engineering Library TOP Storage Unit	#REF!	#REF!	#REF!	$4,011	$0	$4,011
64901	MCS Peripheral Asset Replacement - 2015	#REF!	#REF!	#REF!	$43,151	$0	$43,151
96118	QC Milli-Q Water System Asset Replacement	#REF!	#REF!	#REF!	$0	$0	$0
64898	Supplemental Terumo Sterile Connecting Device (SCD IIB) for Upstream	#REF!	#REF!	#REF!	$0	$0	$0
64889	QC Microbiology Freezers	#REF!	#REF!	#REF!	$0	$0	$0
96129	Guided Ware Radar V-4045	#REF!	#REF!	#REF!	$0	$0	$0
96130	QC M9 TOC Analyzers	#REF!	#REF!	#REF!	$0	$0	$0
96132	Mezzanine Safety Shower/Eye Wash Station Install	#REF!	#REF!	#REF!	$0	$0	$0
96133	QC Rapid Scan RDI System	#REF!	#REF!	#REF!	$0	$0	$0
96134	QC Liquid Handler	#REF!	#REF!	#REF!	$0	$0	$0
96135	QC Spectrophotmeters	#REF!	#REF!	#REF!	$0	$0	$0
96136	V-3007 Replacement	#REF!	#REF!	#REF!	$0	$0	$0
96137	Security Cameras Improvement on Parking Lot	#REF!	#REF!	#REF!	$200,000	$0	$200,000
96138	Appleton Tank Mover	#REF!	#REF!	#REF!	$0	$0	$0
96139	Storm Water Containment Pond	#REF!	#REF!	#REF!	$0	$0	$0
96140	Lower North Lot Storm Water Mitigation:	#REF!	#REF!	#REF!	$0	$0	$0
96141	Manufacturing Ventilation Drops	#REF!	#REF!	#REF!	$0	$0	$0
96995	Asset Replacement 2015 - Quality	#REF!	#REF!	#REF!	$407,893	$0	$407,893
96994	Asset Replacement 2015 - Manufacturing	#REF!	#REF!	#REF!	$263,008	$5,260	$268,268
96997	Asset Replacement 2015 - Facilities Ops	#REF!	#REF!	#REF!	$31,233	$0	$31,233
96998	Asset Replacement 2015 - BMSO	#REF!	#REF!	#REF!	$0	$0	$0
	Total Current Estimate	#REF!	#REF!	#REF!	$1,462,223	$5,260	$1,467,483

	T0 Budget	$3,412,436	$29,495	$3,441,931	$7,020,749	$0	$7,020,749

	(*) Total Pull-In and and New Projects			#REF!

		2015	2016
	Current Estimates (T3)	#REF!	$1,467k
	T0 Budget	$3,442k	$7,021k

	Asset Replacement	$707k	48%
	Other	$760k	52%

## Constraint_Analysis_2017_(Live)
		Bio Drug Substance - Oceanside					Updated: 6/28/16
		Constraint Analysis
		2016 T3					2017				Delta MO5 - T0

	2016	Project Indicator	Project number	Project Name	SPgM	Program	Tag	Score	Score A,B,C, E	PMO Lead		Avg. Roche Resources			Capital	Expense	Total		Delta Capital	Delta Expense	Delta Total		Project Total
1		Individual Project	74268	P2 Downstream Processing Expansion (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	E	Execute 2		21.21			$33,364,075	$916,060	$34,280,135		#REF!	#REF!	#REF!		$193,915,669
2		Individual Project	74454	Seed Lab (20L Bioreactor) (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	E	Execute		0.02			$438,751	$2,075	$440,826		#REF!	#REF!	#REF!		$2,838,356
3		Individual Project	74453	NPI Pool Tanks (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	E	PTAA		0			$37,505	$0	$37,505		#REF!	#REF!	#REF!		$1,223,000
4		Individual Project	74382	Sci&Eng Lab Mods and Equipment	Jim Neeleman	Launch and Commercial Excellence	P2	7.6	E	Execute 2		1.13			$390,885	$0	$390,885		#REF!	#REF!	#REF!		$14,009,740
5		Individual Project	74119	Harvest Upgrade (New Centrifuge) (NIC)	Zaymar Sedra	Fit for Purpose	P2	60	E	Execute 2		2.30			$7,236,886	$51,254	$7,288,140		#REF!	#REF!	#REF!		$15,479,491
6		Startup	74277	P2 DPE Start-Up	Zaymar Sedra	Fit for Purpose	P2	60	A	Execute		0			$40,280,925	$0	$40,280,925		#REF!	#REF!	#REF!		$51,497,000
7		Startup	74127	Harvest Modifications Start-up	Deidre Dunham	Launch Facility	P2	60	A	Budgeted		1			$2,275,000	$0	$2,275,000		#REF!	#REF!	#REF!		$2,400,000
8		Individual Project	74406	Corrosive Chemical Compliance	Scott Fields	Reliability and Value	E	34	E	Execute		0.11			$83,733	$0	$83,733		#REF!	#REF!	#REF!		$1,910,997
9		Individual Project	74302	Waterpooling Remediation	Jim Neeleman	Reliability and Value	E	23	E	Execute 2		0.83			$50,426	$0	$50,426		#REF!	#REF!	#REF!		$2,085,021
10		Individual Project	74279	New Media Technology - HTST / Adventitious	Scott Fields	Reliability and Value	E	19.2	E	Execute 2		5.15			$1,553,492	$37,670	$1,591,162		#REF!	#REF!	#REF!		$9,046,079
11		Individual Project	74418	QC Lab Reconfiguration & Equipment	Jim Neeleman	Launch and Commercial Excellence	E	15.8	E	Execute 1		0.28			$289,726	$0	$289,726		#REF!	#REF!	#REF!		$3,789,146
12		Individual Project	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Scott Fields	Reliability and Value	E	7.7	R	Execute		0.21			$23,445	$0	$23,445		#REF!	#REF!	#REF!		$470,674
13		Individual Project	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	Jim Neeleman	Reliability and Value	E	0		Execute		0			$654,000	$0	$654,000		#REF!	#REF!	#REF!		$960,000
14		Individual Project	74510	PCS Asset Replacement - 2016	Zaymar Sedra	Fit for Purpose	E	N/A	B	Execute		0.18			$149,000	$0	$149,000		#REF!	#REF!	#REF!		$1,915,058
15		Individual Project	74486	PCS Controller Cabinet Asset Replacement	Melanie Yevilov	Highly Capable Workforce	E	N/A	B	Execute		0.42			$110,000	$0	$110,000		#REF!	#REF!	#REF!		$2,404,000
16		Individual Project	74487	Process VSD and SOV Asset Replacement	Melanie Yevilov	Highly Capable Workforce	E	N/A	R	Execute		0.33			$2,925,031	$18,000	$2,943,031		#REF!	#REF!	#REF!		$6,542,828
17		Individual Project	74526	Utility and Process Safety System	Scott Fields	Reliability and Value	E	13.3	C	FXNL LT Appr		0			$57,596	$0	$57,596		#REF!	#REF!	#REF!		$1,940,000
18		Individual Project	74511	QR018 Compliance Steam and Condensate Containment	Jim Neeleman	Reliability and Value	E	13.3		Execute		1.82			$3,074,500	$0	$3,074,500		#REF!	#REF!	#REF!		$5,017,800
19		Global	96174	Fall Protection Phase II	TBD	TBD	E	3.6		CA Routing		0			$5,000	$0	$5,000		#REF!	#REF!	#REF!		$135,000
20		Individual Project	74435	Hastelloy Chromatography Column (160cm)	Zaymar Sedra	Fit for Purpose	E	17.1		FXNL LT Appr		2.39			$1,149,000	$0	$1,149,000		#REF!	#REF!	#REF!		$1,549,000
21		Individual Project	74546	Mezzanine Safety Shower/Eye Wash Station Install	Melanie Yevilov	Highly Capable Workforce	E	2.9		IMPACT Appr		0			$436,000	$0	$436,000		#REF!	#REF!	#REF!		$886,000
22		Expense	97003	MFG Systems Integration Improvement Phase 1 - 2015	Deidre Dunham	Reliability and Value	Ex	15.3	A	Execute 1		0.94			$0	$135,000	$135,000		#REF!	#REF!	#REF!		$427,227
23		Expense	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Deidre Dunham	Reliability and Value	Ex	3.4	A	Execute 1		0.68			$0	$574,661	$574,661		#REF!	#REF!	#REF!		$1,510,946
24		Expense	N/A	CRB, travel, ofc supplies, others	Scott Fields	Reliability and Value	Ex	N/A	E			0			$0	$317,000	$317,000		#REF!	#REF!	#REF!		$317,000
25		Expense	TBD	PAIR	Scott Fields	Reliability and Value	Ex	0		Execute		0			$0	$4,788,348	$4,788,348		#REF!	#REF!	#REF!		$7,890,698
26				Everything above this line is currently in Execution
27		Individual Project	74491	Etro Tech Transfer (NIC)	Deidre Dunham	Launch and Commercial Excellence	P2	60	A	Hold		28.30			$9,065,569	$3,771,061	$12,836,630		#REF!	#REF!	#REF!		$18,122,360
28		Individual Project	96124	Perjeta Tech Transfer	#REF!	#REF!	P2	60		Idea		0			$8,793,594	$147,070	$8,940,664		#REF!	#REF!	#REF!		$89,599,744
57		Individual	96210	P2 User Furnished Equipment Procurement	TBD	TBD	BL	9		FXNL LT Appr		0			$950,000	$150,000	$1,100,000		#REF!	#REF!	#REF!		$2,200,000
35		Global	96220	400L Mixing Vessel	Jim Neeleman	Launch and Commercial Excellence	BL	17.3		FXNL LT Appr		0			$50,000	$12,000	$62,000		#REF!	#REF!	#REF!		$402,000
46		Global	96218	Column Maintenance Platform Installation	Melanie Yevilov	Highly Capable Workforce	BL	13.3		FXNL LT Appr		0			$100,000	$0	$100,000		#REF!	#REF!	#REF!		$175,000
29		Individual Project	96177	Efficiency Projects	Scott Fields	Reliability and Value	BL	60		Placeholder		1.00			$3,000,000	$0	$3,000,000		#REF!	#REF!	#REF!		$15,000,000
30		Expense	97072	Tangential Flow Filtration Cassettes Management	Zaymar Sedra	Reliability and Value	BL	40		FXNL LT Appr		0			$0	$1,030,000	$1,030,000		#REF!	#REF!	#REF!		$1,030,000
31		Individual	96221	Corrosive Chemical Compliance - CUB and Warehouse	Scott Fields	Reliability and Value	BL	34		FXNL LT Appr		0.38			$2,900,000	$0	$2,900,000		#REF!	#REF!	#REF!		$2,920,000
32		Individual	96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting	Scott Fields	Reliability and Value	BL	20.0		FXNL LT Appr		0.75			$500,000	$500,000	$1,000,000		#REF!	#REF!	#REF!		$1,000,000
33		Individual	96222	Pressure Safety Program - Mechanical	Melanie Yevilov	Highly Capable Workforce	BL	18.8		FXNL LT Appr		1.50			$2,000,000	$0	$2,000,000		#REF!	#REF!	#REF!		$2,000,000
34		Individual	96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000	Scott Fields	Reliability and Value	BL	17.8		FXNL LT Appr		1.75			$500,000	$50,000	$550,000		#REF!	#REF!	#REF!		$550,000
36		Individual Project	74278	K6 Program - Project 3 - Replace Cold Room Compressors	Melanie Yevilov	Highly Capable Workforce	BL	16.5	A	FXNL LT Appr		0.36			$528,000	$75,000	$603,000		#REF!	#REF!	#REF!		$10,759,000
37		Expense	97054	HVAC Retro Commissioning	Deidre Dunham	Reliability and Value	BL	15.6		FXNL LT Appr		0.10			$0	$113,000	$113,000		#REF!	#REF!	#REF!		$157,000
38		Global	96133	QC Rapid Scan RDI System	Jim Neeleman	Launch and Commercial Excellence	BL	15.3	C	Hold		0.75			$210,000	$0	$210,000		#REF!	#REF!	#REF!		$210,000
39		Global	96181	Fall Protection Phase III	Melanie Yevilov	Highly Capable Workforce	BL	15.1		FXNL LT Appr		0.06			$130,000	$20,000	$150,000		#REF!	#REF!	#REF!		$150,000
40		Global	96209	Harvest Depth Filter Installation Tool	Melanie Yevilov	Highly Capable Workforce	BL	15.1		FXNL LT Appr		0.27			$100,000	$0	$100,000		#REF!	#REF!	#REF!		$100,000
41		Individual	96219	Harvest Filter Housing A Removal/Installation Improvements	Melanie Yevilov	Highly Capable Workforce	BL	15.1		FXNL LT Appr		0.19			$400,000	$100,000	$500,000		#REF!	#REF!	#REF!		$500,000
42		Global	96183	Site Signage Upgrade	TBD	TBD	BL	13.7		Idea		0.25			$175,000	$25,000	$200,000		#REF!	#REF!	#REF!		$200,000
44		Expense	97038	PCS Functional Specification Development Project (CAPA 960297)	Deidre Dunham	Reliability and Value	BL	13.5	B	FXNL LT Appr		10			$0	$500,000	$500,000		#REF!	#REF!	#REF!		$8,000,000
45		Individual	96191	Utility and Process Safety System Phase 2	TBD	TBD	BL	13.3		Idea		0			$2,000,000	$0	$2,000,000		#REF!	#REF!	#REF!		$2,000,000
43				Expense Line - $9.4 excluding Etro
47		Expense	97071	Pipe Labelling Improvement	Melanie Yevilov	Highly Capable Workforce	BL	13.3		FXNL LT Appr		0.25			$0	$2,100,000	$2,100,000		#REF!	#REF!	#REF!		$2,100,000
48		Expense	97039	PCS Remediation for EBR Review by Exception - PI	Zaymar Sedra	Fit for Purpose	BL	13	B	Idea		0			$0	$250,000	$250,000		#REF!	#REF!	#REF!		$5,875,000
49		Expense	97037	Recipe Reconfiguration Alignment for Operating Systems	Zaymar Sedra	Fit for Purpose	BL	13		FXNL LT Appr		0			$0	$250,000	$250,000		#REF!	#REF!	#REF!		$3,500,000
50		Global	96217	Pallet Wrapper	#REF!	#REF!	BL	11.6		FXNL LT Appr		0.06			$50,000	$0	$50,000		#REF!	#REF!	#REF!		$50,000
51				Capital Line - $24.2
52		Expense	97070	Pressure Safety Program Automation - PI	Melanie Yevilov	Highly Capable Workforce	BL	11.3		FXNL LT Appr		1.50			$0	$300,000	$300,000		#REF!	#REF!	#REF!		$300,000
54		Individual Project	74409	K6 Program - Project 1 - Replace DX HVAC Units	Jim Neeleman	Launch and Commercial Excellence	BL	11.3	A	Execute		0.06			$310,000	$22,000	$332,000		#REF!	#REF!	#REF!		$332,000
55		Individual	96213	Replacement of Obsolete Benchtop Horiba pH Meter	Zaymar Sedra	Fit for Purpose	BL	10.4		FXNL LT Appr		1.50			$1,000,000	$200,000	$1,200,000		#REF!	#REF!	#REF!		$1,200,000
56		Global	96139	Trash Bin Storm Water Mitigation	Deidre Dunham	Exceptional Culture	BL	9.6		FXNL LT Appr		0.06			$200,000	$0	$200,000		#REF!	#REF!	#REF!		$200,000
58		Expense	97045	Site Exterior Lighting Upgrade - Title 24	Zaymar Sedra	Fit for Purpose	BL	2.4	C	FXNL LT Appr		0.04			$0	$100,000	$100,000		#REF!	#REF!	#REF!		$200,000
59		Individual Project	74513	Electric Vehicle Charging Stations	Deidre Dunham	Exceptional Culture	BL	2.2		Hold		0			$712,000	$18,000	$730,000		#REF!	#REF!	#REF!		$730,000
60		Global	96991	Asset Replacement 2017 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$250,000	$2,500	$252,500		#REF!	#REF!	#REF!		$252,500
61		Global	96995	Asset Replacement 2017 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$361,465	$0	$361,465		#REF!	#REF!	#REF!		$361,465
62		Global	96994	Asset Replacement 2017 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$78,889	$0	$78,889		#REF!	#REF!	#REF!		$78,889
63		Global	96992	Asset Replacement 2017 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$583,915	$5,000	$588,915		#REF!	#REF!	#REF!		$588,915
64		Global	96993	Asset Replacement 2017 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$182,500	$0	$182,500		#REF!	#REF!	#REF!		$182,500
65		Global	96997	Asset Replacement 2017 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$28,025	$0	$28,025		#REF!	#REF!	#REF!		$28,025
66		Global	96998	Asset Replacement 2017 - Sci&Eng (cc1198)	Jim Neeleman	Reliable	BL	N/A	R	FXNL LT Appr		0			$100,951	$0	$100,951		#REF!	#REF!	#REF!		$100,951
67		Global	96991	Asset Replacement 2017 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$250,000	$2,500	$252,500		#REF!	#REF!	#REF!		$252,500
68		Global	96995	Asset Replacement 2017 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$361,465	$0	$361,465		#REF!	#REF!	#REF!		$361,465
69		Global	96994	Asset Replacement 2017 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$78,889	$0	$78,889		#REF!	#REF!	#REF!		$78,889
70		Global	96992	Asset Replacement 2017 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$583,915	$5,000	$588,915		#REF!	#REF!	#REF!		$588,915
71		Global	96993	Asset Replacement 2017 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$182,500	$0	$182,500		#REF!	#REF!	#REF!		$182,500
72		Global	96997	Asset Replacement 2017 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	BL	N/A	R	FXNL LT Appr		0			$28,025	$0	$28,025		#REF!	#REF!	#REF!		$28,025
73		Global	96998	Asset Replacement 2017 - Sci&Eng (cc1198)	Jim Neeleman	Reliable	BL	N/A	R	FXNL LT Appr		0			$100,951	$0	$100,951		#REF!	#REF!	#REF!		$100,951
74		Global	96136	V-3007 Replacement	Zaymar Sedra	Fit for Purpose	BL	N/A	B	FXNL LT Appr		0.75			$120,000	$0	$120,000		#REF!	#REF!	#REF!		$240,000
75		Individual Project	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	Jim Neeleman	Launch and Commercial Excellence	BL	N/A		FXNL LT Appr		0			$0	$200,000	$200,000		#REF!	#REF!	#REF!		$2,935,000
76		Global	96069	Warehouse Crown Forklift Asset Replacement	Scott Fields	Reliability and Value	BL	N/A		Hold		0			$144,407	$0	$144,407		#REF!	#REF!	#REF!		$144,407
77		Expense	97009	MES Asset Replacement - 2017	#REF!	#REF!	BL	N/A		Idea		0			$0	$400,000	$400,000		#REF!	#REF!	#REF!		$975,000
78		Expense	97012	Site Data Historian Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$0	$366,000	$366,000		#REF!	#REF!	#REF!		$366,000
79		Expense	97015	MCS Backup System Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	BL	N/A		FXNL LT Appr		0			$0	$390,000	$390,000		#REF!	#REF!	#REF!		$390,000
80		Expense	97031	MCS Data Analytics Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	BL	N/A		Idea		0			$0	$325,000	$325,000		#REF!	#REF!	#REF!		$325,000
82		Global	96164	Hazardous Materials Containers Washing Station	Jim Neeleman	Launch and Commercial Excellence	BL	0		Hold		0			$30,000	$0	$30,000		#REF!	#REF!	#REF!		$30,000
84		Global	96163	MFG Depth Filter Housing	Deidre Dunham	Exceptional Culture	BL	0		Idea		0			$300,000	$100,000	$400,000		#REF!	#REF!	#REF!		$400,000
85		Individual	96180	TMAC Waste System Improvements	TBD	TBD	BL	0		Hold		0			$1,500,000	$0	$1,500,000		#REF!	#REF!	#REF!		$1,500,000
86		Global	96201	Storm Water BMP for Upper Lot	TBD	TBD	BL	0		Idea		0			$200,000	$0	$200,000		#REF!	#REF!	#REF!		$200,000
87				Contigency					#REF!	#REF!	#REF!
88				Site Judgedown					#REF!	#REF!	#REF!
89				TOTAL					88.9			$133,725,032	$18,369,199	$152,094,231		#REF!	#REF!	#REF!		$510,414,728
90				OCN TOTAL CAPACITY					94.0

				2017				Delta MO5 - T0
				Resource			Capital	Expense	Total		Capital	Expense	Delta Total		Lifetime Total
				P2/CMC Projects			P2					54.0			$101,883,190	$4,887,520	$106,770,710		#REF!	#REF!	#REF!		$389,085,360
				Non P2/CMC Proposed in execution			E					11.7			$10,560,949	$55,670	$10,616,619		#REF!	#REF!	#REF!		$38,651,604
				Expense Only Projects in Execution			Ex					1.6			$0	$5,815,009	$5,815,009		#REF!	#REF!	#REF!		$10,145,871
				Total Below the Line			BL					21.6			$21,280,893	$7,611,000	$28,891,893					$69,754,893
				Total					88.9			$133,725,032	$18,369,199	$152,094,231					$507,637,728
				Non P2/CMC Endorsed Projects
				Below Line (including Expense Only)
				Contingency					#REF!	#REF!	#REF!
				Site Judgedown					#REF!	#REF!	#REF!
				TOTAL					177.7			$267,450,063	$36,738,399	$304,188,462		#REF!	#REF!	#REF!		$1,015,275,456
				Deferred or Need Scope Defined					14					$30,992,893
				Deferred					1					$0				$0	$4,912,650

				#REF!	#REF!

		Assumptions:
		Site Capital judge down is based on costs below 2016 Execution Targets.
		Total Expense budget is $9.9M
		Resource Capacity: Historical 50 FTE + 10 FTE TT, 2015 20 hired for P2, 2016 14 hired for TT = 94 FTE.
		Resource Demand to support network projects is 10 FTE
		OLT Decision: Focusing on projects already in execution, Tech Transfer and shutdown critical.
		Site judgedown applies in MO5 for all projects below the line as we did in T0.

				Target < $25M

				Total (*)	Incl. 10% Adjustment		Total	Incl. 10% Adjustment
				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Expense	#REF!
				Expense	#REF!	YEAR 2015 / TOTAL BUDGET

				Capital (Line Item + Global)	#REF!	#REF!		#REF!

				Expense	#REF!

				Expense (All)	#REF!	-	This total includes Above the line Auto. Expense Projects

				Total (*)	Incl. Adjustment		Total	Incl. Adjustment
				Capital	#REF!	#REF!		#REF!	#REF!

				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Expense	#REF!
				YEAR 2016 / TOTAL BUDGET

				Capital (Line Item + Global)	#REF!	#REF!		#REF!

				Expense (All)	#REF!	- / This total includes Above the line Auto. Expense Projects

## Constraint_Analysis_MO5
		Bio Drug Substance - Oceanside					Locked: 5/25/16
		Constraint Analysis
		Current Estimate - 5/25/2016					T0				MO5				2017				Delta MO5 - T0

	2016	Project Indicator	Project number	Project Name	SPgM	Program	Score	Score A,B,C, E	PMO Lead		Avg. Roche Resources	Capital	Expense	Total		Capital	Expense	Total		Capital	Expense	Total		Delta Capital	Delta Expense	Delta Total		Project Total
1	1	Individual Project	74268	P2 Downstream Processing Expansion (NIC)	Zaymar Sedra	Fit for Purpose	60	E	Execute 2		21.21	$104,650,502	$825,644	$105,476,146		$92,403,605	$1,248,192	$93,651,797		$33,364,075	$916,060	$34,280,135		-$12,246,897	$422,548	-$11,824,349		$194,047,008
2	1	Individual Project	74455	3rd HCCF Vessel (NIC)	Zaymar Sedra	Fit for Purpose	60	E	Execute		0.07	$2,328,891	$27,591	$2,356,482		$2,027,438	$43,784	$2,071,222		$113,412	$464	$113,876		-$301,453	$16,193	-$285,260		$3,721,000
3	1	Individual Project	74454	Seed Lab (20L Bioreactor) (NIC)	Zaymar Sedra	Fit for Purpose	60	E	Execute		0.02	$938,961	$10,802	$949,763		$954,867	$141,531	$1,096,398		$352,550	$2,075	$354,625		$15,906	$130,729	$146,635		$2,838,360
4	1	Individual Project	74453	NPI Pool Tanks (NIC)	Zaymar Sedra	Fit for Purpose	60	E	PTAA		0	$452,919	$10,802	$463,721		$684,545	$2,883	$687,428		$3,878	$0	$3,878		$231,626	-$7,919	$223,707		$1,272,546
5	1	Individual Project	74382	Sci&Eng Lab Mods and Equipment	Jim Neeleman	Launch and Commercial Excellence	7.6	E	Execute 2		1.13	$7,008,000	$393,000	$7,401,000		$6,232,184	$458,027	$6,690,211		$488,779	$0	$488,779		-$775,816	$65,027	-$710,789		$13,187,622
6	1	Individual Project	74119	Harvest Upgrade (New Centrifuge) (NIC)	Zaymar Sedra	Fit for Purpose	60	E	Execute 2		2.30	$7,233,192	$28,727	$7,261,919		$7,001,377	$37,498	$7,038,875		$4,833,864	$51,254	$4,885,118		-$231,815	$8,771	-$223,044		$15,479,491
7	1	Startup	74277	P2 DPE Start-Up	Zaymar Sedra	Fit for Purpose	60	A	Execute		0	$8,000,000	$0	$8,000,000		$4,461,207	$0	$4,461,207		$40,280,925	$0	$40,280,925		-$3,538,793	$0	-$3,538,793		$51,497,000
8	1	Expense	98026	Launch Capability Program (LCP)	Jim Neeleman	Launch and Commercial Excellence	0	D	Execute		12.00	$0	$800,000	$800,000		$0	$800,000	$800,000		$0	$0	$0		$0	$0	$0		$800,000
9	1	Individual Project	74426	Process VSD and SOV Replacement - 2015	Scott Fields	Reliability and Value	N/A	E	Execute		0.30	$489,000	$0	$489,000		$495,036	$0	$495,036		$0	$0	$0		$6,036	$0	$6,036		$689,657
10	1	Global	64901	MCS Peripheral Asset Replacement - 2015	Scott Fields	Reliability and Value	0	E	Execute		0	$100,000	$0	$100,000		$99,984	$0	$99,984		$0	$0	$0		-$16	$0	-$16		$323,201
11	1	Individual Project	74368	Dev/Val Automation Capacity Expansion	Jim Neeleman	Launch and Commercial Excellence	N/A	E	Execute		0	$10,000	$0	$10,000		$10,000	$0	$10,000		$0	$0	$0		$0	$0	$0		$625,000
12	1	Global	73387	MCSBACKUP Phase 2 Tape Retrieval	Scott Fields	Reliability and Value	N/A	E	Execute		0.5	$5,000	$0	$5,000		$5,000	$0	$5,000		$0	$0	$0		$0	$0	$0		$50,791
13	1	Individual Project	74406	Corrosive Chemical Compliance	Scott Fields	Reliability and Value	34	E	Execute		0.11	$1,812,000	$0	$1,812,000		$1,596,303	$0	$1,596,303		$83,733	$0	$83,733		-$215,697	$0	-$215,697		$1,783,061
14	1	Individual Project	73367	FS & DS Automation Integration	Zaymar Sedra	Fit for Purpose	24.4	E	Execute 2		0.31	$10,000	$0	$10,000		$26,719	$0	$26,719		$0	$0	$0		$16,719	$0	$16,719		$749,690
15	1	Individual Project	74302	Waterpooling Remediation	Scott Fields	Reliability and Value	23	E	Execute 2		0.83	$435,000	$0	$435,000		$369,680	$0	$369,680		$51,636	$0	$51,636		-$65,320	$0	-$65,320		$2,086,231
16	1	Individual Project	73356	Supplemental BDU Sampling	Jim Neeleman	Launch and Commercial Excellence	19.5	E	Execute 2		0	$200,000	$0	$200,000		$157,774	$0	$157,774		$0	$0	$0		-$42,226	$0	-$42,226		$1,836,669
17	1	Individual Project	74279	New Media Technology - HTST / Adventitious	Scott Fields	Reliability and Value	19.2	E	Execute 2		5.15	$5,444,000	$0	$5,444,000		$4,810,886	$1,768	$4,812,654		$1,602,703	$0	$1,602,703		-$633,114	$1,768	-$631,346		$8,923,144
18	1	Global	76643	Optimize Column Movement Device	Melanie Yevilov	Highly Capable Workforce	18.6	E	Execute		0.02	$128,000	$0	$128,000		$143,425	$0	$143,425		$0	$0	$0		$15,425	$0	$15,425		$269,899
19		Individual Project	74524	Bioburden 2606 IPA Exhaust Improvement	Scott Fields	Reliability and Value	18		Execute		0	$12,000	$0	$12,000		$0	$8,519	$8,519		$0	$550,000	$550,000		-$12,000	$8,519	-$3,481		$558,519
20	1	Global	73384	Caustic Bath Upgrade	Melanie Yevilov	Highly Capable Workforce	16.5	E	Execute		0	$9,000	$0	$9,000		$11,541	$459	$12,000		$0	$0	$0		$2,541	$459	$3,000		$13,421
21	1	Individual Project	74490	Hyfish Material Screening Operation	Scott Fields	Reliability and Value	16.3	A	Execute		0.05	$460,000	$0	$460,000		$422,881	$0	$422,881		$0	$0	$0		-$37,119	$0	-$37,119		$1,282,919
22	1	Individual Project	74418	QC Lab Reconfiguration & Equipment	Jim Neeleman	Launch and Commercial Excellence	15.8	E	Execute 1		0.28	$3,675,000	$0	$3,675,000		$1,918,122	$113,000	$2,031,122		$1,568,006	$0	$1,568,006		-$1,756,878	$113,000	-$1,643,878		$3,823,874		03/24/16 Capital and expense portions changed to align with better cash flow forecasting.
23	1	Global	73399	Frit Handling and Storage	Melanie Yevilov	Highly Capable Workforce	11.3	A	Execute		0.11	$108,000	$15,000	$123,000		$191,950	$15,000	$206,950		$0	$0	$0		$83,950	$0	$83,950		$225,944
24	1	Individual Project	74373	WFI Generation and Storage System / CUB Expansion	Zaymar Sedra	Fit for Purpose	11.1	E	Execute 2		3.08	$5,342,000	$12,500	$5,354,500		$5,523,133	$13,075	$5,536,208		$0	$0	$0		$181,133	$575	$181,708		$13,800,942
25	1	Individual Project	74416	Asphyxiant Gas Remediation	Melanie Yevilov	Highly Capable Workforce	11.1	A	Execute 1		0.06	$99,000	$0	$99,000		$142,115	$0	$142,115		$400,000	$0	$400,000		$43,115	$0	$43,115		$578,774
26	1	Individual Project	74404	Mezzanine Lift Media Prep: Phase 1B	Melanie Yevilov	Highly Capable Workforce	10.7	E	Execute		0.01	$330,000	$0	$330,000		$201,044	-$431	$200,613		$0	$0	$0		-$128,956	-$431	-$129,387		$483,391
27	1	Global	73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Scott Fields	Reliability and Value	10.5	R	Execute		0	$95,000	$0	$95,000		$204,700	$0	$204,700		$0	$0	$0		$109,700	$0	$109,700		$218,047
28		Global	73388	SIMCA Online Real Time Process Monitoring System	Jim Neeleman	Launch and Commercial Excellence	7.8		Execute		0.00	$58,000	$0	$58,000		$0	$0	$0		$0	$0	$0		-$58,000	$0	-$58,000		$262,943
29	1	Individual Project	74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Scott Fields	Reliability and Value	7.7	R	Execute		0.21	$350,000	$0	$350,000		$198,196	$0	$198,196		$22,991	$0	$22,991		-$151,804	$0	-$151,804		$463,843
30	1	Individual Project	74392	Water Reclaim System	Scott Fields	Reliability and Value	6.1	E	Execute		0.47	$676,000	$0	$676,000		$162,102	$0	$162,102		$0	$0	$0		-$513,898	$0	-$513,898		$341,187		03/22/16 Project rescoped and reduced by $332k per MD.
31	1	Global	73409	Solar Power Enabling Project	Melanie Yevilov	Highly Capable Workforce	5.1	R	Execute		0.02	$271,000	$0	$271,000		$305,902	$0	$305,902		$0	$0	$0		$34,902	$0	$34,902		$438,125
32	1	Individual Project	74489	4040 Avenida Conference Center Acquisition	Deidre Dunham	Exceptional Culture	3.1	A	Execute		0	$688,000	$0	$688,000		$686,850	$0	$686,850		$0	$0	$0		-$1,150	$0	-$1,150		$3,387,850
33	1	Global	64914	QC M9 TOC Analyzers	Jim Neeleman	Launch and Commercial Excellence	N/A		Execute		0	$106,000	$0	$106,000		$18,930	$0	$18,930		$0	$0	$0		-$87,070	$0	-$87,070		$106,000
34	1	Global	64923	QC Met-One Air Sampler Replacement 2015	Jim Neeleman	Launch and Commercial Excellence	N/A		Execute		0	$60,000	$0	$60,000		$15,885	$0	$15,885		$0	$0	$0		-$44,115	$0	-$44,115		$60,000
35	1	Global	64927	QC Gel Imager Replacement 2015	Jim Neeleman	Launch and Commercial Excellence	N/A		Execute		0	$15,000	$0	$15,000		$2,660	$0	$2,660		$0	$0	$0		-$12,340	$0	-$12,340		$15,000
36	1	Global	65009	Drum Mover/Raw Material Tenderizer	Melanie Yevilov	Highly Capable Workforce	0		Execute		0	$0	$25,000	$25,000		$30,000	$4,000	$34,000		$0	$0	$0		$30,000	-$21,000	$9,000		$34,000		01/12/16 Project moved above the line per IMPACT discussion.
37	1	Global	65005	Analytical Scale	Scott Fields	Reliability and Value	0		Execute		0	$0	$0	$0		$24,238	$0	$24,238		$0	$0	$0		$24,238	$0	$24,238		$24,238		01/12/16 Project moved above the line per IMPACT discussion. 03/17/16 Funded by Material Ops AR bucket, as per AW.
38		Global	65015	Lower Solid Collector for Centrifuge	Scott Fields	Reliability and Value	0		Execute		0	$0	$0	$0		$245,000	$0	$245,000		$0	$0	$0		$245,000	$0	$245,000		$245,000		02/11/16 Project added and moved above the line.
39	1	Global	65018	Spare Bowl for Hermetic Centrifuge	Zaymar Sedra	Fit for Purpose	0		Execute		0	$0	$0	$0		$320,000	$0	$320,000		$0	$0	$0		$320,000	$0	$320,000		$320,000		02/12/16 Project added and moved above the line per IMPACT discussion.
40		Global	65021	Hazardous Material Response Cart	Melanie Yevilov	Highly Capable Workforce	3.9		Execute		0	$0	$0	$0		$19,424	$0	$19,424		$0	$0	$0		$19,424	$0	$19,424		$19,424		02/22/16 Project moved above the line.
41		Global	65020	QC Auto-Pipettor for Potency Assay	Scott Fields	Reliability and Value	0		Execute		0	$0	$0	$0		$27,987	$0	$27,987		$0	$0	$0		$27,987	$0	$27,987		$27,987		03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio. Funded by QC AR Bucket.
42		Global	65023	QC Plate Washer for Potency Assay	Jim Neeleman	Launch and Commercial Excellence	0		Execute		0	$0	$0	$0		$56,795	$0	$56,795		$0	$0	$0		$56,795	$0	$56,795		$56,795		03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio. Funded by QC AR Bucket.
43		Global	65024	Sci&Eng Lab Incubator and Freezer Asset Replacement	Jim Neeleman	Launch and Commercial Excellence	0		Execute		0	$0	$0	$0		$140,000	$0	$140,000		$488,779	$0	$488,779		$140,000	$0	$140,000		$628,779		03/05/16 Project moved into Execution. 02/22/16 Project added to portfolio. 03/17/16 Funded by Engineering AR bucket, as per AW.
44		Global	65037	Analytical Scales (CAPA 1150248)	Scott Fields	Reliability and Value	0		Execute		0	$0	$0	$0		$23,914	$0	$23,914		$0	$0	$0		$23,914	$0	$23,914		$23,914		03/16/16 Project added to portfolio and above the line. 03/22/16 Project moved above Execution line.
45		Global	65040	Sci&Eng Cryofreezer	Jim Neeleman	Launch and Commercial Excellence	0		Execute		0	$0	$0	$0		$20,185	$0	$20,185		$0	$0	$0		$20,185	$0	$20,185		$20,185		03/17/16 Project added to portfolio and above the line. Funded by Engineering AR Bucket per AW.
46		Global	65048	Process Maintenance Boroscope	Scott Fields	Reliability and Value	0	R	Execute		0	$0	$0	$0		$37,000	$0	$37,000		$0	$0	$0		$37,000	$0	$37,000		$37,000		03/25/16 Project added to portfolio. 03/28/16 Project funded by Engineering AR bucket, per AW. 03/31/16 Project moved above the line.
47		Global	65044	Additional MCS Backup Storage	Scott Fields	Reliability and Value	0		Execute		0	$0	$0	$0		$62,000	$0	$62,000		$0	$0	$0		$62,000	$0	$62,000		$62,000		03/15/16 Project added to portfolio and moved above the line. 03/17/16 Funded by Engineering AR bucket, per AW. 04/05/16 15K moved from Capital to Expense.
48		Individual Project	74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	Scott Fields	Reliability and Value	0		FXNL LT Appr		0	$0	$0	$0		$306,000	$0	$306,000		$654,000	$0	$654,000		$306,000	$0	$306,000		$960,000		03/15/16 Project added to portfolio and moved above the line.
49	1	Expense	97053	Pressure Safety Program - PI Phase	TBD	TBD	8.8		Idea		0	$0	$100,000	$100,000		$0	$100,000	$100,000		$0	$0	$0		$0	$0	$0		$100,000		03/15/16 Project moved above the line.
50		Expense	97059	B311 & B321 Gowning Room Modifications	Scott Fields	Reliability and Value	0		Execute		0.05	$0	$0	$0		$0	$107,000	$107,000		$0	$0	$0		$0	$107,000	$107,000		$107,000		01/13/16 Project added to portfolio. PO's approved by AW.
51	1	Expense	TBD	Piping Corrosion	Scott Fields	Reliability and Value	0		Execute		TBD	$0	$3,100,000	$3,100,000		$0	$3,091,211	$3,091,211		$0	$0	$0		$0	-$8,789	-$8,789		$3,091,211
52	1	Expense	97058	Parking Pavement Repair	Scott Fields	Reliability and Value	0	A	Execute		0.00	$0	$80,000	$80,000		$0	$245,040	$245,040		$0	$0	$0		$0	$165,040	$165,040		$245,040
53	1	Expense	97007	Automation System Lifecycle MCS Upgrade - PI	Scott Fields	Reliability and Value	27.6		Execute		1.79	$0	$270,000	$270,000		$0	$295,169	$295,169		$0	$0	$0		$0	$25,169	$25,169		$295,169
54	1	Expense	97003	MFG Systems Integration Improvement Phase 1 - 2015	Scott Fields	Reliability and Value	15.3	A	Execute 1		0.94	$0	$443,000	$443,000		$0	$443,000	$443,000		$0	$0	$0		$0	$0	$0		$443,000
55	1	Expense	97048	Arc Flash Prevention	Melanie Yevilov	Highly Capable Workforce	5.9		Execute		0	$0	$318,000	$318,000		$0	$319,456	$319,456		$0	$0	$0		$0	$1,456	$1,456		$319,456
56	1	Expense	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Scott Fields	Reliability and Value	3.4	A	Execute 1		0.68	$0	$1,180,000	$1,180,000		$0	$933,708	$933,708		$0	$781,722	$781,722		$0	-$246,292	-$246,292		$1,785,657
57	1	Expense	N/A	CRB, travel, ofc supplies, trailer, others	Scott Fields	Reliability and Value	N/A	E			0	$0	$627,000	$627,000		$0	$317,400	$317,400		$0	$0	$0		$0	-$309,600	-$309,600		$317,400
58	1	Individual Project	74510	PCS Asset Replacement - 2016	Zaymar Sedra	Fit for Purpose	N/A	B	Execute		0.18	$1,869,000	$0	$1,869,000		$1,745,958	$69	$1,746,027		$149,000	$0	$149,000		-$123,042	$69	-$122,973		$1,895,027		03/22/16 moved above Execution line.
59	1	Expense		PCS Asset Replacement Depreciation Write-Off					$0	$800,000	$800,000			$800,000	$800,000					$0	$0	$0		$800,000		03/22/16 moved above Execution line.
60	1	Individual Project	74486	PCS Controller Cabinet Asset Replacement	Melanie Yevilov	Highly Capable Workforce	5.4	B	Execute		0.42	$2,404,000	$0	$2,404,000		$2,294,000	$0	$2,294,000		$110,000	$0	$110,000		-$110,000	$0	-$110,000		$2,404,000		03/22/16 moved above Execution line.
61	1	Individual Project	74487	Process VSD and SOV Asset Replacement	Melanie Yevilov	Highly Capable Workforce	N/A	R	Execute		0.33	$4,542,000	$7,000	$4,549,000		$3,599,318	$0	$3,599,318		$2,925,031	$18,000	$2,943,031		-$942,682	-$7,000	-$949,682		$6,542,349		03/22/16 moved above Execution line.
62	1	Individual Project	74427	MCS Network Infrastructure Asset Replacement - 2016	Scott Fields	Reliability and Value	N/A	R	Execute		0.29	$1,944,000	$0	$1,944,000		$1,944,000	$0	$1,944,000		$0	$0	$0		$0	$0	$0		$4,284,000		03/22/16 moved above Execution line.
63	1	Individual Project	74526	Utility and Process Safety System	Scott Fields	Reliability and Value	13.3	C	FXNL LT Appr		0	$1,700,000	$0	$1,700,000		$1,190,000	$0	$1,190,000		$510,000	$0	$510,000		-$510,000	$0	-$510,000		$1,700,000		03/24/16 Capital portion changed to align with better cash flow forecasting.
64	1	Individual Project	74511	QR018 Compliance Steam and Condensate Containment	Scott Fields	Reliability and Value	13.3		Execute		1.82	$2,457,000	$45,000	$2,502,000		$1,943,300	$0	$1,943,300		$3,074,500	$0	$3,074,500		-$513,700	-$45,000	-$558,700		$5,017,800		03/24/16 Cash flow updated according to latest estimates.
65				Everything above this line is currently in Execution
66	1	Startup	74127	Harvest Modifications Start-up	Deidre Dunham	Launch Facility	60	A	Budgeted		2.40	$125,000	$0	$125,000		$125,000	$0	$125,000		$2,275,000	$0	$2,275,000		$0	$0	$0		$2,400,000
67	1	Startup	74491	Etro Tech Transfer (NIC)	Deidre Dunham	Launch and Commercial Excellence	60	A	Idea		28.30	$7,015,007	$200,000	$7,215,007		$6,094,794	$116,900	$6,211,694		$12,701,630	$135,000	$12,836,630		-$920,213	-$83,100	-$1,003,313		$22,025,135		05/13/16 Cash flow reverted back to original forecast. 03/31/16 Cash flow updated according to latest estimates.
68		Global	96991	Asset Replacement 2016 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$229,675	$0	$229,675		$0	$0	$0		$229,675	$0	$229,675		$503,549		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
69		Global	96995	Asset Replacement 2016 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$98,980	$0	$98,980		$0.00	$0	$0		$98,980	$0	$98,980		$203,947		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
70		Global	96994	Asset Replacement 2016 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$131,504	$0	$131,504		$0	$0	$0		$131,504	$0	$131,504		$134,134		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
71		Global	96992	Asset Replacement 2016 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$13,848	$0	$13,848		$0	$0	$0		$13,848	$0	$13,848		$63,240		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
72		Global	96993	Asset Replacement 2016 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$25,188	$0	$25,188		$0	$0	$0		$25,188	$0	$25,188		$25,188		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
73		Global	96997	Asset Replacement 2016 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	N/A		FXNL LT Appr		0	$0	$0	$0		$15,617	$0	$15,617		$0	$0	$0		$15,617	$0	$15,617		$15,617		02/12/16 50% of capital portion of AR buckets added above the line per IMPACT discussion.
74	1	Global	74431	Buffer Prep Mezzanine Lift Construction	Scott Fields	Reliability and Value	10.7	A	JPMT Appr		0.09	$442,000	$0	$442,000		$442,000	$0	$442,000		$0	$0	$0		$0	$0	$0		$442,000		03/15/16 Project moved above the line.
75		Global	96174	Fall Protection Phase II	TBD	TBD	0		Idea		0	$0	$0	$0		$135,000	$0	$135,000		$0	$0	$0		$135,000	$0	$135,000		$135,000		03/17/16 Project added to portfolio and moved above the line.
76	1	Global	96137	Security Systems Upgrade	Deidre Dunham	Exceptional Culture	6.7	C	Hold		0	$250,000	$0	$250,000		$175,000	$0	$175,000		$0	$0	$0		-$75,000	$0	-$75,000		$175,000		5/10/16 project moved above the line per IMPACT discussion. 4/14/16 Project cashflow updated according to latest estimates.
77		Global	96152	Appleton Tank Mover	Melanie Yevilov	Highly Capable Workforce	8.9		Hold		0	$0	$0	$0		$73,000	$0	$73,000		$0	$0	$0		$73,000	$0	$73,000		$73,000		5/10/16 project moved above the line per IMPACT discussion.
78		Global	96207	Weigh and Dispense Sink (CAPA1123109)			0				0	$0	$0	$0		$25,000	$5,000	$30,000					$25,000	$5,000	$30,000		$30,000		5/10/16 project moved above the line per IMPACT discussion and funded by Engineering AR bucket. 5/9/16 Project added to portfolio.
79	1	Individual Project	96132	Mezzanine Safety Shower/Eye Wash Station Install	Melanie Yevilov	Highly Capable Workforce	2.9		IMPACT Appr		0	$210,000	$0	$210,000		$100,000	$0	$100,000		$785,864	$0	$785,864		-$110,000	$0	-$110,000		$885,864		5/10/16 project moved above the line per IMPACT discussion.
80	1	Expense	97057	Conference Room 315 Expansion	Deidre Dunham	Exceptional Culture	0		Idea		0	$0	$300,000	$300,000		$0	$108,000	$108,000		$0	$192,000	$192,000		$0	-$192,000	-$192,000		$300,000		5/10/16 project moved above the line per IMPACT discussion.
81				Execution Target Line
82	1	Global	96991	Asset Replacement 2016 - Engineering (cc642)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$987,350	$19,747	$1,007,097		$493,675	$14,747	$508,422		$0	$0	$0		-$493,675	-$5,000	-$498,675		$503,549
83	1	Global	96995	Asset Replacement 2016 - Quality (cc583)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$407,893	$0	$407,893		$203,947	$0	$203,947		$0	$0	$0		-$203,947	$0	-$203,947		$203,947
84	1	Global	96994	Asset Replacement 2016 - Manufacturing (cc659)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$263,008	$5,260	$268,268		$131,504	$5,260	$136,764		$0	$0	$0		-$131,504	$0	-$131,504		$134,134
85	1	Global	96992	Asset Replacement 2016 - Material Ops (cc484)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$124,000	$2,480	$126,480		$62,000	$2,480	$64,480		$0	$0	$0		-$62,000	$0	-$62,000		$63,240		03/17/16 $4k moved to Material Ops AR Bucket above the line.
86	1	Global	96993	Asset Replacement 2016 - Manufacturing (cc1359)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$50,375	$0	$50,375		$25,188	$0	$25,188		$0	$0	$0		-$25,188	$0	-$25,188		$25,188
87	1	Global	96997	Asset Replacement 2016 - Maintenance (cc1236)	Zaymar Sedra	Fit for Purpose	N/A	R	FXNL LT Appr		0	$31,233	$0	$31,233		$15,617	$0	$15,617		$0	$0	$0		-$15,617	$0	-$15,617		$15,617
88		Global	96169	Level Indicator Transmitters	Zaymar Sedra	Fit for Purpose	0	R	Idea		0	$0	$0	$0		$70,000	$0	$70,000		$0	$0	$0		$70,000	$0	$70,000		$70,000		03/10/16 Project added to portfolio.
89	1	Global	96159	OCC Network Remediation	Zaymar Sedra	Fit for Purpose	22.8		Idea		0	$150,000	$0	$150,000		$150,000	$0	$150,000		$0	$0	$0		$0	$0	$0		$150,000
90		Individual Project	74435	Hastelloy Chromatography Column (160cm)	Zaymar Sedra	Fit for Purpose	17.1		FXNL LT Appr		2.39	$1,549,000	$0	$1,549,000		$0	$0	$0		$1,549,000	$0	$1,549,000		-$1,549,000	$0	-$1,549,000		$1,549,000
91	1	Global	96135	QC Spectrophotmeters	Melanie Yevilov	Highly Capable Workforce	14.4	C	Hold		0.18	$327,522	$0	$327,522		$23,000	$0	$23,000		$0	$0	$0		-$304,522	$0	-$304,522		$23,000
92	1	Individual Project	74385	Media Prep Endotoxin/Bioburden Sampling	Scott Fields	Reliability and Value	6.5	B	Idea		2.28	$500,000	$0	$500,000		$250,000	$0	$250,000		$2,750,000	$0	$2,750,000		-$250,000	$0	-$250,000		$3,000,000
93		Global	96164	Hazardous Materials Containers Washing Station	Melanie Yevilov	Highly Capable Workforce	0		Placeholder		0	$30,000	$0	$30,000		$0	$0	$0		$30,000	$0	$30,000		-$30,000	$0	-$30,000		$30,000
94	1	Global	96167	Emergency Generator High Level Alarm	Scott Fields	Reliability and Value	0		Idea		0	$25,000	$0	$25,000		$25,000	$0	$25,000		$0	$0	$0		$0	$0	$0		$25,000
95	1	Global	96168	Replace Warehouse #321 Sprinkler Heads	Melanie Yevilov	Highly Capable Workforce	0		Idea		0	$20,000	$0	$20,000		$20,000	$0	$20,000		$0	$0	$0		$0	$0	$0		$20,000
96	1	Expense	97045	Site Exterior Lighting Upgrade - Title 24	Scott Fields	Reliability and Value	0	C	FXNL LT Appr		0	$0	$200,000	$200,000		$0	$100,000	$100,000		$0	$100,000	$100,000		$0	-$100,000	-$100,000		$200,000
97		Global	96208	RF Sealer Generator			0				0	$0	$0	$0		$17,250	$0	$17,250					$17,250	$0	$17,250		$17,250		5/11/16 Project added to portfolio.
98		Expense	97040	Tech Transfer: Master Data Management	Jim Neeleman	Launch and Commercial Excellence	24.3	B	FXNL LT Appr		2.00	$0	$250,000	$250,000		$0	$0	$0		$0	$0	$0		$0	-$250,000	-$250,000		$0		4/12/16 Project will be funded by PTD, per MB.
99		Expense	97038	PCS Functional Specification Development Project (CAPA 960297)	Scott Fields	Reliability and Value	13.5	B	FXNL LT Appr		0	$0	$1,000,000	$1,000,000		$0	$0	$0		$0	$4,750,000	$4,750,000		$0	-$1,000,000	-$1,000,000		$8,000,000
100		Expense	97039	PCS Remediation for EBR Review by Exception - PI	Melanie Yevilov	Highly Capable Workforce	13.0	B	Idea		0	$0	$250,000	$250,000		$0	$0	$0		$0	$250,000	$250,000		$0	-$250,000	-$250,000		$5,875,000
101		Individual Project	74527	Vessel 1020 Upgrade	Zaymar Sedra	Fit for Purpose	13.5	B	Idea		3.75	$2,646,000	$0	$2,646,000		$0	$0	$0		$4,859,000	$0	$4,859,000		-$2,646,000	$0	-$2,646,000		$4,859,000
102		Global	96134	QC Liquid Handler	Jim Neeleman	Launch and Commercial Excellence	13.2	C	Canceled		0.18	$134,917	$0	$134,917		$0	$0	$0		$0	$0	$0		-$134,917	$0	-$134,917		$0		4/12/16 Project cancelled; was covered in scope of project 65020.
103		Individual Project	74409	K6 Program - Project 1 - Replace DX HVAC Units	Zaymar Sedra	Fit for Purpose	11.3	A	Execute		0.06	$1,902,000	$22,000	$1,924,000		$0	$0	$0		$310,000	$22,000	$332,000		-$1,902,000	-$22,000	-$1,924,000		$1,924,000		01/12/16 Project deferred per IMPACT discussion.
104		Individual Project	74525	CIP Reliability and Efficiency - PI	Scott Fields	Reliability and Value	0	C			0.83	$0	$400,000	$400,000		$0	$0	$0		$0	$0	$0		$0	-$400,000	-$400,000		$0
105		Global	96139	Trash Bin Storm Water Mitigation	Scott Fields	Reliability and Value	6.3		Hold		0	$200,000	$0	$200,000		$0	$0	$0		$200,000	$0	$200,000		-$200,000	$0	-$200,000		$200,000		03/17/16 Project moved above the line per AW.
106		Expense	97054	HVAC Retro Commissioning	Scott Fields	Reliability and Value	15.6		FXNL LT Appr		0.10	$0	$0	$0		$0	$0	$0		$0	$113,000	$113,000		$0	$0	$0		$157,000
107		Global	96136	V-3007 Replacement	Zaymar Sedra	Fit for Purpose	N/A	B	FXNL LT Appr		0.75	$0	$0	$0		$0	$0	$0		$120,000	$0	$120,000		$0	$0	$0		$240,000
108		Individual Project	74432	K6 Program - Project 4 - Replace Chillers	Zaymar Sedra	Fit for Purpose	16.5		FXNL LT Appr		0.05	$0	$0	$0		$0	$0	$0		$2,650,000	$350,000	$3,000,000		$0	$0	$0		$19,300,000
109		Individual Project	74278	K6 Program - Project 3 - Replace Cold Room Compressors	Zaymar Sedra	Fit for Purpose	16.5	A	FXNL LT Appr		0.36	$0	$0	$0		$0	$0	$0		$528,000	$75,000	$603,000		$0	$0	$0		$10,759,000
110		Individual Project	74512	K6 Program - Project 2 - B381 Compliance	Zaymar Sedra	Fit for Purpose	16.5		FXNL LT Appr		0.18	$0	$0	$0		$0	$0	$0		$333,333	$22,222	$355,556		$0	$0	$0		$800,000
111		Global	96133	QC Rapid Scan RDI System	Jim Neeleman	Launch and Commercial Excellence	15.3	C	Hold		0.75	$0	$0	$0		$0	$0	$0		$210,000	$0	$210,000		$0	$0	$0		$210,000
112		Individual Project	96165	WAN Link Redundancy	Scott Fields	Reliability and Value	14.1		Idea		0	$0	$0	$0		$0	$0	$0		$2,000,000	$0	$2,000,000		$0	$0	$0		$2,000,000
113		Individual Project	74371	Odor Treatment	Melanie Yevilov	TBD	6.8	A	FXNL LT Appr		0.20	$0	$0	$0		$0	$0	$0		$750,000	$0	$750,000		$0	$0	$0		$5,500,000
114		Individual Project	74513	Electric Vehicle Charging Stations	Deidre Dunham	Exceptional Culture	2.2		Hold		0	$0	$0	$0		$0	$0	$0		$712,000	$18,000	$730,000		$0	$0	$0		$730,000
115		Global	96163	MFG Depth Filter Housing	Scott Fields	Reliability and Value	0		Idea		0	$0	$0	$0		$0	$0	$0		$300,000	$100,000	$400,000		$0	$0	$0		$400,000
116		Individual Project	74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	Jim Neeleman	Launch and Commercial Excellence	N/A		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$200,000	$200,000		$0	$0	$0		$2,935,000
117		Global	96069	Warehouse Crown Forklift Asset Replacement	Zaymar Sedra	Fit for Purpose	N/A		Hold		0	$0	$0	$0		$0	$0	$0		$144,407	$0	$144,407		$0	$0	$0		$144,407
118		Individual Project	96105	TMAC Tenderizer	Melanie Yevilov	Highly Capable Workforce	0		Hold		0	$0	$0	$0		$0	$0	$0		$0	$0	$0		$0	$0	$0		$0
119		Individual Project	96109	Sci&Eng Lab Equipment for NPI and Launch Capability	Jim Neeleman	Launch and Commercial Excellence	0		Placeholder		0	$0	$0	$0		$0	$0	$0		$600,000	$0	$600,000		$0	$0	$0		$6,000,000
120		Individual Project	96112	Maintenance Ops Shop Buildout	Zaymar Sedra	Fit for Purpose	0		Budgeted		0	$0	$0	$0		$0	$0	$0		$500,000	$0	$500,000		$0	$0	$0		$3,000,000
121		Individual Project	96114	QC Testing Equipment for Launch Capability and Storage Requirements	Jim Neeleman	Launch and Commercial Excellence	0		Placeholder		0	$0	$0	$0		$0	$0	$0		$600,000	$0	$600,000		$0	$0	$0		$7,200,000
122		Individual Project	96116	PCS Process Support Equipment Integration	Deidre Dunham	TBD	0		Idea		0	$0	$0	$0		$0	$0	$0		$0	$0	$0		$0	$0	$0		$3,000,000
123		Individual Project	96124	Perjeta Tech Transfer	Jim Neeleman	Launch and Commercial Excellence	0		Idea		0	$0	$0	$0		$0	$0	$0		$8,793,594	$147,070	$8,940,664		$0	$0	$0		$89,599,744
124		Expense	97061	Tangential Flow Filtration Cassettes Management	Scott Fields	Reliability and Value	40		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$550,000	$550,000		$0	$0	$0		$550,000
125		Expense	97005	MCS Peripheral Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	0		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$312,000	$312,000		$0	$0	$0		$312,000
126		Expense	97009	MES Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	0		Idea		0	$0	$0	$0		$0	$0	$0		$0	$400,000	$400,000		$0	$0	$0		$975,000
127		Expense	97012	Site Data Historian Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	0		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$366,000	$366,000		$0	$0	$0		$366,000
128		Expense	97015	MCS Backup System Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	0		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$390,000	$390,000		$0	$0	$0		$390,000
129		Expense	97030	MFG Systems Integration Improvement Phase 3 - 2017	Zaymar Sedra	Fit for Purpose	0		Idea		0	$0	$0	$0		$0	$0	$0		$0	$1,625,000	$1,625,000		$0	$0	$0		$1,625,000
130		Expense	97031	MCS Data Analytics Asset Replacement - 2017	Zaymar Sedra	Fit for Purpose	0		Idea		0	$0	$0	$0		$0	$0	$0		$0	$325,000	$325,000		$0	$0	$0		$325,000
131		Expense	97037	Recipe Reconfiguration Alignment for Operating Systems	Jim Neeleman	Launch and Commercial Excellence	13		FXNL LT Appr		0	$0	$0	$0		$0	$0	$0		$0	$3,750,000	$3,750,000		$0	$0	$0		$3,750,000
132		Expense	97060	QC Gas Cabinet Removal	TBD	TBD	0		FXNL LT Appr		0	$0	$0	$0		$0	$75,000	$75,000		$0	$0	$0		$0	$75,000	$75,000		$75,000
133		Individual Project	96177	Efficiency Projects	Scott Fields	Reliability and Value	0		Placeholder		0	$0	$0	$0		$0	$0	$0		$3,000,000	$0	$3,000,000		$0	$0	$0		$15,000,000
134				Contigency					$2,200,000	$662,487	$2,862,487		$3,800,236		$3,800,236					$1,600,236	-$662,487	$937,749		$937,749
135				Site Judgedown					-$8,348,298	-$2,552,487	-$10,900,785		-$1,487,180	-$197,487	-$1,684,667					$6,861,119	$2,355,000	$9,216,119		$9,216,119
136				TOTAL					99.6	$177,757,472	$9,878,553	$184,773,538		$157,000,000	$9,769,257	$166,769,257		$137,779,690	$16,511,868	$154,291,558		-$20,757,472	-$109,296	-$20,866,768		$597,844,194
136				OCN TOTAL CAPACITY					94.0

				T0				MO5				2017				Delta MO5 - T0
				Resource	Capital	Expense	Total		Capital	Expense	Total		Capital	Expense	Total		Capital	Expense	Delta Total		Lifetime Total
				P2/CMC Projects					67.4	$137,752,472	$2,296,566	$140,049,038		$119,985,017	$2,848,814	$122,833,831		$94,414,113	$1,104,854	$95,518,966		-$17,767,455	$552,248	-$17,215,207		$307,268,161
				Non P2/CMC Proposed in execution					11.5	$22,889,000	$49,500	$22,938,500		$19,033,361	$155,390	$19,188,751		$4,217,848	$550,000	$4,767,848		-$1,953,639	$102,890	-$1,850,749		$45,857,445
				Expense Only Projects in Execution					3.5	$0	$6,018,000	$6,018,000		$0	$5,851,984	$5,851,984		$0	$781,722	$781,722		$0	-$266,016	-$266,016		$6,703,933
				Shutdown Critical Projects					3.0	$14,916,000	$852,000	$15,768,000		$12,716,576	$800,069	$13,516,645		$6,768,531	$18,000	$6,786,531		-$2,199,424	-$51,931	-$2,251,355		$22,643,176
				Non P2/CMC Endorsed Projects					0.1	$8,348,298	$27,487	$8,375,785		$1,464,811	$113,000	$1,577,811		$10,483,864	$5,314,000	$15,797,864		$562,811	-$187,000	$375,811		$2,986,537
				Below Line (including Expense Only)					14.0	$0	$2,525,000	$2,525,000		$1,487,180	$197,487	$1,684,667		$30,939,334	$13,865,292	$44,804,627		-$7,861,119	-$1,952,000	-$9,813,119		$202,231,074
				Contingency					$2,200,000	$662,487	$2,862,487		$3,800,236	$0	$3,800,236		$0	$0			$1,600,236	-$662,487	$937,749		$937,749
				Site Judgedown					-$8,348,298	-$2,552,487	-$10,900,785		-$1,487,180	-$197,487	-$1,684,667		$0	$0	$0		$6,861,119	$2,355,000	$9,216,119		$9,216,119
				TOTAL					99.6	$177,757,472	$9,878,553	$184,773,538		$157,000,000	$9,769,257	$166,769,257		$146,823,690	$21,633,868	$168,457,558		-$20,757,472	-$109,296	-$20,866,768		$597,844,194
				Deferred or Need Scope Defined					2					$0	$0	$0					$40,096,000
				Deferred					14					$1,487,180	$122,487	$1,609,667					$0				$0	$66,983,923

				(7,304,626)	0
				Controllable Delta (IC)					55,138,000	8,774,987			47,833,374	8,178,470					(7,304,626)	(596,517)
				Non-Controllable Delta (NIC)	Total Delta					122,619,472	1,103,566			109,166,626	1,590,787					(13,452,846)	487,221
				177,757,472	9,878,553			157,000,000	9,769,257					(20,757,472)	(109,296)

		Assumptions:
		Site Capital judge down is based on costs below 2016 Execution Targets.
		Total Expense budget is $9.9M
		Resource Capacity: Historical 50 FTE + 10 FTE TT, 2015 20 hired for P2, 2016 14 hired for TT = 94 FTE.
		Resource Demand to support network projects is 10 FTE
		OLT Decision: Focusing on projects already in execution, Tech Transfer and shutdown critical.
		Site judgedown applies in MO5 for all projects below the line as we did in T0.

				Target < $25M					$20,498,172	TRUE

				Total (*)	Incl. 10% Adjustment		Total	Incl. 10% Adjustment
				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Capital	#REF!	#REF!		#REF!	#REF!
				Expense	#REF!	-		#REF!	-
				Total Cap + Exp	#REF!	#REF!		#REF!	#REF!

				Expense	#REF!
				Expense	#REF!	YEAR 2015 / TOTAL BUDGET

				Capital (Line Item + Global)	#REF!	#REF!		#REF!

				Expense	#REF!

				Expense (All)	#REF!	-	This total includes Above the line Auto. Expense Projects

				Total (*)	Incl. Adjustment		Total	Incl. Adjustment
				Capital	$4,523,260	$3,618,608		$891,126	$712,900

				Capital	$149,828,434	$149,245,906		$24,591,428	$19,673,142
				Expense	$2,184,814	-		$7,008,440	-
				Total Cap + Exp	$152,013,248	$149,245,906		$31,599,868	$19,673,142

				Expense	$46,946	-		$22,487	-
				Total Cap + Exp	$308,596,702	$302,110,420		$64,113,349	$40,059,185

				Expense	#REF!
				YEAR 2016 / TOTAL BUDGET

				Capital (Line Item + Global)	$154,351,694	$152,864,514		#REF!

				Expense (All)	#REF!	- / This total includes Above the line Auto. Expense Projects

## Constraint_Analysis_T0
		Bio Drug Substance - Oceanside					This version is in the portfolio
		Constraint Analysis
		2016 T0					2015				2016

	2016	Project Indicator	Status	Project number	Project Name	Category	Score	Score A,B,C, E	Program	PMO Lead	Capital	Expense	Avg. Roche Resources		Avg. Roche Resources	Capital	Expense				Total		Project Total
1	1	Individual Project	The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	74268	P2 Downstream Processing Expansion	Capacity	60	E	Launch Facility	Execute 2	$46,114,483	$3,345,844	29.71		21.21	$104,650,502	$825,644				$105,476,146		$194,047,008
2	1	Individual Project		74455	3rd HCCF Vessel	Capacity	60	E	Reliable	Execute	$1,079,394	$10,113	0.50		0.07	$2,328,891	$27,591				$2,356,482		$3,713,805
3	1	Individual Project		74454	Seed Lab (20L Bioreactor)	Capacity	60	E	Reliable	Execute	$755,170	$7,076	0.33		0.02	$938,961	$10,802				$949,763		$1,899,375
4	1	Individual Project		74453	NPI Pool Tanks	Capacity	60	E	Launch Facility	PTAA	$545,400	$0	0.00		0	$452,919	$10,802				$463,721		$1,009,121
5	1	Individual Project	To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	74382	Sci&Eng Lab Mods and Equipment	New Product Intro	7.6	E	Launch Facility	Execute 2	$5,270,000	$2,000	3.95		1.13	$7,008,000	$393,000				$7,401,000		$12,673,000
6	1	Individual Project	Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	74119	Harvest Upgrade (New Centrifuge)	Capacity	60	E	Launch Facility	Execute 2	$4,491,546	$42,076	2.47		2.30	$7,233,192	$28,727				$7,261,919		$12,909,963
7		Startup		74277	P2 DPE Start-Up	Capacity	60	A	Launch Facility	Execute	$0	$0	0.00		0	$8,000,000	$0				$8,000,000		$52,445,136
8		Expense		98026	Launch Capability Program (LCP)	New Product Intro	60	D	Launch Facility	Execute	$0	$0	3.79		12.00	$0	$800,000				$800,000		$800,000
9	1	Individual Project	FXNL LT Appr	74426	Process VSD and SOV Replacement - 2015	Efficiency	N/A	E	Reliable	Execute	$203,000	$0	0.00		0.30	$489,000	$0				$489,000		$692,000
10		Global		64901	MCS Peripheral Asset Replacement - 2015	Utility	N/A	E	Reliable	Execute	$225,200	$100,000	4.44		0	$100,000	$0				$100,000		$425,200
11		Individual Project		74368	Dev/Val Automation Capacity Expansion	Life Cycle Mgmt	N/A	E	Agile	Execute	$56,000	$0	0.16		0	$10,000	$0				$10,000		$625,000
12	1	Global		73387	MCSBACKUP Phase 2 Tape Retrieval	Other	N/A	E	Agile	Execute	$42,000	$5,000	0.00		0	$5,000	$0				$5,000		$52,000
13	1	Individual Project	Bldg. 311 is exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	74406	Corrosive Chemical Compliance	Life Cycle Mgmt	34	E	Reliable	Execute	$98,000	$0	0.09		0.11	$1,812,000	$0				$1,812,000		$1,910,000
14	1	Individual Project	Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	73367	FS & DS Automation Integration	Sustainability	24.4	E	Reliable	Execute 2	$477,000	$0	0.26		0.31	$10,000	$0				$10,000		$733,193
15	1	Individual Project	Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	74302	Waterpooling Remediation	Life Cycle Mgmt	23	E	Reliable	Execute 2	$510,000	$0	0.21		0.83	$435,000	$0				$435,000		$945,000
16	1	Individual Project	CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	73356	Supplemental BDU Sampling	Compliance	19.5	E	ACCR	Execute 2	$1,474,665	$0	0.34		0	$200,000	$0				$200,000		$1,674,665
17	1	Individual Project	In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	74279	New Media Technology - HTST / Adventitious	Life Cycle Mgmt	19.2	E	Reliable	Execute 2	$2,072,000	$2,000	0.00		5.15	$5,444,000	$0				$5,444,000		$9,106,000
18	1	Global	With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	76643	Optimize Column Movement Device	Compliance	18.6	E	Reliable	Execute	$68,000	$0	1.68		0.02	$128,000	$0				$128,000		$196,000
19	1	Individual Project		74524	Bioburden 2606 IPA Exhaust Improvement	Efficiency	18	A	Reliable	FXNL LT Appr	$0	$0	0.36		0.08	$12,000	$0				$12,000		$1,112,000
20	#REF!	Global		73384	Caustic Bath Upgrade	Utility	16.5	E	Reliable	Execute	$25,000	$0	0.24		0	$9,000	$0				$9,000		$51,106
21	1	Individual Project		74490	Hyfish Material Screening Operation	Efficiency	16.3	A	Reliable	Execute	$782,000	$0	0.00		0.05	$460,000	$0				$460,000		$1,242,000
22	1	Individual Project	Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	74418	QC Lab Reconfiguration & Equipment	Compliance	15.8	E	Reliable	Execute 1	$213,000	$0	0.28		0.28	$3,675,000	$0				$3,675,000		$3,888,000
23	1	Individual Project	Existing DX HVAC units use R-41A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 241, 361, and 371.	74409	K6 Program - Project 1 - Replace DX HVAC Units	Efficiency	11.3	A	ACCR	Execute	$90,000	$0	0.04		0.06	$1,902,000	$22,000				$1,924,000		$2,014,000
24		Global		73399	Frit Handling and Storage	Efficiency	11.3	A	Agile	Execute	$15,000	$0	0.01		0.11	$108,000	$15,000				$123,000		$138,000				2016		Total (*)	Incl. 10% Adjustment		Total	Incl. 10% Adjustment
25	1	Individual Project	The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	74373	WFI Generation and Storage System / CUB Expansion	Life Cycle Mgmt	11.1	E	Reliable	Execute 2	$6,162,014	$93,208	0.10		3.08	$5,342,000	$12,500				$5,354,500		$11,609,722				Global Credit	Capital	$1,200,200	$1,080,180		#REF!	#REF!
26	#REF!	Individual Project	FXNL LT Appr	74416	Asphyxiant Gas Remediation	Safety	11.1	A	Reliable	Execute 1	$33,392	$0	0.00		0.06	$99,000	$0				$99,000		$132,392					Expense	$127,000	-		#REF!	-
27	#REF!	Individual Project	To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	74404	Mezzanine Lift Media Prep: Phase 1B	Capacity	10.7	E	Reliable	Execute	$262,000	$0	1.79		0.01	$330,000	$0				$330,000		$592,000					Total Cap + Exp	$1,327,200	$1,080,180		#REF!	#REF!
28		Global		73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Safety	10.5	R	Reliable	Execute	$116,000	$0	0.07		0	$95,000	$0				$95,000		$211,000
29	1	Global	As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	73388	SIMCA Online Real Time Process Monitoring System	Life Cycle Mgmt	7.8	E	Reliable	Execute	$264,000	$22,000	0.03		0	$58,000	$0				$58,000		$344,000				Line Item / Projects	Capital	$73,887,064	$66,498,357		#REF!	#REF!
30	#REF!	Individual Project		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Compliance	7.7	R	Reliable	Execute	$311,000	$0	0.05		0.21	$350,000	$0				$350,000		$661,000					Expense	$3,502,317	-		#REF!	-
31	#REF!	Individual Project	CA Submitted	74392	Water Reclaim System	Compliance	6.1	E	ACCR	Execute	$180,000	$0	4.09		0.47	$676,000	$0				$676,000		$1,656,000					Total Cap + Exp	$77,389,381	$66,498,357		#REF!	#REF!
32		Global		73409	Solar Power Enabling Project	Compliance	5.1	R	Reliable	Execute	$184,000	$0	0.14		0.02	$271,000	$0				$271,000		$455,000
33	1	Individual Project		74489	4040 Avenida Conference Center Acquisition	TBD	3.1	A	Agile	Execute	$2,700,000	$0	0.00		0	$688,000	$0				$688,000		$3,388,000				Non-Automation	Expense	$201,000
34		Global		64914	QC M9 TOC Analyzers		N/A		Reliable	Execute	$0	$0	0.00		0	$106,000	$0				$106,000		$106,000				Automation	Expense	$245,000	YEAR 2015 / TOTAL BUDGET
35	1	Global		64923	QC Met-One Air Sampler Replacement 2015		N/A		Reliable	Execute	$0	$0	0.00		0	$60,000	$0				$60,000		$60,000
36	1	Global		64927	QC Gel Imager Replacement 2015		N/A		Reliable	Execute	$0	$0	0.00		0	$15,000	$0				$15,000		$15,000				GRAND TOTAL	Capital (Line Item + Global)	$75,087,264	$67,578,537		$71,653,854
37	#REF!	Expense			Piping Corrosion	#N/A	N/A		#N/A	#N/A	$0	$0	0.00		TBD	$0	$3,100,000				$3,100,000		$3,100,000					Expense (All)	$4,075,317	-	This total includes Above the line Auto. Expense Projects
38		Expense		97058	Parking Pavement Repair	Safety	0	A	TBD	Execute	$0	$120,000	0.11		0.00	$0	$80,000				$80,000		$200,000
39	1	Expense		97007	Automation System Lifecycle MCS Upgrade - PI	Compliance	27.6		Reliable	Execute	$0	$0	0.63		1.79	$0	$270,000				$270,000		$270,000
40	1	Expense	#N/A	97003	MFG Systems Integration Improvement Phase 1 - 2015	Efficiency	15.3	A	Agile	Execute 1	$0	$15,000	1.13		0.94	$0	$443,000				$443,000		$458,000
41		Expense		97048	Arc Flash Prevention	Efficiency	5.9		Reliable	JPMT Appr	$0	$48,000	0.00		0	$0	$318,000				$318,000		$366,000
42		Expense	#N/A	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	Life Cycle Mgmt	3.4	A	Agile	Execute 1	$0	$40,000	0.34		0.68	$0	$1,180,000				$1,180,000		$1,220,000				2016		Total (*)	Incl. Adjustment		Total	Incl. Adjustment
43		Expense		N/A	CRB, travel, ofc supplies, trailer, others	#N/A	N/A	E			$0	$0	0.00		0	$0	$627,000				$627,000		$627,000				Global Credit	Capital	$2,968,859	$2,375,087		$3,684,251	$2,947,401
44					Everything above this line is currently in Execution					Expense	$42,487	-		$49,487	-
45		Startup		74127	Harvest Modifications Start-up	Capacity	60	A	Launch Facility	Budgeted	$0	$0	0.00		2.40	$125,000	$0				$125,000		$2,400,000					Total Cap + Exp	$3,011,346	$2,375,087		$3,733,738	$2,947,401
46		Individual Project		74491	Etro Tech Transfer	New Product Intro	60	A	Launch Facility	Idea	$0	$0	0.00		28.30	$7,015,007	$200,000				$7,215,007		$22,025,135
47	1	Individual Project	Upgrade PCS hardware and software for Development, Validation and Production environments. Coordinate with P2 Project Team to deploy during the 2016 Plant Shutdown.	74510	PCS Asset Replacement - 2016	Life Cycle Mgmt	N/A	B	Reliable	JPMT Appr	$0	$0	0.00		0.18	$1,869,000					$1,869,000		$1,869,000
48	#REF!	Expense			PCS Asset Replacement Depreciation Write-Off					$800,000				$800,000		$800,000				Line Item / Projects	Capital	$176,151,472	$170,596,946		$32,570,305	$26,056,244
49	#REF!	Individual Project		74486	PCS Controller Cabinet Asset Replacement	Life Cycle Mgmt	5.4	B	Reliable	IMPACT Appr	$0	$0	0.00		0.42	$2,404,000	$0				$2,404,000		$6,042,000					Expense	$1,583,066	-		$9,622,487	-
50		Individual Project		74487	Process VSD and SOV Asset Replacement	Life Cycle Mgmt	N/A	R	Reliable	IMPACT Appr	$0	$0	0.00		0.33	$4,542,000	$7,000				$4,549,000		$17,422,000					Total Cap + Exp	$177,734,538	$170,596,946		$42,192,792	$26,056,244
51		Individual Project		74427	MCS Network Infrastructure Asset Replacement - 2016	Life Cycle Mgmt	N/A	R	Reliable	JPMT Appr	$7,000	$0	0.00		0.29	$1,944,000	$0				$1,944,000		$1,951,000
52	1	Individual Project		74511	Steaming Remediation - QR018 Compliance	Life Cycle Mgmt	13.3		Reliable	BMLT Appr	$0	$0	0.00		1.82	$2,457,000	$45,000				$2,502,000		$4,973,000
53		Individual Project		74526	Utility and Process Safety System	Compliance	12.4	C	Reliable	FXNL LT Appr	$0	$0	0.00		0	$1,700,000	$0				$1,700,000		$1,700,000				Non-Automation	Expense	$7,618,000
54					Execution Target Line					Automation	Expense	$0	YEAR 2016 / TOTAL BUDGET
55		Global		96991	Asset Replacement 2016 - Engineering (cc642)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$987,350	$19,747				$1,007,097		$1,007,097
56	#REF!	Global		96995	Asset Replacement 2016 - Quality (cc583)		N/A	R	Reliable	FXNL LT Appr	$261,000	$0	0.00		0	$407,893	$0				$407,893		$668,893				GRAND TOTAL	Capital (Line Item + Global)	$179,120,331	$172,972,033		$182,215,586
57		Global		96994	Asset Replacement 2016 - Manufacturing (cc659)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$263,008	$5,260				$268,268		$268,268					Expense (All)	$9,243,553	- / This total includes Above the line Auto. Expense Projects
58	1	Global	Asset Replacment	96992	Asset Replacement 2016 - Material Ops (cc484)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$124,000	$2,480				$126,480		$126,480				(**) Excludes Network projects "D".
59	1	Global		96993	Asset Replacement 2016 - Manufacturing (cc1359)	Life Cycle Mgmt	N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$50,375	$0				$50,375		$50,375				(*) Includes Asset Replacement.
60	#REF!	Global		96997	Asset Replacement 2016 - Maintenance (cc1236)		N/A	R	Reliable	FXNL LT Appr	$0	$0	0.00		0	$31,233	$0				$31,233		$31,233
61	1	Global		96159	OCC Network Remediation	Efficiency	22.8		TBD	Idea	$0	$0	0.00		0	$150,000	$0				$150,000		$150,000
62	1	Individual Project		74435	Hastelloy Chromatography Column (160cm)	TBD	16.2		Reliable	FXNL LT Appr	$0	$0	0.00		2.39	$1,549,000	$0				$1,549,000		$1,549,000
63		Global		96135	QC Spectrophotmeters	Compliance	14.4	C	Reliable	Hold	$0	$0	0.00		0.18	$327,522	$0				$327,522		$327,522
64		Individual Project		74527	Vessel 1020 Upgrade	TBD	13.5	B	Reliable	Idea	$0	$0	0.00		3.75	$2,646,000	$0				$2,646,000		$13,659,000
65	#REF!	Global		96134	QC Liquid Handler	Efficiency	13.2	C	Reliable	Hold	$0	$0	0.00		0.18	$134,917	$0				$134,917		$134,917
66	1	Global		74431	Buffer Prep Mezzanine Lift Construction	Safety	10.7	A	Reliable	JPMT Appr	$0	$0	0.00		0.09	$442,000	$0				$442,000		$442,000
67		Global		96137	Security Cameras Improvement on Parking Lot	Efficiency	6.7	C	Reliable	Hold	$0	$0	0.00		0	$250,000	$0				$250,000		$250,000
68		Individual Project		74385	Media Prep Endotoxin/Bioburden Sampling	Efficiency	6.5	B	Reliable	Idea	$0	$0	0.00		2.28	$500,000	$0				$500,000		$3,000,000
69		Global		96139	Trash Bin Storm Water Mitigation	TBD	6.3		Reliable	Hold	$0	$0	0.16		0	$200,000	$0				$200,000		$200,000
70		Global		96132	Mezzanine Safety Shower/Eye Wash Station Install		2.9		Reliable	IMPACT Appr	$0	$0	0.00		0	$210,000	$0				$210,000		$210,000
71		Global		96164	Hazardous Materials Containers Washing Station		0		TBD	Placeholder	$0	$0	0.00		0	$30,000	$0				$30,000		$30,000
72		Global		96167	Emergency Generator High Level Alarm		0		TBD	Idea	$0	$0	0.27		0	$25,000	$0				$25,000		$25,000
73		Global		96168	Replace Warehouse #321 Sprinkler Heads		0		TBD	Idea	$0	$0	0.03		0	$20,000	$0				$20,000		$20,000
74	#REF!	Expense		97040	Tech Transfer: Master Data Management	Compliance	24.3	B	Reliable	FXNL LT Appr	$0	$0	0.00		2.00	$0	$250,000				$250,000		$555,750
75		Expense		97038	PCS Functional Specification Development Project (CAPA 960297)	Safety	13.5	B	Reliable	FXNL LT Appr	$0	$0	0.00		0	$0	$1,000,000				$1,000,000		$8,000,000
76	#REF!	Expense		97039	PCS Remediation for EBR Review by Exception - PI	Efficiency	13.0	B	Agile	Idea	$0	$0	0.00		0	$0	$250,000				$250,000		$5,875,000
77		Expense		97053	Pressure Safety Program - PI Phase		8.8		TBD	Idea	$0	$0	0.00		0	$0	$100,000				$100,000		$100,000
78		Expense		97045	Site Exterior Lighting Upgrade - Title 24	Compliance	0	C	ACCR	FXNL LT Appr	$0	$0	0.00		0	$0	$200,000				$200,000		$200,000
79		Expense		97056	Drum Mover/Raw Material Tenderizer		0		TBD	FXNL LT Appr	$0	$0	0.00		0	$0	$25,000				$25,000		$25,000
80		Individual Project		74525	CIP Reliability and Efficiency - PI	Life Cycle Mgmt	0	C	Reliable	Idea	$0	$0	0.00		0.83	$0	$400,000				$400,000		$4,400,000
81		Expense		97057	Conference Room 315 Expansion		0		TBD	Idea	$0	$0	0.00		0.00	$0	$300,000				$300,000		$300,000
82	#REF!	Expense		97054	HVAC Retro Commissioning	TBD	15.6		ACCR	FXNL LT Appr	$0	$0	0.00		0.10	$0	$0				$0		$175,000
83	1	Global		96136	V-3007 Replacement	Sustainability	N/A	B	Reliable	FXNL LT Appr	$0	$0	0.00		0.75	$0	$0				$0		$240,000
84	1	Individual Project		74432	K6 Program - Project 4 - Replace Chillers	#REF!	16.5		ACCR	FXNL LT Appr	$0	$0	0.00		0.05	$0	$0				$0		$19,300,000
85		Individual Project		74278	K6 Program - Project 3 - Replace Cold Room Compressors	Other	16.5	A	ACCR	FXNL LT Appr	$0	$0	0.21		0.36	$0	$0				$0		$10,759,000
86	1	Individual Project		74512	K6 Program - Project 2 - B381 Compliance	Efficiency	16.5		ACCR	FXNL LT Appr	$0	$0	0.14		0.18	$0	$0				$0		$700,000
87	#REF!	Global		96133	QC Rapid Scan RDI System	Efficiency	15.3	C	Reliable	Hold	$0	$0	0.00		0.75	$0	$0				$0		$210,000
88	1	Individual Project		96165	WAN Link Redundancy	#REF!	14.1		TBD	Idea	$0	$0	0.00		0	$0	$0				$0		$2,000,000
89	#REF!	Individual Project		96160	B331 Fire Code Compliance	TBD	10.8		TBD	FXNL LT Appr	$0	$0	0.00		0	$0	$0				$0		$1,000,000
90	1	Individual Project		74371	Odor Treatment	TBD	6.8	A	ACCR	FXNL LT Appr	$100,000	$0	0.10		0.20	$0	$0				$0		$5,600,000
91		Individual Project		74513	Electric Vehicle Charging Stations	Compliance	2.2		Agile	Hold	$0	$0	0.00		0	$0	$0				$0		$730,000
92		Global		96163	MFG Depth Filter Housing		0		TBD	Idea	$0	$0	0.00		0	$0	$0				$0		$400,000
100.3809524		Network		98001	CMC Continuum	Capacity		D	Launch Facility	#N/A			0.15		0	$0	$0				$0
101.6095238		Network		98005	PTB-016: Empower 3 Rollout	0		D	0.00	#N/A			1.15		0.13	$0	$0				$0
102.8380952		Network		98019	PTQ-017 GMP Livelink to Condor	0		D	Multi Product	#N/A			1.32		0.20	$0	$0				$0
104.0666667		Network		98010	PTB-011: NTWK Microbial Control Task Force (GSP085 Implementation)	0		D	0.00	#N/A			0.07		1.10	$0	$0				$0
105.2952381		Network		98011	PTQ-xxx PQS: GSP085 - Microbiological Testing of Non-Sterile Material	0		D	Multi Product	#N/A			1.07		0	$0	$0				$0
106.5238095		Network		98006	GMP Document Lifecycle - 2014/2015	Compliance		D	Reliable	#N/A			0.96		0	$0	$0				$0
107.752381		Network		98022	PTQ-002 ALEX LES (Lab Execution System) Project	0		D	ACCR	#N/A			0.60		3.30	$0	$0				$0
108.9809524		Network		98028	PT-IPC1: Calman Replacement	0		D	Reliable	#N/A			0.25		0.28	$0	$0				$0
110.2095238		Network		98029	PTA-008 Business Continuity Management	0		D	ACCR	#N/A			1.08		0.15	$0	$0				$0
111.4380952		Network		98013	PTB-002 Gentamicin Removal Strategy for Commercial Processes	0		D	Multi Product	#N/A			0.90		0	$0	$0				$0
112.6666667		Network		98018	PTQ-xxx PQS: GSP034 - Biologics Cleaning Initiative	0		D	Multi Product	#N/A			0.27		0	$0	$0				$0
113.8952381		Network		98014	PTB-003 Analysis of Global Tank Management Process and System Improvements	0		D	Multi Product	#N/A			0.21		0	$0	$0				$0
115.1238095		Network		98017	PTQ-005 Coremap	0		D	Multi Product	#N/A			0.20		0	$0	$0				$0
116.352381		Network		98034	PTS201416-Global Warehouse Capacity Management	0		D	Multi Product	#N/A			0.10		0.20	$0	$0				$0
117.5809524		Network		98037	PTB-023: Rapid Bioburden Method for Pre-filtration Media	Efficiency					2.10	$0	$0				$0
118.8095238		Network		98038	PTB-025: Warehouse Business Continuity Mgt	Life Cycle Mgmt					0.92	$0	$0				$0
120.0380952		Network		98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay	Compliance					1.06	$0	$0				$0
121.2666667		Network		98040	PTQ-038: Quality Compliance Scorecard (QCS) Phase 2	Compliance					0	$0	$0				$0
122.4952381		Network		98041	PTQ-041: Simply Core for PT	Efficiency					0.04	$0	$0				$0
123.7238095		Network		98042	PTQ-046: Quality and Compliance Risk Roll Up	Efficiency					0.03	$0	$0				$0
124.952381		Network		98043	PTQ-050: QC Network Capacity Model	Capacity					0.03	$0	$0				$0
126.1809524		Network		98044	PTQ-051: FileNet Replacement Assessment	Efficiency					0.20	$0	$0				$0
127.4095238		Network		98009	PTB-006 Material of Construction (MOC) Program (GSP100 Implementation)	0		D	Multi Product	#N/A			0.06		0	$0	$0				$0
				Site Judgedown					-$10,661,762					-$6,148,298	-$1,890,000	$0	$0	$0	-$8,038,298
101					TOTAL					$64,425,501	$3,852,317	57.3		96.7	$177,757,472	$9,878,553	$195,674,323	$195,674,323	$626,234,679	$187,636,025		$430,560,356
102					OCN TOTAL CAPACITY					49.75		94.0

				Capital	Expense	Resourc.		Resource	Capital	Expense				Total		Protect Total
				P2/CMC Projects					$58,255,993	$3,407,109	37.0		67.43	$137,752,472	$2,296,566	$0	$0	$0	$140,049,038		$303,922,543
				Non P2/CMC Proposed Projects in execution					11.15	$22,889,000	$49,500	$0	$0	$0	$22,938,500	0	$44,034,278
				Expense Only Projects in Execution					3.40	$0	$6,018,000	$0	$0	$0	$6,018,000		$6,241,000
				Shutdown Critical Projects not in execution					$3,743,000	$223,000	7.4		3.04	$14,916,000	$852,000	$0	$0	$0	$15,768,000		$34,757,000
				Non P2/CMC Proposed Projects not in execution					#REF!	#REF!	#REF!		8.86	$8,348,298	$27,487	$0	$0	$0	$8,375,785		$22,149,785
				Expense Only Projects not in Execution					2.00	$0	$1,825,000	$0	$0	$0	$1,825,000		$14,755,750
				IMPACT Recommended Deferral					0.83	$0	$700,000	$0	$0	$0	$700,000		$4,700,000
				Site Judgedown					-$10,661,762	$0				-$6,148,298	-$1,890,000	$0	$0	$0	-$8,038,298
				TOTAL					#REF!	#REF!	#REF!		97	$177,757,472	$9,878,553	$0	$0	$0	$187,636,025		$430,560,356
				Deferred or Need Scope Defined					2	$-	$-	$-	$-	$-	$-	$-	$41,114,000
				Deferred or Need Scope Defined					2.38	$0	$0	$0	$0	$0	$0		$41,114,000
				Deferred					#REF!	#REF!	#REF!		14	$8,348,298	$2,552,487	$0	$0	$0	$10,900,785	$0	$82,719,535

		Assumptions:
		Site Capital judge down is based on costs below 2016 Execution Targets.
		Total Expense budget is $9.9M
		Resource Capacity: Historical 50 FTE + 10 FTE TT, 2015 20 hired for P2, 2016 14 hired for TT = 94 FTE.
		Resource Demand to support network projects is 10 FTE
		OLT Decision: Focusing on projects already in execution, Tech Transfer and shutdown critical.

		12/8/15: AW to check w/ Susan & JimN on 74416 - Asphyxiant Gas Remediation.
		12/8/15: AW to check w/ Susan & Sumner on 74371, 96139, 96140 if defer.
		12/8/15: AW to check w/ Sumner 74512 for 2016 w/ project 74409.
		12/8/15: SS to review SHE projects w/ Melanie.

## 2016_Budget_(Live)
		Oceanside
		T3 2016 - CAPEX Forecast Portfolio View: Capital Projects Including Expense Portions

		No.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	T3 2016 / (2016 Preview)	T3 2016 / (2017 Preview)	T3 2016 / (2018 Preview)	T3 2016 / (2019 Preview)	T3 2016 / (2020 Preview)	T3 2016 / (2021 Preview)	TOTAL T3 Budget	Exp + YE + T3 (CY) Total Project Cost	T3 2016 (Year 2016) Expense Portion	T3 2016 (Year 2017) Expense Portion	T3 2016 (Year 2018) Expense Portion	T3 2016 (Year 2019) Expense Portion	T3 2016 (Year 2020) Expense Portion	T3 2016 (Year 2021) Expense Portion
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business			-	3,580,630	786,250	3,511,935	3,863,129	4,249,441	4,674,386	5,141,824	5,656,007	27,096,721	31,463,601	51,487	-	-	-	-	-					3,460,448 / 5-Year CAPEX Through 2020 / CHF	3,863,129	4,249,441	4,674,386	5,141,824
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business			-	14,427,220	9,765,687	1,891,042	2,080,146	2,288,161	2,516,977	2,768,675	3,045,542	14,590,542	38,783,449	-	-	-	-	-	-					1,891,042	2,080,146	2,288,161	2,516,977	2,768,675
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,535,902	1,704,489	-	-	-	-	-	1,704,489	3,240,391	34,808	-	-	-	-	-					1,669,681	0	0	0	0
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg	-	-	2,701,000	685,700	-	-	-	-	-	685,700	3,386,700	-	-	-	-	-	-					685,700	0	0	0	0
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill	-	-	36,659	126,295	-	-	-	-	-	126,295	162,954	-	-	-	-	-	-					126,295	0	0	0	0
7		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD	-	-	-	-	-	-	-	10,000,000	-	10,000,000	10,000,000	-	-	-	-	-	-					0	0	0	0	10,000,000
8		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	103,025	1,724,239	83,733	-	-	-	-	1,807,972	1,910,997	-	-	-	-	-	-					1,724,239	83,733	0	0	0
9		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.	-	489,325	56,153	10,000	-	-	-	-	-	10,000	555,477	-	-	-	-	-	-					10,000	0	0	0	0
10		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio	-	-	-	306,000	654,000	-	-	-	-	960,000	960,000	-	-	-	-	-	-					306,000	654,000	0	0	0
11		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	-	3,000,000	3,000,000	3,000,000	3,000,000	3,000,000	15,000,000	15,000,000	-	-	-	-	-	-					0	3,000,000	3,000,000	3,000,000	3,000,000
12		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison	-	-	-	-	730,000	-	-	-	-	730,000	730,000	-	18,000	-	-	-	-					0	712,000	0	0	0
13		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.	-	246,193	476,778	26,719	-	-	-	-	-	26,719	749,690	-	-	-	-	-	-					26,719	0	0	0	0
14		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones	-	-	3,555,499	4,635,852	7,288,140	-	-	-	-	11,923,992	15,479,491	21,631	51,254	-	-	-	-					4,614,221	7,236,886	0	0	0
15		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio	-	-	-	400,000	1,149,000	-	-	-	-	1,549,000	1,549,000	-	-	-	-	-	-					400,000	1,149,000	0	0	0
16		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic	-	-	860,038	601,445	-	-	-	-	-	601,445	1,461,483	-	-	-	-	-	-					601,445	0	0	0	0
17		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing / Pierre Luong	-	-	-	-	332,000	-	-	-	-	332,000	332,000	-	22,000	-	-	-	-					0	310,000	0	0	0
18		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	-	355,556	444,444	-	-	800,000	800,000	-	-	22,222	27,778	-	-					0	0	333,333	416,667	0
19		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	603,000	4,828,000	4,828,000	500,000	-	10,759,000	10,759,000	-	75,000	-	-	-	-					0	528,000	4,828,000	4,828,000	500,000
20		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	-	3,000,000	6,650,000	6,000,000	3,650,000	19,300,000	19,300,000	-	-	350,000	-	-	-					0	0	2,650,000	6,650,000	6,000,000
21		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox	-	-	-	-	-	-	500,000	2,500,000	-	3,000,000	3,000,000	-	-	-	-	-	-					0	0	0	500,000	2,500,000
22		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin	-	-	-	1,466,000	-	-	-	-	2,340,000	3,806,000	3,806,000	-	-	-	-	-	-					1,466,000	0	0	0	0
23		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark	-	-	242,656	204,573	23,445	-	-	-	-	228,018	470,674	-	-	-	-	-	-					204,573	23,445	0	0	0
24		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan	-	17,731	265,047	270,009	-	-	-	-	-	270,009	552,787	(431)	-	-	-	-	-					270,440	0	0	0	0
25		74546	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	450,000	436,000	-	-	-	-	886,000	886,000	-	-	-	-	-	-					450,000	436,000	0	0	0
26		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez	-	523,433	1,984,354	4,947,130	1,591,162	-	-	-	-	6,538,292	9,046,079	88,096	37,670	-	-	-	-					4,859,034	1,553,492	0	0	0
27		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton	-	-	581,240	604,255	37,505	-	-	-	-	641,760	1,223,000	2,484	-	-	-	-	-					601,771	37,505	0	0	0
28		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai	-	-	-	-	-	750,000	4,750,000	-	-	5,500,000	5,500,000	-	-	-	500,000	-	-					0	0	750,000	4,250,000	0
29		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison	-	6,699,119	58,484,942	93,629,477	34,280,135	-	-	-	-	127,909,612	193,915,669	1,766,871	916,060	-	-	-	-					91,862,606	33,364,075	0	0	0
30		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	1,766,058	149,000	-	-	-	-	1,915,058	1,915,058	219	-	-	-	-	-					1,765,839	149,000	0	0	0
31		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	2,294,000	110,000	-	-	-	-	2,404,000	2,404,000	-	-	-	-	-	-					2,294,000	110,000	0	0	0
32		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton	-	-	-	-	200,000	900,000	900,000	935,000	-	2,935,000	2,935,000	-	200,000	-	-	-	-					0	0	900,000	900,000	935,000
33		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia	-	-	-	-	-	1,500,000	1,500,000	-	-	3,000,000	3,000,000	-	-	750,000	750,000	-	-					0	0	750,000	750,000	0
34		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark	-	-	194,621	589,735	-	-	-	-	-	589,735	784,356	-	-	-	-	-	-					589,735	0	0	0	0
35		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	3,599,797	2,943,031	-	-	-	-	6,542,828	6,542,828	-	18,000	-	-	-	-					3,599,797	2,925,031	0	0	0
36		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	2,500,000	3,000,000	-	-	5,500,000	5,500,000	-	-	-	-	-	-					0	0	2,500,000	3,000,000	0
37		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	-	458,000	5,000,000	-	5,458,000	5,458,000	-	-	-	-	-	-					0	0	0	458,000	5,000,000
38		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez	-	-	224,746	3,274,674	289,726	-	-	-	-	3,564,400	3,789,146	114,000	-	-	-	-	-					3,160,674	289,726	0	0	0
39		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison	-	-	-	1,943,300	3,074,500	-	-	-	-	5,017,800	5,017,800	-	-	-	-	-	-					1,943,300	3,074,500	0	0	0
40		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic	-	-	6,008,632	7,610,223	390,885	-	-	-	-	8,001,108	14,009,740	195,338	-	-	-	-	-					7,414,885	390,885	0	0	0
41		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,387,337	1,010,193	440,826	-	-	-	-	1,451,019	2,838,356	97,323	2,075	-	-	-	-					912,870	438,751	0	0	0
42		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley	-	258,306	1,420,589	157,774	-	-	-	-	-	157,774	1,836,669	-	-	-	-	-	-					157,774	0	0	0	0
43		96180	TMAC Waste System Improvements	CTT	Stay in Business	TBD	Pierre Luong	-	-	-	-	1,500,000	-	-	-	-	1,500,000	1,500,000	-	-	-	-	-	-					0	1,500,000	0	0	0
44		96191	Utility and Process Safety System Phase 2	RTO	Stay in Business	TBD	Charles Fuller / Scott Breier	-	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,000	-	-	-	-	-	-					0	2,000,000	0	0	0
45		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	1,882,404	57,596	-	-	-	-	1,940,000	1,940,000	-	-	-	-	-	-					1,882,404	57,596	0	0	0
46		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez	-	-	-	-	-	3,800,000	100,000	-	-	3,900,000	3,900,000	-	-	100,000	-	-	-					0	0	3,700,000	100,000	0
47		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-					0	0	0	0	0
48		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	179,085	143,846	-	-	-	-	-	143,846	322,931	-	-	-	-	-	-					143,846	0	0	0	0
49		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen	-	1,194,816	470,099	369,680	50,426	-	-	-	-	420,106	2,085,021	-	-	-	-	-	-					369,680	50,426	0	0	0
51		96210	P2 User Furnished Equipment Procurement	CTT	TBD	TBD	Ben Chmielewski	-	-	-	1,100,000	1,100,000	-	-	-	-	2,200,000	2,200,000	150,000	150,000	-	-	-	-					950,000	950,000	0	0	0
52		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai	-	1,738,974	6,525,760	5,536,207	-	-	-	-	-	5,536,207	13,800,941	23,739	-	-	-	-	-					5,512,468	0	0	0	0
53		96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting	QSP	Improvements and Efficiencies	Reliability and Value	Bahar Dahi	1	-	-	-	1,000,000	-	-	-	-	1,000,000	1,000,001	-	500,000	-	-	-	-
54		96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000	QSP	Improvements and Efficiencies	Reliability and Value	Bahar Dahi	2	-	-	-	550,000	-	-	-	-	550,000	550,002	-	50,000	-	-	-	-
55		96213	Replacement of Obsolete Benchtop Horiba pH Meter	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi	3	-	-	-	1,200,000	-	-	-	-	1,200,000	1,200,003	-	200,000	-	-	-	-
57		96219	Harvest Filter Housing A Removal/Installation Improvements	QSP	Improvements and Efficiencies	Highly Capable Workforce	Marcus Espinoza	5	-	-	-	500,000	-	-	-	-	500,000	500,005	-	100,000	-	-	-	-
58		96221	Corrosive Chemical Compliance - CUB and Warehouse	RTO	SHE and K-Directives	Reliability and Value	Susan Schmidt	6	-	-	-	2,900,000	20,000	-	-	-	2,920,000	2,920,006	-	-	-	-	-	-
58		96222	Pressure Safety Program - Mechanical	RTO	SHE and K-Directives	Highly Capable Workforce	Nick Loebs	6	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,006	-	-	-	-	-	-
58		96223	Pressure Safety Program - Automation	RTO	SHE and K-Directives	Highly Capable Workforce	Nick Loebs	6	-	-	-	-	2,500,000	-	-	-	2,500,000	2,500,006	-	-	-	-	-	-
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	1,364,276	12,836,630	3,347,374	507,790	66,290	-	18,122,360	18,122,360	69,004	3,771,061	80,000	20,600	4,800	-					1,295,272	9,065,569	3,267,374	487,190	61,490
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	8,940,664	78,779,345	1,431,430	369,105	79,200	89,599,744	89,599,744	-	147,070	16,999,060	55,330	19,800	40,920					0	8,793,594	61,780,285	1,376,100	349,305
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	8,940,664	31,169,850	1,431,430	41,541,944	41,541,944	-	-	-	147,070	6,402,538	55,330					0	0	0	8,793,594	24,767,312
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	-	8,940,664	28,753,027	37,693,691	37,693,691	-	-	-	-	147,070	6,194,763					0	0	0	0	8,793,594
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton	-	-	-	125,000	2,275,000	-	-	-	-	2,400,000	2,400,000	-	-	-	-	-	-					125,000	2,275,000	0	0	0
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton	-	-	-	4,461,207	40,280,925	6,754,868	-	-	-	51,497,000	51,497,000	-	-	-	-	-	-					4,461,207	40,280,925	6,754,868	0	0
65			Contingency					-	-	-	-	-	-	-	0	-	-	-	-	-	-					0	0	0	0	0
66		96999	Site Management Adjustments (if any)					-	-	-	-	-	-	-	0	-	-	-	-	-	-					0	0	0	0	0
			Total					29	29,175,747	97,846,098	154,423,534	140,940,604	118,572,745	44,201,691	76,391,408	47,955,205	582,485,186	710,329,057	2,614,569	6,258,190	18,301,282	1,500,778	6,574,208	6,291,013					151,808,965

			Global Credit					18,007,850	10,551,937	5,402,977	5,943,275	6,537,602	7,191,362	7,910,499	8,701,548	41,687,263	70,247,050	51,487	0	0	0	0	0					150,087,036
			Individual Credit					11,167,897	87,294,161	143,070,074	62,514,110	20,633,556	26,130,444	27,935,000	8,990,000	289,273,184	388,557,238	2,494,078	1,490,059	1,222,222	1,277,778	0	0					1,721,930
			Tech Transfer					0	0	1,364,276	21,777,294	82,126,719	10,879,884	40,545,909	30,263,657	186,957,739	186,957,739	69,004	3,918,131	17,079,060	223,000	6,574,208	6,291,013
			Start-up					0	0	4,586,207	42,555,925	6,754,868	0	0	0	53,897,000	53,897,000	0	0	0	0	0	0
			Adjustment					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
			Contigency					0	0	0	0	0	0	0	0	0	0	0	0	0	0
			TOTAL CAPEX					29,175,747	97,846,098	154,423,534	132,790,604	116,052,745	44,201,691	76,391,408	47,955,205	571,815,186	699,659,028	2,614,569	5,408,190	18,301,282	1,500,778	6,574,208	6,291,013

							$160,231,036					$10,144,001
							5,807,503					7,529,432					SHE and K-Directives	Stay in Business	Strategic	Tech Transfers	Improvements and Efficiencies	New Technologies
			Improvements and Efficiencies					1,011,445	8,129,000	4,500,000	5,000,000	15,500,000	3,000,000		31,487,802	31,487,802					2016	$4,596,793	$18,099,894	$120,002,603	$4,665,669	$1,011,445	$4,947,130
			New Technologies					4,947,130	1,591,162	0	0	0	0		6,175,294	6,175,294					2017	$6,412,329	$16,647,677	$84,993,416	$22,067,020	$8,129,000	$1,591,162
			SHE and K-Directives					4,596,793	6,412,329	11,453,556	16,672,444	6,500,000	3,650,000		48,547,130	48,547,130					2018	$11,453,556	$13,737,602	$6,754,868	$82,126,719	$4,500,000	$-
			Stay in Business					18,099,894	16,647,677	13,737,602	11,649,362	13,845,499	11,041,548		70,973,443	70,973,443					2019	$16,672,444	$11,649,362	$-	$10,879,884	$5,000,000	$-
			Strategic					120,002,603	84,993,416	6,754,868	0	0	0		203,568,728	203,568,728					2020	$6,500,000	$13,845,499	$-	$40,545,909	$15,500,000	$-
			Tech Transfers					4,665,669	22,067,020	82,126,719	10,879,884	40,545,909	30,263,657		171,692,841	171,692,841					2021	$3,650,000	$11,041,548	$-	$30,263,657	$3,000,000	$-
			Total					532,445,239	532,445,239

		Oceanside
		T3 2016 - Capital Forecast - Site Business Plan View: Capital Projects Without Expense Portions

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	T3 2016 / (2016 Preview)	T3 2016 / (2017 Preview)	T3 2016 / (2018 Preview)	T3 2016 / (2019 Preview)	T3 2016 / (2020 Preview)	T3 2016 / (2021 Preview)	TOTAL T3 Budget
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business					3,583,187	3,941,505	4,335,656	4,769,222	5,246,144	5,770,758	27,646,472		-	-	-	-	-	-
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business					1,929,408	2,122,349	2,334,584	2,568,042	2,824,847	3,107,331	14,886,562		-	-	-	-	-	-
3		96204	322 MRO Racks	RTO	SHE and K-Directives	TBD	Pierre Luong				-	500,000	-	-	-	-	500,000		-	-	-	-	-	-
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				1,669,681	-	-	-	-	-	1,669,681		-	-	-	-	-	-
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg				685,700	-	-	-	-	-	685,700		-	-	-	-	-	-
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill				126,295	-	-	-	-	-	126,295		-	-	-	-	-	-
7		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD				-	-	-	-	10,000,000	-	10,000,000		-	-	-	-	-	-
8		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai				1,724,239	83,733	-	-	-	-	1,807,972		-	-	-	-	-	-
9		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.				10,000	-	-	-	-	-	10,000		-	-	-	-	-	-
10		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio				306,000	654,000	-	-	-	-	960,000		-	-	-	-	-	-
11		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD				-	3,000,000	3,000,000	3,000,000	3,000,000	3,000,000	15,000,000		-	-	-	-	-	-
12		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison				-	712,000	-	-	-	-	712,000		-	-	-	-	-	-
13		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.				26,719	-	-	-	-	-	26,719		-	-	-	-	-	-
14		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones				4,614,221	7,236,886	-	-	-	-	11,851,107		-	-	-	-	-	-
15		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio				400,000	1,149,000	-	-	-	-	1,549,000		-	-	-	-	-	-
16		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic				601,445	-	-	-	-	-	601,445		-	-	-	-	-	-
17		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing / Pierre Luong				-	310,000	-	-	-	-	310,000		-	-	-	-	-	-
18		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	-	333,333	416,667	-	-	750,000		-	-	-	-	-	-
19		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	528,000	4,828,000	4,828,000	500,000	-	10,684,000		-	-	-	-	-	-
20		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	-	2,650,000	6,650,000	6,000,000	3,650,000	18,950,000		-	-	-	-	-	-
21		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox				-	-	-	500,000	2,500,000	-	3,000,000		-	-	-	-	-	-
22		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin				1,466,000	-	-	-	-	2,340,000	3,806,000		-	-	-	-	-	-
23		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark				204,573	23,445	-	-	-	-	228,018		-	-	-	-	-	-
24		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan				270,440	-	-	-	-	-	270,440		-	-	-	-	-	-
25		74546	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza				450,000	436,000	-	-	-	-	886,000		-	-	-	-	-	-
26		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez				4,859,034	1,553,492	-	-	-	-	6,412,526		-	-	-	-	-	-
27		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton				601,771	37,505	-	-	-	-	639,276		-	-	-	-	-	-
28		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai				-	-	750,000	4,250,000	-	-	5,000,000		-	-	-	-	-	-
29		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison				91,862,606	33,364,075	-	-	-	-	125,226,681		-	-	-	-	-	-
30		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin				1,765,839	149,000	-	-	-	-	1,914,839		-	-	-	-	-	-
31		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark				2,294,000	110,000	-	-	-	-	2,404,000		-	-	-	-	-	-
32		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton				-	-	900,000	900,000	935,000	-	2,735,000		-	-	-	-	-	-
33		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia				-	-	750,000	750,000	-	-	1,500,000		-	-	-	-	-	-
34		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark				589,735	-	-	-	-	-	589,735		-	-	-	-	-	-
35		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				3,599,797	2,925,031	-	-	-	-	6,524,828		-	-	-	-	-	-
36		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	2,500,000	3,000,000	-	-	5,500,000		-	-	-	-	-	-
37		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	-	458,000	5,000,000	-	5,458,000		- / 5-Year CAPEX Through 2020 / USD	-	-	-	-	-
38		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez				3,160,674	289,726	-	-	-	-	3,450,400		-	-	-	-	-	-
39		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison				1,943,300	3,074,500	-	-	-	-	5,017,800		-	-	-	-	-	-
40		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic				7,414,885	390,885	-	-	-	-	7,805,770		-	-	-	-	-	-
41		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				912,870	438,751	-	-	-	-	1,351,621		-	-	-	-	-	-
42		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley				157,774	-	-	-	-	-	157,774		-	-	-	-	-	-
43		96180	TMAC Waste System Improvements	CTT	Stay in Business	TBD	Pierre Luong				-	1,500,000	-	-	-	-	1,500,000		-	-	-	-	-	-
44		96191	Utility and Process Safety System Phase 2	RTO	Stay in Business	TBD	Charles Fuller / Scott Breier				-	2,000,000	-	-	-	-	2,000,000		-	-	-	-	-	-
45		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller				1,882,404	57,596	-	-	-	-	1,940,000		-	-	-	-	-	-
46		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez				-	-	3,700,000	100,000	-	-	3,800,000		-	-	-	-	-	-
47		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell				-	-	-	-	-	-	-		-	-	-	-	-	-
48		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai				143,846	-	-	-	-	-	143,846		-	-	-	-	-	-
49		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen				369,680	50,426	-	-	-	-	420,106		-	-	-	-	-	-
51		96210	P2 User Furnished Equipment Procurement	CTT	TBD	TBD	Ben Chmielewski				950,000	950,000	-	-	-	-	1,900,000		-	-	-	-	-	-
52		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai				5,512,468	-	-	-	-	-	5,512,468		-	-	-	-	-	-
53		96211	Replacement of Swedgelok Fitting of N2 Gas Piping of U-4000 Skid with Sanitary Fitting	QSP	Improvements and Efficiencies	Reliability and Value	Bahar Dahi				-	500,000	-	-	-	-	500,000
54		96212	Replacement of Back Pressure Control Valve on Formulation Skid U-4000	QSP	Improvements and Efficiencies	Reliability and Value	Bahar Dahi				-	500,000	-	-	-	-	500,000
55		96213	Replacement of Obsolete Benchtop Horiba pH Meter	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi				-	1,000,000	-	-	-	-	1,000,000
57		96219	Harvest Filter Housing A Removal/Installation Improvements	QSP	Improvements and Efficiencies	Highly Capable Workforce	Marcus Espinoza				-	400,000	-	-	-	-	400,000
58		96221	Corrosive Chemical Compliance - CUB and Warehouse	RTO	SHE and K-Directives	Reliability and Value	Susan Schmidt				-	2,900,000	20,000	-	-	-	2,920,000
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				1,295,272	9,065,569	3,267,374	487,190	61,490	-	14,176,895		-	-	-	-	-	-
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	8,793,594	61,780,285	1,376,100	349,305	38,280	72,337,564		-	-	-	-	-	-
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	8,793,594	24,767,312	1,376,100	34,937,006		-	-	-	-	-	-
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	-	8,793,594	22,558,264	31,351,858		-	-	-	-	-	-
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton				125,000	2,275,000	-	-	-	-	2,400,000		-	-	-	-	-	-
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton				4,461,207	40,280,925	6,754,868	-	-	-	51,497,000		-	-	-	-	-	-
65			Contingency					-	-	-	-	-	-	-		-	-	-	-	-	-
66		96999	Site Management Adjustments (if any)					-	-	-	-	-	-	-		-	-	-	-	-	-
			Total					0	0	0	151,970,070	133,302,993	97,904,100	42,846,815	69,977,691	41,840,733	537,842,403	0	0	0	0	0	0	0

			Improvements and Efficiencies					1,011,445	7,261,000	3,750,000	4,250,000	15,500,000	3,000,000		31,772,445
			New Technologies					4,859,034	1,553,492	0	0	0	0		6,412,526
			SHE and K-Directives					4,597,224	4,815,329	8,581,333	16,144,667	6,500,000	3,650,000		40,638,553
			Stay in Business					18,209,293	16,550,257	13,770,240	11,795,264	14,005,990	11,218,089		74,331,044
			Strategic					117,860,409	84,024,027	6,754,868	0	0	0		208,639,304
			Tech Transfers					4,482,665	18,148,889	65,047,659	10,656,884	33,971,701	23,972,644		132,307,797
			Total					494,101,669

		Oceanside
		T3 2016 - Expense Forecast - Expense Only and Expense Portions of Capital Projects to Identify Opportunity to Fund Expense Only Projects

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	T3 2016 / (2016 Preview)	T3 2016 / (2017 Preview)	T3 2016 / (2018 Preview)	T3 2016 / (2019 Preview)	T3 2016 / (2020 Preview)	T3 2016 / (2021 Preview)	TOTAL T3 Budget	Exp + YE + T3 (CY) Total Project Expense	T3 2016 (Year 2016) Expense Portion	T3 2016 (Year 2017) Expense Portion	T3 2016 (Year 2018) Expense Portion	T3 2016 (Year 2019) Expense Portion	T3 2016 (Year 2020) Expense Portion	T3 2016 (Year 2021) Expense Portion
1		97048	Arc Flash Prevention	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	318,000	-	-	-	-	-	318,000	318,000	318,000	-	-	-	-	-					0	0	0	0	0
2		97007	Automation System Lifecycle MCS Upgrade	QSP	Improvements and Efficiencies	Reliability and Value	Myles Sumlin	-	-	-	295,781	-	-	-	-	-	295,781	295,781	295,781	-	-	-	-	-					0	0	0	0	0
3		97059	B311 & B321 Gowning Room Modifications	RTO	Stay in Business	Reliability and Value	TBD	-	-	-	100,492	-	-	-	-	-	100,492	100,492	100,492	-	-	-	-	-					0	0	0	0	0
4		97057	Conference Room 315 Expansion	TBD	Improvements and Efficiencies	Exceptional Culture	N/A	-	-	-	150,000	-	-	-	-	-	150,000	150,000	150,000	-	-	-	-	-					0	0	0	0	0
5		97042	CRB Project Budget Estimating	QSP	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	250,400	250,400	-	-	-	-	500,800	500,800	250,400	250,400	-	-	-	-					0	0	0	0	0
6		97054	HVAC Retro Commissioning	CTT	Stay in Business	Reliability and Value		-	-	-	-	113,000	44,000	-	-	-	157,000	157,000	-	113,000	44,000	-	-	-					0	0	0	0	0
7		82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	CTT	Stay in Business	Reliability and Value	Jonathan Clark	-	-	70,227	866,058	574,661	-	-	-	-	1,440,719	1,510,946	866,058	574,661	-	-	-	-					0	0	0	0	0
8		97044	IMPACT Support	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	8,000	8,000	-	-	-	-	16,000	16,000	8,000	8,000	-	-	-	-					0	0	0	0	0
9		98026	Launch Capability Program (LCP)	QSP	Tech Transfers	Launch and Commercial Excellence	TBD	-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
10		97001	Lunches	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	4,000	4,000	-	-	-	-	8,000	8,000	4,000	4,000	-	-	-	-					0	0	0	0	0
11		97015	MCS Backup System Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	390,000	-	-	-	-	390,000	390,000	-	390,000	-	-	-	-					0	0	0	0	0
12		97016	MCS Backup System Asset Replacement - 2020	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	439,000	-	439,000	439,000	-	-	-	-	439,000	-					0	0	0	0	0
13		97031	MCS Data Analytics Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	TBD	-	-	-	-	325,000	-	-	-	-	325,000	325,000	-	325,000	-	-	-	-					0	0	0	0	0
14		97032	MCS Data Analytics Asset Replacement - 2020	QSP	Stay in Business	Reliable	TBD	-	-	-	-	-	-	-	360,000	-	360,000	360,000	-	-	-	-	360,000	-					0	0	0	0	0
15		97005	MCS Peripheral Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	-	312,000	-	-	-	312,000	312,000	-	-	312,000	-	-	-					0	0	0	0	0
16		97006	MCS Peripheral Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	332,000	-	332,000	332,000	-	-	-	-	332,000	-					0	0	0	0	0
17		97063	MCS Peripheral Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-					0	0	0	0	0
18		97009	MES Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	400,000	575,000	-	-	-	975,000	975,000	-	400,000	575,000	-	-	-					0	0	0	0	0
19		97010	MES Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	500,000	525,000	1,025,000	1,025,000	-	-	-	-	500,000	525,000					0	0	0	0	0
20		97003	MFG Systems Integration Improvement Phase 1 - 2015	CTT	Improvements and Efficiencies	Reliability and Value	Eric Davis	-	-	-	292,227	135,000	-	-	-	-	427,227	427,227	292,227	135,000	-	-	-	-					0	0	0	0	0
21		97030	MFG Systems Integration Improvement Phase 3 - 2017	QSP	Improvements and Efficiencies	Fit for Purpose	TBD	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-	-					0	0	0	0	0
22		97002	Office Supplies inc. Laptops	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	45,000	45,000	-	-	-	-	90,000	90,000	45,000	45,000	-	-	-	-					0	0	0	0	0
23		97058	Parking Pavement Repair	CTT	Stay in Business	Reliability and Value	Sumner Tison	-	-	-	245,040	-	-	-	-	-	245,040	245,040	245,040	-	-	-	-	-					0	0	0	0	0
24		97008	PCS Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	487,500	487,500	-	-	975,000	975,000	-	-	487,500	487,500	-	-					0	0	0	0	0
25		97064	PCS Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	463,000	463,000	463,000	-	-	-	-	-	463,000					0	0	0	0	0
26			PCS Asset Replacement Depreciation Write-Off	TBD	TBD			-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
27		97066	PCS Automated Documentation Asset Replacement - 2021	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	-	-	-	360,000	360,000	360,000	-	-	-	-	-	360,000					0	0	0	0	0
28		97033	PCS Automated Documentation Upgrade	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	325,000	-	-	-	325,000	325,000	-	-	325,000	-	-	-					0	0	0	0	0
29		97038	PCS Functional Specification Development Project (CAPA 960297)	RTO	Strategic	Reliability and Value	Sarah Maruccia	-	-	-	-	500,000	2,250,000	2,250,000	3,000,000	-	8,000,000	8,000,000	-	500,000	2,250,000	2,250,000	3,000,000	-					0	0	0	0	0
30		97039	PCS Remediation for EBR Review by Exception - PI	QSP	Improvements and Efficiencies	Highly Capable Workforce	Malou Jacinto / Stephanie Huntress	-	-	-	-	250,000	2,250,000	3,375,000	-	-	5,875,000	5,875,000	-	250,000	2,250,000	3,375,000	-	-					0	0	0	0	0
31		97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	488,000	-	-	-	488,000	488,000	-	-	488,000	-	-	-					0	0	0	0	0
32		97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	488,000	-	488,000	488,000	-	-	-	-	488,000	-					0	0	0	0	0
33		TBD	PAIR	TBD	Stay in Business	Reliability and Value	Samuel Calhoun	-	-	-	3,102,350	4,788,348	-	-	-	-	7,890,698	7,890,698	3,102,350	4,788,348	-	-	-	-					0	0	0	0	0
34		97060	QC Gas Cabinet Removal	QSP	TBD	TBD	Joe Molon	-	-	-	75,000	-	-	-	-	-	75,000	75,000	75,000	-	-	-	-	-					0	0	0	0	0
35		97037	Recipe Reconfiguration Alignment for Operating Systems	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Marco Baca	-	-	-	-	250,000	1,500,000	1,750,000	-	-	3,500,000	3,500,000	-	250,000	1,500,000	1,750,000	-	-					0	0	0	0	0
36		97012	Site Data Historian Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	366,000	-	-	-	-	366,000	366,000	-	366,000	-	-	-	-					0	0	0	0	0
37		97013	Site Data Historian Asset Replacement - 2019	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	488,000	-	-	488,000	488,000	-	-	-	488,000	-	-					0	0	0	0	0
38		97065	Site Data Historian Asset Replacement - 2021	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	-	488,000	488,000	488,000	-	-	-	-	-	488,000					0	0	0	0	0
39		97045	Site Exterior Lighting Upgrade - Title 24	CTT	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	100,000	100,000	-	-	-	-	200,000	200,000	100,000	100,000	-	-	-	-					0	0	0	0	0
41		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	SHE and K-Directives	Reliability and Value	Geoff Wing	-	-	-	14,571	-	-	-	-	-	14,571	14,571	14,571	-	-	-	-	-					0	0	0	0	0
42		97053	Pressure Safety Program - PI	RTO	SHE and K-Directives	Highly Capable Workforce	Nick Loebs	1	-	-	100,000	-	-	-	-	-	100,000	100,001	100,000	-	-	-	-	-					0	0	0	0	0
43		97067	OCN Lean Implementation	CTT	TBD	Highly Capable Workforce	Jim Szepesy	2	-	-	-	85,000	40,000	-	-	-	125,000	125,002	-	85,000	40,000	-	-	-					0	0	0	0	0
44		97068	OCN Resource Planning and Management Tool	CTT	TBD	Highly Capable Workforce	Melanie Yevilov / Michael Herrler	3	-	-	-	85,000	15,000	15,000	15,000	-	130,000	130,003	-	85,000	15,000	15,000	15,000	-					0	0	0	0	0
45		97043	Travel Expenses	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	10,000	10,000	-	-	-	-	20,000	20,000	10,000	10,000	-	-	-	-					0	0	0	0	0
			Capital Projects - Expense Portion					0	0	70,227	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540	7,647,987	7,718,214	2,614,569	6,258,190	18,301,282	1,500,778	6,574,208	6,291,013					0
			Total					6	0	70,227	9,611,192	11,186,555	9,813,568	9,338,500	5,474,960	2,101,540	47,526,315	47,666,776	10,191,488	14,937,599	26,587,782	9,866,278	11,708,208	8,127,013

			Improvements and Efficiencies					988,408	885,400	3,750,000	5,125,000	0	0			$10,144,001
			New Technologies					0	0	325,000	0	0	360,000			$(47,487)
			SHE and K-Directives					532,571	100,000	0	0	0	0
			Stay in Business					4,380,940	7,024,009	1,906,500	975,500	2,119,000	1,476,000
			Strategic					0	500,000	2,250,000	2,250,000	3,000,000	0
			Tech Transfers					800,000	0	0	0	0	0

## MO5_2016_Budget
		Oceanside
		MO5 2016 - CAPEX Forecast Portfolio View: Capital Projects Including Expense Portions

		No.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget	Exp + YE + MO5 (CY) Total Project Cost	MO5 2016 (Year 2016) Expense Portion	MO5 2016 (Year 2017) Expense Portion	MO5 2016 (Year 2018) Expense Portion	MO5 2016 (Year 2019) Expense Portion	MO5 2016 (Year 2020) Expense Portion	MO5 2016 (Year 2021) Expense Portion
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business			3,580,630	3,580,630	786,250	2,112,075	3,328,651	3,661,516	4,027,668	4,430,435	4,873,478	23,347,794	31,295,304	9,000	40,000	-	-	-	-		5-Year CAPEX Through 2020 / USD					2,979,100	3,328,651	3,661,516	4,027,668	4,430,435
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business			14,427,220	14,427,220	9,765,687	1,137,271	1,792,351	1,971,586	2,168,744	2,385,619	2,624,180	12,571,889	51,192,016	-	-	-	-	-	-					1,629,410	1,792,351	1,971,586	2,168,744	2,385,619
3		96204	322 MRO Racks	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	500,000	-	-	-	-	500,000	500,000	-	-	-	-	-	-					0	500,000	0	0	0
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,535,902	2,071,222	113,876	-	-	-	-	2,185,098	3,721,000	43,784	464	-	-	-	-					2,027,438	113,412	0	0	0
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg	-	-	2,701,000	686,850	-	-	-	-	-	686,850	3,387,850	-	-	-	-	-	-					686,850	0	0	0	0
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill	-	-	36,659	142,115	400,000	-	-	-	-	542,115	578,774	-	-	-	-	-	-					142,115	400,000	0	0	0
7		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	SHE and K-Directives	Reliability and Value	Geoff Wing	-	-	-	8,519	550,000	-	-	-	-	558,519	558,519	8,519	550,000	-	-	-	-					0	0	0	0	0
8		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD	-	-	-	-	-	-	-	10,000,000	-	10,000,000	10,000,000	-	-	-	-	-	-					0	0	0	0	10,000,000
9		74525	CIP Reliability and Efficiency - PI	RTO	Improvements and Efficiencies	Reliability and Value	Pierre Luong (TBD)	263,570	-	-	-	-	-	-	-	-	-	263,570	-	-	-	-	-	-					0	0	0	0	0
10		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	103,025	1,596,303	83,733	-	-	-	-	1,680,036	1,783,061	-	-	-	-	-	-					1,596,303	83,733	0	0	0
11		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.	392,072	489,325	56,153	10,000	-	-	-	-	-	10,000	947,549	-	-	-	-	-	-					10,000	0	0	0	0
12		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio	-	-	-	306,000	654,000	-	-	-	-	960,000	960,000	-	-	-	-	-	-					306,000	654,000	0	0	0
13		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	-	3,000,000	3,000,000	3,000,000	3,000,000	3,000,000	15,000,000	15,000,000	-	-	-	-	-	-					0	3,000,000	3,000,000	3,000,000	3,000,000
14		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison	-	-	-	-	730,000	-	-	-	-	730,000	730,000	-	18,000	-	-	-	-					0	712,000	0	0	0
15		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.	-	246,193	476,778	26,719	-	-	-	-	-	26,719	749,690	-	-	-	-	-	-					26,719	0	0	0	0
16		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones	489,325	-	3,555,499	7,038,875	4,885,118	-	-	-	-	11,923,993	15,968,816	37,498	51,254	-	-	-	-					7,001,377	4,833,864	0	0	0
17		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio	-	-	-	-	1,549,000	-	-	-	-	1,549,000	1,549,000	-	-	-	-	-	-					0	1,549,000	0	0	0
18		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic	-	-	860,038	422,881	-	-	-	-	-	422,881	1,282,919	-	-	-	-	-	-					422,881	0	0	0	0
19		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	246,193	-	-	-	332,000	1,592,000	-	-	-	1,924,000	2,170,193	-	22,000	-	-	-	-					0	310,000	1,592,000	0	0
20		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	355,556	444,444	-	-	-	800,000	800,000	-	22,222	27,778	-	-	-					0	333,333	416,667	0	0
21		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	603,000	4,828,000	4,828,000	500,000	-	10,759,000	10,759,000	-	75,000	-	-	-	-					0	528,000	4,828,000	4,828,000	500,000
22		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	3,000,000	6,650,000	6,000,000	3,650,000	-	19,300,000	19,300,000	-	350,000	-	-	-	-					0	2,650,000	6,650,000	6,000,000	3,650,000
23		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox	-	-	-	-	500,000	2,500,000	-	-	-	3,000,000	3,000,000	-	-	-	-	-	-					0	500,000	2,500,000	0	0
24		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin	-	-	-	1,944,000	-	-	-	-	2,340,000	4,284,000	4,284,000	-	-	-	-	-	-					1,944,000	0	0	0	0
25		74385	Media Prep Endotoxin/Bioburden Sampling	QSP	Stay in Business	Reliability and Value	Matt Forbes	-	-	-	250,000	2,750,000	-	-	-	-	3,000,000	3,000,000	-	-	-	-	-	-					250,000	2,750,000	0	0	0
26		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark	-	-	242,656	198,196	22,991	-	-	-	-	221,187	463,843	-	-	-	-	-	-					198,196	22,991	0	0	0
27		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan	-	17,731	265,047	200,613	-	-	-	-	-	200,613	483,391	(431)	-	-	-	-	-					201,044	0	0	0	0
28		96132	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	100,000	785,864	-	-	-	-	885,864	885,864	-	-	-	-	-	-					100,000	785,864	0	0	0
29		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez	-	523,433	1,984,354	4,812,654	1,602,703	-	-	-	-	6,415,357	8,923,144	1,768	-	-	-	-	-					4,810,886	1,602,703	0	0	0
30		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton	-	-	581,240	687,428	3,878	-	-	-	-	691,306	1,272,546	2,883	-	-	-	-	-					684,545	3,878	0	0	0
31		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai	-	-	-	-	750,000	4,750,000	-	-	-	5,500,000	5,500,000	-	-	500,000	-	-	-					0	750,000	4,250,000	0	0
32		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison	17,731	6,699,119	58,484,942	93,651,797	34,280,135	-	-	-	-	127,931,932	193,133,724	1,248,192	916,060	-	-	-	-					92,403,605	33,364,075	0	0	0
33		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	1,746,027	149,000	-	-	-	-	1,895,027	1,895,027	69	-	-	-	-	-					1,745,958	149,000	0	0	0
34		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	2,294,000	110,000	-	-	-	-	2,404,000	2,404,000	-	-	-	-	-	-					2,294,000	110,000	0	0	0
35		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton	-	-	-	-	200,000	900,000	900,000	935,000	-	2,935,000	2,935,000	-	200,000	-	-	-	-					0	0	900,000	900,000	935,000
36		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia	-	-	-	-	-	1,500,000	1,500,000	-	-	3,000,000	3,000,000	-	-	750,000	750,000	-	-					0	0	750,000	750,000	0
37		96205	Pressure Safety	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	3,500,000	-	-	-	-	3,500,000	3,500,000	-	-	-	-	-	-					0	3,500,000	0	0	0
38		96192	Pressure Safety Facility Mitigations	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	2,500,000	-	-	-	-	2,500,000	2,500,000	-	-	-	-	-	-					0	2,500,000	0	0	0
39		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	3,599,318	2,943,031	-	-	-	-	6,542,349	6,542,349	-	18,000	-	-	-	-					3,599,318	2,925,031	0	0	0
40		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark	523,433	-	194,621	495,036	-	-	-	-	-	495,036	1,213,090	-	-	-	-	-	-					495,036	0	0	0	0
41		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	2,500,000	3,000,000	-	-	5,500,000	5,500,000	-	-	-	-	-	-					0	0	2,500,000	3,000,000	0
42		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	-	458,000	5,000,000	-	5,458,000	5,458,000	-	-	-	-	-	-					0	0	0	458,000	5,000,000
43		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez	6,699,119	-	224,746	2,031,122	1,568,006	-	-	-	-	3,599,128	10,522,993	113,000	-	-	-	-	-					1,918,122	1,568,006	0	0	0
44		96114	QC Testing Equipment for Launch Capability and Storage Requirements	QSP	Tech Transfers	Launch and Commercial Excellence	TBD	-	-	-	-	600,000	2,600,000	1,000,000	3,000,000	-	7,200,000	7,200,000	-	-	-	-	-	-					0	600,000	2,600,000	1,000,000	3,000,000
45		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison	762,597	-	-	1,943,300	3,074,500	-	-	-	-	5,017,800	5,780,397	-	-	-	-	-	-					1,943,300	3,074,500	0	0	0
46		96109	Sci&Eng Lab Equipment for NPI and Launch Capability	QSP	Tech Transfers	Launch and Commercial Excellence	Fikret Kulenovic	-	-	-	-	600,000	2,100,000	900,000	2,400,000	-	6,000,000	6,000,000	-	-	-	-	-	-					0	600,000	2,100,000	900,000	2,400,000
47		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic	-	-	6,008,632	6,690,211	488,779	-	-	-	-	7,178,990	13,187,622	458,027	-	-	-	-	-					6,232,184	488,779	0	0	0
48		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,387,337	1,096,398	354,625	-	-	-	-	1,451,023	2,838,360	141,531	2,075	-	-	-	-					954,867	352,550	0	0	0
49		74280	Spare Hasstelloy Columns	QSP	Stay in Business	Agile		-	762,597	1,603,881	-	-	-	-	-	-	-	2,366,477	-	-	-	-	-	-					0	0	0	0	0
50		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley	-	258,306	1,420,589	157,774	-	-	-	-	-	157,774	1,836,669	-	-	-	-	-	-					157,774	0	0	0	0
51		96180	TMAC Waste System Improvements	RTO	Stay in Business	TBD	TBD	-	-	-	-	1,500,000	-	-	-	-	1,500,000	1,500,000	-	-	-	-	-	-					0	1,500,000	0	0	0
52		96191	UPSS Phase 2	RTO	Stay in Business	TBD	TBD	-	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,000	-	-	-	-	-	-					0	2,000,000	0	0	0
53		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	1,190,000	510,000	-	-	-	-	1,700,000	1,700,000	-	-	-	-	-	-					1,190,000	510,000	0	0	0
54		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez	-	-	-	-	4,859,000	-	-	-	-	4,859,000	4,859,000	-	-	-	-	-	-					0	4,859,000	0	0	0
55		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell	-	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,000	-	-	-	-	-	-					0	2,000,000	0	0	0
56		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	179,085	162,102	-	-	-	-	-	162,102	341,187	-	-	-	-	-	-					162,102	0	0	0	0
57		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen	-	1,194,816	470,099	369,680	51,636	-	-	-	-	421,316	2,086,231	-	-	-	-	-	-					369,680	51,636	0	0	0
58		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai		1,738,974	6,525,760	5,536,208	-	-	-	-	-	5,536,208	13,800,942	13,075	-	-	-	-	-					5,523,133	0	0	0	0
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	6,211,694	12,836,630	3,347,374	507,790	66,290	-	22,969,778	22,969,778	116,900	135,000	80,000	20,600	4,800	-					6,094,794	12,701,630	3,267,374	487,190	61,490
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	8,940,664	78,779,345	1,431,430	369,105	79,200	89,599,744	89,599,744	-	147,070	169,290	55,330	19,800	40,920					0	8,793,594	78,610,055	1,376,100	349,305
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	8,940,664	31,169,850	1,431,430	41,541,944	41,541,944	-	-	-	147,070	169,290	55,330					0	0	0	8,793,594	31,000,560
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	-	8,940,664	28,753,027	37,693,691	37,693,691	-	-	-	-	147,070	169,290					0	0	0	0	8,793,594
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton	-	-	-	125,000	2,275,000	-	-	-	-	2,400,000	2,400,000	-	-	-	-	-	-					125,000	2,275,000	0	0	0
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton	-	-	-	4,461,207	40,280,925	6,754,868	-	-	-	51,497,000	51,497,000	-	-	-	-	-	-					4,461,207	40,280,925	6,754,868	0	0
65			Contingency					3,800,236	-	-	-	-	-	3,800,236	3,800,236	-	-	-	-	-	-					3,800,236	0	0	0	0
66		96999	Site Management Adjustments (if any)					(3,847,202)	(10,661,762)	(1,684,667)	-	-	-	-	-	(1,684,667)	(16,193,631)	(197,487)	-	-	-	-	-					(1,487,180)	0	0	0	0
			Expense Only Projects					0	0	70,227	7,734,984	16,904,722	10,419,500	4,682,500	1,787,000	2,187,000	43,715,706	43,785,933	7,734,984	16,904,722	10,419,500	4,682,500	1,787,000	1,836,000
			Total					27,401,890	26,091,141	88,858,444	166,769,257	170,819,374	138,298,633	43,344,796	77,633,962	45,288,315	642,154,338	784,505,813	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,101,540					157,000,000

			Global Credit					18,007,850	10,551,937	4,655,456	5,121,002	5,633,102	6,196,412	6,816,053	7,497,658	35,919,683	82,487,320	46,946	0	0	0	0	0					157,000,000
			Individual Credit					11,930,494	88,898,042	141,465,347	84,460,431	33,364,444	21,586,000	28,485,000	5,340,000	314,701,223	424,923,798	2,067,914	2,225,076	1,277,778	750,000	0	0					0
			Tech Transfer					0	0	6,211,694	21,777,294	82,126,719	10,879,884	40,545,909	30,263,657	191,805,157	191,805,157	116,900	282,070	249,290	223,000	340,960	265,540
			Start-up					0	0	4,586,207	42,555,925	6,754,868	0	0	0	53,897,000	53,897,000	0	0	0	0	0	0
			Adjustment					(3,847,202)	(10,661,762)	(1,684,667)	0	0	0	0	0	(1,684,667)	(16,193,631)	(197,487)	0	0	0	0	0
			TOTAL CAPEX					26,091,141	88,788,216	155,234,038	153,914,652	127,879,133	38,662,296	75,846,962	43,101,315	594,638,396	736,919,644	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540

							$166,769,257					$9,769,257
							-					-
			Improvements and Efficiencies					432,881	7,779,000	7,000,000	4,500,000	13,000,000	3,000,000		32,711,881
			New Technologies					4,812,654	1,602,703	0	0	0	0		6,415,357
			SHE and K-Directives					3,399,652	13,870,153	18,264,444	10,828,000	4,150,000	0		50,512,249
			Stay in Business					17,958,787	23,435,160	9,033,102	10,554,412	12,751,053	9,837,658		73,732,513
			Strategic					122,045,195	82,682,336	6,754,868	0	0	0		211,482,400
			Tech Transfers					8,269,535	24,545,300	86,826,719	12,779,884	45,945,909	30,263,657		178,367,347
			Total					553,221,747

		Oceanside
		MO5 2016 - Capital Forecast - Site Business Plan View: Capital Projects Without Expense Portions

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business					2,995,532	3,295,085	3,624,593	3,987,052	4,385,758	4,824,333	23,112,353		-	-	-	-	-	-
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business					1,612,979	1,774,276	1,951,704	2,146,874	2,361,562	2,597,718	12,445,113		-	-	-	-	-	-
3		96204	322 MRO Racks	RTO	SHE and K-Directives	TBD	TBD				-	500,000	-	-	-	-	500,000		-	-	-	-	-	-
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				2,027,438	113,412	-	-	-	-	2,140,850		-	-	-	-	-	-
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg				686,850	-	-	-	-	-	686,850		-	-	-	-	-	-
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill				142,115	400,000	-	-	-	-	542,115		-	-	-	-	-	-
7		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	SHE and K-Directives	Reliability and Value	Geoff Wing				-	-	-	-	-	-	-		-	-	-	-	-	-
8		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD				-	-	-	-	10,000,000	-	10,000,000		-	-	-	-	-	-
9		74525	CIP Reliability and Efficiency - PI	RTO	Improvements and Efficiencies	Reliability and Value	Pierre Luong (TBD)				-	-	-	-	-	-	-		-	-	-	-	-	-
10		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai				1,596,303	83,733	-	-	-	-	1,680,036		-	-	-	-	-	-
11		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.				10,000	-	-	-	-	-	10,000		-	-	-	-	-	-
12		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio				306,000	654,000	-	-	-	-	960,000		-	-	-	-	-	-
13		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD				-	3,000,000	3,000,000	3,000,000	3,000,000	3,000,000	15,000,000		-	-	-	-	-	-
14		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison				-	712,000	-	-	-	-	712,000		-	-	-	-	-	-
15		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.				26,719	-	-	-	-	-	26,719		-	-	-	-	-	-
16		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones				7,001,377	4,833,864	-	-	-	-	11,835,240		-	-	-	-	-	-
17		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio				-	1,549,000	-	-	-	-	1,549,000		-	-	-	-	-	-
18		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic				422,881	-	-	-	-	-	422,881		-	-	-	-	-	-
19		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	310,000	1,592,000	-	-	-	1,902,000		-	-	-	-	-	-
20		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	333,333	416,667	-	-	-	750,000		-	-	-	-	-	-
21		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	528,000	4,828,000	4,828,000	500,000	-	10,684,000		-	-	-	-	-	-
22		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	2,650,000	6,650,000	6,000,000	3,650,000	-	18,950,000		-	-	-	-	-	-
23		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox				-	500,000	2,500,000	-	-	-	3,000,000		-	-	-	-	-	-
24		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin				1,944,000	-	-	-	-	2,340,000	4,284,000		-	-	-	-	-	-
25		74385	Media Prep Endotoxin/Bioburden Sampling	QSP	Stay in Business	Reliability and Value	Matt Forbes				250,000	2,750,000	-	-	-	-	3,000,000		-	-	-	-	-	-
26		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark				198,196	22,991	-	-	-	-	221,187		-	-	-	-	-	-
27		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan				201,044	-	-	-	-	-	201,044		-	-	-	-	-	-
28		96132	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza				100,000	785,864	-	-	-	-	885,864		-	-	-	-	-	-
29		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez				4,810,886	1,602,703	-	-	-	-	6,413,589		-	-	-	-	-	-
30		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton				684,545	3,878	-	-	-	-	688,423		-	-	-	-	-	-
31		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai				-	750,000	4,250,000	-	-	-	5,000,000		-	-	-	-	-	-
32		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison				92,403,605	33,364,075	-	-	-	-	125,767,680		-	-	-	-	-	-
33		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin				1,745,958	149,000	-	-	-	-	1,894,958		-	-	-	-	-	-
34		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark				2,294,000	110,000	-	-	-	-	2,404,000		-	-	-	-	-	-
35		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton				-	-	900,000	900,000	935,000	-	2,735,000		-	-	-	-	-	-
36		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia				-	-	750,000	750,000	-	-	1,500,000		-	-	-	-	-	-
37		96205	Pressure Safety	RTO	SHE and K-Directives	TBD	TBD				-	3,500,000	-	-	-	-	3,500,000		-	-	-	-	-	-
38		96192	Pressure Safety Facility Mitigations	RTO	SHE and K-Directives	TBD	TBD				-	2,500,000	-	-	-	-	2,500,000		-	-	-	-	-	-
39		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				3,599,318	2,925,031	-	-	-	-	6,524,349		-	-	-	-	-	-
40		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark				495,036	-	-	-	-	-	495,036		-	-	-	-	-	-
41		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	2,500,000	3,000,000	-	-	5,500,000		-	-	-	-	-	-
42		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	-	458,000	5,000,000	-	5,458,000		- / 5-Year CAPEX Through 2020 / USD	-	-	-	-	-
43		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez				1,918,122	1,568,006	-	-	-	-	3,486,128		-	-	-	-	-	-
44		96114	QC Testing Equipment for Launch Capability and Storage Requirements	QSP	Tech Transfers	Launch and Commercial Excellence	TBD				-	600,000	2,600,000	1,000,000	3,000,000	-	7,200,000		-	-	-	-	-	-
45		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison				1,943,300	3,074,500	-	-	-	-	5,017,800		-	-	-	-	-	-
46		96109	Sci&Eng Lab Equipment for NPI and Launch Capability	QSP	Tech Transfers	Launch and Commercial Excellence	Fikret Kulenovic				-	600,000	2,100,000	900,000	2,400,000	-	6,000,000		-	-	-	-	-	-
47		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic				6,232,184	488,779	-	-	-	-	6,720,963		-	-	-	-	-	-
48		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				954,867	352,550	-	-	-	-	1,307,417		-	-	-	-	-	-
49		74280	Spare Hasstelloy Columns	QSP	Stay in Business	Agile					-	-	-	-	-	-	-		-	-	-	-	-	-
50		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley				157,774	-	-	-	-	-	157,774		-	-	-	-	-	-
51		96180	TMAC Waste System Improvements	RTO	Stay in Business	TBD	TBD				-	1,500,000	-	-	-	-	1,500,000		-	-	-	-	-	-
52		96191	UPSS Phase 2	RTO	Stay in Business	TBD	TBD				-	2,000,000	-	-	-	-	2,000,000		-	-	-	-	-	-
53		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller				1,190,000	510,000	-	-	-	-	1,700,000		-	-	-	-	-	-
54		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez				-	4,859,000	-	-	-	-	4,859,000		-	-	-	-	-	-
55		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell				-	2,000,000	-	-	-	-	2,000,000		-	-	-	-	-	-
56		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai				162,102	-	-	-	-	-	162,102		-	-	-	-	-	-
57		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen				369,680	51,636	-	-	-	-	421,316		-	-	-	-	-	-
58		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai				5,523,133	-	-	-	-	-	5,523,133		-	-	-	-	-	-
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				6,094,794	12,701,630	3,267,374	487,190	61,490	-	22,612,478		-	-	-	-	-	-
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	8,793,594	78,610,055	1,376,100	349,305	38,280	89,167,334		-	-	-	-	-	-
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	8,793,594	31,000,560	1,376,100	41,170,254		-	-	-	-	-	-
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	-	8,793,594	28,583,737	37,377,331		-	-	-	-	-	-
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton				125,000	2,275,000	-	-	-	-	2,400,000		-	-	-	-	-	-
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton				4,461,207	40,280,925	6,754,868	-	-	-	51,497,000		-	-	-	-	-	-
65			Contingency					3,800,236	-	-	-	-	-	3,800,236		-	-	-	-	-	-
66		96999	Site Management Adjustments (if any)					(1,487,180)	-	-	-	-	-	(1,487,180)		-	-	-	-	-	-
			Total					0	0	0	157,000,000	151,355,865	126,295,261	37,626,811	75,437,268	42,760,168	590,475,374	0	0	0	0	0	0	0

			Improvements and Efficiencies					432,881	7,761,000	6,250,000	3,750,000	13,000,000	3,000,000		31,193,881
			New Technologies					4,810,886	1,602,703	0	0	0	0		6,413,589
			SHE and K-Directives					3,391,564	12,850,930	17,736,667	10,828,000	4,150,000	0		48,957,161
			Stay in Business					17,911,772	23,165,519	8,976,297	10,491,927	12,682,319	9,762,051		73,227,834
			Strategic					120,100,206	81,712,483	6,754,868	0	0	0		208,567,557
			Tech Transfers					8,039,635	24,263,230	86,577,429	12,556,884	45,604,949	29,998,117		177,042,127
			Total					545,402,149

		Oceanside
		MO5 2016 - Expense Forecast - Expense Only and Expense Portions of Capital Projects to Identify Opportunity to Fund Expense Only Projects

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget	Exp + YE + MO5 (CY) Total Project Expense	MO5 2016 (Year 2016) Expense Portion	MO5 2016 (Year 2017) Expense Portion	MO5 2016 (Year 2018) Expense Portion	MO5 2016 (Year 2019) Expense Portion	MO5 2016 (Year 2020) Expense Portion	MO5 2016 (Year 2021) Expense Portion
1		97048	Arc Flash Prevention	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	319,456	-	-	-	-	-	319,456	319,456	319,456	-	-	-	-	-					0	0	0	0	0
2		97007	Automation System Lifecycle MCS Upgrade	QSP	Improvements and Efficiencies	Reliability and Value	Myles Sumlin	-	-	-	295,169	-	-	-	-	-	295,169	295,169	295,169	-	-	-	-	-					0	0	0	0	0
3		97059	B311 & B321 Gowning Room Modifications	RTO	Stay in Business	Reliability and Value	TBD	-	-	-	107,000	-	-	-	-	-	107,000	107,000	107,000	-	-	-	-	-					0	0	0	0	0
4		97057	Conference Room 315 Expansion	TBD	Improvements and Efficiencies	Exceptional Culture	N/A	-	-	-	108,000	192,000	-	-	-	-	300,000	300,000	108,000	192,000	-	-	-	-					0	0	0	0	0
5		97042	CRB Project Budget Estimating	QSP	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	250,400	-	-	-	-	-	250,400	250,400	250,400	-	-	-	-	-					0	0	0	0	0
6		97054	HVAC Retro Commissioning	CTT	Stay in Business	Reliability and Value		-	-	-	-	113,000	44,000	-	-	-	157,000	157,000	-	113,000	44,000	-	-	-					0	0	0	0	0
7		82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	CTT	Stay in Business	Reliability and Value	Jonathan Clark	-	-	70,227	933,708	781,722	-	-	-	-	1,715,430	1,785,657	933,708	781,722	-	-	-	-					0	0	0	0	0
8		97044	IMPACT Support	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	8,000	-	-	-	-	-	8,000	8,000	8,000	-	-	-	-	-					0	0	0	0	0
9		98026	Launch Capability Program (LCP)	QSP	Tech Transfers	Launch and Commercial Excellence	TBD	-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
10		97001	Lunches	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	4,000	-	-	-	-	-	4,000	4,000	4,000	-	-	-	-	-					0	0	0	0	0
11		97015	MCS Backup System Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	390,000	-	-	-	-	390,000	390,000	-	390,000	-	-	-	-					0	0	0	0	0
12		97016	MCS Backup System Asset Replacement - 2020	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	439,000	-	439,000	439,000	-	-	-	-	439,000	-					0	0	0	0	0
13		97031	MCS Data Analytics Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	TBD	-	-	-	-	325,000	-	-	-	-	325,000	325,000	-	325,000	-	-	-	-					0	0	0	0	0
14		97032	MCS Data Analytics Asset Replacement - 2020	QSP	Stay in Business	Reliable	TBD	-	-	-	-	-	-	-	360,000	-	360,000	360,000	-	-	-	-	360,000	-					0	0	0	0	0
15		97005	MCS Peripheral Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	312,000	-	-	-	-	312,000	312,000	-	312,000	-	-	-	-					0	0	0	0	0
16		97006	MCS Peripheral Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	332,000	-	-	332,000	332,000	-	-	-	332,000	-	-					0	0	0	0	0
17		97063	MCS Peripheral Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	351,000	351,000	351,000	-	-	-	-	-	-					0	0	0	0	0
18		97009	MES Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	400,000	575,000	-	-	-	975,000	975,000	-	400,000	575,000	-	-	-					0	0	0	0	0
19		97010	MES Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	500,000	525,000	1,025,000	1,025,000	-	-	-	-	500,000	525,000					0	0	0	0	0
20		97003	MFG Systems Integration Improvement Phase 1 - 2015	CTT	Improvements and Efficiencies	Reliability and Value	Eric Davis	-	-	-	443,000	-	-	-	-	-	443,000	443,000	443,000	-	-	-	-	-					0	0	0	0	0
21		97030	MFG Systems Integration Improvement Phase 3 - 2017	QSP	Improvements and Efficiencies	Fit for Purpose	TBD	-	-	-	-	1,625,000	-	-	-	-	1,625,000	1,625,000	-	1,625,000	-	-	-	-					0	0	0	0	0
22		97002	Office Supplies inc. Laptops	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	45,000	-	-	-	-	-	45,000	45,000	45,000	-	-	-	-	-					0	0	0	0	0
23		97058	Parking Pavement Repair	CTT	Stay in Business	Reliability and Value	Sumner Tison	-	-	-	245,040	-	-	-	-	-	245,040	245,040	245,040	-	-	-	-	-					0	0	0	0	0
24		97008	PCS Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	487,500	487,500	-	-	975,000	975,000	-	-	487,500	487,500	-	-					0	0	0	0	0
25		97064	PCS Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	463,000	463,000	463,000	-	-	-	-	-	463,000					0	0	0	0	0
26			PCS Asset Replacement Depreciation Write-Off	TBD	TBD			-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
27		97066	PCS Automated Documentation Asset Replacement - 2021	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	-	-	-	360,000	360,000	360,000	-	-	-	-	-	360,000					0	0	0	0	0
28		97033	PCS Automated Documentation Upgrade	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	325,000	-	-	-	325,000	325,000	-	-	325,000	-	-	-					0	0	0	0	0
29		97038	PCS Functional Specification Development Project (CAPA 960297)	RTO	Strategic	Reliability and Value	Sarah Maruccia	-	-	-	-	4,750,000	3,250,000	-	-	-	8,000,000	8,000,000	-	4,750,000	3,250,000	-	-	-					0	0	0	0	0
30		97039	PCS Remediation for EBR Review by Exception - PI	QSP	Improvements and Efficiencies	Highly Capable Workforce	Malou Jacinto / Stephanie Huntress	-	-	-	-	250,000	2,250,000	3,375,000	-	-	5,875,000	5,875,000	-	250,000	2,250,000	3,375,000	-	-					0	0	0	0	0
31		97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	488,000	-	-	-	488,000	488,000	-	-	488,000	-	-	-					0	0	0	0	0
32		97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	488,000	-	488,000	488,000	-	-	-	-	488,000	-					0	0	0	0	0
33		TBD	Piping Corrosion	TBD	Stay in Business	Reliability and Value	TBD	-	-	-	3,091,211	3,000,000	3,000,000	-	-	-	9,091,211	9,091,211	3,091,211	3,000,000	3,000,000	-	-	-					0	0	0	0	0
34		97053	Pressure Safety Program - PI Phase	TBD	SHE and K-Directives	TBD	TBD	-	-	-	100,000	-	-	-	-	-	100,000	100,000	100,000	-	-	-	-	-					0	0	0	0	0
35		97060	QC Gas Cabinet Removal	QSP	TBD	TBD	Joe Molon	-	-	-	75,000	-	-	-	-	-	75,000	75,000	75,000	-	-	-	-	-					0	0	0	0	0
36		97037	Recipe Reconfiguration Alignment for Operating Systems	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Marco Baca	-	-	-	-	3,750,000	-	-	-	-	3,750,000	3,750,000	-	3,750,000	-	-	-	-					0	0	0	0	0
37		97012	Site Data Historian Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	366,000	-	-	-	-	366,000	366,000	-	366,000	-	-	-	-					0	0	0	0	0
38		97013	Site Data Historian Asset Replacement - 2019	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	488,000	-	-	488,000	488,000	-	-	-	488,000	-	-					0	0	0	0	0
39		97065	Site Data Historian Asset Replacement - 2021	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	-	488,000	488,000	488,000	-	-	-	-	-	488,000					0	0	0	0	0
40		97045	Site Exterior Lighting Upgrade - Title 24	CTT	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	100,000	100,000	-	-	-	-	200,000	200,000	100,000	100,000	-	-	-	-					0	0	0	0	0
41		97061	Tangential Flow Filtration Cassettes Management	RTO	Improvements and Efficiencies	Reliability and Value	Stephanie Huntress	-	-	-	-	550,000	-	-	-	-	550,000	550,000	-	550,000	-	-	-	-					0	0	0	0	0
42		97043	Travel Expenses	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	10,000	-	-	-	-	-	10,000	10,000	10,000	-	-	-	-	-					0	0	0	0	0
			Capital Projects - Expense Portion					0	0	70,227	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540	7,647,987	7,718,214	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540					0
			Total					0	0	70,227	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,452,540	51,363,693	51,504,148	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,101,540

			Improvements and Efficiencies					1,096,569	6,367,000	2,250,000	3,375,000	0	0			$9,769,257
			New Technologies					0	0	325,000	0	0	360,000			$-
			SHE and K-Directives					519,456	100,000	0	0	0	0
			Stay in Business					4,443,959	5,687,722	4,594,500	1,307,500	1,787,000	1,827,000
			Strategic					0	4,750,000	3,250,000	0	0	0
			Tech Transfers					800,000	0	0	0	0	0

## T0_2016_Budget
		Oceanside
		T0 2016 - CAPEX Forecast

		Nro.	Project Name	Driver	Program	SME	Expenditure YE 2013	T3 2015 / (2014 Preview)	T0 2016 / (2015 Preview)	T0 2016 / (2016 Preview)	T0 2016 / (2017 Preview)	T0 2016 / (2018 Preview)	T0 2016 / (2019 Preview)	T0 2016 / (2020 Preview)	T0 2016 / (2021 Preview)	TOTAL T0 Budget	Exp + YE + T0 (CY) Total Project Cost	T0 2016 (Year 2015) Expense Portion	T0 2016 (Year 2016) Expense Portion	T0 2016 (Year 2017) Expense Portion	T0 2016 (Year 2018) Expense Portion	T0 2016 (Year 2019) Expense Portion	T0 2016 (Year 2020) Expense Portion
1		6DM	GNE Oceanside Prod Ops				3,580,630	372,740	750,350	3,023,010	3,325,311	3,657,842	4,023,627	4,425,989	4,868,588	19,206,130	23,159,500	0		0	0	0	0
2		90024	NIMO Small Projects - Misc				14,427,220	1,962,568	1,542,507	1,627,775	1,790,552	1,969,607	2,166,568	2,383,225	2,621,548	11,480,235	27,870,023	184,000	42,487	0	0	0	0
3		74455	3rd HCCF Vessel	QSP	Reliable	Mark Jones / Paul Coon		0	1,089,507	2,356,482	267,816	0	0	0	0	3,713,805	3,713,805	10,113	27,591	0	0	0	0
4		74489	4040 Avenida Conference Center Acquisition	QSP	Agile	Kara Swedberg		0	2,700,000	688,000	0	0	0	0	0	3,388,000	3,388,000	0	0	0	0	0	0
5		74416	Asphyxiant Gas Remediation	RTO	Reliable	Gary Merrill		0	33,392	99,000	0	0	0	0	0	132,392	132,392	0	0	0	0	0	0
6		96160	B331 HVAC Fire Code Compliance	RTO	TBD	Marcus Espinoza		0	0	0	1,000,000	0	0	0	0	1,000,000	1,000,000	0	0	0	0	0	0
7		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	Reliable	Geoff Wing		0	0	12,000	550,000	550,000	0	0	0	1,112,000	1,112,000	0	0	0	0	0	0
8		96113	Bulk Product Storage -20/-40	QSP	Launch Facility	TBD		0	0	0	0	0	0	10,000,000	0	10,000,000	10,000,000	0	0	0	0	0	0
9		74525	CIP Reliability and Efficiency - PI	RTO	Reliable	Pierre Luong	263,570	0	0	400,000	1,000,000	2,000,000	1,000,000	0	0	4,400,000	4,663,570	0	400,000	0	0	0	0
10		74406	Corrosive Chemical Compliance	RTO	Reliable	Tim Lai		0	98,000	1,812,000	0	0	0	0	0	1,910,000	1,910,000	0	0	0	0	0	0
11		74368	Dev/Val Automation Capacity Expansion	QSP	Agile	Matt Hunt / Ravi M.	392,072	576,000	56,000	10,000	0	0	0	0	0	66,000	1,034,072	0	0	0	0	0	0
12		74513	Electric Vehicle Charging Stations	CTT	Agile	Sumner Tison		0	0	0	730,000	0	0	0	0	730,000	730,000	0	0	18,000	0	0	0
13		73367	FS & DS Automation Integration	CTT	Reliable	Pat Sraubol / Ravi M.		246,193	477,000	10,000	0	0	0	0	0	487,000	733,193	0	0	0	0	0	0
14		74119	Harvest Upgrade (New Centrifuge)	QSP	Launch Facility	Ken Hamilton Mark Jones	489,325	0	4,533,622	7,261,919	1,114,422	0	0	0	0	12,909,963	13,399,288	42,076	28,727	51,254	0	0	0
15		74435	Hastelloy Chromatography Column (160cm)	QSP	Reliable	Bahar Dahi / Juan Pacio		0	0	1,549,000	0	0	0	0	0	1,549,000	1,549,000	0	0	0	0	0	0
16		74490	Hyfish Material Screening Operation	QSP	Reliable	Fikret Kulenovic		0	782,000	460,000	0	0	0	0	0	1,242,000	1,242,000	0	0	0	0	0	0
17		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	ACCR	Geoff Wing	246,193	0	90,000	1,924,000	0	0	0	0	0	2,014,000	2,260,193	0	22,000	22,000	0	0	0
18		74512	K6 Program - Project 2 - B381 Compliance	CTT	ACCR	Geoff Wing		0	0	0	700,000	0	0	0	0	700,000	700,000	0	0	0	22,222	27,778	0
19		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	ACCR	Geoff Wing		0	0	0	603,000	4,828,000	4,828,000	500,000	0	10,759,000	10,759,000	0	0	75,000	0	0	0
20		74432	K6 Program - Project 4 - Replace Chillers	CTT	ACCR	Geoff Wing		0	0	0	3,000,000	6,650,000	6,000,000	3,650,000	0	19,300,000	19,300,000	0	0	0	350,000	0	0
21		96112	Maintenance Ops Shop Buildout	QSP	Agile	Hayden Knox		0	0	0	1,000,000	2,000,000	0	0	0	3,000,000	3,000,000	0	0	0	0	0	0
22		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Reliable	Myles Sumlin		0	7,000	1,944,000	0	0	0	0	0	1,951,000	1,951,000	0	0	0	0	0	0
23		74385	Media Prep Endotoxin/Bioburden Sampling	QSP	Reliable	Matt Forbes		0	0	500,000	2,500,000	0	0	0	0	3,000,000	3,000,000	0	0	0	0	0	0
24		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Reliable	Jonathan Clark		0	311,000	350,000	0	0	0	0	0	661,000	661,000	0	0	0	0	0	0
25		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	Reliable	Dick Sloan		17,730	262,000	330,000	0	0	0	0	0	592,000	609,730	0	0	0	0	0	0
26		74279	New Media Technology - HTST / Adventitious	RTO	Reliable	Will Jimenez		597,000	2,074,000	5,444,000	1,588,000	0	0	0	0	9,106,000	9,703,000	2,000	0	37,670	0	0	0
27		74453	NPI Pool Tanks	QSP	Launch Facility	Ken Hamilton		0	545,400	463,721	0	0	0	0	0	1,009,121	1,009,121	0	10,802	0	0	0	0
28		74371	Odor Treatment	CTT	ACCR	Tim Lai		0	100,000	0	1,000,000	4,500,000	0	0	0	5,600,000	5,600,000	0	0	0	0	500,000	0
29		74268	P2 Downstream Processing Expansion	QSP	Launch Facility	Mark Jones / Dirk Ellison	17,731	6,699,119	49,460,327	105,476,146	32,420,345	0	0	0	0	187,356,818	194,073,668	3,345,844	825,644	916,060	0	0	0
30		74510	PCS Asset Replacement - 2016	QSP	Reliable	Myles Sumlin		0	0	1,869,000	0	0	0	0	0	1,869,000	1,869,000	0	0	0	0	0	0
31		74486	PCS Controller Cabinet Asset Replacement	RTO	Reliable	Jonathan Clark		0	0	2,404,000	1,546,000	2,092,000	0	0	0	6,042,000	6,042,000	0	0	0	0	0	0
32		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Reliable	Hieu Ton		0	0	0	958,000	958,000	935,000	0	0	2,851,000	2,851,000	0	0	200,000	0	0	0
33		96116	PCS Process Support Equipment Integration	QSP	Agile	Sarah Maruccia		0	0	0	1,500,000	1,500,000	0	0	0	3,000,000	3,000,000	0	0	0	750,000	750,000	0
34		74487	Process VSD and SOV Asset Replacement	QSP	Reliable	Jonathan Clark		0	0	4,549,000	7,426,000	5,447,000	0	0	0	17,422,000	17,422,000	0	7,000	18,000	0	0	0
35		74426	Process VSD and SOV Replacement - 2015	QSP	Reliable	Jonathan Clark	523,433	0	203,000	489,000	0	0	0	0	0	692,000	1,215,433	0	0	0	0	0	0
36		74418	QC Lab Reconfiguration & Equipment	QSP	Reliable	Amanda Gutierrez	6,699,119	0	213,000	3,675,000	0	0	0	0	0	3,888,000	10,587,119	0	0	0	0	0	0
37		96114	QC Testing Equipment for Launch Capability and Storage Requirements	QSP	Launch Facility	TBD		0	0	0	600,000	2,600,000	1,000,000	3,000,000	0	7,200,000	7,200,000	0	0	0	0	0	0
38		96109	Sci&Eng Lab Equipment for NPI and Launch Capability	QSP	Launch Facility	Fikret Kulenovic		0	0	0	600,000	2,100,000	900,000	2,400,000	0	6,000,000	6,000,000	0	0	0	0	0	0
39		74382	Sci&Eng Lab Mods and Equipment	QSP	Launch Facility	Fikret Kulenovic		0	5,272,000	7,401,000	0	0	0	0	0	12,673,000	12,673,000	2,000	393,000	0	0	0	0
40		74454	Seed Lab (20L Bioreactor)	QSP	Reliable	Mark Jones / Paul Coon		0	762,246	949,763	187,366	0	0	0	0	1,899,375	1,899,375	7,076	10,802	2,075	0	0	0
41		74511	Steaming Remediation - QR018 Compliance	QSP	Reliable	Anastasia Gandrik / Sumner Tison	762,597	0	0	2,502,000	2,471,000	0	0	0	0	4,973,000	5,735,597	0	45,000	0	0	0	0
42		73356	Supplemental BDU Sampling	CTT	ACCR	Paul Crowley		258,306	1,474,665	200,000	0	0	0	0	0	1,674,665	1,932,971	0	0	0	0	0	0
43		96105	TMAC Tenderizer	QSP	Reliable	Pierre Luong		0	0	0	575,000	0	0	0	0	575,000	575,000	0	0	0	0	0	0
44		74526	Utility and Process Safety System	RTO	Reliable	Pierre Luong		0	0	1,700,000	0	0	0	0	0	1,700,000	1,700,000	0	0	0	0	0	0
45		74527	Vessel 1020 Upgrade	QSP	Reliable	Will Jimenez		0	0	2,646,000	11,013,000	0	0	0	0	13,659,000	13,659,000	0	0	0	100,000	0	0
46		96165	WAN Link Redundancy	TBD	TBD	TBD		0	0	0	2,000,000	0	0	0	0	2,000,000	2,000,000	0	0	0	0	0	0
47		74392	Water Reclaim System	CTT	ACCR	Tim Lai		0	180,000	676,000	800,000	0	0	0	0	1,656,000	1,656,000	0	0	0	0	0	0
48		74302	Waterpooling Remediation	RTO	Reliable	Ken Hmilton / Tim Chen		1,194,816	510,000	435,000	0	0	0	0	0	945,000	2,139,816	0	0	0	0	0	0
49		74373	WFI Generation and Storage System / CUB Expansion	QSP	Reliable	Tim Lai	1,738,974	1,738,974	6,255,222	5,354,500	0	0	0	0	0	11,609,722	15,087,670	93,208	12,500	0	0	0	0
50		74491	Etro Tech Transfer	QSP	Launch Facility	Semsi Ensari		0	0	7,215,007	11,873,438	2,998,140	294,120	68,160	0	22,448,865	22,448,865	0	200,000	3,771,061	80,000	20,600	4,800
51		96124	TT Per Tech Transfer	QSP	Launch Facility	Semsi Ensari		0	0	0	8,050,000	8,450,000	0	0	0	16,500,000	16,500,000	0	0	147,070	16,999,060	55,330	19,800
52		96125	Cren Tech Transfer	QSP	Launch Facility	Semsi Ensari		0	0	0	0	8,050,000	8,450,000	0	0	16,500,000	16,500,000	0	0	0	0	147,070	6,402,538
53		96126	IL22 Tech Transfer	QSP	Launch Facility	Semsi Ensari		0	0	0	0	0	8,050,000	8,450,000	0	16,500,000	16,500,000	0	0	0	0	0	147,070
54		74127	Harvest Modifications Start-up	QSP	Launch Facility	Ken Hamilton		0	0	125,000	2,275,000	0	0	0	0	2,400,000	2,400,000	0	0	0	0	0	0
55		74277	P2 DPE Start-Up	QSP	Launch Facility	Dirk Ellison/ Ken Hamilton		0	0	8,000,000	44,445,136	0	0	0	0	52,445,136	52,445,136	0	0	0	0	0	0
56		96999	Site Management Adjustments (if any)	0					(5,913,298)	0	0	0	0	0	(5,913,298)	(5,913,298)	0	235,000	0	0	0	0
			Total				29,140,864	13,663,446	79,782,238	180,018,025	148,909,387	60,350,590	37,647,315	34,877,374	7,490,136	541,584,928	584,389,238	3,686,317	2,260,553	5,258,190	18,301,282	1,500,778	6,574,208

			Global Credit					2,335,308	2,292,857	4,650,785	5,115,864	5,627,450	6,190,195	6,809,214	7,490,136	30,686,365	51,029,523	184,000	42,487	0	0	0	0
			Individual Credit					11,328,138	77,489,381	165,940,531	76,149,949	35,225,000	14,663,000	9,550,000	0	379,017,861	401,479,013	3,502,317	1,783,066	1,340,059	1,222,222	1,277,778	0
			Tech Transfer					0	7,215,007	19,923,438	19,498,140	16,794,120	8,518,160	0	71,948,865	71,948,865	0	200,000	3,918,131	17,079,060	223,000	6,574,208
			Start-up					0	0	8,125,000	46,720,136	0	0	0	0	54,845,136	54,845,136	0	0	0	0	0	0
			Adjustment					0	0	(5,913,298)	0	0	0	0	0	(5,913,298)	(5,913,298)	0	235,000	0	0	0	0
			TOTAL CAPEX					13,663,446	79,782,238	180,018,025	147,909,387	60,350,590	37,647,315	24,877,374	7,490,136	530,584,928	573,389,238	3,686,317	2,260,553	5,258,190	18,301,282	1,500,778	6,574,208

## MO5_2016_Variance_IMPACT
				Expense	New Project
				Delayed	Combined
		Oceanside					Canceled/On Hold
		T0 2016 - Variance Analysis

				2015 Preview				2016 Preview (Capital Only)					2015-2020 (2015 Expenditure + Budget)					Expense Portion			Expense Portion					2015				2016

		Nro.	Project Name	Expenditure YE 2013		T0 2016	MO5 2016	Variance		MO5 2016	T3 2016	Variance		T0 2015 / (2016 Preview)	T0 2015 / (2017 Preview)	T0 2015 / (2018 Preview)	T0 2015 / (2019 Preview)	T0 2015 / (2020 Preview)		Exp YE + T0 (CY) Total Project Cost	Exp YE + T3 (CY) Total Project Cost	Variance	Comments		T0 2014 / (Year 2014) Expense Portion	T3 2015 (Year 2014) Expense Portion	Variance		T3 2015 / (Year 2015) Expense Portion	T0 2015 / (Year 2015) Expense Portion	Variance	MO5 2016 / (Year 2016) Expense Portion	T3 2016 / (Year 2016) Expense Portion	Variance		CHANGE 2015	CHANGE 5-Y-O	PPE / Forecast / 2014		T3 2014 (Y 2014)	T3 2014 (Y 2015)	T3 2014 (Y 2016)	T3 2014 (Y 2017)	T3 2014 (Y 2018)	T3 2014 (Y 2019)		PPE / Forecast / 2014	PPE / Forecast / 2015	PPE / Forecast / 2016	PPE / Forecast / 2017	PPE / Forecast / 2018	PPE / Forecast / 2019	UP	DOWN		CAPEX CHANGE 2016	UP	DOWN		EXPENSE CHANGE 2016	UP	DOWN
1		6DM	GNE Oceanside Prod Ops	3,580,630		1,019,880	#REF!	#REF!		2,995,532	3,478,469	482,937		1,230,000	1,270,000	1,305,000	1,345,000	1,385,000		11,508,250	#REF!	#REF!					28,850	28,850	46,946	51,487	4,541		Estimate Increase (2016)	Estimate Decrease	#REF!		372,740	995,000	1,230,000	1,270,000	1,305,000	1,345,000		372,740	995,000	1,230,000	1,270,000	1,305,000	1,345,000	#REF!	#REF!		Estimate Increase (2016)	482,937	0		Estimate Increase (2016)	4,541	0
2		90024	NIMO Small Projects - Misc	14,427,220		2,422,051	#REF!	#REF!		1,612,979	1,873,022	260,043		5,790,749	5,785,440	5,786,069	5,805,000	5,979,000		47,958,097	#REF!	#REF!					29,495	22,791	(6,704)			0		Estimate Increase (2016)	Estimate Increase	#REF!		1,962,568	4,992,933	5,790,749	5,785,440	5,786,069	5,805,000		1,762,568	4,605,933	5,790,749	5,785,440	5,786,069	5,805,000	#REF!	#REF!		Estimate Increase (2016)	260,043	0			0	0
3		74455	3rd HCCF Vessel				#REF!	#REF!		2,027,438	1,669,681	(357,757)					3,721,999	#REF!	#REF!					27,591	34,808	7,217	43,784	34,808	(8,976)		Cashflow Timing - Down (2016)	New Project	#REF!		765,000					760,000					#REF!	#REF!		Cashflow Timing - Down (2016)	0	(357,757)		Cashflow Timing - Down (2016)	0	(8,976)
4		74489	4040 Avenida Conference Center Acquisition				#REF!	#REF!		686,850	685,700	(1,150)					2,700,000	#REF!	#REF!					0	0		0	0	0		Estimate Decrease (2016)					#REF!	#REF!		Estimate Decrease (2016)	0	(1,150)			0	0
6		74416	Asphyxiant Gas Remediation				#REF!	#REF!		142,115	126,295	(15,820)					555,000	#REF!	#REF!					0	0	0	0	0	0		Estimate Decrease (2016)	New Project	#REF!		3,190,000					3,165,000					#REF!	#REF!		Estimate Decrease (2016)	0	(15,820)			0	0
7		74435	Hastelloy Chromatography Column (160cm)			378,000	#REF!	#REF!		0	400,000	400,000		0	0	0	0	0		1,154,102	#REF!	#REF!	New					0	0	0	0	0	0		Cashflow Timing - Up (2016)		#REF!		100,000					98,000					#REF!	#REF!		New Project	400,000	0			0	0
8		74406	Corrosive Chemical Compliance			1,503,000	#REF!	#REF!		1,596,303	1,724,239	127,936		0	0	0	0	0		1,953,000	#REF!	#REF!	New					0	0	0	0	0	0		Cashflow Timing - Up (2016)		#REF!		1,641,502					1,591,502					#REF!	#REF!		Cashflow Timing - Up (2016)	127,936	0			0	0
9		74368	Dev/Val Automation Capacity Expansion				#REF!	#REF!		10,000	10,000	0		0	0	0	0	0		69,000	#REF!	#REF!	New					0	0	0	0	0	0			Estimate Increase	#REF!		1,641,502					1,591,502					#REF!	#REF!			0	0			0	0
10		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)					306,000	306,000	0					0	0	0	0	0	0					0	0			0	0
11		73367	FS & DS Automation Integration			670,000	#REF!	#REF!		26,719	26,719	0		0	0	0	0	0		602,000	#REF!	#REF!					0	0	0	0	0	0				#REF!		1,100,000	2,150,000	6,050,000					1,080,000	2,030,000	6,015,000				#REF!	#REF!			0	0			0	0
12		74119	Harvest Upgrade (New Centrifuge)			12,808,000	#REF!	#REF!		7,001,377	4,614,221	(2,387,156)		0	0	0	0	0		15,487,855	#REF!	#REF!	On Hold					28,727	21,631	(7,096)	37,498	21,631	(15,867)		Cashflow Timing - Down (2016)	Scope Reduction	#REF!			2,344,000	937,600					2,344,000	937,600				#REF!	#REF!		Cashflow Timing - Down (2016)	0	(2,387,156)		Cashflow Timing - Down (2016)	0	(15,867)
13		74490	Hyfish Material Screening Operation				#REF!	#REF!		422,881	601,445	178,564					1,468,000	#REF!	#REF!					0	0	0	0	0	0		Cashflow Timing - Up (2016)					Cashflow Timing - Up (2016)	178,564	0			0	0
14		74427	MCS Network Infrastructure Asset Replacement - 2016				#REF!	#REF!		1,944,000	1,466,000	(478,000)		0	0	0	0	0		1,950,000	#REF!	#REF!					0	0	0	0	0	0		Estimate Decrease (2016)		#REF!			950,000					950,000					#REF!	#REF!		Estimate Decrease (2016)	0	(478,000)			0	0
15		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement			730,000	#REF!	#REF!		198,196	204,573	6,377		0	0	0	0	0		662,000	#REF!	#REF!					0	0	0	0	0	0		Cashflow Timing - Up (2016)		#REF!			675,000	675,000					675,000	675,000				#REF!	#REF!		Cashflow Timing - Up (2016)	6,377	0			0	0
16		74404	Mezzanine Lift Media Prep: Phase 1B			658,000	#REF!	#REF!		201,044	270,440	69,396		8,026,000	399,000	0	0	0		617,000	#REF!	#REF!	1					0	(431)	(431)	(431)	(431)	0		Cashflow Timing - Up (2016)	Estimate Decrease	#REF!					200,000	1,800,000	1,000,000					200,000	1,800,000	1,000,000	#REF!	#REF!		Cashflow Timing - Up (2016)	69,396	0			0	0
17		74279	New Media Technology - HTST / Adventitious			2,694,000	#REF!	#REF!		4,810,886	4,859,034	48,148		0	0	0	0	0		8,969,000	#REF!	#REF!					0	88,096	88,096	1,768	88,096	86,328		Cashflow Timing - Up (2016)	Estimate Increase	#REF!				300,000	200,000					300,000	200,000			#REF!	#REF!		Cashflow Timing - Up (2016)	48,148	0		Cashflow Timing - Up (2016)	86,328	0
18		74453	NPI Pool Tanks				#REF!	#REF!		684,545	601,771	(82,774)					1,194,400	#REF!	#REF!					10,802	2,484	(8,318)	2,883	2,484	(399)		Cashflow Timing - Down (2016)	New Project	#REF!				100,000	200,000	200,000					100,000	200,000	200,000		#REF!	#REF!		Cashflow Timing - Down (2016)	0	(82,774)		Cashflow Timing - Down (2016)	0	(399)
19		74268	P2 Downstream Processing Expansion			64,079,888	#REF!	#REF!		92,403,605	91,862,606	(540,999)		528,000	4,828,000	4,828,000	500,000	0		187,347,889	#REF!	#REF!					825,644	1,766,871	941,227	1,248,192	1,766,871	518,679		Cashflow Timing - Down (2016)		#REF!				600,000	400,000					600,000	400,000			#REF!	#REF!		Cashflow Timing - Down (2016)	0	(540,999)		Estimate Increase (2016)	518,679	0
20		74426	Process VSD and SOV Replacement - 2015			2,000,000	#REF!	#REF!		495,036	589,735	94,699		1,950,000	0	0	0	0		707,000	#REF!	#REF!	New					0	0	0	0	0	0		Estimate Increase (2016)	Scope Reduction	#REF!		317000	2,849,723					317000	2,849,723					#REF!	#REF!		Estimate Increase (2016)	94,699	0			0	0
21		74487	Process VSD and SOV Asset Replacement				#REF!	#REF!		3,599,318	3,599,797	479					7,544,313	#REF!	#REF!					7,000	0	(7,000)	0	0	0		Cashflow Timing - Up (2016)	New Project					#REF!	#REF!		Cashflow Timing - Up (2016)	479	0			0	0
22		74418	QC Lab Reconfiguration & Equipment			4,159,728	#REF!	#REF!		1,918,122	3,160,674	1,242,552		0	0	0	0	0		4,161,000	#REF!	#REF!	Expense					0	114,000	114,000	113,000	114,000	1,000		Cashflow Timing - Up (2016)					#REF!	#REF!		Cashflow Timing - Up (2016)	1,242,552	0		Estimate Increase (2016)	1,000	0
23		74382	Sci&Eng Lab Mods and Equipment			9,479,000	#REF!	#REF!		6,232,184	7,414,885	1,182,701		0	0	0	0	0		12,721,000	#REF!	#REF!	From Indv. To Global					393,000	195,338	(197,662)	458,027	195,338	(262,689)		Cashflow Timing - Up (2016)					#REF!	#REF!		Cashflow Timing - Up (2016)	1,182,701	0			0	(262,689)
24		74454	Seed Lab (20L Bioreactor)				#REF!	#REF!		954,867	912,870	(41,997)					2,603,998	#REF!	#REF!					10,802	97,323	86,521	141,531	97,323	(44,208)		Estimate Decrease (2016)	New Project					#REF!	#REF!		Estimate Decrease (2016)	0	(41,997)			0	(44,208)
25		73356	Supplemental BDU Sampling			2,369,000	#REF!	#REF!		157,774	157,774	0		0	0	0	0	0		2,064,000	#REF!	#REF!					0	0	0	0	0	0			Estimate Decrease					#REF!	#REF!			0	0			0	0
26		74392	Water Reclaim System			1,228,000	#REF!	#REF!		162,102	143,846	(18,256)		1,755,000	0	0	0	0		1,680,000	#REF!	#REF!					0	0	0	0	0	0		Scope Reduction					#REF!	#REF!		Scope Reduction	0	(18,256)			0	0
27		74302	Waterpooling Remediation			1,904,001	#REF!	#REF!		369,680	369,680	0		958,000	935,000	0	0	0		1,866,000	#REF!	#REF!	New					0	0	0	0	0	0			Estimate Decrease					#REF!	#REF!			0	0			0	0
28		74526	Utility and Process Safety System				#REF!	#REF!		1,190,000	1,882,404	692,404		958,000	935,000	0	0	0		0	#REF!	#REF!	New					0	0	0	0	0	0		Cashflow Timing - Up (2016)	Estimate Decrease					#REF!	#REF!		Cashflow Timing - Up (2016)	692,404	0			0	0
29		74510	PCS Asset Replacement - 2016				#REF!	#REF!		1,745,958	1,765,839	19,881					0	#REF!	#REF!	New					0	219	219	69	219	150		Cashflow Timing - Up (2016)	Estimate Decrease					#REF!	#REF!		Cashflow Timing - Up (2016)	19,881	0		Estimate Increase (2016)	150	0
30		74486	PCS Controller Cabinet Asset Replacement				#REF!	#REF!		2,294,000	2,294,000	0					6,000,000	#REF!	#REF!	New					0	0	0	0	0	0			Estimate Decrease					#REF!	#REF!			0	0			0	0
31		74511	QR018 Compliance Steam and Condensate Containment				#REF!	#REF!		1,943,300	1,943,300	0					0	#REF!	#REF!					45,000	0	(45,000)	0	0	0			Estimate Decrease					#REF!	#REF!			0	0			0	0
32		74373	WFI Generation and Storage System / CUB Expansion			7,705,000	#REF!	#REF!		5,523,133	5,512,468	(10,665)		2,000,000	4,250,000	7,000,000	4,250,000	0		11,835,000	#REF!	#REF!	New					12,500	23,739	11,239	13,075	23,739	10,664		Estimate Decrease (2016)	Estimate Increase					Estimate Decrease (2016)	0	(10,665)		Estimate Increase (2016)	10,664	0
34		74385	Media Prep Endotoxin/Bioburden Sampling				#REF!	#REF!		250,000	0	(250,000)					0	#REF!	#REF!					0	0		0	0	0		Delayed	New Project					#REF!	#REF!		Delayed	0	(250,000)			0	0
36		74546	Mezzanine Safety Shower/Eye Wash Station Install				#REF!	#REF!		100,000	450,000	350,000					210,000	#REF!	#REF!					0	0	0	0	0	0		Estimate Increase (2016)	New Project					#REF!	#REF!		Estimate Increase (2016)	350,000	0			0	0
37		74491	Etro Tech Transfer				#REF!	#REF!		6,094,794	1,295,272	(4,799,522)					16,900,000	#REF!	#REF!					200,000	69,004	(130,996)	116,900	69,004	(47,896)			New Project					#REF!	#REF!			0	(4,799,522)			0	(47,896)
38		74127	Harvest Modifications Start-up				#REF!	#REF!		125,000	125,000	0		800,000	1,600,000	0	0	0		2,400,000	#REF!	#REF!					0	0	0	0	0	0				#REF!				800,000	1,600,000					800,000	1,600,000			#REF!	#REF!			0	0			0	0
39		74277	P2 DPE Start-Up				#REF!	#REF!		4,461,207	4,461,207	0		8,000,000	43,500,000	0	0	0		52,445,136	#REF!	#REF!					0	0	0	0	0	0				#REF!				8,000,000	43,500,000					8,000,000	43,500,000			#REF!	#REF!			0	0			0	0
38		96210	P2 User Furnished Equipment Procurement				#REF!	#REF!		0	950,000	950,000		800,000	1,600,000	0	0	0		0	#REF!	#REF!					0	150,000	150,000	0	150,000	150,000		Cashflow Timing - Up (2016)		#REF!				800,000	1,600,000					800,000	1,600,000			#REF!	#REF!		Cashflow Timing - Up (2016)	950,000	0			150,000	0
40		N/A	Contingency					3,800,236	0	(3,800,236)					0	0	0		Estimate Increase (2016)					Estimate Decrease (2016)	0	(3,800,236)			0	0
41		96999	Total Site Management Adjustment			(10,041,260)	#REF!	#REF!		(1,487,180)	0	1,487,180		0	0	0	0	0		(13,888,462)	#REF!	#REF!					235,000	0	(235,000)	(197,487)	0	197,487		Estimate Increase (2016)		#REF!		-2,143,645	-10,176,700	-500,000					-2,143,645	-10,176,700	-500,000				#REF!	#REF!		Estimate Decrease (2016)	1,487,180	0		Estimate Decrease (2016)	197,487	0
		Total Capex				105,766,288	#REF!	#REF!		157,000,000	151,808,965	(5,191,035)		31,995,749	63,502,440	18,919,069	11,900,000	7,364,000		397,166,576	#REF!	#REF!			0	0	0		1,825,561	2,614,723	789,162	2,025,754	2,614,569	588,814				#REF!		46,173,179	153,327,173	120,976,448	74,598,053	14,069,069	8,650,000		42,160,506	147,785,386	117,349,265	74,215,581	14,069,069	8,650,000					7,593,297	(12,784,332)

		EXPENSE ONLY PROJECTS					150,087,036	(1,721,930)
		98026	Launch Capability Program (LCP)					800,000	800,000	0					0	0
		74524	Bioburden 2606 IPA Exhaust Improvement					8,519	14,571	6,052					Removed	6,052	0
		97058	Parking Pavement Repair			3,441,931	#REF!	#REF!					245,040	245,040	0					0	0
		97007	Automation System Lifecycle MCS Upgrade			112,365,617	#REF!	#REF!					295,169	295,781	612					Estimate Increase (2016)	612	0
		97003	MFG Systems Integration Improvement Phase 1 - 2015			0	#REF!	#REF!					443,000	292,227	(150,773)					0	(150,773)
		97048	Arc Flash Prevention			(10,041,260)	#REF!	#REF!					319,456	318,000	(1,456)					#REF!					Estimate Increase (2016)	0	(1,456)
		82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)			105,766,288	#REF!	#REF!					933,708	866,058	(67,650)					#REF!					Cashflow Timing - Down (2016)	0	(67,650)
		N/A	CRB, travel, ofc supplies, others					317,400	317,400	0					Estimate Decrease (2016)	0	0
			PCS Asset Replacement Depreciation Write-Off					800,000	800,000	0					0	0
		TBD	PAIR					3,091,211	3,102,350	11,139					Estimate Decrease (2016)	11,139	0
		97045	Site Exterior Lighting Upgrade - Title 24					100,000	100,000	0					0	0
		97057	Conference Room 315 Expansion					108,000	150,000	42,000					Cashflow Timing - Down (2016)	42,000	0
		97059	B311 & B321 Gowning Room Modifications					107,000	100,492	(6,508)					New Project	0	(6,508)
		97060	QC Gas Cabinet Removal					75,000	75,000	0					0	0
		97053	Pressure Safety Program					100,000	100,000	0					New Project	0	0
		97069	Manufacturing Bullpen					0	150,000	150,000					New Project	150,000	0
		97999	Total Site Management Adjustment					0	0	0					Estimate Increase (2016)	0	0
		Total Expense				404,264,221	#REF!	#REF!					57,770,749	121,549,440	30,747,069	16,650,000	7,364,000		707,155,849	#REF!	#REF!			0	0	0		3,565,309	5,121,365	1,556,056	7,743,503	7,726,919	(16,584)					1,178,652	(606,422)
		Grand Total					9,769,257	10,341,488	572,230
		Constraint Analysis					9,769,257	10,144,001	572,230					572,230
				-	(197,487)	-

				Global Credit					4,608,510	5,351,490	742,980		7,020,749	7,055,440	7,091,069	7,150,000	7,364,000		59,466,347	#REF!	#REF!			0	0	0		29,495	51,641	22,146	46,946	51,487
				Individual Credit					145,492,227	140,921,268	(4,570,959)	0	10,504,000	5,227,000	4,828,000	500,000	0	0	279,633,555	#REF!	#REF!			0	0	0		1,361,066	2,344,078	983,012	2,059,395	1,913,459
				Start-up					4,586,207	4,586,207	0		8,800,000	45,100,000	0	0	0		71,745,136	#REF!	#REF!			0	0	0		200,000	69,004	(130,996)	116,900	150,000
				Adjustment					(1,487,180)	0	1,487,180		0	0	0	0	0		(13,888,462)	#REF!	#REF!			0	0	0		235,000	0	(235,000)	(197,487)	0
				TOTAL CAPEX					153,199,764	150,858,965	(2,340,799)		26,324,749	57,382,440	11,919,069	7,650,000	7,364,000		396,956,576	#REF!	#REF!			0	0	0		1,825,561	2,464,723	639,162	2,025,754	2,114,946

## Waterfall_Graphs
CAPEX					ID	Project	Up	Down	Comments	PD	SME
YTD	Base	Blank	Up	Down	Value	Label				99999	#N/A	#N/A	#N/A	Estimate Increase (2016)	#N/A	#N/A
MO5	157,000,000				157,000,000					74546	Mezzanine Safety Shower/Eye Wash Station Install	350,000	-	Estimate Increase (2016)	Mel Davis	Marcus Espinoza
New Project		157,000,000	400,000	-	400,000	400,000				74511	QR018 Compliance Steam and Condensate Containment	-	-	Project Intake stage longer than forecasted.	Mel Davis	Anastasia Gandrik / Sumner Tison
Cashflow Timing - Up (2016)		157,400,000	4,518,438	-	4,518,438	4,518,438				74279	New Media Technology - HTST / Adventitious	48,148	-	Design development of skids during design stage.	Alister Hufton	Will Jimenez
Estimate Increase (2016)		161,918,438	1,187,679	-	1,187,679	1,187,679				74382	Sci&Eng Lab Mods and Equipment	1,182,701	-	Design development caused delays in finalizing equipment design.	Alister Hufton	Fikret Kulenovic
Delayed		162,856,117	-	250,000	(250,000)	250,000				74491	Etro Tech Transfer	-	(4,799,522)	CA approval delay and 1 month ER/QR schedule shift into 2017	N/A	Semsi Ensari
Removed		162,856,117	-	-	-	-				74487	Process VSD and SOV Asset Replacement	479	-	Project Intake stage longer than forecasted.	Alister Hufton	Jonathan Clark
Estimate Decrease (2016)		158,508,250	-	4,347,867	(4,347,867)	4,347,867				74435	Hastelloy Chromatography Column (160cm)	400,000	-	Currently deferred to 2017. IMPACT to review.	Alister Hufton	Bahar Dahi / Juan Pacio
Cashflow Timing - Down (2016)		155,139,564	-	3,368,686	(3,368,686)	3,368,686				74409	#N/A	#N/A	#N/A	Deferred to 2017.	Alister Hufton	Geoff Wing / Pierre Luong
Scope Reduction		155,121,308	-	18,256	(18,256)	18,256				74527	#N/A	#N/A	#N/A	Deferred to 2017.	Mel Davis	Will Jimenez
T3	151,808,965				155,121,308					74277	P2 DPE Start-Up	-	-	Cashflow reforecast.	Alister Hufton	Dirk Ellison/ Ken Hamilton
				74268	P2 Downstream Processing Expansion	-	(540,999)	Cashflow reforecast based on schedule.	PTAA	Mark Jones / Dirk Ellison
				$3,312,343

2016 Capital Budget - T3 vs MO5 Overview

				Increase
				Decrease

				M05 Total Capital $153,052 / Chart Total $24,706

				Deferred to 2017; IMPACT TO REVIEW

				Project intake longer than forecast

				Design development caused delays in finalizing equipment design

				Design development of skids during design stage

				Project Intake stage longer than forecasted

Expense Only
YTD	Base	Blank	Up	Down	Value	Label				No.	EXPENSE Only Projects	Up	Down	Comments	Column1	Column2
T0	9,878,553				9,878,553					99999	Total Site Management Adjustment	-	-	Estimate Increase (2016)
New Project		9,878,553	150,000	-	150,000	150,000				74268	P2 Downstream Processing Expansion	518,679	-	Increased travel cost projections based on trend information, trailer cleaning included in scope of project, and Fluor forecast change	PTAA	Mark Jones / Dirk Ellison
Cashflow Timing - Up (2016)		10,028,553	86,328	-	86,328	86,328				97058	Parking Pavement Repair	-	-	Scope increase	Mel Davis	Sumner Tison
Estimate Increase (2016)		10,114,881	535,646	-	535,646	535,646				74454	Seed Lab (20L Bioreactor)	-	(44,208)	Fluor's projected expense (predominantly demolition) cost.	PTAA	Mark Jones / Paul Coon
Removed		10,650,527	-	-	-	-				74418	QC Lab Reconfiguration & Equipment	1,000	-	Cash flow reforecast.	Mel Davis	Amanda Gutierrez
Estimate Decrease (2016)		10,650,527	-	-	-	-				97059	B311 & B321 Gowning Room Modifications	-	(6,508)	New Project	Mel Davis	TBD
Cashflow Timing - Down (2016)		10,557,636	-	92,892	(92,892)	92,892				97060	QC Gas Cabinet Removal	-	-	New Project	Mel Davis	Joe Molon
Scope Reduction		10,557,636	-	-	-	-				74382	Sci&Eng Lab Mods and Equipment	-	(262,689)	Reallocation of demolition costs.	Alister Hufton	Fikret Kulenovic
Delayed		10,557,636	-	-	-	-				74491	Etro Tech Transfer	-	(47,896)	Reallocated to site	N/A	Semsi Ensari
MO5	10,341,488				10,557,636					97045	Site Exterior Lighting Upgrade - Title 24	-	-	Partially deferred to 2017.	Mel Davis	Charles Fuller
				82000	I&C Eng. and Instr. Config. Mgmt. System Remediation (CAPA 982343)	-	(67,650)	Cash flow reforecast.	Alister Hufton	Jonathan Clark
				97040	Tech Transfer: Master Data Management	#N/A	#N/A	Removed - PT Project	N/A	Marco Baca
				97039	PCS Remediation for EBR Review by Exception - PI	#N/A	#N/A	Cashflow Timing - Down (2016)	Alister Hufton	Malou Jacinto / Stephanie Huntress
2016 Expense Budget - T3 vs T0 Overview					99999	Total Site Management Adjustment	#N/A	#N/A	Estimate Decrease (2016)
				N/A	CRB, travel, ofc supplies, trailer, others	-	-	Project controls capitalized.
				74525	CIP Reliability and Efficiency - PI	#N/A	#N/A	Removed / Departmental
				97038	PCS Functional Specification Development Project (CAPA 960297)	#N/A	#N/A	Deferred to 2017/2018.	Alister Hufton	Sarah Maruccia

				Deferred to 2017/2018

				Removed (departmental)

				Project controls capitalized

				Estimate decrease (2016)

				Partially deferred to 2017

CAPEX
YTD	Base	Blank	Up	Down	Value	Label
T0	177,757,472
MO5	153,051,764					Reallocation of demolition cost

2016 Capital Budget - T0 vs MO5 Overview					New Project

				New Project

Expense Only
YTD	Base	Blank	Up	Down	Value	Label
T0	9,878,553				9,878,553	9,878,553
MO5	9,656,257				9,656,258	9,656,258

2016 Expense Budget - T0 vs MO5 Overview
MO5 2016 Major Line Item Changes - 2016 Capital Projects 2016 Expense Budget - T0 vs MO5 Overview
Cashflow reforecast based on schedule
Cashflow reforecast
Deferred to 2017
Deferred to 2017

CA approval delay and 1 month ER/QR schedule shift into 2017
Increased travel trend, trailer cleaning scope , Fluor forecast change
Fluor's projected expense (predominantly demolition) cost
Increased scope
Cash flow reforecast
Cash flow reforecast
Removed - PTAA funded
Cash flow timing down (deferred)
M05 Total Expense $9,657
Chart Total $223
Estimated increase (2016)
Reallocated to site and schedule shift

## T0_2016_Variance_Expense
				Expense	New Project
				Delayed	Combined
		Oceanside					Canceled/On Hold
		T0 2016 - Variance Analysis

				2015 Preview				2016 Preview					2015-2020 (2015 Expenditure + Budget)					Expense Portion			Expense Portion					2015				2016

		Nro.	Project Name	Expenditure YE 2013		T0 2015	T3 2015	Variance		T3 2015	T0 2016	Variance		T0 2015 / (2016 Preview)	T0 2015 / (2017 Preview)	T0 2015 / (2018 Preview)	T0 2015 / (2019 Preview)	T0 2015 / (2020 Preview)		Exp YE + T0 (CY) Total Project Cost	Exp YE + T3 (CY) Total Project Cost	Variance	Comments		T0 2014 / (Year 2014) Expense Portion	T3 2015 (Year 2014) Expense Portion	Variance		T0 2015 / (Year 2015) Expense Portion	T3 2015 / (Year 2015) Expense Portion	Variance	T3 2015 (Year 2016) Expense Portion	T0 2016 (Year 2016) Expense Portion	Variance		CHANGE 2015	CHANGE 5-Y-O	PPE / Forecast / 2014		T3 2014 (Y 2014)	T3 2014 (Y 2015)	T3 2014 (Y 2016)	T3 2014 (Y 2017)	T3 2014 (Y 2018)	T3 2014 (Y 2019)		PPE / Forecast / 2014	PPE / Forecast / 2015	PPE / Forecast / 2016	PPE / Forecast / 2017	PPE / Forecast / 2018	PPE / Forecast / 2019	UP	DOWN		CHANGE 2016	UP	DOWN
1	1	6DM	GNE Oceanside Prod Ops	3,580,630		1,019,880	#REF!	#REF!		1,230,000	3,612,857	2,382,857		1,230,000	1,270,000	1,305,000	1,345,000	1,385,000		11,508,250	#REF!	#REF!					#REF!	#REF!	0	50,850	50,850				#REF!		372,740	995,000	1,230,000	1,270,000	1,305,000	1,345,000		372,740	995,000	1,230,000	1,270,000	1,305,000	1,345,000	#REF!	#REF!		Estimate Increase (2016)	2,332,007	0
2	1	90024	NIMO Small Projects - Misc	14,427,220		2,422,051	#REF!	#REF!		5,790,749	2,331,026	(3,459,723)		5,790,749	5,785,440	5,786,069	5,805,000	5,979,000		47,958,097	#REF!	#REF!					29,495	#REF!	#REF!	28,903	22,286	(6,617)				#REF!		1,962,568	4,992,933	5,790,749	5,785,440	5,786,069	5,805,000		1,762,568	4,605,933	5,790,749	5,785,440	5,786,069	5,805,000	#REF!	#REF!		Estimate Decrease (2016)	0	(3,453,107)
		97012	Site Data Historian Asset Replacement - 2017					366,000	0	(366,000)					Delayed	0	(366,000)
		97022	MFG Systems Integration Improvement Phase 2 - 2016					0	0	0					Removed	0	0
		97029	Study for K6 Program - Project 4 - Replace Chillers					0	0	0					Removed	0	0
		97037	Recipe Reconfiguration Alignment for Operating Systems					3,750,000	0	(3,750,000)					Delayed	0	(3,750,000)
3	2	82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)				#REF!	#REF!		980,000	866,058	(113,942)					1,520,000	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		Cashflow Timing - Up (2016)	0	(113,942)
4	2	N/A	CRB, travel, ofc supplies, trailer, others				#REF!	#REF!		627,000	627,000	0		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!			0	0
5		97007	Automation System Lifecycle MCS Upgrade				#REF!	#REF!		2,100,000	295,781	(1,804,219)					3,000,000	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		Cashflow Timing - Down (2016)	0	(1,804,219)
6		97048	Arc Flash Prevention				#REF!	#REF!		0	318,000	318,000					0	#REF!	#REF!					#REF!		0	0	0				#REF!					#REF!	#REF!		New Project	318,000	0
7	2		Piping Corrosion				#REF!	#REF!		0	3,100,000	3,100,000		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	3,100,000	0
8	2	97040	Tech Transfer: Master Data Management				#REF!	#REF!		555,750	0	(555,750)					555,750	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!			0	(555,750)
9	2	97054	HVAC Retro Commissioning				#REF!	#REF!		0	0	0					0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	0	0
10		97038	PCS Functional Specification Development Project (CAPA 960297)				#REF!	#REF!		2,000,000	0	(2,000,000)					8,000,000	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		Scope Reduction	0	(2,000,000)
11	2	97039	PCS Remediation for EBR Review by Exception - PI				#REF!	#REF!		500,000	0	(500,000)		0	0	0	0	0		6,125,000	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		Cashflow Timing - Up (2016)	0	(500,000)
12	2	97053	Pressure Safety Program - PI				#REF!	#REF!		0	100,000	100,000		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	100,000	0
13	2	97055	#N/A				#REF!	#REF!		0	0	0		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	0	0
14		97045	Site Exterior Lighting Upgrade - Title 24				#REF!	#REF!		0	100,000	100,000					400,000	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	100,000	0
15	2	97056	#N/A				#REF!	#REF!		0	0	0		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	0	0
16	2	97057	Conference Room 315 Expansion				#REF!	#REF!		0	150,000	150,000		0	0	0	0	0		0	#REF!	#REF!					#REF!	#REF!	0	0	0				#REF!					#REF!	#REF!		New Project	150,000	0
		Total				3,441,931	#REF!	#REF!		17,899,499	11,500,722	(6,398,777)		7,020,749	7,055,440	7,091,069	7,150,000	7,364,000		79,067,097	#REF!	#REF!			0	0	0		29,495	#REF!	#REF!	28,903	73,136	44,233				#REF!		46,173,179	153,327,173	120,976,448	74,598,053	14,069,069	8,650,000		42,160,506	147,785,386	117,349,265	74,215,581	14,069,069	8,650,000					6,100,007	(12,543,018)

				Global Credit		3,441,931	#REF!	#REF!		7,020,749	5,943,883	(1,076,866)		7,020,749	7,055,440	7,091,069	7,150,000	7,364,000		59,466,347	#REF!	#REF!			0	0	0		29,495	#REF!	#REF!		73,136					(6,443,011)
				Expense		0	#REF!	#REF!		6,762,750	5,556,839	(1,205,911)	0	0	0	0	0	0	0	19,600,750	#REF!	#REF!			0	0	0		0	#REF!	#REF!		0
				TOTAL Expense		3,441,931	#REF!	#REF!		13,783,499	11,500,722	(2,282,777)		7,020,749	7,055,440	7,091,069	7,150,000	7,364,000		79,067,097	#REF!	#REF!			0	0	0		29,495	#REF!	#REF!		73,136					#REF!

				17,870,597	11,427,586

				#REF!

## Ideas
	QC Asset Replacement 2015

			QTY	Siu-Fai Estimate	ACTUAL REQUESTED
EMD Chemical Air Sampler (Model #MAS 100 )			3.00	$40,797	$25,000	11/5/2015 CA Issued forOsomometer instead
MetOne Particle Counter (Model#3445)		Contact: csyrengelas@beckman.com; 720-244-7730; includes validation and paperless pdf, IOQ also included	3.00	$60,084	$64,800	7/15/15 CA Issued.
Agilent Analyzer (Model #8453) - Spectometer		Contact: debbie_mulcahy@agilent.com (858)-450-8133, includes general, advanced, and security pack software	1.00	$25,336	$27,000	7/15/15 CA Issued.
Biowhittaker Plate Reader (Model #ELX808)			1.00	$22,850	$23,760	7/15/15 CA Issued.
(-20C) Freezers (Revco) VWR 35960-176		(-20C) 23.3cuft VWR 35960-176	2.00	$21,785	$24,000	5/06/15 CA Issued.
Mettler Toledo Balance (Model# AX205		Discontinued, alternate XPE205 (VWR 10025-662) Validation included (IQOQPQ= 1213.25)	2.00	$42,061	$45,360	7/15/15 CA Issued.
Gel imager		New requests	1.00	$14,335	$15,120	7/15/15 CA Issued.
SpeedVac			1.00	$10,978	$11,880	7/15/15 CA Issued.
Endotoxin hand-hold Nexgen-PTS			2.00	$16,000
M9 TOC analyzers			2.00	$104,000	$106,000	6/12/15 CA Issued
			Subtotal	$358,226
			Tax	$28,658
			Freight	$3,582
				$390,466		BALANCE
				$391,000	$342,920	48,080.00

	Media Prep Bioburden Project - Matt Forbes

Projects identified on SBP Review
TBD	QC Testing Equipment for Launch Capability and Storage Requirements
TBD	IPA Exposure Remediation and QC Lab Ventilation
TBD	Lighting Work on OCN Campus Pathways
TBD	TMAC Tenderizer
TBD	Upstream Capacity Buildout
TBD	Phosphoric Acid Remediation
TBD	EBR Review by Exception - PCS Remediation
TBD	MPI Pull Tanks
TBD	Sci&Eng Lab Equipment for MPI and Launch Capability
74378	Automation Proximity Switch Additions to Manufacturing Areas
TBD	PCS Controller Cabinet Retrofit (UL Compliance)
TBD	PCS Functional Specification Remediation Project (CAPA 960297)
74385	Media Prep Endotoxin/Bioburden Sampling
TBD	Maintenance Ops Shop Buildout

SHE Idea Projects
0/1	Project Name	Scope of Work	2016 T0 Constraint Analysis	2017	2018	Requester	SHE Rep	CRB PM	SME	Budget	Funding	P-Score	New Idea	Study	Intake	Design	Need By	Status	Upcoming Milestones	2016	2017	2018	K9 Risk Level & Area	Year Risk Identify	Approximate Age of Risk	Priority for Execution	Functions Affected by Risk	2016 Credit App	Contractor(s)	Amount in Credit App	Budget Timing- 2016	Amount IMPACT- 2016	Amount SHE Budget- 2017	Amount IMPACT- 2017	0
1	TMAC Waste System Improvements	Engineering is Lead. Changing of TMAC piping to allow for GMP chemical delivery and offload of TMAC to occur simultaneously. Also, meter needs to be installed to accurately track offload. P=UPDATE	Deferred			Susan Schmidt		Jim Koons	TBD		Capital				X		2016				x		Yellow- Compliance	2014	2 years	Lower	BMSO, FOS	No					$1,500,000
1	Fall Protection Phase 3	Address areas not addressed by Phase 1 &2	no- pushed to 2017					x		Red- Safety	2014	2 years	Top	Site	No					$100,000
1	Cafe Flooring	Address Slip/trip/ fall	no					x		Yellow- Safety	2014	3 years	Lower	Site	No
1	Site Signage Upgrade	Address gaps in site signage- CESA audit finding	no					x		Green- Compliance	2013	3 years	Middle	Site	No					$200,000
1	Conference Center	Slip/trip/fall	no					x		Green- Safety	2016	< 1 year	Lower	Site	No					$200,000
1	Machine Guarding- Warehouse	Install guarding on plastic wrapper	no					x		Yellow- Safety	2015	1 year	Lower	BMSO	No
1	Office Ergonomics- phase 2	Address office areas that 2015 retrofit did not address	no					x		Yellow- Safety	2015	1 year	Lower	Site	No
1	K22 Direcitve Compliance- Chemical Safety	New K-Direcitve	No					x		Green- Compliance	2015	1 year	Lower	Site	No
1	Eye wash stations in mfg. gowning rooms	Use of corrosives requires SS/ EW. Locker room showers meet requirement.	No.					x	x		Yellow- Safety & Compliance	2016	< 1 year	Midddle	MFG	No					$20,000
1	Pipe Labelling	Audit finding needs project to close					x	x					$100,000
1	Lab Compliance Issues following Lab Rennovation Projects	Compliance risks tbd					x
1	UPSS phase 2	Address fire/ life safety and process safety alarms	no					x		Red- Safety	2015	2 years	Top	Site					$2,000,000
1	Pressure Safety Facility Mitigations	STARIs	no					x		Red- Safety	2012	5 years	Top	MFG					$2,500,000
1	Column Packing Fall Hazard	K9	no					x		Orange- Safety	2015	2 years	Top	MFG					$300,000
1	Harvest Depth Filter Mitigations (fall/ ergo)	K9	no					x		Yellow- Safety	2015	1 year	Middle	MFG
1	K6- All Design	K6	no					x	x	Green			Top	Site
1	Fire Safety- Gap Assessment Mitigations (TBD)	TBD from study in 2016	no					x	x	TBD
1	Security Systems Upgrade					x	x					$200,000
1	Crane & Hoist Mitigation	CESA Audit Finding					x		TBD			Top	MFG
1	Site Safety Signage	CESA Audit Finding					x
1	Bottle Washing: FIFRA Program	Continued recycling of haz. waste bottles	no					x		TBD					$30,000
1	Storm Water BMP for upper lot					x					$200,000
1	Drum Crusher	Old unit needs 17K of repairs					x					$25,000
1	PI- Ammonia RMP Study					x					$30,000
1	322 MRO Racks	Property Loss Audit Finding; Install new racks that meet Fire Code					x					$500,000
1	Pressure Safety	STARIs					x					$3,500,000
1	Lab Earthquake restraints	Property Loss Audit Finding					x					$20,000
0	B311 Mezzanine Safety Shower and Eye Stations	Install new ES and SS devices to the mezzanines (verify scope sheet is available). Project Managment is Lead	Yes. Below Execution Line			Steve Novak	Michael Navadeh	Jim Koons	TBD	960k	Capital			n/a	X	X	2016	Mel Davis is currently working with MFG to determine exact scope of project.	Finalizing Design Deliverables with MFG		x		Yellow- Compliance/ safety	2012	4 years	Middle	MFG	No				1000		1000
0	K6- DX HVAC Units	Engineering executing	No. Below the line					x		Yellow- Sustainability/ Compliance	n/a	n/a	Middle	FOS, BMSO	No
0	CIP Optimization	Technology is Lead	Yes. Below Execution Line.					x	x		Green- Sustainability	2015	1 year	Middle	MFG	No
0	Appleton Tank Movers	Purchase new Appleton Tank Movers in 2015 for Mfg and Mat Ops. Pilot. Purchase additional 2 if work well.	no	X		Susan Schmidt	Sean Sullivan	Tucker Creighton	Dave McGraw, Richard Dimler	80K	Capital	Benefit:1.1 Cost/Effort:.5 Overall:8.9	x				2016		Project on hold till further notice.		x		Yellow- Safety	2015	1 year	Lower	MFG	No					90
0	Electrical Arc Flash (Medium Risk)	Address medium risk Arc Flash hazards	no					x		Yellow- Safety	2015	1 year	Lower	FOS	No
0	Trash Bin Storm Water Mitigation Construction	Address storm water issue under REM trash bins	Yes. Below Execution Line			Gary Merrill	Gary Merrill	TBD	TBD	200k	Capital		x	x	X		2016	Evaluating the best design for containment of Nitrates. French Drains, Containment pit, or Cover are all viable solutions.	RFP to FPBA/CRB	x	x		Orange- Compliance	2016	0 years	Top	BMSO	No	CRB		October			200
0	Filter Housing	MFG depth filters need to be serviced on top of platforms causing fall hazards and ergonomic risks.	no			Chris Letourneau	Nick Loebs			TBD					X		TBD	Email has been sent to MFG to confirm that they still need assistance with this. Possible solution may have been made in-house. Nick Loebs will be delivered an update NLT 021316 from Marc Espinoza.	Scoping Project	x	x		Orange- Safety	2015	1 years	Middle	MFG	Yes	CRB
0	SOV Panels	Technology is Lead	Yes- above Execution Line					x	x	x	Green- Safety	2014	2 years	Lower	FOS, Tech	No
0	Corrosive Chemical Compliance	Meet Fire Department approved Performance Based Standard for use of corrosives. 50K SHE Expenser $ for FPBA Architects.	Yes- above Execution Line					x	x		Red- Compliance	2014	2 years	Top	MFG	No	CRB		March (Expense) December (capital)	50

96161	QC Lab Gas Cabinet Removal			TBD	TBD	Improvements and Efficiencies	TBD			Idea	TBD	TBD	Mel Davis	TBD					#REF!					#REF!	#REF!
96182	Cafe Flooring	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96185	Machine Guarding- Warehouse	SHE Identified Project on 5/9/16		TBD	RTO	TBD	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96186	Office Ergonomics- phase 2	SHE Identified Project on 5/9/16		TBD	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96187	K22 Direcitve Compliance- Chemical Safety	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96190	Lab Compliance Issues following Lab Rennovation Projects	SHE Identified Project on 5/9/16		TBD	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96194	Harvest Depth Filter Mitigations (fall/ ergo)	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96195	K6- All Design	SHE Identified Project on 5/9/16 - Will return to IMPACT for next phase.		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	Pierre Luong					#REF!					#REF!
96196	Fire Safety- Gap Assessment Mitigations (TBD)	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96198	Crane & Hoist Mitigation	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!
96199	Site Safety Signage	SHE Identified Project on 5/9/16		TBD	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD					#REF!					#REF!

2017 ARR

## SBP_CHF
		Oceanside
		MO5 2016 - CAPEX Forecast Portfolio View: Capital Projects Including Expense Portions

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget	Exp + YE + MO5 (CY) Total Project Cost	MO5 2016 (Year 2016) Expense Portion	MO5 2016 (Year 2017) Expense Portion	MO5 2016 (Year 2018) Expense Portion	MO5 2016 (Year 2019) Expense Portion	MO5 2016 (Year 2020) Expense Portion	MO5 2016 (Year 2021) Expense Portion
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business			3,580,630	3,580,630	786,250	3,026,046	3,328,651	3,661,516	4,027,668	4,430,435	4,873,478	23,347,794	31,295,304	46,946	-	-	-	-	-					2,979,100	3,328,651	3,661,516	4,027,668	4,430,435
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business			14,427,220	14,427,220	9,765,687	1,629,410	1,792,351	1,971,586	2,168,744	2,385,619	2,624,180	12,571,889	51,192,016	-	-	-	-	-	-					1,629,410	1,792,351	1,971,586	2,168,744	2,385,619
3		96204	322 MRO Racks	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	500,000	-	-	-	-	500,000	500,000	-	-	-	-	-	-					0	500,000	0	0	0
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,535,902	2,071,222	113,876	-	-	-	-	2,185,098	3,721,000	43,784	464	-	-	-	-					2,027,438	113,412	0	0	0
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg	-	-	2,701,000	686,850	-	-	-	-	-	686,850	3,387,850	-	-	-	-	-	-					686,850	0	0	0	0
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill	-	-	36,659	142,115	400,000	-	-	-	-	542,115	578,774	-	-	-	-	-	-					142,115	400,000	0	0	0
7		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	SHE and K-Directives	Reliability and Value	Geoff Wing	-	-	-	8,519	550,000	-	-	-	-	558,519	558,519	8,519	550,000	-	-	-	-					0	0	0	0	0
8		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD	-	-	-	-	-	-	-	10,000,000	-	10,000,000	10,000,000	-	-	-	-	-	-					0	0	0	0	10,000,000
9		74525	CIP Reliability and Efficiency - PI	RTO	Improvements and Efficiencies	Reliability and Value	Pierre Luong (TBD)	263,570	-	-	-	-	-	-	-	-	-	263,570	-	-	-	-	-	-					0	0	0	0	0
10		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	103,025	1,596,303	83,733	-	-	-	-	1,680,036	1,783,061	-	-	-	-	-	-					1,596,303	83,733	0	0	0
11		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.	392,072	489,325	56,153	10,000	-	-	-	-	-	10,000	947,549	-	-	-	-	-	-					10,000	0	0	0	0
12		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio	-	-	-	306,000	654,000	-	-	-	-	960,000	960,000	-	-	-	-	-	-					306,000	654,000	0	0	0
13		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	-	3,000,000	3,000,000	3,000,000	3,000,000	3,000,000	15,000,000	15,000,000	-	-	-	-	-	-					0	3,000,000	3,000,000	3,000,000	3,000,000
14		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison	-	-	-	-	730,000	-	-	-	-	730,000	730,000	-	18,000	-	-	-	-					0	712,000	0	0	0
15		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.	-	246,193	476,778	26,719	-	-	-	-	-	26,719	749,690	-	-	-	-	-	-					26,719	0	0	0	0
16		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones	489,325	-	3,555,499	7,038,875	4,885,118	-	-	-	-	11,923,993	15,968,816	37,498	51,254	-	-	-	-					7,001,377	4,833,864	0	0	0
17		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio	-	-	-	-	1,549,000	-	-	-	-	1,549,000	1,549,000	-	-	-	-	-	-					0	1,549,000	0	0	0
18		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic	-	-	860,038	422,881	-	-	-	-	-	422,881	1,282,919	-	-	-	-	-	-					422,881	0	0	0	0
19		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	246,193	-	-	-	332,000	1,592,000	-	-	-	1,924,000	2,170,193	-	22,000	-	-	-	-					0	310,000	1,592,000	0	0
20		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	355,556	444,444	-	-	-	800,000	800,000	-	22,222	27,778	-	-	-					0	333,333	416,667	0	0
21		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	603,000	4,828,000	4,828,000	500,000	-	10,759,000	10,759,000	-	75,000	-	-	-	-					0	528,000	4,828,000	4,828,000	500,000
22		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing	-	-	-	-	3,000,000	6,650,000	6,000,000	3,650,000	-	19,300,000	19,300,000	-	350,000	-	-	-	-					0	2,650,000	6,650,000	6,000,000	3,650,000
23		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox	-	-	-	-	500,000	2,500,000	-	-	-	3,000,000	3,000,000	-	-	-	-	-	-					0	500,000	2,500,000	0	0
24		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin	-	-	-	1,944,000	-	-	-	-	2,340,000	4,284,000	4,284,000	-	-	-	-	-	-					1,944,000	0	0	0	0
25		74385	Media Prep Endotoxin/Bioburden Sampling	QSP	Stay in Business	Reliability and Value	Matt Forbes	-	-	-	250,000	2,750,000	-	-	-	-	3,000,000	3,000,000	-	-	-	-	-	-					250,000	2,750,000	0	0	0
26		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark	-	-	242,656	198,196	22,991	-	-	-	-	221,187	463,843	-	-	-	-	-	-					198,196	22,991	0	0	0
27		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan	-	17,731	265,047	200,613	-	-	-	-	-	200,613	483,391	(431)	-	-	-	-	-					201,044	0	0	0	0
28		96132	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	100,000	785,864	-	-	-	-	885,864	885,864	-	-	-	-	-	-					100,000	785,864	0	0	0
29		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez	-	523,433	1,984,354	4,812,654	1,602,703	-	-	-	-	6,415,357	8,923,144	1,768	-	-	-	-	-					4,810,886	1,602,703	0	0	0
30		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton	-	-	581,240	687,428	3,878	-	-	-	-	691,306	1,272,546	2,883	-	-	-	-	-					684,545	3,878	0	0	0
31		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai	-	-	-	-	750,000	4,750,000	-	-	-	5,500,000	5,500,000	-	-	500,000	-	-	-					0	750,000	4,250,000	0	0
32		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison	17,731	6,699,119	58,484,942	93,651,797	34,280,135	-	-	-	-	127,931,932	193,133,724	1,248,192	916,060	-	-	-	-					92,403,605	33,364,075	0	0	0
33		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	1,746,027	149,000	-	-	-	-	1,895,027	1,895,027	69	-	-	-	-	-					1,745,958	149,000	0	0	0
34		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	2,294,000	110,000	-	-	-	-	2,404,000	2,404,000	-	-	-	-	-	-					2,294,000	110,000	0	0	0
35		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton	-	-	-	-	200,000	900,000	900,000	935,000	-	2,935,000	2,935,000	-	200,000	-	-	-	-					0	0	900,000	900,000	935,000
36		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia	-	-	-	-	-	1,500,000	1,500,000	-	-	3,000,000	3,000,000	-	-	750,000	750,000	-	-					0	0	750,000	750,000	0
37		96205	Pressure Safety	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	3,500,000	-	-	-	-	3,500,000	3,500,000	-	-	-	-	-	-					0	3,500,000	0	0	0
38		96192	Pressure Safety Facility Mitigations	RTO	SHE and K-Directives	TBD	TBD	-	-	-	-	2,500,000	-	-	-	-	2,500,000	2,500,000	-	-	-	-	-	-					0	2,500,000	0	0	0
39		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	3,599,318	2,943,031	-	-	-	-	6,542,349	6,542,349	-	18,000	-	-	-	-					3,599,318	2,925,031	0	0	0
40		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark	523,433	-	194,621	495,036	-	-	-	-	-	495,036	1,213,090	-	-	-	-	-	-					495,036	0	0	0	0
41		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	2,500,000	3,000,000	-	-	5,500,000	5,500,000	-	-	-	-	-	-					0	0	2,500,000	3,000,000	0
42		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark	-	-	-	-	-	-	458,000	5,000,000	-	5,458,000	5,458,000	-	-	-	-	-	-					0	0	0	458,000	5,000,000
43		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez	6,699,119	-	224,746	2,031,122	1,568,006	-	-	-	-	3,599,128	10,522,993	113,000	-	-	-	-	-					1,918,122	1,568,006	0	0	0
44		96114	QC Testing Equipment for Launch Capability and Storage Requirements	QSP	Tech Transfers	Launch and Commercial Excellence	TBD	-	-	-	-	600,000	2,600,000	1,000,000	3,000,000	-	7,200,000	7,200,000	-	-	-	-	-	-					0	600,000	2,600,000	1,000,000	3,000,000
45		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison	762,597	-	-	1,943,300	3,074,500	-	-	-	-	5,017,800	5,780,397	-	-	-	-	-	-					1,943,300	3,074,500	0	0	0
46		96109	Sci&Eng Lab Equipment for NPI and Launch Capability	QSP	Tech Transfers	Launch and Commercial Excellence	Fikret Kulenovic	-	-	-	-	600,000	2,100,000	900,000	2,400,000	-	6,000,000	6,000,000	-	-	-	-	-	-					0	600,000	2,100,000	900,000	2,400,000
47		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic	-	-	6,008,632	6,690,211	488,779	-	-	-	-	7,178,990	13,187,622	458,027	-	-	-	-	-					6,232,184	488,779	0	0	0
48		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon	-	-	1,387,337	1,096,398	354,625	-	-	-	-	1,451,023	2,838,360	141,531	2,075	-	-	-	-					954,867	352,550	0	0	0
49		74280	Spare Hasstelloy Columns	QSP	Stay in Business	Agile		-	762,597	1,603,881	-	-	-	-	-	-	-	2,366,477	-	-	-	-	-	-					0	0	0	0	0
50		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley	-	258,306	1,420,589	157,774	-	-	-	-	-	157,774	1,836,669	-	-	-	-	-	-					157,774	0	0	0	0
51		96180	TMAC Waste System Improvements	RTO	Stay in Business	TBD	TBD	-	-	-	-	1,500,000	-	-	-	-	1,500,000	1,500,000	-	-	-	-	-	-					0	1,500,000	0	0	0
52		96191	UPSS Phase 2	RTO	Stay in Business	TBD	TBD	-	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,000	-	-	-	-	-	-					0	2,000,000	0	0	0
53		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	1,190,000	510,000	-	-	-	-	1,700,000	1,700,000	-	-	-	-	-	-					1,190,000	510,000	0	0	0
54		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez	-	-	-	-	4,859,000	-	-	-	-	4,859,000	4,859,000	-	-	-	-	-	-					0	4,859,000	0	0	0
55		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell	-	-	-	-	2,000,000	-	-	-	-	2,000,000	2,000,000	-	-	-	-	-	-					0	2,000,000	0	0	0
56		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai	-	-	179,085	162,102	-	-	-	-	-	162,102	341,187	-	-	-	-	-	-					162,102	0	0	0	0
57		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen	-	1,194,816	470,099	369,680	51,636	-	-	-	-	421,316	2,086,231	-	-	-	-	-	-					369,680	51,636	0	0	0
58		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai		1,738,974	6,525,760	5,536,208	-	-	-	-	-	5,536,208	13,800,942	13,075	-	-	-	-	-					5,523,133	0	0	0	0
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	6,211,694	12,836,630	3,347,374	507,790	66,290	-	22,969,778	22,969,778	116,900	135,000	80,000	20,600	4,800	-					6,094,794	12,701,630	3,267,374	487,190	61,490
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	8,940,664	78,779,345	1,431,430	369,105	79,200	89,599,744	89,599,744	-	147,070	169,290	55,330	19,800	40,920					0	8,793,594	78,610,055	1,376,100	349,305
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	8,940,664	31,169,850	1,431,430	41,541,944	41,541,944	-	-	-	147,070	169,290	55,330					0	0	0	8,793,594	31,000,560
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari	-	-	-	-	-	-	-	8,940,664	28,753,027	37,693,691	37,693,691	-	-	-	-	147,070	169,290					0 / 5-Year CAPEX Through 2020 / USD	0	0	0	8,793,594
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton	-	-	-	125,000	2,275,000	-	-	-	-	2,400,000	2,400,000	-	-	-	-	-	-					125,000	2,275,000	0	0	0
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton	-	-	-	4,461,207	40,280,925	6,754,868	-	-	-	51,497,000	51,497,000	-	-	-	-	-	-					4,461,207	40,280,925	6,754,868	0	0
65			Contingency					3,800,236	-	-	-	-	-	3,800,236	3,800,236	-	-	-	-	-	-					3,800,236	0	0	0	0
66		96999	Site Management Adjustments (if any)					(3,847,202)	(10,661,762)	(1,684,667)	-	-	-	-	-	(1,684,667)	(16,193,631)	(197,487)	-	-	-	-	-					(1,487,180)	0	0	0	0
			Expense Only Projects					0	0	70,227	7,734,984	16,904,722	10,419,500	4,682,500	1,787,000	2,187,000	43,715,706	43,785,933	7,734,984	16,904,722	10,419,500	4,682,500	1,787,000	1,836,000
			Total					27,401,890	26,091,141	88,858,444	166,769,257	170,819,374	138,298,633	43,344,796	77,633,962	45,288,315	642,154,338	784,505,813	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,101,540					157,000,000

			Global Credit					18,007,850	10,551,937	4,655,456	5,121,002	5,633,102	6,196,412	6,816,053	7,497,658	35,919,683	82,487,320	46,946	0	0	0	0	0					157,000,000
			Individual Credit					11,930,494	88,898,042	141,465,347	84,460,431	33,364,444	21,586,000	28,485,000	5,340,000	314,701,223	424,923,798	2,067,914	2,225,076	1,277,778	750,000	0	0					0
			Tech Transfer					0	0	6,211,694	21,777,294	82,126,719	10,879,884	40,545,909	30,263,657	191,805,157	191,805,157	116,900	282,070	249,290	223,000	340,960	265,540
			Start-up					0	0	4,586,207	42,555,925	6,754,868	0	0	0	53,897,000	53,897,000	0	0	0	0	0	0
			Adjustment					(3,847,202)	(10,661,762)	(1,684,667)	0	0	0	0	0	(1,684,667)	(16,193,631)	(197,487)	0	0	0	0	0
			TOTAL CAPEX					26,091,141	88,788,216	155,234,038	153,914,652	127,879,133	38,662,296	75,846,962	43,101,315	594,638,396	736,919,644	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540

							$166,769,257					$9,769,257
							-					-
			Improvements and Efficiencies					432,881	7,779,000	7,000,000	4,500,000	13,000,000	3,000,000		32,711,881
			New Technologies					4,812,654	1,602,703	0	0	0	0		6,415,357
			SHE and K-Directives					3,399,652	13,870,153	18,264,444	10,828,000	4,150,000	0		50,512,249
			Stay in Business					17,958,787	23,435,160	9,033,102	10,554,412	12,751,053	9,837,658		73,732,513
			Strategic					122,045,195	82,682,336	6,754,868	0	0	0		211,482,400
			Tech Transfers					8,269,535	24,545,300	86,826,719	12,779,884	45,945,909	30,263,657		178,367,347
			Total					553,221,747

		Oceanside
		MO5 2016 - Capital Forecast - Site Business Plan View: Capital Projects Without Expense Portions

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget
1		6DM	GNE Oceanside Prod Ops	QSP	Stay in Business					2,883,439	3,171,783	3,488,961	3,837,857	4,221,643	4,643,807	22,247,489
2		90024	NIMO Small Projects - Misc	QSP	Stay in Business					1,552,621	1,707,883	1,878,671	2,066,538	2,273,192	2,500,511	11,979,417
3		96204	322 MRO Racks	RTO	SHE and K-Directives	TBD	TBD				-	481,290	-	-	-	-	481,290
4		74455	3rd HCCF Vessel	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				1,951,571	109,168	-	-	-	-	2,060,739
5		74489	4040 Avenida Conference Center Acquisition	QSP	Strategic	Exceptional Culture	Kara Swedberg				661,148	-	-	-	-	-	661,148
6		74416	Asphyxiant Gas Remediation	RTO	SHE and K-Directives	Highly Capable Workforce	Gary Merrill				136,797	385,032	-	-	-	-	521,829
7		74524	Bioburden 2606 IPA Exhaust Improvement	RTO	SHE and K-Directives	Reliability and Value	Geoff Wing				-	-	-	-	-	-	-
8		96113	Bulk Product Storage -20/-40	QSP	Improvements and Efficiencies	Launch Facility	TBD				-	-	-	-	9,625,800	-	9,625,800
9		74525	CIP Reliability and Efficiency - PI	RTO	Improvements and Efficiencies	Reliability and Value	Pierre Luong (TBD)				-	-	-	-	-	-	-
10		74406	Corrosive Chemical Compliance	RTO	SHE and K-Directives	Reliability and Value	Tim Lai				1,536,569	80,600	-	-	-	-	1,617,169
11		74368	Dev/Val Automation Capacity Expansion	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Matt Hunt / Ravi M.				9,626	-	-	-	-	-	9,626
12		74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	RTO	Stay in Business	Reliability and Value	Juan Pacio				294,549	629,527	-	-	-	-	924,077
13		96177	Efficiency Projects	TBD	Improvements and Efficiencies	Reliability and Value	TBD				-	2,887,740	2,887,740	2,887,740	2,887,740	2,887,740	14,438,700
14		74513	Electric Vehicle Charging Stations	CTT	Improvements and Efficiencies	Exceptional Culture	Sumner Tison				-	685,357	-	-	-	-	685,357
15		73367	FS & DS Automation Integration	CTT	Tech Transfers	Fit for Purpose	Pat Sraubol / Ravi M.				25,719	-	-	-	-	-	25,719
16		74119	Harvest Upgrade (New Centrifuge)	QSP	Strategic	Fit for Purpose	Ken Hamilton Mark Jones				6,739,385	4,652,980	-	-	-	-	11,392,365
17		74435	Hastelloy Chromatography Column (160cm)	QSP	Improvements and Efficiencies	Fit for Purpose	Bahar Dahi / Juan Pacio				-	1,491,036	-	-	-	-	1,491,036
18		74490	Hyfish Material Screening Operation	QSP	Improvements and Efficiencies	Reliability and Value	Fikret Kulenovic				407,057	-	-	-	-	-	407,057
19		74409	K6 Program - Project 1 - Replace DX HVAC Units	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	298,400	1,532,427	-	-	-	1,830,827
20		74512	K6 Program - Project 2 - B381 Compliance	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	320,860	401,075	-	-	-	721,935
21		74278	K6 Program - Project 3 - Replace Cold Room Compressors	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	508,242	4,647,336	4,647,336	481,290	-	10,284,205
22		74432	K6 Program - Project 4 - Replace Chillers	CTT	SHE and K-Directives	Fit for Purpose	Geoff Wing				-	2,550,837	6,401,157	5,775,480	3,513,417	-	18,240,891
23		96112	Maintenance Ops Shop Buildout	QSP	Improvements and Efficiencies	Fit for Purpose	Hayden Knox				-	481,290	2,406,450	-	-	-	2,887,740
24		74427	MCS Network Infrastructure Asset Replacement - 2016	QSP	Stay in Business	Reliability and Value	Myles Sumlin				1,871,256	-	-	-	-	2,252,437	4,123,693
25		74385	Media Prep Endotoxin/Bioburden Sampling	QSP	Stay in Business	Reliability and Value	Matt Forbes				240,645	2,647,095	-	-	-	-	2,887,740
26		74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	QSP	Stay in Business	Reliability and Value	Jonathan Clark				190,780	22,131	-	-	-	-	212,910
27		74404	Mezzanine Lift Media Prep: Phase 1B	QSP	SHE and K-Directives	Highly Capable Workforce	Dick Sloan				193,521	-	-	-	-	-	193,521
28		96132	Mezzanine Safety Shower/Eye Wash Station Install	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza				96,258	756,457	-	-	-	-	852,715
29		74279	New Media Technology - HTST / Adventitious	RTO	New Technologies	Reliability and Value	Will Jimenez				4,630,863	1,542,730	-	-	-	-	6,173,592
30		74453	NPI Pool Tanks	QSP	Strategic	Fit for Purpose	Ken Hamilton				658,929	3,733	-	-	-	-	662,663
31		74371	Odor Treatment	CTT	SHE and K-Directives	TBD	Tim Lai				-	721,935	4,090,965	-	-	-	4,812,900
32		74268	P2 Downstream Processing Expansion	QSP	Strategic	Fit for Purpose	Mark Jones / Dirk Ellison				88,945,863	32,115,591	-	-	-	-	121,061,454
33		74510	PCS Asset Replacement - 2016	QSP	Stay in Business	Fit for Purpose	Myles Sumlin				1,680,624	143,424	-	-	-	-	1,824,049
34		74486	PCS Controller Cabinet Asset Replacement	RTO	Stay in Business	Highly Capable Workforce	Jonathan Clark				2,208,159	105,884	-	-	-	-	2,314,042
35		74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	QSP	Stay in Business	Launch and Commercial Excellence	Hieu Ton				-	-	866,322	866,322	900,012	-	2,632,656
36		96116	PCS Process Support Equipment Integration	QSP	Improvements and Efficiencies	TBD	Sarah Maruccia				-	-	721,935	721,935	-	-	1,443,870
37		96205	Pressure Safety	RTO	SHE and K-Directives	TBD	TBD				-	3,369,030	-	-	-	-	3,369,030
38		96192	Pressure Safety Facility Mitigations	RTO	SHE and K-Directives	TBD	TBD				-	2,406,450	-	-	-	-	2,406,450
39		74487	Process VSD and SOV Asset Replacement	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				3,464,632	2,815,576	-	-	-	-	6,280,208
40		74426	Process VSD and SOV Replacement - 2015	QSP	Stay in Business	Reliability and Value	Jonathan Clark				476,512	-	-	-	-	-	476,512
41		96178	Process VSD and SOV Replacement - Phase 2	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	2,406,450	2,887,740	-	-	5,294,190
42		96179	Process VSD and SOV Replacement - Phase 3	QSP	Stay in Business	Highly Capable Workforce	Jonathan Clark				-	-	-	440,862	4,812,900	-	5,253,762		5-Year CAPEX Through 2020 / CHF
43		74418	QC Lab Reconfiguration & Equipment	QSP	Tech Transfers	Launch and Commercial Excellence	Amanda Gutierrez				1,846,346	1,509,331	-	-	-	-	3,355,677
44		96114	QC Testing Equipment for Launch Capability and Storage Requirements	QSP	Tech Transfers	Launch and Commercial Excellence	TBD				-	577,548	2,502,708	962,580	2,887,740	-	6,930,576
45		74511	QR018 Compliance Steam and Condensate Containment	QSP	Stay in Business	Reliability and Value	Anastasia Gandrik / Sumner Tison				1,870,582	2,959,452	-	-	-	-	4,830,034
46		96109	Sci&Eng Lab Equipment for NPI and Launch Capability	QSP	Tech Transfers	Launch and Commercial Excellence	Fikret Kulenovic				-	577,548	2,021,418	866,322	2,310,192	-	5,775,480
47		74382	Sci&Eng Lab Mods and Equipment	QSP	Strategic	Launch and Commercial Excellence	Fikret Kulenovic				5,998,976	470,489	-	-	-	-	6,469,465
48		74454	Seed Lab (20L Bioreactor)	QSP	Strategic	Fit for Purpose	Mark Jones / Paul Coon				919,136	339,357	-	-	-	-	1,258,493
49		74280	Spare Hasstelloy Columns	QSP	Stay in Business	Agile					-	-	-	-	-	-	-
50		73356	Supplemental BDU Sampling	CTT	Stay in Business	Launch and Commercial Excellence	Paul Crowley				151,870	-	-	-	-	-	151,870
51		96180	TMAC Waste System Improvements	RTO	Stay in Business	TBD	TBD				-	1,443,870	-	-	-	-	1,443,870
52		96191	UPSS Phase 2	RTO	Stay in Business	TBD	TBD				-	1,925,160	-	-	-	-	1,925,160
53		74526	Utility and Process Safety System	RTO	SHE and K-Directives	Reliability and Value	Charles Fuller				1,145,470	490,916	-	-	-	-	1,636,386
54		74527	Vessel 1020 Upgrade	QSP	Stay in Business	Fit for Purpose	Will Jimenez				-	4,677,176	-	-	-	-	4,677,176
55		96165	WAN Link Redundancy	TBD	Improvements and Efficiencies	Reliability and Value	Kelly Calderwell				-	1,925,160	-	-	-	-	1,925,160
56		74392	Water Reclaim System	CTT	SHE and K-Directives	Reliability and Value	Tim Lai				156,036	-	-	-	-	-	156,036
57		74302	Waterpooling Remediation	RTO	Stay in Business	Reliability and Value	Ken Hmilton / Tim Chen				355,847	49,704	-	-	-	-	405,550
58		74373	WFI Generation and Storage System / CUB Expansion	QSP	Strategic	Fit for Purpose	Tim Lai				5,316,457	-	-	-	-	-	5,316,457
59		74491	Etro Tech Transfer (NIC)	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				5,866,727	8,726,335	3,145,109	468,959	59,189	-	18,266,319
60		96124	Perjeta Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	8,464,538	59,468,467	1,324,606	336,234	36,848	69,630,692
61		96125	Flu A TechTransfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	8,464,538	23,840,519	1,324,606	33,629,663
62		96126	Flu B Tech Transfer	QSP	Tech Transfers	Launch and Commercial Excellence	Semsi Ensari				-	-	-	-	8,464,538	21,714,134	30,178,671
63		74127	Harvest Modifications Start-up	QSP	Strategic	Launch Facility	Ken Hamilton				120,323	2,189,870	-	-	-	-	2,310,192
64		74277	P2 DPE Start-Up	QSP	Strategic	Fit for Purpose	Dirk Ellison/ Ken Hamilton				4,294,269	38,773,613	6,502,101	-	-	-	49,569,982
65			Contingency					3,658,031	-	-	-	-	-	3,658,031
66		96999	Site Management Adjustments (if any)					(1,431,529)	-	-	-	-	-	(1,431,529)
			Total					0	0	0	151,125,060	142,192,129	105,369,292	36,218,816	66,614,406	35,360,083	536,879,785

			Improvements and Efficiencies					416,683	7,470,583	6,016,125	3,609,675	12,513,540	2,887,740		32,914,346
			New Technologies					4,630,863	1,542,730	0	0	0	0		6,173,592
			SHE and K-Directives					3,264,652	12,370,049	17,072,961	10,422,816	3,994,707	0		47,125,184
			Stay in Business					17,241,513	22,298,665	8,640,404	10,099,319	12,207,747	9,396,755		79,884,404
			Strategic					115,606,056	78,654,802	6,502,101	0	0	0		200,762,959
			Tech Transfers					7,738,792	19,855,300	67,137,702	12,087,005	37,898,412	23,075,587		167,792,798
			Contingecy and Site Judgedown					2,226,502	-	-	-	-	-		2,226,502
			Total					536,879,785

		Oceanside
		MO5 2016 - Expense Forecast - Expense Only and Expense Portions of Capital Projects to Identify Opportunity to Fund Expense Only Projects

		Nro.	Project Name	Driver	Category	Program	SME	Expenditure YE 2013	Expenditure YE 2014	Expenditure YE 2015	MO5 2016 / (2016 Preview)	MO5 2016 / (2017 Preview)	MO5 2016 / (2018 Preview)	MO5 2016 / (2019 Preview)	MO5 2016 / (2020 Preview)	MO5 2016 / (2021 Preview)	TOTAL MO5 Budget	Exp + YE + MO5 (CY) Total Project Expense	MO5 2016 (Year 2016) Expense Portion	MO5 2016 (Year 2017) Expense Portion	MO5 2016 (Year 2018) Expense Portion	MO5 2016 (Year 2019) Expense Portion	MO5 2016 (Year 2020) Expense Portion	MO5 2016 (Year 2021) Expense Portion
1		97048	Arc Flash Prevention	RTO	SHE and K-Directives	Highly Capable Workforce	Marcus Espinoza	-	-	-	319,456	-	-	-	-	-	319,456	319,456	319,456	-	-	-	-	-					0	0	0	0	0
2		97007	Automation System Lifecycle MCS Upgrade	QSP	Improvements and Efficiencies	Reliability and Value	Myles Sumlin	-	-	-	295,169	-	-	-	-	-	295,169	295,169	295,169	-	-	-	-	-					0	0	0	0	0
3		97059	B311 & B321 Gowning Room Modifications	RTO	Stay in Business	Reliability and Value	TBD	-	-	-	107,000	-	-	-	-	-	107,000	107,000	107,000	-	-	-	-	-					0	0	0	0	0
4		97057	Conference Room 315 Expansion	TBD	Improvements and Efficiencies	Exceptional Culture	N/A	-	-	-	108,000	192,000	-	-	-	-	300,000	300,000	108,000	192,000	-	-	-	-					0	0	0	0	0
5		97042	CRB Project Budget Estimating	QSP	Improvements and Efficiencies	Reliability and Value	TBD	-	-	-	250,400	-	-	-	-	-	250,400	250,400	250,400	-	-	-	-	-					0	0	0	0	0
6		97054	HVAC Retro Commissioning	CTT	Stay in Business	Reliability and Value		-	-	-	-	113,000	44,000	-	-	-	157,000	157,000	-	113,000	44,000	-	-	-					0	0	0	0	0
7		82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	CTT	Stay in Business	Reliability and Value	Jonathan Clark	-	-	70,227	933,708	781,722	-	-	-	-	1,715,430	1,785,657	933,708	781,722	-	-	-	-					0	0	0	0	0
8		97044	IMPACT Support	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	8,000	-	-	-	-	-	8,000	8,000	8,000	-	-	-	-	-					0	0	0	0	0
9		98026	Launch Capability Program (LCP)	QSP	Tech Transfers	Launch and Commercial Excellence	TBD	-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
10		97001	Lunches	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	4,000	-	-	-	-	-	4,000	4,000	4,000	-	-	-	-	-					0	0	0	0	0
11		97015	MCS Backup System Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	390,000	-	-	-	-	390,000	390,000	-	390,000	-	-	-	-					0	0	0	0	0
12		97016	MCS Backup System Asset Replacement - 2020	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	439,000	-	439,000	439,000	-	-	-	-	439,000	-					0	0	0	0	0
13		97031	MCS Data Analytics Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	TBD	-	-	-	-	325,000	-	-	-	-	325,000	325,000	-	325,000	-	-	-	-					0	0	0	0	0
14		97032	MCS Data Analytics Asset Replacement - 2020	QSP	Stay in Business	Reliable	TBD	-	-	-	-	-	-	-	360,000	-	360,000	360,000	-	-	-	-	360,000	-					0	0	0	0	0
15		97005	MCS Peripheral Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	312,000	-	-	-	-	312,000	312,000	-	312,000	-	-	-	-					0	0	0	0	0
16		97006	MCS Peripheral Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	332,000	-	-	332,000	332,000	-	-	-	332,000	-	-					0	0	0	0	0
17		97063	MCS Peripheral Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	351,000	351,000	351,000	-	-	-	-	-	-					0	0	0	0	0
18		97009	MES Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Ravi Medandravu	-	-	-	-	400,000	575,000	-	-	-	975,000	975,000	-	400,000	575,000	-	-	-					0	0	0	0	0
19		97010	MES Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	500,000	525,000	1,025,000	1,025,000	-	-	-	-	500,000	525,000					0	0	0	0	0
20		97003	MFG Systems Integration Improvement Phase 1 - 2015	CTT	Improvements and Efficiencies	Reliability and Value	Eric Davis	-	-	-	443,000	-	-	-	-	-	443,000	443,000	443,000	-	-	-	-	-					0	0	0	0	0
21		97030	MFG Systems Integration Improvement Phase 3 - 2017	QSP	Improvements and Efficiencies	Fit for Purpose	TBD	-	-	-	-	1,625,000	-	-	-	-	1,625,000	1,625,000	-	1,625,000	-	-	-	-					0	0	0	0	0
22		97002	Office Supplies inc. Laptops	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	45,000	-	-	-	-	-	45,000	45,000	45,000	-	-	-	-	-					0	0	0	0	0
23		97058	Parking Pavement Repair	CTT	Stay in Business	Reliability and Value	Sumner Tison	-	-	-	245,040	-	-	-	-	-	245,040	245,040	245,040	-	-	-	-	-					0	0	0	0	0
24		97008	PCS Asset Replacement - 2019	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	487,500	487,500	-	-	975,000	975,000	-	-	487,500	487,500	-	-					0	0	0	0	0
25		97064	PCS Asset Replacement - 2021	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	-	463,000	463,000	463,000	-	-	-	-	-	463,000					0	0	0	0	0
26			PCS Asset Replacement Depreciation Write-Off	TBD	TBD			-	-	-	800,000	-	-	-	-	-	800,000	800,000	800,000	-	-	-	-	-					0	0	0	0	0
27		97066	PCS Automated Documentation Asset Replacement - 2021	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	-	-	-	360,000	360,000	360,000	-	-	-	-	-	360,000					0	0	0	0	0
28		97033	PCS Automated Documentation Upgrade	QSP	New Technologies	Reliable	TBD	-	-	-	-	-	325,000	-	-	-	325,000	325,000	-	-	325,000	-	-	-					0	0	0	0	0
29		97038	PCS Functional Specification Development Project (CAPA 960297)	RTO	Strategic	Reliability and Value	Sarah Maruccia	-	-	-	-	4,750,000	3,250,000	-	-	-	8,000,000	8,000,000	-	4,750,000	3,250,000	-	-	-					0	0	0	0	0
30		97039	PCS Remediation for EBR Review by Exception - PI	QSP	Improvements and Efficiencies	Highly Capable Workforce	Malou Jacinto / Stephanie Huntress	-	-	-	-	250,000	2,250,000	3,375,000	-	-	5,875,000	5,875,000	-	250,000	2,250,000	3,375,000	-	-					0	0	0	0	0
31		97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	488,000	-	-	-	488,000	488,000	-	-	488,000	-	-	-					0	0	0	0	0
32		97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020	QSP	Stay in Business	Reliable	Ravi Medandravu	-	-	-	-	-	-	-	488,000	-	488,000	488,000	-	-	-	-	488,000	-					0	0	0	0	0
33		TBD	Piping Corrosion	TBD	Stay in Business	Reliability and Value	TBD	-	-	-	3,091,211	3,000,000	3,000,000	-	-	-	9,091,211	9,091,211	3,091,211	3,000,000	3,000,000	-	-	-					0	0	0	0	0
34		97053	Pressure Safety Program - PI Phase	TBD	SHE and K-Directives	TBD	TBD	-	-	-	100,000	-	-	-	-	-	100,000	100,000	100,000	-	-	-	-	-					0	0	0	0	0
35		97060	QC Gas Cabinet Removal	QSP	TBD	TBD	Joe Molon	-	-	-	75,000	-	-	-	-	-	75,000	75,000	75,000	-	-	-	-	-					0	0	0	0	0
36		97037	Recipe Reconfiguration Alignment for Operating Systems	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	Marco Baca	-	-	-	-	3,750,000	-	-	-	-	3,750,000	3,750,000	-	3,750,000	-	-	-	-					0	0	0	0	0
37		97012	Site Data Historian Asset Replacement - 2017	QSP	Stay in Business	Fit for Purpose	Myles Sumlin	-	-	-	-	366,000	-	-	-	-	366,000	366,000	-	366,000	-	-	-	-					0	0	0	0	0
38		97013	Site Data Historian Asset Replacement - 2019	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	488,000	-	-	488,000	488,000	-	-	-	488,000	-	-					0	0	0	0	0
39		97065	Site Data Historian Asset Replacement - 2021	QSP	Stay in Business	Reliable	Myles Sumlin	-	-	-	-	-	-	-	-	488,000	488,000	488,000	-	-	-	-	-	488,000					0	0	0	0	0
40		97045	Site Exterior Lighting Upgrade - Title 24	CTT	SHE and K-Directives	Reliability and Value	Charles Fuller	-	-	-	100,000	100,000	-	-	-	-	200,000	200,000	100,000	100,000	-	-	-	-					0	0	0	0	0
41		97061	Tangential Flow Filtration Cassettes Management	RTO	Improvements and Efficiencies	Reliability and Value	Stephanie Huntress	-	-	-	-	550,000	-	-	-	-	550,000	550,000	-	550,000	-	-	-	-					0	0	0	0	0
42		97043	Travel Expenses	QSP	Stay in Business	Reliability and Value	TBD	-	-	-	10,000	-	-	-	-	-	10,000	10,000	10,000	-	-	-	-	-					0	0	0	0	0
			Capital Projects - Expense Portion					0	0	70,227	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540	7,647,987	7,718,214	2,034,273	2,507,146	1,527,068	973,000	340,960	265,540					0
			Total					0	0	70,227	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,452,540	51,363,693	51,504,148	9,769,257	19,411,868	11,946,568	5,655,500	2,127,960	2,101,540

			Improvements and Efficiencies					1,096,569	6,367,000	2,250,000	3,375,000	0	0			$9,769,257
			New Technologies					0	0	325,000	0	0	360,000			$-
			SHE and K-Directives					519,456	100,000	0	0	0	0
			Stay in Business					4,443,959	5,687,722	4,594,500	1,307,500	1,787,000	1,827,000
			Strategic					0	4,750,000	3,250,000	0	0	0
			Tech Transfers					800,000	0	0	0	0	0

## SmartSheet_Dashboard
Project Number	Project Name	Total	Capital	Expense	Internal	External	Program	Status
74489	4040 Avenida Conference Center Acquisition	685700	685700	0	0.0	0.0	Exceptional Culture	Execute
74513	Electric Vehicle Charging Stations	0	0	0	0.0	0.0	Exceptional Culture	Hold
96137	Security Systems Upgrade	200000	200000	0	0.0	0.0	Exceptional Culture	JPMT Appr
96197	Security Systems Upgrade	0	0	0	0.0	0.0	#N/A	#N/A
97057	Conference Room 315 Expansion	150000	0	150000	0.0	0.0	Exceptional Culture	Idea

73367	FS & DS Automation Integration	26719	26719	0	0.2	0.8	Fit for Purpose	Execute 2
74119	Harvest Upgrade (New Centrifuge)	4635852	4614221	21631	0.4	0.8	Fit for Purpose	Execute 2
74268	P2 Downstream Processing Expansion	93629477	91862606	1766871	3.7	7.6	Fit for Purpose	Execute 2
74277	P2 DPE Start-Up	4461207	4461207	0	0.0	0.0	Fit for Purpose	Execute
74278	K6 Program - Project 3 - Replace Cold Room Compressors	0	0	0	0.2	0.0	Fit for Purpose	FXNL LT Appr
74373	WFI Generation and Storage System / CUB Expansion	5536207	5512468	23739	4.4	11.1	Fit for Purpose	Execute 2
74409	K6 Program - Project 1 - Replace DX HVAC Units	0	0	0	0.1	1.5	Fit for Purpose	Execute
74432	K6 Program - Project 4 - Replace Chillers	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
74435	Hastelloy Chromatography Column (160cm)	400000	400000	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
74453	NPI Pool Tanks	604255	601771	2484	0.0	0.0	Fit for Purpose	PTAA
74454	Seed Lab (20L Bioreactor)	1010193	912870	97323	0.0	0.0	Fit for Purpose	Execute
74455	3rd HCCF Vessel	1704489	1669681	34808	0.0	0.0	Fit for Purpose	Execute
74510	PCS Asset Replacement - 2016	1766058	1765839	219	0.0	0.0	Fit for Purpose	Execute
74512	K6 Program - Project 2 - B381 Compliance	0	0	0	0.1	1.5	Fit for Purpose	FXNL LT Appr
74527	Vessel 1020 Upgrade	0	0	0	0.0	0.0	Fit for Purpose	Idea
96069	Warehouse Crown Forklift Asset Replacement	0	0	0	0.0	0.0	Fit for Purpose	Hold
96112	Maintenance Ops Shop Buildout	0	0	0	0.0	0.0	Fit for Purpose	Budgeted
96136	V-3007 Replacement	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
96159	OCC Network Remediation	150000	150000	0	0.0	0.0	Fit for Purpose	Idea
65018	Spare Bowl for Hermetic Centrifuge	320000	320000	0	0.0	0.0	Fit for Purpose	Execute
96169	Level Indicator Transmitters	70000	70000	0	0.0	0.0	Fit for Purpose	Idea
96991	Asset Replacement 2016 - Engineering (cc642)	1007097	987350	19747	0.0	0.0	Fit for Purpose	FXNL LT Appr
96992	Asset Replacement 2016 - Material Ops (cc484)	126480	124000	2480	0.0	0.0	Fit for Purpose	FXNL LT Appr
96993	Asset Replacement 2016 - Manufacturing (cc1359)	50375	50375	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
96994	Asset Replacement 2016 - Manufacturing	268268	263008	5260	0.0	0.0	Fit for Purpose	FXNL LT Appr
96995	Asset Replacement 2016 - Quality	407893	407893	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
96996	Asset Replacement 2016 - Technology	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
96997	Asset Replacement 2016 - Facilities Ops	31233	31233	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
97005	MCS Peripheral Asset Replacement - 2017	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
97009	MES Asset Replacement - 2017	0	0	0	0.0	0.0	Fit for Purpose	Idea
97012	Site Data Historian Asset Replacement - 2017	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
97015	MCS Backup System Asset Replacement - 2017	0	0	0	0.0	0.0	Fit for Purpose	FXNL LT Appr
97029	Study for K6 Program - Project 4 - Replace Chillers	0	0	0	0.0	0.0	#N/A	#N/A
97030	MFG Systems Integration Improvement Phase 3 - 2017	0	0	0	0.0	0.0	Fit for Purpose	Canceled
97031	MCS Data Analytics Asset Replacement - 2017	0	0	0	0.0	0.0	Fit for Purpose	Idea

73384	Caustic Bath Upgrade	459	459	0	0.0	0.0	Highly Capable Workforce	Execute
73399	Frit Handling and Storage	153215	153215	0	0.0	0.0	Highly Capable Workforce	Execute
73409	Solar Power Enabling Project	307216	307216	0	0.2	0.0	Highly Capable Workforce	Execute
74404	Mezzanine Lift Media Prep: Phase 1B	270009	270440	-431	0.1	0.0	Highly Capable Workforce	Execute
74416	Asphyxiant Gas Remediation	126295	126295	0	0.1	0.4	Highly Capable Workforce	Execute 1
74486	PCS Controller Cabinet Asset Replacement	2294000	2294000	0	0.0	0.0	Highly Capable Workforce	Execute
74487	Process VSD and SOV Asset Replacement	3599797	3599797	0	0.0	0.0	Highly Capable Workforce	Execute
76643	Optimize Column Movement Device	143425	143425	0	0.0	0.0	Highly Capable Workforce	Execute
96105	TMAC Tenderizer	0	0	0	0.0	0.0	Highly Capable Workforce	Hold
96132	Mezzanine Safety Shower/Eye Wash Station Install	0	0	0	0.3	0.0	#N/A	#N/A
96135	QC Spectrophotometers	0	0	0	0.0	0.0	Highly Capable Workforce	Canceled
65066	Appleton Tank Mover	73000	73000	0	0.0	0.0	Highly Capable Workforce	Hold
65021	Hazardous Material Response Cart	17985	17985	0	0.0	0.0	Highly Capable Workforce	Execute
96164	Hazardous Materials Containers Washing Station	0	0	0	0.0	0.0	Highly Capable Workforce	Hold
96168	Replace Warehouse #321 Sprinkler Heads	20000	20000	0	0.0	0.0	Highly Capable Workforce	Idea
65009	Drum Mover/Raw Material Tenderizer	34000	30000	4000	0.0	0.0	Highly Capable Workforce	Execute
96178	Process VSD and SOV Replacement - Phase 2	0	0	0	0.0	0.0	Highly Capable Workforce	Idea
96179	Process VSD and SOV Replacement - Phase 3	0	0	0	0.0	0.0	Highly Capable Workforce	Idea
97039	PCS Remediation for EBR Review by Exception - PI	0	0	0	0.0	0.0	Highly Capable Workforce	Idea
97048	Arc Flash Prevention	318000	0	318000	0.0	0.0	Highly Capable Workforce	Execute

64914	QC M9 TOC Analyzers	17480	17480	0	0.0	0.0	Launch and Commercial Excellence	Execute
64923	QC Met-One Air Sampler Replacement 2015	15885	15885	0	0.0	0.0	Launch and Commercial Excellence	Execute
64927	QC Gel Imager Replacement 2015	987	987	0	0.0	0.0	Launch and Commercial Excellence	Execute
73356	Supplemental BDU Sampling	157774	157774	0	1.7	6.6	Launch and Commercial Excellence	Execute 2
73388	SIMCA Online Real Time Process Monitoring System	0	0	0	0.2	0.6	Launch and Commercial Excellence	Execute
74368	Dev/Val Automation Capacity Expansion	10000	10000	0	0.0	0.0	Launch and Commercial Excellence	Execute
74382	Sci&Eng Lab Mods and Equipment	7610223	7414885	195338	4.0	1.8	Launch and Commercial Excellence	Execute 2
74418	QC Lab Reconfiguration & Equipment	3274674	3160674	114000	1.8	3.6	Launch and Commercial Excellence	Execute 1
74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	0	0	0	1.0	2.0	Launch and Commercial Excellence	FXNL LT Appr
74491	Etro Tech Transfer	1364276	1295272	69004	0.0	0.0	Launch and Commercial Excellence	Hold
96109	Sci&Eng Lab Equipment for NPI and Launch Capability	0	0	0	0.0	0.0	Launch and Commercial Excellence	Canceled
96114	QC Testing Equipment for Launch Capability and Storage Requirements	0	0	0	0.0	0.0	Launch and Commercial Excellence	Canceled
96124	Perjeta Tech Transfer	0	0	0	0.0	0.0	Launch and Commercial Excellence	Idea
96125	Flu A TechTransfer	0	0	0	0.0	0.0	Launch and Commercial Excellence	Idea
96126	Flu B Tech Transfer	0	0	0	0.0	0.0	Launch and Commercial Excellence	Idea
96133	QC Rapid Scan RDI System	0	0	0	0.0	0.0	Launch and Commercial Excellence	Hold
96134	QC Liquid Handler	0	0	0	0.0	0.0	#N/A	#N/A
65023	QC Plate Washer for Potency Assay	56795	56795	0	0.0	0.0	Launch and Commercial Excellence	Execute
65024	Sci&Eng Lab Incubator and Freezer Asset Replacement	129028	129028	0	0.0	0.0	Launch and Commercial Excellence	Execute
65040	Sci&Eng Cryofreezer	20185	20185	0	0.0	0.0	Launch and Commercial Excellence	Execute
97037	Recipe Reconfiguration Alignment for Operating Systems	0	0	0	0.0	0.0	Launch and Commercial Excellence	FXNL LT Appr
97040	Tech Transfer: Master Data Management	0	0	0	0.0	0.0	Launch and Commercial Excellence	FXNL LT Appr
97051	MFG Electronic Use Logs (Syncade)	0	0	0	0.0	0.0	Launch and Commercial Excellence	Placeholder

64901	MCS Peripheral Asset Replacement - 2015	43151	43151	0	0.1	0.0	Reliability and Value	Execute
73387	MCSBACKUP Phase 2 Tape Retrieval	0	0	0	0.1	0.0	Reliability and Value	Execute
73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	215828	215828	0	0.0	0.4	Reliability and Value	Execute
74279	New Media Technology - HTST / Adventitious	4947130	4859034	88096	4.1	7.9	Reliability and Value	Execute 2
74302	Waterpooling Remediation	369680	369680	0	0.3	0.8	Reliability and Value	Execute 2
74385	Media Prep Endotoxin/Bioburden Sampling	0	0	0	0.0	0.0	Reliability and Value	Hold
74392	Water Reclaim System	143846	143846	0	0.3	0.0	Reliability and Value	Execute
74406	Corrosive Chemical Compliance	1724239	1724239	0	0.3	0.0	Reliability and Value	Execute
74426	Process VSD and SOV Replacement - 2015	589735	589735	0	0.1	0.7	Reliability and Value	Execute
74427	MCS Network Infrastructure Asset Replacement - 2016	1466000	1466000	0	0.0	0.0	Reliability and Value	Execute
74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	204573	204573	0	0.2	0.8	Reliability and Value	Execute
74431	Buffer Prep Mezzanine Lift Construction	442000	442000	0	0.2	0.0	Reliability and Value	JPMT Appr
74490	Hyfish Material Screening Operation	601445	601445	0	0.0	2.0	Reliability and Value	Execute
74511	QR018 Compliance Steam and Condensate Containment	1943300	1943300	0	0.0	0.0	Reliability and Value	Execute
74524	Bioburden 2606 IPA Exhaust Improvement	14571	0	14571	0.0	0.0	Reliability and Value	Execute
74526	Utility and Process Safety System	1882404	1882404	0	0.0	1.0	Reliability and Value	FXNL LT Appr
96139	Trash Bin Storm Water Mitigation	0	0	0	0.3	0.9	Exceptional Culture	FXNL LT Appr
96160	B331 HVAC Fire Code Compliance	0	0	0	0.0	0.0	#N/A	#N/A
96163	MFG Depth Filter Housing	0	0	0	0.0	0.0	Reliability and Value	Idea
96165	WAN Link Redundancy	0	0	0	0.0	0.0	Reliability and Value	Hold
96167	Emergency Generator High Level Alarm	25000	25000	0	0.0	0.0	Reliability and Value	Idea
65005	Analytical Scale	24238	24238	0	0.0	0.0	Reliability and Value	Execute
65020	QC Auto-Pipettor for Potency Assay	27987	27987	0	0.0	0.0	Reliability and Value	Execute
65015	Lower Solid Collector for Centrifuge	142000	142000	0	0.0	0.0	Reliability and Value	Execute
74535	Draining of Top Mounted Agitator Well (CAPA 1140940)	306000	306000	0	0.4	2.0	Reliability and Value	Execute
65044	Additional MCS Backup Storage	62000	62000	0	0.0	0.0	Reliability and Value	Execute
65037	Analytical Scales (CAPA 1150248)	23997	23997	0	0.0	0.0	Reliability and Value	Execute
65048	Process Maintenance Boroscope	35008	35008	0	0.0	0.0	Reliability and Value	Execute
96177	Efficiency Projects	0	0	0	0.0	0.0	Reliability and Value	Placeholder
TBD	Piping Corrosion	3102350	0	3102350	0.0	0.0	Reliability and Value	Execute
96207	Weigh and Dispense Sink (CAPA1123109)	165000	150000	15000	0.1	0.1	Reliability and Value	FXNL LT Appr
96208	RF Sealer Generator	0	0	0	0.0	0.0	TBD	Idea
97042	CRB Project Budget Estimating	250400	0	250400	0.0	0.0	Reliability and Value	Execute
97043	Travel Expenses	10000	0	10000	0.0	0.0	Reliability and Value	Execute
97001	Lunches	4000	0	4000	0.0	0.0	Reliability and Value	Execute
97002	Office Supplies inc. Laptops	45000	0	45000	0.0	0.0	Reliability and Value	Execute
97044	IMPACT Support	8000	0	8000	0.0	0.0	Reliability and Value	Execute
82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)	866058	0	866058	0.3	0.0	Reliability and Value	Execute 1
97003	MFG Systems Integration Improvement Phase 1 - 2015	292227	0	292227	1.1	0.0	Reliability and Value	Execute 1
97007	Automation System Lifecycle MCS Upgrade	295781	0	295781	0.6	1.5	Reliability and Value	Execute
97020	Trailers (inc. fluor mods space and PacVan, janitorial, coffe/tea, mat services, pest control)	0	0	0	0.0	0.0	#N/A	#N/A
97038	PCS Functional Specification Development Project (CAPA 960297)	0	0	0	0.0	0.0	Reliability and Value	FXNL LT Appr
97045	Site Exterior Lighting Upgrade - Title 24	100000	0	100000	0.0	0.0	Reliability and Value	FXNL LT Appr
97054	HVAC Retro Commissioning	0	0	0	0.0	0.0	Reliability and Value	FXNL LT Appr
97058	Parking Pavement Repair	245040	0	245040	0.0	0.0	Reliability and Value	Execute
97059	B311 & B321 Gowning Room Modifications	100492	0	100492	0.0	0.0	Reliability and Value	Execute
97061	Tangential Flow Filtration Cassettes Management	0	0	0	0.0	0.0	#N/A	#N/A

74371	Odor Treatment	0	0	0	0.1	0.0	TBD	FXNL LT Appr
74376	Paperless Sys Val Lifecycle Mgmt	0	0	0	0.0	0.0	#N/A	#N/A
74383	Vent Housings (six) on Production Bioreactors	0	0	0	0.0	0.0	#N/A	#N/A
96022	WFI Pump Autostart	0	0	0	0.0	0.0	TBD	Hold
96116	PCS Process Support Equipment Integration	0	0	0	0.0	0.0	TBD	Idea
96161	QC Lab Gas Cabinet Removal	0	0	0	0.0	0.0	#N/A	#N/A
73442	V-2170 Agitator Drain Valve	0	0	0	0.0	0.0	#N/A	#N/A
96174	Fall Protection Phase II	130000	130000	0	0.0	0.0	TBD	CA Routing
96180	TMAC Waste System Improvements	0	0	0	0.0	0.0	TBD	Hold
96181	Fall Protection Phase 3	0	0	0	0.0	0.0	Highly Capable Workforce	FXNL LT Appr
96182	Cafe Flooring	0	0	0	0.0	0.0	#N/A	#N/A
96183	Site Signage Upgrade	0	0	0	0.0	0.0	TBD	Idea
96184	Conference Center	0	0	0	0.0	0.0	#N/A	#N/A
96185	Machine Guarding- Warehouse	0	0	0	0.0	0.0	#N/A	#N/A
96186	Office Ergonomics- phase 2	0	0	0	0.0	0.0	#N/A	#N/A
96187	K22 Direcitve Compliance- Chemical Safety	0	0	0	0.0	0.0	#N/A	#N/A
96188	Eye wash stations in mfg. gowning rooms	0	0	0	0.0	0.0	#N/A	#N/A
96189	Pipe Labelling	0	0	0	0.0	0.0	#N/A	#N/A
96190	Lab Compliance Issues following Lab Rennovation Projects	0	0	0	0.0	0.0	#N/A	#N/A
96191	UPSS Phase 2	0	0	0	0.0	0.0	TBD	Idea
96192	Pressure Safety Facility Mitigations	0	0	0	0.0	0.0	#N/A	#N/A
96193	Column Packing Fall Hazard	0	0	0	0.0	0.0	TBD	Canceled
96194	Harvest Depth Filter Mitigations (fall/ ergo)	0	0	0	0.0	0.0	#N/A	#N/A
96195	K6- All Design	0	0	0	0.0	0.0	#N/A	#N/A
96196	Fire Safety- Gap Assessment Mitigations (TBD)	0	0	0	0.0	0.0	#N/A	#N/A
96198	Crane & Hoist Mitigation	0	0	0	0.0	0.0	#N/A	#N/A
96199	Site Safety Signage	0	0	0	0.0	0.0	#N/A	#N/A
96200	Bottle Washing: FIFRA Program	0	0	0	0.0	0.0	#N/A	#N/A
96201	Storm Water BMP for upper lot	0	0	0	0.0	0.0	TBD	Idea
96202	Drum Crusher	0	0	0	0.0	0.0	#N/A	#N/A
96204	322 MRO Racks	0	0	0	0.0	0.0	TBD	Hold
96205	Pressure Safety	0	0	0	0.0	0.0	#N/A	#N/A
96206	Lab Earthquake restraints	0	0	0	0.0	0.0	#N/A	#N/A
97049	SIMCA Online - Downstream Application	0	0	0	0.0	0.0	TBD	Execute
97052	MFG P1 Actemra Horiba Replacement	0	0	0	0.0	0.0	TBD	Placeholder
97053	Pressure Safety Program - PI Phase	100000	0	100000	0.0	0.0	Highly Capable Workforce	Execute
97060	QC Gas Cabinet Removal	75000	0	75000	0.0	0.0	TBD	FXNL LT Appr
97062	PI- Ammonia RMP Study	0	0	0	0.0	0.0	TBD	Idea
96999	Site Management Adjustments (if any)	0	0	0	0.0	0.0	0	TBD
74126	Debottlenecking Start-up	0	0	0	0.0	0.0	#N/A	#N/A
96104	Lighting Work on OCN Campus Pathways	0	0	0	0.0	0.0	#N/A	#N/A
96143	Paperless Metone	0	0	0	0.0	0.0	ACCR	Hold
73366	MCS (PCS and MES) System Access and Account Management Enhancement	0	0	0	0.0	0.0	#N/A	#N/A
73406	Guided Wave Radar V-4045 & V-4055	17477	17477	0	0.4	0.4	Agile	Execute
74280	Spare Hasstelloy Columns	0	0	0	0.0	0.0	Agile	Execute
74386	4040 Avenida Conference Center	0	0	0	0.1	0.0	#N/A	#N/A
74485	4040 Avenida Conference Center Improvements	0	0	0	0.1	0.0	#N/A	#N/A
76642	AV System and Equipment Refresh	0	0	0	0.0	0.0	#N/A	#N/A
96040	GWR 1080/1090	0	0	0	0.5	0.3	Agile	Hold
97021	QC Lab Space Integrity	0	0	0	0.0	0.0	#N/A	#N/A
97022	MFG Systems Integration Improvement Phase 2 - 2016	0	0	0	0.0	0.0	#N/A	#N/A
97034	Landscaping Design	0	0	0	0.0	0.0	#N/A	#N/A
64709	MES Load Balancers (F5)	0	0	0	0.0	0.0	#N/A	#N/A
64777	Biosafety & Laminar Flow Hood Asset Replacement	0	0	0	0.1	0.0	#N/A	#N/A
64786	Cedex System for Sci&Eng Asset Replacement	0	0	0	0.1	0.0	#N/A	#N/A
64843	QC Potency Centrifuges - Asset Replacement 2014	0	0	0	0.0	0.0	#N/A	#N/A
64844	QC Ice Maker - Asset Replacement 2014	0	0	0	0.0	0.0	#N/A	#N/A
64873	QC Milli-Q Water System Asset Replacement	0	0	0	0.0	0.0	#N/A	#N/A
64882	QC Microbiology Incubators	0	0	0	0.0	0.0	#N/A	#N/A
64889	QC Microbiology Freezers	0	0	0	0.0	0.0	#N/A	#N/A
64898	Terumo Sterile BCT SCDIIB Welders	0	0	0	0.0	0.0	#N/A	#N/A
64899	Engineering Library TOP Storage Unit	4011	4011	0	0.0	0.0	Reliable	Execute
64922	QC Mettler Toledo Balances Replacement 2015	0	0	0	0.0	0.0	#N/A	#N/A
64924	QC Biotek LAL Reader Replacement 2015	0	0	0	0.0	0.0	#N/A	#N/A
64925	QC UV Vis Spectometer Replacement 2015	21531	21531	0	0.0	0.0	Reliable	Execute
64926	QC SpeedVac Replacement 2015	0	0	0	0.0	0.0	#N/A	#N/A
73368	Cooling Tower Water Filtration System	0	0	0	0.0	0.0	#N/A	#N/A
73383	Actemra Freezer Installation	0	0	0	0.1	0.2	#N/A	#N/A
73392	Automated Cooling of V-2194	0	0	0	0.0	0.0	#N/A	#N/A
74244	Cell Culture Sampling - NovaFlex	0	0	0	0.3	2.5	#N/A	#N/A
74449	TDS Remediation 2015	0	0	0	0.1	0.0	#N/A	#N/A
96117	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2019	0	0	0	0.0	0.0	Reliable	Idea
96140	North Lot Storm Water Mitigation	0	0	0	0.0	0.0	#N/A	#N/A
64992	QC Osmometer Asset Replacement	0	0	0	0.0	0.0	Reliable	Execute
64994	Helium Sniffer Replacement	0	0	0	0.0	0.0	Reliable	Execute
96998	Asset Replacement 2016 - BMSO	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97006	MCS Peripheral Asset Replacement - 2019	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97063	MCS Peripheral Asset Replacement - 2021	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97008	PCS Asset Replacement - 2019	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97064	PCS Asset Replacement - 2021	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97010	MES Asset Replacement - 2020	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97011	Site Data Historian Upgrade - 2014	0	0	0	0.0	0.0	#N/A	#N/A
97013	Site Data Historian Asset Replacement - 2019	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97065	Site Data Historian Asset Replacement - 2021	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97016	MCS Backup System Asset Replacement - 2020	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97017	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2014	0	0	0	0.0	0.0	#N/A	#N/A
97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020	0	0	0	0.0	0.0	Reliable	FXNL LT Appr
97032	MCS Data Analytics Asset Replacement - 2020	0	0	0	0.0	0.0	Reliable	Idea
97033	PCS Automated Documentation Upgrade	0	0	0	0.0	0.0	Reliable	Idea
97066	PCS Automated Documentation Asset Replacement - 2021	0	0	0	0.0	0.0	Reliable	Idea
97036	Locker Room Floor Replacement	0	0	0	0.0	0.0	#N/A	#N/A
97046	Hazardous Waste Storage Bunker	0	0	0	0.0	0.0	Reliable	Execute
97047	Flammable Storage Cabinets Upgrade	0	0	0	0.0	0.0	Reliable	Execute
73377	Upstream Capacity Buildout (PI/CD)	0	0	0	0.8	0.0	#N/A	#N/A
74127	Harvest Modifications Start-up	125000	125000	0	0.0	0.0	Launch Facility	Budgeted
74488	Etro Molecule	0	0	0	11.0	0.0	#N/A	#N/A
96113	Bulk Product Storage -20/-40	0	0	0	0.0	0.0	Launch Facility	Placeholder

## Deleted_Projects
64709	MES Load Balancers (F5)
64777	Biosafety & Laminar Flow Hood Asset Replacement
64786	Cedex System for Sci&Eng Asset Replacement
64843	QC Potency Centrifuges - Asset Replacement 2014
64844	QC Ice Maker - Asset Replacement 2014
64873	QC Milli-Q Water System Asset Replacement
64882	QC Microbiology Incubators
64889	QC Microbiology Freezers
64898	Terumo Sterile BCT SCDIIB Welders
64922	QC Mettler Toledo Balances Replacement 2015
64924	QC Biotek LAL Reader Replacement 2015
64926	QC SpeedVac Replacement 2015
73323	Stainless Steel HMI Replacement
73328	Filter Integrity Testers
73363	Bioreactor Piping Corrections (CAPA)
73366	MCS (PCS and MES) System Access and Account Management Enhancement
73368	Cooling Tower Water Filtration System
73377	Upstream Capacity Buildout (PI/CD)
73383	Actemra Freezer Installation
73388	SIMCA Online Real Time Process Monitoring System
73392	Automated Cooling of V-2194
74126	Debottlenecking Start-up
74244	Cell Culture Sampling - NovaFlex
74280	Spare Hasstelloy Columns
74374	Process Data Analytics
74376	Paperless Sys Val Lifecycle Mgmt
74383	Vent Housings (six) on Production Bioreactors
74386	4040 Avenida Conference Center
74430	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)
74449	TDS Remediation 2015
74485	4040 Avenida Conference Center Improvements
74488	Etro Molecule
76585	Fan Wall Implementation
76642	AV System and Equipment Refresh
96022	WFI Pump Autostart
96040	GWR 1080/1090
96098	Process VSD and SOV Replacement - Phase 2
96104	Lighting Work on OCN Campus Pathways
96105	TMAC Tenderizer
96108	PCS Remediation for EBR Review by Exception
96111	PCS Functional Specification Development Project (CAPA 96297)
96134	QC Liquid Handler
96140	Lower North Lot Storm Water Mitigation
96141	Manufacturing Ventilation Drops
96142	QC Lab Equipment Replacement 2015
96143	Paperless Metone
64992	QC Osmometer Asset Replacement
64994	Helium Sniffer Replacement
96160	B331 HVAC Fire Code Compliance
74525	CIP Reliability and Efficiency - PI
73442	V-2170 Agitator Drain Valve
97011	Site Data Historian Upgrade - 2014
97017	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2014
97021	QC Lab Space Integrity
97022	MFG Systems Integration Improvement Phase 2 - 2016
97026	Drain Pan Modification
97029	Study for K6 Program - Project 4 - Replace Chillers
97034	Landscaping Design
97041	Artificial Turf

	LE vs. Target	Comments (Major Variances)
New and Cancelled	- 0.2	+ 0.3 Draining of Top Mounted Agitator Well (CAPA 1140940)
		- 0.5 Water Reclaim System
Projects vs. Target	- 1.6	- 0.2 New Media Technology - HTST / Adventitious
		+ 2.2 WFI Generation and Storage System / CUB Expansion
		+ 0.5 Sci&Eng Lab Mods and Equipment
Project Cashout	- 23.5	- 1.0 Etro Tech Transfer
Changes vs. Target		- 0.9 Process VSD and SOV Asset Replacement
		- 1.0 Hastelloy Chromatography Column (160cm)
		- 1.9 K6 Program - Project 1 - Replace DX HVAC Units
		- 2.6 Vessel 1020 Upgrade
		- 3.5 P2 DPE Start-Up
		- 11.8 P2 Downstream Processing Expansion
Management Adj.	+ 7.8
Global Credit	+ 0.2
Total Cashout excl. / Start Up & Validation	- 17.3
Start Up & Validation	- 3.5	- 3.5 P2 DPE Start-Up
Total Cashout	- 20.8

VAR		CONST
74455		74268
74489		74455
74524		74454
74416		74453
74435		74382
74406		74119
74368		74277
74535		74426
73367		74368
74119		74406
74490		73367
74427		74302
74429		73356
74404		74279
74279		74490
74453		74418
74268		74373
74426		74416
74487		74404
74418		74429
74382		74392
74454		74489
73356		74535
74392		74546
74302		74510
74526		74486
74510		74487
74486		74427
74511		74526
74373		74511
74409		74127
74385		74491
74527		74435
74546		74385
74491		96210
74127
74277

## 'file:///C:/Users/webster5/Desktop/Portfolio/Portfolio%20Backups/2016_05_May/2016%20Master%20Project%20Portfolio%20BU%2096_MO5%20FINAL.xlsm'#Lookups
Alister Huffton		Blake Brown			Department
Deidre Dunham		Charlie Bisbee			Global
Jim Neeleman		Ching Lee			Individual
John Keller		CRB			Start-up
Juergen Kemeter		CRB Partial			TBD
Mel Davis		Dave Stewart			Expense
Melanie Yevilov		DBX			N/A
N/A		Dirk Ellison
Scott Fields		Dona Bloch
TBD		Greg Crecely
Zaymar Sedra		Jessica Justice
		Jim Koons
		John Urban
		M. Gabrenas
		Marcus Espinoza
		Melanie Yevilov
		N/A
		Nicole Nepomuceno
		No CRB
		Pamela Baker
		Pete Magill
		Rami Barghout
		REM
		Rich Johnson			Delayed
		Scott Brier			Estimate Decrease (2016)
		Siu Fai Tsang			Estimate Increase (2016)
		Steve Novak			New Project
		TBD			Removed
		Tony Rico			Scope Reduction
		Tucker Creighton

## 'file:///C:/Users/webster5/Desktop/Portfolio/Portfolio%20Backups/2016_05_May/2016%20Master%20Project%20Portfolio%20BU%2096_MO5%20FINAL.xlsm'#Resource_2016_
147

## 'file:///C:/Users/webster5/Desktop/Portfolio/Portfolio%20Backups/2016_05_May/2016%20Master%20Project%20Portfolio%20BU%2096_MO5%20FINAL.xlsm'#MO5_2016_Budget_(Live)
Improvements and Efficiencies

## 'file:///C:/Users/webster5/AppData/Roaming/Microsoft/Excel/2016%20Master%20Project%20Portfolio%20BU%20110%20(version%201).xlsb'#2016_Master_Portfolio
64899	Engineering Library TOP Storage Unit		6/01/15 Changed to Exec. Mel working with CRB on the estimate.	Global	QSP	Improvements and Efficiencies	Reliable		Installation of a new vertical carousel system to store apporved project Turn Over Package (TOPs). Existing TOP storage capacity will be depleted by the end of 2015.	Execute	Jim Neeleman	Tucker Creighton	Mel Davis	Jeff Walcher	85000	82000	3000		No	N/A	N/A	N/A
64901	MCS Peripheral Asset Replacement - 2015		6/08/15 CA Appr. 6/05/15 CA submitted. 6/01/15 CA issued. 5/07/15 Appr by PMT. 5/04/15 Project budgeted as expense but has been reclassified as capital. Repalcing 45 carts for mobile HMI (capital >$5k) and ipad cases with scanners (expense <$5k).	Global	QSP	Stay in Business	Reliability and Value		Resolves OSHA Regulatory Agency finding which required OCN to cease use of HMIs. The improvement of the HMI platform will also give operators access to Syncade, Doclink, and DeltaV on four windows displayed on two screens.	Execute	Scott Fields	N/A	Alister Hufton	Matt Hunt	325000	225000	100000			0	0.9	0
64914	QC M9 TOC Analyzers	Asset Replacement	7/14/15 CA Appr. 7/09/15 Changed to CA Submitted.	Global	QSP	New Technologies	Launch and Commercial Excellence		There is a global effort to harmonize all GNE/Roche sites to use the same GE model for the TOC assay testing.The intent of this project is to replace the existing TOC analyzers in the lab which are at the end of their lifecycle and purchase the recommended GNE/Roche model. Scope of work includes: Purchase two TOC analyzers, qualification, GMP release and turnover package for each.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	106000	106000				N/A	N/A	N/A
64923	QC Met-One Air Sampler Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2016	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Launch and Commercial Excellence		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	68100	65100	3000			N/A	N/A	N/A
64925	QC UV Vis Spectometer Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2018	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Reliable		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	28350	28350				N/A	N/A	N/A
64927	QC Gel Imager Replacement 2015	Originally submitted as QC Lab Equipment Replacement 2020	8/10/15 CA Appr. 7/31/15 CA Submited. 7/15/15 CA Routing. 7/08/15 SS submitted.	Global	QSP	Stay in Business	Launch and Commercial Excellence		QC equipment that has reached the end of life cycle and needs replacement. Equipment in ARR.	Execute	Jim Neeleman	N/A	N/A	Siu Fai Tsang	15750	15750				N/A	N/A	N/A
73356	Supplemental BDU Sampling	6/13/14 Needs to come back to jPMT before resolving some issues. Network Portfolio Key Site Project. "Green Planning" approved at IMPACT $1,782,500 ... $350,500 for PI phase, will return to IMPACT in Feb 2014 for final funding request. Per CAPA 746996 and recent regulatory commitments to the EMA, additional testing of the Actemra drug substance is required at the end of the dispensing operation to ensure product homogeneity. Furthermore, a separate sample of the drug substance is required by Chugai for the QC testing in Japan. Optimization of the sample volumes is critical so as to mitigate the impact to the inventoried bulk yield and drug substance supply. CAPA 746966	9/22/14 Approved WBS for Phase II. 8/22/14 Changed budget according to appr CA. 7/22/14 Apprd by IMPACT CA2 $2,304 CAP $2,292 $12.5 EXP Total Project $2,690,092. 7/17/14 Appr at jPMT. 7/11/14 According to Deidre's input, this project will be executed and we will keep the same budget. 6/11/14 - Changed to Exec. JN	Individual	CTT	Stay in Business	Launch and Commercial Excellence		CAPA 746996. Investigation 724033 determined that dilution occurs in the Actemra SC die to the presence of residual buffer in the transfer line which entered the conditioning vessel prior to the dispensing operation. These additional controls were also requested by the EMA health authority. Also Chugai requires a separate sample for release of the product in Japan.	Execute 2	Jim Neeleman	Greg Crecely	Mel Davis	Paul Crowley	385500	355000	30500	Yes	Yes	3.3	3	19.5
73367	FS & DS Automation Integration	Maria's email these two projects Functional Specification Development (P36) - $280k and PCS Automation Documentation project (73367) - $650k are capitalized, and both projects are combined into one project - titled FS & DS automation integration.	12/16/14 Changed to Execure 2. 11/22/14 CA Submited. 11/18/14 CA issued. 11/04/14 Appr by IMPACT for Phase 2 on the PCS Autom. Doc. . 10/30/14 Appr by jPMT Phase 2 for PCS Automation Documentation portion. Total project $612,547.	Individual	CTT	Tech Transfers	Fit for Purpose		Compliance risk. Strategy for P2 Project Readiness. Reduce number of validation deviations for DDS error.	Execute 2	Zaymar Sedra	John Urban	Mel Davis	Pat Sraubol / Ravi M.	325000	325000		Yes	Yes	3.9	2.8	24.4
73384	Caustic Bath Upgrade	Project reviewed and treated as pull-in. This project was present along the Optimize Column Movement Device, but was requested to be submit by itself.	11/7/14 WBS received. 10/31/14 CA Submitted. 10/22/14 CA on Hold as it needs to be prioritized for 2015 budget.	Global	QSP	Stay in Business	Highly Capable Workforce		The increased run rates, and the column packing activities require a safer, more reliable method for out of place cleaning. A safety job hazard assessment was performed comparing a score of 60 (high risk priority) for the current operation, to a score of 16 (low risk priority) for the proposed solution. It is the right thing to do for our employees.	Execute	Melanie Yevilov	N/A	N/A	Bahar Dahi / Juan Pacio	34000	34000			No	2	0.8	16.5
73387	MCSBACKUP Phase 2 Tape Retrieval		11/27/14 WBS received. 11/11/14 CA submitted.	Global	QSP	New Technologies	Reliability and Value	A2 Business Efficiency	Phase 2 for the MCSBACKUP deployment. Need to ensure data can be retrieved and stored per GMP requirement.	Execute	Scott Fields	John Urban	Mel Davis	Myles Sumlin	64000	60000	4000		No	N/A	N/A	N/A
73388	SIMCA Online Real Time Process Monitoring System		12/10/14 WBS received. 12/02/14 CA Submitted. 11/20/14 CA issued. 11/18/14 Appr by IMPACT. 11/13/14 Appr by jPMT.	Global	QSP	New Technologies	Launch and Commercial Excellence		As we have run rates have increased we have seen more issues occur due to operational equipment issues. Discrepancies have also increased (i.e. Post DBX actemra campaign.) Can contribute to sight goal of investigation free lots. SIMCA is expected to improve process monitoring in real time, decrease discrepancies and investigations, potential save batches.	Execute	Jim Neeleman	John Urban	Mel Davis	Michael Villacorta	321000	298505	22495	No	No	1.2	2.5	7.8
73398	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2015	Asset Replacement. Repalcing 49 units and adding 15 new ones.	7/14/15 CA Appr. 7/09/15 Changed to CA Submitted. 6/12/15 Changed to CA Routing. 6/04/15 Changed to Appr PMT. 11/12/14 SS submitted. 10/16/14 P-scored at jPMT.	Global	QSP	Stay in Business	Reliability and Value		Improve current wireless access points in "dead spots" within the MFG to satisfy new user requirements and improve network performance. Current system is not reliable and puts in risk operations for lack of control in the system due to connectivity failure.	Execute	Scott Fields	John Urban	Mel Davis	Shane Smith	274000	274000			No	1.4	2	10.5
73399	Frit Handling and Storage	04/29/16 Total reflects approved CA amount, in addition to $60k for design change. 03/04/15 It has been moved to above the line and need to come to IMPACT for approval. Below the line. Budget $113k 2015. This project was presented along the Optimize Column Movement Device, but was requested to be submitted by itself.	7/21/15 CA Appr. 7/15/15 CA Submitted. 07/13/15 CA Routing. 07/7/15 Changed to IMPACT Appr. 06/18/15 Changed to PMT Appr. 05/07/15 Per Juan, this project is deffered for bandwith reasons and vendor shop load. 03/04/15 Changed to FXNL Appr per Dave email. 12/18/14 Changed to on Hold. 10/22/14 CA on Hold as it needs to be prioritized for 2015 budget.	Global	QSP	Tech Transfers	Highly Capable Workforce	A2 Business Efficiency	The current system has some inefficiency: a) the storage does not segregate the frits based on product b) the frit handling requires four people, and c) there is not enough space inside column packing. On the contrary, the new handling and storage methods greatly reduce footprint, increase frit protection, eliminates risk for injury and personnel needed for frit replacement.	Execute	Melanie Yevilov	N/A	N/A	Bahar Dahi / Juan Pacio	154000	154000			No	1.4	0.6	11.3
73406	Guided Wave Radar V-4045 & V-4055		8/10/15 CA Appr. 8/6/15 CA Submitted. 7/23/15 CA Routing. 7/16/15 PMT Appr. 7/15/15 Revised SS submitted to include V-4055 on the scope. 6/4/15 SS submitted.	Global	QSP	New Technologies	Agile		Ongoing issue which can directly impact product quality and yield. To mitigate the issue the load cells are not being used anymore, instead V-4040 load cells and the BDU are used to estimate weight. Provides more robust process with less external influence and less human intervention.	Execute	Zaymar Sedra	John Urban	Alister Hufton	Juan Pacio / Tammy Price	61000	61000				1.5	1	12
73409	Solar Power Enabling Project	Original named Fencing Solar Power Panel Area. Presented at PMT with a range of $460-576k incl. 20% contg.	9/4/15 CA Appr. 8/30/15 CA Submitted. 8/13/15 CA Routing. 8/04/15 IMPACt Appr. 7/30/15 PMT Appr. 7/16/15 PMT approval deferred. 3/23/15 Cashflow and RR updated.	Global	QSP	SHE and K-Directives	Highly Capable Workforce		OCN has made the decision to do a Solar Lease Agreement (SPPA). This project facilitates the installation of solar panels and associated infrastructure as required by the lease agreement. The solar project supports the Roche Eco-Balance network initiative for sustainability. Projected energy savings over the life of the lease are estimated at $10 million (or higher as energy rates continue to increase).	Execute	Melanie Yevilov	Jim Koons	Mel Davis	Sumner Tison	570000	461000	109000	No	No	0.8	2.2000000000000002	5.0999999999999996
74119	Harvest Upgrade (New Centrifuge)	In MO5 and T3 the these three projects were reported separately. For 2015 T0 were combined (Centrifuge, Seed Lab, New HCCF). For 2015 MO5 will be seperated again as three projects.	9/04/15 CA2 Appr. 8/13/15 Full green CA submitted. 8/10/15 CA Routing for full green. 02/25/15 CA Appr. 11/10/14 Ken will submit reviewed cashflow by 11/19 No SS necessary. 8/11/14 OLT and PMs decided to combined all three projects in one, so this one includes Add New HCCF and Seed Lab (Six 20L Bioreactors) 7/3/14 Per Ken's input, we will leave the same budget as we are still defining the scope. 7/2/14 Sent out email to Ken.	Individual	QSP	Strategic	Fit for Purpose		Hermetic centrifugation has been specified by PTDU as a required technical capability of platform processes in order to minimize risk of antibody reduction and batch losses.	Execute 2	Zaymar Sedra	N/A	PTAA	Ken Hamilton Mark Jones	15479000	476000	15003000	Yes	No	N/A	N/A	60
74127	Harvest Modifications Start-up		7/3/14 Per Ken's input, we will leave the same budget as still we are defining the scope.	Start-up	QSP	Strategic	Launch Facility			Budgeted	Deidre Dunham	Rich Johnson	Alister Hufton	Ken Hamilton				Yes	No	N/A	N/A	60
74268	P2 Downstream Processing Expansion	Network Portfolio Key Site Project. CA1 approved for $3,377,000 - PI Phase only. M05 2015=$63,700,000 + $1,000,000 Expense. 2016 = $44,390,917. 2017= $234,619. Total project costs = $121,365,536	8/13/15 Full green CA submitted. 8/10/15 CA Routing for final phase. 7/2/14 Followup with Mark and Paola regarding budget adjustment. 6/11/14 - Changed to Exec. JN	Individual	QSP	Strategic	Fit for Purpose		The CMContinuum WS3.1 LM Launch Facilities Workstream developed a subsequently recommended to the PTLT for a regional DS Launch Model of which a second purification suite at OCN was a necessary part. Simultaneous manufacturing in two purification suites, supplied from existing cell culture operations while attaining the current run rate of OCN. This project will achieve compliance with the approved strategy for network launch capability and permit the network to execute against the endorsement LM Drug Substance Launch Facilities strategy, part of which is enabling launch of products with a standard and demand at OCN in the USA.	Execute 2	Zaymar Sedra	Dirk Ellison	PTAA	Mark Jones / Dirk Ellison	193916000	185694000	8222000	Yes	Yes	N/A	N/A	60
74277	P2 DPE Start-Up		8/13/15 Full green CA submitted.	Start-up	QSP	Strategic	Fit for Purpose		Site support for the design, testing for the engineering runs, plant time for 12 runs, and materials that can be used for both engineering runs and qualification runs. The ISD is based on licensure of the potential product candidates for OCN according to the CMContinuum Designated Launch Facility Strategy.	Execute	Zaymar Sedra	Rich Johnson	Alister Hufton	Dirk Ellison/ Ken Hamilton	51500000	51100000	400000		No	N/A	N/A	60
74278	K6 Program - Project 3 - Replace Cold Room Compressors	Change -20 freezer compressors. Phase 2 of the k6 proejcts. Phase 1 would be Replace DX Units.	11/17/14 Project reviewed. 7/1/14 Budget confimed by Sumner. Dave confirmed not SS will be needed for now. Sent out email asking for it. 6/30/14 Changed SME to Sumner.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Complies with Roche K6 directive to reduce R-41A and R-22 refrigerants. Will reduce R-22 refrigerant in all cold rooms across the site by 2018 and R-404 refigerant in the main freezer by 2022. Free standing lab freezers are out fo scope.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Geoff Wing					No	4.4000000000000004	5.2	16.5
74279	New Media Technology - HTST / Adventitious	04/03/15 HTST options reviewed by OLT and received endorsement to proceed with the next phase of funding approval with a project total of $9.5MM. In order to achieve this project total, several items were removed (slides 5 & 6) and the contingency was reduced. In order to maintain a working contingency, each of the project components like install, design, project management, etc. will be judged-down by 10% and the project costs and accountable disciplines. That 10% will be combined with and held as contingency to provide a management reserve. CAPAs 577402 and 740579. Network Portfolio Key Site Project. M05 2015 = $0 Capital + $0 Expense. CAPA - commitment to FDA. Leptospira mitigation. Implement additional adventitious agent barriers (e.g. solution autoclaving, heat treatment, or viral filtration) for solutions which are not HTST compatible. M05 2015 = $7,000,000 Capital + $75,000 Expense. Implement HTST for spinner through N-2 cell culture stages for all solutions which are compatible with HTST treatment. CAPA - commitment to FDA. Leptospira mitigation. To address improved viral control ($2M = 2014, $5M 2015)	06/02/15 WBS confirmed. 05/22/15 CA Appr. 04/30/15 CA submitted. 04/24/15 CA issued. 03/31/15 Appr by IMPACT but will be subject to SMART & OLT endorsement. 03/26/15 Phase 2 Appr by PMT10/7/14 CA Appr. Changed to Exc 1. 9/17/14 Budget updated accord. CA. 6/30/14 Budget updated according to Scott's input. 6/11/14 Changed to RTO- JN. 6/10/14 Appr by IMPACT. 6/05/14 - Appr by jPMT. CA1 $1,321k, CA2 $7,961k inc Contingency. Total $9,282k.	Individual	RTO	New Technologies	Reliability and Value		In order to fulfill commitment to FDA. OCN currently does not have viral barriers for small scale cell culture medias and solutions. Satifies CAPA 585313, 740579.	Execute 2	Scott Fields	John Urban	Alister Hufton	Will Jimenez	1115000	1095000	20000		Yes	3.7	3.8	19.2
74280	Spare Hasstelloy Columns	M05 2015 = $1,700,000 Capital + $10,000 Expense. Need column strategy and matrix of current columns to show need for new. Confirm if this is risk mitigation, essential for PCO/run rate. Buy new Hasstelloy Columns (to avoid having to unpack between campaigns and provide backups, 1.8 and 1.4 minimum needed 2014, 1.6 2015)	7/17/14 Changed to Exec. Budget adjusted according to the IMPACT Presentation and CA.	Individual	QSP	Stay in Business	Agile	A5 Product Change Over	Project reduces risk to 5 day PCO my mitigating operation risk at ProA step for both Actemra and Rituxan campaigns. To maintain run rate of 3.p rpw a 3rd column needs to be packed to support the ProA step. With this project the risk of not achieving 5 day PCO is minimized.	Execute	Melanie Yevilov	John Urban	Mel Davis	Bahar/Karen	2500000	2499000	1000	No	Yes	1.8	2.4	11.6
74302	Waterpooling Remediation	9/08/15 Project will be susprended until S/D 16. The total project estimate for the MP and BP is $$2,068, if the adittional areas are added to the scope the total estimate woud be $3,06M. Decision from quality council determined a phased implementation approach and the total cost is being reassessed. Uncertatinty on this project as it was partially approved for Buffer and Media Prep Areas, but depending on the results and lessons learned, the second phase might follow. Network Portfolio Key Site Project. $500K requested, cut to $490K during budget review. This figure to increase to $1.1M to account for all the required external support (viz automation, val & QEV). Note, the early estimate did not have have the fuller analysis that has now been done. Revised to $1.3M, $650K in 2013, $650K in 2014. CAPA 719091	12/09/14 WBS received. 11/17/14 CA submitted. 11/04/14 CA issued. 10/10/14 Appr by BMLT for Phase II. 9/23/14 Appr by IMPACT for Pahse II 9/17/14 Appr by jPMT Phase II with a funding request of $378k inc 10% conting. 7/15/14 Adjust budget according to IMPACT, back to $3,190k. Changed Status to Appr. 7/14/14 Partially approved for Media Prep and Buffer Prep Areas. Phase 2 execution will depend on progress and results of Phase 1 NN. 6/24/14 - Per IMPACT Meeting this project has been canceled by Quality Council. They will come back to IMPACT on 7/08/14 with Close Out Report and Fianancial Summary . 6/11/14 - Changed to Exec. JN	Individual	RTO	Stay in Business	Reliability and Value		Global Quality, the site has a CAPA 719091 to mitigate water pooling in response to Global CAPA. Complete not later than Sep 2014. Achieve compliance with Roche/GNE Global and OCN Site Quality.	Execute 2	Scott Fields	John Urban	Alister Hufton	Ken Hmilton / Tim Chen	1690000	1665000	25000	No	Yes	3.4	2.2999999999999998	23
74368	Dev/Val Automation Capacity Expansion	6/19/14 - Per Maria's email PCS Development and Validation Environments Capacity Expansion (DeltaV) (74368) is combined with LivePoint Data Analyzer Software Expansion. Both projects are capitalized into one project Dev/Val Automation Capacity Expansion.	7/07/14 Purchase additional development and validation license for Data Analytics System (DA) was added to this project $24k capital. Combined 74368, LivePoint, Data Analytics DEV/VAL System	Individual	QSP	Improvements and Efficiencies	Launch and Commercial Excellence	A1 Automation Improvement	The DEL/VAL system expansion in order to increase the amount of project work, reduce delays in projects, allow MAR charges that correct current automation issues. Evaluation of system indicated we will fall short of required resources for MAR work with upcoming projects.	Execute	Jim Neeleman	Greg Crecely	Alister Hufton	Matt Hunt / Ravi M.	24000	24000		Yes	No	?		N/A
74371	Odor Treatment	12/10/15 Susan/Sumner get OLT decision to defer. 2016 = $1,000,000 Capital. M05 2017 = $4,000,000 Capital	12/15/15 Originally called Waste Water Recovery 11/11/15 PI to start Mid-2016. 03/25/15 Feasibility study will be done in June with a potential to be combined with TDS Remediation. 03/20/15 Per Tim's email this project is pushed out one year. 11/18/14 SC submitted. 11/07/14 Project reviewed, Tim to submit SS by 11/18/14 we will do p-score then. 10/27/14 Changed to Budgeted. 6/30/14 Changed to CTT and budget according to Tim input. Tim will work on the SS for Phase 1 & 2. Will be split on two projects. Later, he will submit Phase 3 SS. TL	Individual	CTT	SHE and K-Directives	TBD		Strategic project to detoxify/purify the water and reuse it in the different processes as conservation plan.	FXNL LT Appr	Melanie Yevilov	Jim Koons	Mel Davis	Tim Lai					No	2.9	6.6	6.8
74373	WFI Generation and Storage System / CUB Expansion	This project has been approved by jPMT in combination with CUB Expansion & Storage Tank for a CA1 of $3.9M. $2.9M Equipment and $1M Design.	06/05/15 WBS confirmed. 06/04/15 CA Appr. 04/30/15 CA submitted. 04/21/15 Appr by IMPACT and CA Routing. 04/09/15 Changed to PMT Appr for Phase 2. 11/04/14 WBS received. 11/03/14 CA approved. 10/10/14 Original CA was rejected and NPV was modified. REVISED CA was submitted today. 9/29/14 CA Submitted. 9/5/14 Appr by BMLT. 8/19/14 Appr by IMPACT. 8/14/14 Apprd by jPMT. 7/18/14 Changed to FLT Appr. 7/17/14 Adjusted budget according to Tim's email 20% for 2014. 7/14/14 Changed PMO Lead. 7/03/14 Sent out email. 6/30/14 It will be executed during P2. Start date Q4 2014. Finish date towards the end of 2015. We need to pull in budget to 2014/2015. The SS will be developed once the project is determined to de during P2. TL	Individual	QSP	Strategic	Fit for Purpose		The additional WFI-RO-DI systems will provide system redundancy for repair/maintenance and increased capacity for higher run rates. Current equipment is running at minimum 80% capacity to meet production needs. Existing CUB space is not sufficient. New WFI system cannot be located outside or within any other site building	Execute 2	Zaymar Sedra	Jim Koons	Alister Hufton	Tim Lai	4682000	4625000	57000		Yes	2.9	5.0999999999999996	11.1
74382	Sci&Eng Lab Mods and Equipment	MO5 / T3 = $13,600k. Total Assesed Project was $13,621k and it was judged down to $12,721k which it is the maount presented to Capital.	7/20/15 CA Appr. 6/25/15 Changed to CA Subm. 06/10/15 CA issued. 05/07/15 Phase 2 Appr by PMT. 01/30/15 WBS Received. 10/28/14 CA Submitted. 10/10/14 Appr by BMLT. 9/30/17 Appr by IMPACT. 9/17/14 Appr by jPMT. Changed budget accordingly. 9/10/14 Changed name removing "QC".8/27/14 Changed to Budgeted. From 8/21/14 meeting, this name might change to reflect that this project will be for Sci&Eng lab only. 7/120/14 Adjusted estimate according to Semsi's email. 7/01/14 SS was received but needs to be approved. 6/25/14 - Working on the Scope Sheet. Changed DL to Greg and PMO Lead Jim - JN/DS	Individual	QSP	Strategic	Launch and Commercial Excellence		To expand capacity of Science and Engineering laboratory. Expansion of the laboratory capacity with additional equipment and head count would enable Science and Engineering group to support launching activities at small and pilot scale such as technical transfer, PCPV support, and make-assess-release.	Execute 2	Jim Neeleman	Greg Crecely	Alister Hufton	Fikret Kulenovic	4073000	3652000	421000		Yes	2	5.0999999999999996	7.6
74385	Media Prep Endotoxin/Bioburden Sampling	CAPA 734576. Total Project Cap $3M. 03/09/15 Project included on the SBP with an estimate of $2.5M over 2018-19 with great potential to pull it in.	11/13/15 PI phase 2016 no Capital. Planned for 2017 Capital. 8/17/15 SS Submitted missing signature. 4/09/15 Changed to Idea. 6/27/14 Per email this project is removed for lack of definition at this point. 6/25/14 - Working on Scope Sheet. Change DL to Greg and SME to Fikret and PMO Lead Jim - JN/DS	Individual	QSP	Stay in Business	Reliability and Value		Risk of microbial contamination exists in media prep operations for cell culture media. Contaminants can have a negative impact on product output, product quality and patient safety. facilities. Fail to comply with the committment could result in regulatory. The expected benefit of routine monitoring of bioburden and endotoxin is action. that cell culture media can be confirmed to be free of harmful levels of bacteria, exotoxins and endotoxins. This future state results in increased patient safety, improved undestanding and microbial control of open process.	Idea	Scott Fields	Greg Crecely	TBD	Matt Forbes						1.4	4.2	6.5
74392	Water Reclaim System	04/29/16 AW, ST, TL, and AH decided to only spend remaining funds from PO. It is not required for P2, but due to structural and piping changes it is highly recommended to execute the overlapped portion with P2 to minimize downtime and system impact. There are two phases for the project, the 1st phase is in B341 and the 2nd phase is in B311. The 2nd phase can be staged out further into 2015 or 2016. The business driver is the water reduction goal that has been set forth by SHE corporate, as well as resource conservation.	12/14/15 Scope reduction, removed $800k from 2016 to 2017 per AH. 01/14/14 Changed to Exec. 12/02/14 CA Submitted. 10/14/14 CA issued. 9/2/14 Appr by IMPACT. 8/21/14 Appr by jPMT. 7/14/14 Changed PMO Lead. 7/08/14 Budget updated according to Pull In Meeting. We still need to confirm with estimate. 6/30/14 Entered budget according to Tim input. Tim will work with John on the SS.	Individual	CTT	SHE and K-Directives	Reliability and Value		There is a Roche US SHEP 12 requires annual objectives and targets for water use reduction	Execute	Scott Fields	Jim Koons	Mel Davis	Tim Lai	344000	323000	21000		Yes	0.9	2.2999999999999998	6.1
74404	Mezzanine Lift Media Prep: Phase 1B	8/19/14 CA1 $707,729 incl 20% Contg. 2014 it might start work with the gate for 1A lift and purchase of equipment and 2015 the installation of the new lift. Improvements and additional lift for Media Prep. 3/11/16 Have to wait for eletrical shutdown to tie in 480V, per MD.	10/13/14 WBS Received. 9/24/14 CA Submitted. 9/15/14 Updated the budget according to CA. 8/19/14 Appr by IMPACT. 7/03/14 Appr by jPMT coming to IMPACT. 7/2/14 John input is that they will come to jPMT for approval of additional funding	Individual	QSP	SHE and K-Directives	Highly Capable Workforce		To provide the ability for lifting manufacturing materials and janitorial buckets to mezzanines in order to reduce the risk of personal injury to contractor and employees and improved safety ops.	Execute	Melanie Yevilov	Tucker Creighton	Mel Davis	Dick Sloan	686000	656000	30000		Yes	1.5	1.9	10.7
74406	Corrosive Chemical Compliance	Pull-In a portion in 2014 (PI) for around $150K. 3/11/16 Planned to do 3 phases (separate projects); 311 in 2016, 341 in 2017, and 321 in 2018 as per MD.	01/16/15 WBS Received. 01/14/15 Changed to CA submitted. 11/04/14 Appr by IMPACT. 10/23/14 Appr by jPMT. 10/9/14 Needs to come back to jPMT with the modifications on presentation, estimated 10/23/14. 8/21/14 Changed to LT Appr. 7/14/14 Change the PMO. 7/08/14 Added according to our Pull-In meeting	Individual	RTO	SHE and K-Directives	Reliability and Value		Bldg. 311, Bldg. 321, and Bldg. 341 are exceeding the allowable limit for caustics per CA Fire Code for solutions greater than 1% by volume. OCN is currently out of compliance and being given clearance for now by the local fire department. It is about life safety to our employees and local responding agencies.	Execute	Scott Fields	Jim Koons	Mel Davis	Tim Lai	1953000	1901000	52000		No	6.6	3.9	34
74409	K6 Program - Project 1 - Replace DX HVAC Units	9/17/15 Planning Phase for PI/CD for the K6 Program. Project for Chillers and -20 compressors will request funds independently. 05/01/15 Per Mel's email Phase 1 will only address HVAC DX replacement for B-341 CUB. (6) units total to be replaced. Add CW, HHW, BMS to these (6) units. Phase 2 will be re-defined during the T3 2016 budgeting exercise. These numbers came from the CRB Estimator based on the revised scope of work. Phase 1 of the K6 Project. Nine (9) units in total. Two (2) in Building 361, one (1) in Building 371, six (6) in Building 341. Estimate calculated $72,000 /Each + 45% of CRB commission and 20%	10/16/15 CA Routing. 10/06/15 IMPACT Endorsed. 9/17/15 PMT Appr. 03/25/15 Project cashflow and RR reviewed. 11/10/14 Project reviewed. 8/21/14 Changed to LT Appr. 7/17/14 Changed to Global JK. 7/11/14 Added to prtofolio according to John's email.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Existing DX HVAC units use R-410A refrigerant which must be eliminated per Roche K6 directive. In Scope: DX HVAC units in 321, 322, 341, 361, and 371.	Execute	Zaymar Sedra	John Urban	Alister Hufton	Geoff Wing					No	1.8	2.7	11.3
74416	Asphyxiant Gas Remediation	SHE project. Jim working with SHE to define the SME to coordinate with CRB and getting an estimate. K16. 3/11/16 Project will connect to UPSS; project is currently about 3 months behind, per MD.	12/8/15 Reduced by $400k per IMPACT discussion. 7/15/15 CA Appr. 7/10/15 Changed to CA Submitted. 6/16/15 IMPACT Appr. 6/11/15 Appr by PMT. 04/10/15 Per Gary, scope has been reduced from 11 rooms to 5 rooms, budget has been reduced by 40% Project expected to be complete in 2015. 11/06/14 Project reviewed. 8/21/14 Changed to LT Appr. 8/11/14 Change SME. 7/16/14 Changed to Idea. 7/08/14 High Risk project. It will be not executed this year. IT requires a K-9 Study. 6/30/14 Added according to Liza pull-in list.	Individual	RTO	SHE and K-Directives	Highly Capable Workforce		OCN has identified spaces that are deemed unsafe for occupancy if a Nitrogen release occurs. Currently out of compliance and are being given a hall pass for now by the local safe department.	Execute 1	Melanie Yevilov	Marcus Espinoza	Mel Davis	Gary Merrill	54000	54000			No	1.5	1.6	11.1
74418	QC Lab Reconfiguration & Equipment	Phase 1 Planning $480,452. Phase 2 expected to start in May. Total Project $4,160k. P2 fall off and it has been endorsed by the Steering Committee	11/05/15 PMT Endorsed. 02/16/15 CA Submitted. 01/13/14 CA isued. 12/03/14 BMLT Appr. 11/18/14 Appr by IMPACT. 11/13/14 Approved by jPMT. 8/27/14 Changed to Budgeted. From 8/21/14 meeting, the portion that might be included in 74382 will be rolled up.	Individual	QSP	Tech Transfers	Launch and Commercial Excellence		Problem Statements: 1) Current Configuration could result in a false negative or false positive result in our PCR suite. Oceanside’s PCR suite is used to test Adventitious Material for the Network. 2) QC Equipment needs to be updated for reliance and technology improvements to support CMC Continuum. 3) P2 will create an additional sample load on samples that are not Run rate specific. The current QC labs are not designed to handle this increased sample size.	Execute 1	Jim Neeleman	Greg Crecely	Mel Davis	Amanda Gutierrez	481000	467000	14000		No	3.4	4.4000000000000004	15.8
74426	Process VSD and SOV Replacement - 2015	Asset Replacement - CRB heavely driven	6/25/15 Changed to Execute. 06/10/15 CA Submitted. 05/5/15 Appr by IMPACT. 04/23/15 jPMT Appr. 10/16/14 P-scored at jPMT.	Individual	QSP	Stay in Business	Reliability and Value		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Execute	Scott Fields	Tucker Creighton	Alister Hufton	Jonathan Clark	707000	707000			No	N/A	N/A	N/A
74427	MCS Network Infrastructure Asset Replacement - 2016	S/D critical project. Asset Replacement - The project will proceed with the PI Phase for a feed study.Since the requested amount is expense and less than $500k, a CA is not required. A PO will be requested for $300k. Eric Fallon will be added to the approval chain to endorse the project as the functional leader before the authorized approvers review the shopping cart. When the project returns for the next phase of funding, it should be split into two projects. The MES and PCS activities will become one project while the infrastructure activities will be the other. Please see E07.	10/01/15 PMT Endorsed. 6/25/15 Changed back to FXNL Appr according to Team decision. 6/15/15 Changed to Canceled. Rolled over to E07 - Automation System Lifecycle MCS Upgrade	Individual	QSP	Stay in Business	Reliability and Value		The Network is the backbone of the Manufacturing Control System (MCS). The infrastructure must be kept up to date to avoid downtime. Lifecycle for equipment is 5 - 7 years. Last replacement was 2009. Project implementation requires shutdown.	Execute	Scott Fields	John Urban	Alister Hufton	Myles Sumlin					No	N/A	N/A	N/A
74428	PCS Process Support Equipment Automation (PLC) Asset Replacement	Asset Replacement.	03/03/15 Projects has been push out to 2016 to provide bandwith for Automation I&C. 11/18/14 SS submitted.	Individual	QSP	Stay in Business	Launch and Commercial Excellence		Per site prioritization, this project is necessary to support high run rates at OCN, Currently, the skids are in paper records and do not support release by exception.	FXNL LT Appr	Jim Neeleman	Tucker Creighton	Alister Hufton	Hieu Ton					No	N/A	N/A	N/A
74429	Mettler Toledo Weight Transmitter Conversion to Hardy Weight Transmitter - Asset Replacement	Asset Replacement - CRB heavely driven	7/10/15 CA Appr. 7/01/15 Changed to CA Submitted. 6/10/15 CA issued. 5/28/15 Appr by PMT. 11/18/14 SS submitted. 10/16/14 P-scored at jPMT.	Individual	QSP	Stay in Business	Reliability and Value		Failure of tramsmitters has increased. Once the Mettler Toledo fails an emergency change is initiated. An organized and scheduled conversion would reduce the cost and labor impact for each implementation.	Execute	Scott Fields	Tucker Creighton	Alister Hufton	Jonathan Clark	662000	662000			No	1.5	3.9	7.7
74431	Buffer Prep Mezzanine Lift Construction	Below the line. Budget 2015 Cap $100k; 2016 Cap $428k Exp $30k	11/05/15 PMT Endorsed. 05/18/15 Endorsed by Don to be included in MO5 budget and bring it to execution in 2015. 05/04/15 Great potential to bring this budget above the line. It will be rested to OLT. 12/18/14 Changed to On Hold. 11/12/14 Project reviewd. Total estimate $465k + 20%	Global	RTO	SHE and K-Directives	Reliability and Value		Continued risk to staff injury while transporting materials. Higher run rates increase this risk. VV and Penzburg have list systems to assist with material and equipment movement.	JPMT Appr	Scott Fields	Tucker Creighton	Mel Davis	Tyler Krol					No	1.5	1.9	10.7
74432	K6 Program - Project 4 - Replace Chillers		2/13/15 Changed to Budgeted.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Four (4) existing chillers in B-341 Central Utilities are not K6 compliant due to R-134A refigerant.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Geoff Wing					No	4.4000000000000004	5.2	16.5
74435	Hastelloy Chromatography Column (160cm)		2/12/15 It was decided to passivate the column to extend its useful life On the ARR this column is scheduled to be replaced in 2017, so budget has been shifted accordingly.	Individual	QSP	Improvements and Efficiencies	Fit for Purpose		Only one chromatography column is needed per stage to run the process. The second column is a backup to replace expired resin on the column being used. If a third packed column is not vailable, there is the risk that the second column fails while the first one is being packed. Such an issue would incapacitate production to continue.	FXNL LT Appr	Zaymar Sedra	Jim Koons	Alister Hufton	Bahar Dahi / Juan Pacio					No	2.9	3	17.100000000000001
74453	NPI Pool Tanks		03/30/15 WBS Received. 03/19/15 CA Submitted.	Individual	QSP	Strategic	Fit for Purpose		Purchase and set three additional pool tanks into the P2 now together with the P2 project. Additional pool tank capacity is a known requirement for a significant portion of the PTD pipeline currently under development. This will minimize overall cost by 60% and eliminate the need for future shut down to set these tanks.	PTAA	Zaymar Sedra	N/A	N/A	Ken Hamilton	1223000	1223000			No	N/A	N/A	60
74454	Seed Lab (20L Bioreactor)	Project related to P2 and it has been endorsed by the Steering Committee.	05/22/15 CA Appr. 04/29/15 CA Submitted. 03/16/15 Per Christian email, this project is back and split from Harvest Upgrade. ROLLED OVER. This project was combined with Harvest Mods 74119.	Individual	QSP	Strategic	Fit for Purpose		The additional six 20l bioreactors are due to: (a) the site and network practice of having backups to the seed labs to reduce operationnal risk;. and (b) we use multiple thaws for product launch; this reduces risk to, and duration of, the qual campaign, and therefore provides a stronger package to submit to the regulatory authorities. And, qual campaigns would take longer without this capability. It is established practice in the network to run multiple thaws.	Execute	Zaymar Sedra	TBD	PTAA	Mark Jones / Paul Coon	2604000	2567000	37000		No	N/A	N/A	60
74455	3rd HCCF Vessel	Project related to P2 and it has been endorsed by the Steering Committee.	05/22/15 CA Appr. 04/29/15 CA Submitted. 03/16/15 Per Christian email, this project is back and split from Harvest Upgrade. ROLLED OVER. This project was combined with Harvest Mods 74119.	Individual	QSP	Strategic	Fit for Purpose		The 3rd HCCF vessel is required to provide a buffer for manufacturing to stabilize the current operation; The requirement gets accentuated with P2 due to the need	Execute	Zaymar Sedra	TBD	PTAA	Mark Jones / Paul Coon	3722000	3693000	29000		No	N/A	N/A	60
74486	PCS Controller Cabinet Asset Replacement	Asset Replacement with Safety and Compliance componenets. CAPA 7046	10/20/15 IMPACT Endorsed. 10/08/15 PMT Endorsed. 10/05/15 Appr SS submitted. 5/18/15 3/19/15 SS in progress	Individual	RTO	Stay in Business	Highly Capable Workforce		Genentech standards require that all controller cabinets shall be fully UL508 listed. CAPA 7046 was generated. PCS Delta Controller Cabinet legacy design represents a safety concern to personnel my means of electrocution, and to equipment resulting in critical failure.	Execute	Melanie Yevilov	Tucker Creighton	Alister Hufton	Jonathan Clark						1.4	5	5.4
74487	Process VSD and SOV Asset Replacement	CAPA 982343. Asset Replacement - CRB heavely driven	12/8/15 Subtracted Process VSD and SOV Replacement - 2015 Capital portion per IMPACT discussion. 10/27 IMPACT Endorsed. 10/22/15 PMT Endorsed.	Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Execute	Melanie Yevilov	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A
74489	4040 Avenida Conference Center Acquisition		11/04/15 CA issued. 05/18/15 Changed to Budgeted. Endorsed by Don to be included in MO5 budget and bring it to execution in 2015.	Individual	QSP	Strategic	Exceptional Culture	A2 Business Efficiency		Execute	Deidre Dunham	N/A	Alister Hufton	Kara Swedberg						0.5	2.1	3.1
74490	Hyfish Material Screening Operation		8/06/15 CA Appr. 7/31/15 CA Submitted. 7/29/15 CA Routing. 7/14/15 Project presented at Don requested an offlione meetng for final endoresement. 7/02/15 PMT Appr. 6/12/15 SS submitted.	Individual	QSP	Improvements and Efficiencies	Reliability and Value		Actemra runs have experienced a reduction in yields starting in Q4/2013. An 8% reduction in yield represents a loss of $20 million per 100 runs and potentially impact on site commercial schedule.	Execute	Scott Fields	Greg Crecely	Alister Hufton	Fikret Kulenovic	1367000	1367000				5	5.7	16.3
74491	Etro Tech Transfer	4/14/16 Currently includes ER/QR cost in P2 CA 2 ($17.3M+$6,935,642). 12/18/15 Direction from IMPACT to move resin and its contingency amount of $1.7M from expense to capital may be over estimated by $300k per SE. SE to work with project team to remove spend to avoid double counting. X/X/15 Partial Asset Replacement.	12/21/15 Added $500k into capital to account for resins and buffer expenditures per VG. 12/15/15 Moved $1.7M from expense into Capital per IMPACT. 05/05/15 SS Submitted. 05/06/15 CA Routing.	Start-up	QSP	Tech Transfers	Launch and Commercial Excellence		6/14/16 Change to On Hold due to the uncertatnty with this project.	Hold	Deidre Dunham	N/A	N/A	Semsi Ensari						N/A	N/A	60
74510	PCS Asset Replacement - 2016		10/01/15 PMT Endorsed. 9/02/15 Originally called Automation System Lifecycle MCS Upgrade. 6/19/15 PMT Appr only feed study for $300k.	Individual	QSP	Stay in Business	Fit for Purpose		Upgrade PCS hardware and software for Development, Validation and Production environments. Coordinate with P2 Project Team to deploy during the 2016 Plant Shutdown.	Execute	Zaymar Sedra	TBD	Alister Hufton	Myles Sumlin						N/A	N/A	N/A
74511	QR018 Compliance Steam and Condensate Containment	CAPA 969326	2/19/16 Project name changed to match CA. 10/27 IMPACT Endorsed. 10/22/15 PMT Endorsed. 10/12/15 Submitted SS.	Individual	QSP	Stay in Business	Reliability and Value		Compliance with QR018, meeting CAPA 939326 requirements, and to mitigate equipment degradation due to splashing, pooling and vapor condensation. Mitigation of slipping hazards for personell from condensate pooling and drain splashing. Scope includes both P1 and P2.	Execute	Scott Fields	Rich Johnson	Mel Davis	Anastasia Gandrik / Sumner Tison						2.6	3.8	13.3
74512	K6 Program - Project 2 - B381 Compliance	4/15/16 Prefer to couple with project 74278 to reduce risk of cost overruns, pending general manager endorsement.	11/6/15 SS pending signature.	Individual	CTT	SHE and K-Directives	Fit for Purpose		Existing DX HVAC units in B-381 Conference Center use R-410A refrigerant. This refrigerant is on the list of materials to be eliminated per the Roche K6 directive.	FXNL LT Appr	Zaymar Sedra	John Urban	Mel Davis	Geoff Wing
74513	Electric Vehicle Charging Stations		10/20/15 Presented to IMPACT, however it was put on hold. 8/31/15 SS Submitted.	Individual	CTT	Improvements and Efficiencies	Exceptional Culture		There are no EV charging stations on the site at OCN. This project will install up to five on-site EV charging stations to serve up to 20 vehicles. allowing OCN to remain competitive and a desired employer near talent competititors. Inline with other large local innovative companies. Benefit for Great Place to Work. Reduce Ecobalance contribution. Supports advancement of green vehicles.	Hold	Deidre Dunham	Scott Brier	Mel Davis	Sumner Tison						0.3	1.5	2.2000000000000002
74524	Bioburden 2606 IPA Exhaust Improvement	SHE - Project identified during SBP Review. Might change name to IPA Exhaust Improvement (STARI 16830)	6/25/15 Changed to FXNL.	Individual	RTO	SHE and K-Directives	Reliability and Value		Over exposure to IPA can lead to major health complications. Currently Roche and OSHA "Alert" and "Action" levels of exposure have been exceeded.	Execute	Scott Fields	Marcus Espinoza	Mel Davis	Geoff Wing						2.2999999999999998	1	18
74526	Utility and Process Safety System	2/25/16 Assumptions for T0, unaware of the full scope of the project. Was assumed to be a project-by-project basis, not "full ring" basis--will deliver on Freeze Thaw and CCC projects. 12/10 Renamed from SIL II System. 11/10/15 Potentially replace Asphyxiant Gas Remediation project; P2 Critical. Mel to submit SS by 11/15/15.		Individual	RTO	SHE and K-Directives	Reliability and Value		The OCN site lacks a dedicated Safety Instrumented System to avoid issues with code compliance, avoid accidental trips, maintain and test instruments.	FXNL LT Appr	Scott Fields	John Urban	Mel Davis	Charles Fuller						2.6	3.8	13.3
74527	Vessel 1020 Upgrade	4/14/16 Project is for Actemra.	11/11/15 Will J. to work on SS. 05/18/15 Changed to Budgeted. Endorsed by Don to be included in MO5 budget and bring it to execution in 2015.	Individual	QSP	Stay in Business	Fit for Purpose		The media is being made in a hastelloy tank in buffer prep and then needs to be packed out to be used in the upstream. Technically, we are crossing the US/DS barrier - this is a bad practice and will get more complex when we are mfg concurrent products. The pack out line in buffer prep is also stainless and is currently pitted due to the upstream solution. Replacement of the V1020 will replace the entire piping and media filter with the higher alloy metal.	Idea	Zaymar Sedra	John Urban	Mel Davis	Will Jimenez						2.2999999999999998	3	13.5
76643	Optimize Column Movement Device	Optimization of the Column Moving Device (RTO, CTT). Caustic Bath (RTO, CTT) and Frit Handling & Storage (CTT) were presented all together, however, IMPACT decided to approved only the CMD and asked for the other two items be submitted separately through the PPM process. The Business Driver could be RTO or QSP as is STARI project. It needs a SHA Checlist for each piece.	10/30/14 WBS received. 10/23/14 CA submitted. 9/23/14 Partially appr by IMPACT. Only the CMD.Name changed back to original. 9/11/14 Appr by jPMT. 9/4/14 Name changed according to Bahar input. 7/3/14 dded same budget as MO5. We need to confirm by Sep. 6/24/14 Sent email.	Global	RTO	SHE and K-Directives	Highly Capable Workforce		With the current equipment operators need to bend down carrying heavy hydraulic jacks, synchronize lifting operation making it unsafe and difficult, the whole lifting and moving process takes a long time.	Execute	Melanie Yevilov	John Urban	Mel Davis	Bahar Dahi	353000	353000			Yes	2.4	1.3	18.600000000000001
96022	WFI Pump Autostart	Put it on hold. Original Estimate $286k. Confirm acceptable risk? * We are doing this on HWFI 2 in DBx. Prove program on HWFI 2 and carry over to HWFI 3 *AWFI and HWFI systems, including circulation pumps, do not restart automatically after power loss and recovery. WFI service cannot be disabled for more than 240 minutes. Automation request to include a download parameters from Delta V to pump VFDs, during plant re-start following power loss recovery. New cost includes commisioning/validation/CRB	11/03/14 Per Tim's email, this projects needs to be removed giving priority to P2 and WFI. 7/28/14 Changed PMO Lead 6/17/14 - It can't be done in 2014. Needs IT and Q resources	Global	RTO	Improvements and Efficiencies	TBD		The Oceanside facility needs a robust and efficient auto start procedure for the WFI pumps after a power outage. Power outages causes the WFI pumps to shut down and reboot. The current reset sequence is complicated and time consuming and can take approximately 15 minutes per loop. This project makes significant contribution towards plant reliability and supply to patients.	Hold	Deidre Dunham	CRB	TBD	Tim Lai					N/A	0.6	1.2	4.3
96040	GWR 1080/1090	Below the line. Budget Cap $170k Exp $10k 2015. SS has been submitted. Need NPV. Process Improvement, Material Loss, compliance	12/18/14 Changed to on Hold. 11/11/14 Project reviewed. Linda to submit RR and signed SS by Nov 19. 8/27/14 Changed to Budgeted. 6/30/14 Added budget. Confirmed with Scott it will be executed in 2015. 6/11/14 Changed to Hold - JN. To make room for Agitator Seal Flush. Changed to QSP	Global	QSP	Improvements and Efficiencies	Agile		This continuous improvement project for media prep tanks V1080/V1090 will provide an accurate method to measure tank level. Guided wave radar transmitters will ensure solution preparations are prepared to target specification while utilizing industry/company best practices to minimize operational risk. Currently, not having a reliable and accurate method for measuring tank level increases the risk of producing material outside of acceptable limits with low detectability (potential compliance risk).	Hold	Zaymar Sedra	CRB Partial	TBD	Linda Hope					No	1.3	1.3	10.1
96069	Warehouse Crown Forklift Asset Replacement	Asset Replacement	12/07/15 On Hold until 2017 per Rich Dimler. 7/07/15 CA put on hold. 6/03/15 CA issued. 11/05/14 Put on hold for 2015. 10/30/14 CA on hold. 8/2/14 Infom to IMAPCT. 8/21/14 Inform to jPMT. Budget has been adjusted. 7/3/14 Added budget according to Liza's pull in list	Global	QSP	Life Cycle Mgmt	Fit for Purpose		The lift is needed to assist in the transport of materials within the warehouse for storage or placement. The fit is used to alleviate a person from lifting heavy items that may cause severe injury. Doing nothing it will not ensure safe operations within the warehouse. Part of the 2013 Asset Life Cycle Management Report.	Hold	Zaymar Sedra	Tucker Creighton	Alister Hufton	Richard Dimler					No	N/A	N/A	N/A
96105	TMAC Tenderizer	SHE- Project identified during SBP Review.	4/15/16 Project on Hold pending Rituxan being added to the production plan.	Individual	QSP	Stay in Business	Highly Capable Workforce			Hold	Melanie Yevilov	Marcus Espinoza	Mel Davis	Pierre Luong
96109	Sci&Eng Lab Equipment for NPI and Launch Capability	Technology - Project identified during SBP Review.	10/08/15 PMT Endorsed.	Individual	QSP	Tech Transfers	Launch and Commercial Excellence			Placeholder	Jim Neeleman	Greg Crecely	Alister Hufton	Fikret Kulenovic
96112	Maintenance Ops Shop Buildout	2016 Cap $1M, 2017 Cap. $2M FOS -Project identified during SBP Review.	6/14/16 Deferred to 2019 per Hayden. Deferred to 2017. On Hold.	Individual	QSP	Improvements and Efficiencies	Fit for Purpose	A1 Automation Improvement		Budgeted	Zaymar Sedra	TBD	TBD	Hayden Knox
96113	Bulk Product Storage -20/-40	Technology - Project identified during SBP Review.		Individual	QSP	Improvements and Efficiencies	Launch Facility			Placeholder	Deidre Dunham	TBD	TBD	TBD
96114	QC Testing Equipment for Launch Capability and Storage Requirements	Quality - Project identified during SBP Review.		Individual	QSP	Tech Transfers	Launch and Commercial Excellence			Placeholder	Jim Neeleman	TBD	TBD	TBD
96116	PCS Process Support Equipment Integration			Individual	QSP	Improvements and Efficiencies	TBD	A1 Automation Improvement		Idea	Deidre Dunham	TBD	Alister Hufton	Sarah Maruccia
96117	MCS Manufacturing Area Wireless Access Point Asset Replacement - 2019			Global	QSP	Life Cycle Mgmt	Reliable			Idea	Deidre Dunham	TBD	TBD	Myles Sumlin						N/A	N/A	N/A
96124	Perjeta Tech Transfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Jim Neeleman	N/A	TBD	Semsi Ensari
96125	Flu A TechTransfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Deidre Dunham	N/A	TBD	Semsi Ensari
96126	Flu B Tech Transfer			Start-up	QSP	Tech Transfers	Launch and Commercial Excellence			Idea	Deidre Dunham	N/A	TBD	Semsi Ensari
74546	Mezzanine Safety Shower/Eye Wash Station Install		07/01/2015 SS submitted.	Individual	RTO	SHE and K-Directives	Highly Capable Workforce		Cal/OSHA requires that Safety Showers / Eye Wash stations be within 55' or 10 secs. Currently Manufacturing is using a Manual Liuid Add Process which presents a risk hazardous materials coming into contact with employees.	IMPACT Appr	Melanie Yevilov	TBD	Mel Davis	Marcus Espinoza						0.5	2.5	2.9
96133	QC Rapid Scan RDI System	2016 $210,000	07/01/2015 SS submitted.	Global	QSP	New Technologies	Launch and Commercial Excellence		Install and qualify Rapid Scan RDI System for GMP use in QC Lab. This is a global effort to harmonize Rapid Bioburden equipment to test pre filtration media that can measure and detect small measures of bioburden.	Hold	Jim Neeleman	TBD	TBD	Siu Fai Tsang						2.2999999999999998	2.2000000000000002	15.3
96135	QC Spectrophotometers	2016 $327,522	07/01/2015 SS submitted.	Global	QSP	Improvements and Efficiencies	Highly Capable Workforce		Install and qualify spectrophometers for GMP use in QC Lab to maintain and fast pace on testing for potency assay and reduce risk of job injuries for repetitive motion.	Hold	Melanie Yevilov	TBD	TBD	Siu Fai Tsang						1.8	1	14.4
96136	V-3007 Replacement	4/19/16 SPPM to assess business case prior to T3 updates. 10/05/15 Project being evaluated to dfetermine if it can be done before S/D.	07/01/2015 SS submitted.	Global	QSP	Life Cycle Mgmt	Fit for Purpose		TMAC vessel has been determined to have corrosion and needs to be replaced. Upsizing the pumps and piping for offloading is required to shorten the TMAC waste transfer period. This project is needed to maintain out TMAC system in a reliable and efficient operational state. TMAC vessel is needed for Rituxan. P2 tie-in associated with this vessel.	FXNL LT Appr	Zaymar Sedra	TBD	Mel Davis	Pierre Luong						N/A	N/A	N/A
96137	Security Systems Upgrade	5/12/16 Name changed from Security Cameras Improvement on Parking Lot, per JA. 2016 Cap $200k	07/01/2015 SS submitted.	Global	QSP	SHE and K-Directives	Exceptional Culture		Current security cameras will be obstructed with the installation of the new solar power panels and awnings, raising potential safety and security issues. Security cameras will be installed and tied in to the existing units in order to allow monitoring of the site more effectively.	Hold	Deidre Dunham	TBD	Mel Davis	Juan Aragonez						0.9	1.6	6.7
96139	Trash Bin Storm Water Mitigation	12/10 renamed Trash bins storm water remediation. Study done in 2015 $100k funded by SHE. This is required to meet compliance due to changes introduced by the solar project. This will be all capital and will be about 4-500K. I don't have a scope sheet yet, but this definitely needs to get done next year due to a compliance issue with the City	7/16/2015 SS sumitted.	Global	RTO	SHE and K-Directives	Reliability and Value		Regional Water Board and City of OCN regulation states the need for an approved SWMP. Genentech OCN does not have a documented plan in place. This project will Identify plan requirements. Subsequent activity to include detailed design and construction to implement site changes.Regulatory requirement.	Hold	Scott Fields	TBD	Mel Davis	Gary Merrill						0.9	2	6.3
96143	Paperless Metone	$250k	07/01/2015 SS submitted.	Global	CTT	Improvements and Efficiencies	ACCR		Improvements on data management and storage of Metone. Current system is unreliable and inefficient. Paperless system will upload results into LIMS and eliminate transcription error, use of paper and improve data storage.	Hold	Scott Fields	TBD	TBD	Rick Learn
65066	Appleton Tank Mover		11/12/15 Deferred until 2017. 11/02/15 Canceled as it is not needed for Actemra campaings. 10/15/10 CA Routing.	Global	QSP	SHE and K-Directives	Highly Capable Workforce		Significant risk is involved on moving heavy tanks manually.These movers will mitigate risk of injuries and allow more efficient evolution of moving freeze thaw tanks.	Hold	Melanie Yevilov	Marcus Espinoza	Mel Davis	Marcus Espinoza						1.1000000000000001	0.5	8.9
65021	Hazardous Material Response Cart			Global	RTO	SHE and K-Directives	Highly Capable Workforce		Site has committed to Performance Based Standards with the Fire Department and could be cited for non-compliance or failure to enforce stardards. Clean harbors is in need of a dedicated Hazardous Materials Response Cart to due the increased hours of emergency spill responjse.	Execute	Melanie Yevilov	Marcus Espinoza	Mel Davis	Gary Merrill						0.5	0.4	3.9
64992	QC Osmometer Asset Replacement			Global	RTO	Stay in Business	Reliable		This project is to replace two osmometers for QC in preparation of method transfer and testing for the new product coming into Oceanside manufacturing facility.The model installed in the lab has failed. Service was called and supplier (Advanced Instrument) has informed the model in the lab is obsoleted and beyond service.	Execute	Jim Neeleman	TBD	TBD	Siu Fai Tsang						N/A	N/A	N/A
64994	Helium Sniffer Replacement			Global	QSP	Stay in Business	Reliable		Helium sniffers are needed to ensure vessel integrity. Currently, there is one functional unit on loan from the vendor. Having two additional units will allow performance of helium testing quickly and provide a back up in case of failure.	Execute	Jim Neeleman	TBD	TBD	Chris LeTourneau
96159	OCC Network Remediation			Global	TBD	Improvements and Efficiencies	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	Kelly Calderwell						2.9	1	22.8
96163	MFG Depth Filter Housing			Global	TBD	Stay in Business	Reliability and Value			Idea	Scott Fields	TBD	TBD	Ed Montoya / Clarence Flowers
96164	Hazardous Materials Containers Washing Station		4/18/16 Project on Hold. Determined that the contractors who perform the cleaning would be using a current wash roomt o perform this work and that project was not moved above the line, per Marc Espinoza.	Global	TBD	SHE and K-Directives	Highly Capable Workforce			Placeholder	Melanie Yevilov	TBD	Marcus Espinoza	Gary Merrill
96165	WAN Link Redundancy			Individual	TBD	Improvements and Efficiencies	Reliability and Value			Idea	Scott Fields	TBD	TBD	Kelly Calderwell						2.1	2.2999999999999998	14.1
96167	Emergency Generator High Level Alarm			Global	TBD	SHE and K-Directives	Reliability and Value			Idea	Scott Fields	TBD	TBD	TBD
96168	Replace Warehouse #321 Sprinkler Heads			Global	TBD	SHE and K-Directives	Highly Capable Workforce			Idea	Melanie Yevilov	TBD	TBD	TBD
65005	Analytical Scale	1/20/16 This project is asset replacement per ZS.		Global	QSP	New Technologies	Reliability and Value		Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	Execute	Scott Fields	TBD	TBD	Tyrone White
65009	Drum Mover/Raw Material Tenderizer			Global	CTT	SHE and K-Directives	Highly Capable Workforce		This project will eliminate the unsafe work environment for employees because they will no longer need to lift drums or use the current raw material tenderizer which has been deemed unsafe. This machine can also be a solution for other sites across the network who are looking for the same solution.	Execute	Melanie Yevilov	TBD	TBD	Tyrone White
65020	QC Auto-Pipettor for Potency Assay			Global	CTT	SHE and K-Directives	Reliability and Value		The auto-pipettor will be used for sample dilution in the new BaF cell line to replace manual pipetting to avoid any repetitive injury from manual pipetting.	Execute	Scott Fields	TBD	TBD	Siu Fai Tsang
65023	QC Plate Washer for Potency Assay			Global	CTT	New Technologies	Launch and Commercial Excellence		Etrolizumab will be starting the method transfer to Oceanside by SSF in Q1, 2016. This type of plate washer is unique for this assay with a 7 degree angle head to wash off cell during potency assay.	Execute	Jim Neeleman	TBD	TBD	Siu Fai Tsang
65018	Spare Bowl for Hermetic Centrifuge			Global	TBD	Improvements and Efficiencies	Fit for Purpose			Execute	Zaymar Sedra	TBD	TBD	TBD
65015	Lower Solid Collector for Centrifuge			Global	TBD	Improvements and Efficiencies	Reliability and Value			Execute	Scott Fields	TBD	TBD	TBD
65024	Sci&Eng Lab Incubator and Freezer Asset Replacement			Global	TBD	Stay in Business	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD
96169	Level Indicator Transmitters			Global	TBD	New Technologies	Fit for Purpose		Need to replace the level indicator transmitters (LIT-004) on the following CIP systems, as the existing level indicators are obsolete and one is malfunctioning: 7110, 7210, 7150, 7160, and 7170. These systems impact multiple other systems, so it would be ideal to complete the replacement during shutdown. Replacing 7170 while up and running would be particularly difficult, if not impossible.	Idea	Zaymar Sedra	TBD	TBD	John White
74535	Draining of Top Mounted Agitator Well (CAPA 1140940)		3/16/17 Project amount changed from $842,280 to $1M, as per AW.	Individual	RTO	Stay in Business	Reliability and Value		To align with network commitment per the Multi-Site Assessment #1105078.	FXNL LT Appr	Scott Fields	TBD	John Urban	Juan Pacio
65044	Additional MCS Backup Storage			Global	RTO	Improvements and Efficiencies	Reliability and Value		Currently, there is not enough backup capacity to perform system backup for MES at Oceanside. Data and system backup is a requirement as part of regulatory compliance.	Execute	Scott Fields	TBD	TBD	Michael Loh
65037	Analytical Scales (CAPA 1150248)			Global	QSP	New Technologies	Reliability and Value		Only one scale in the dispensary was capable of measuring weight in milligrams. With the current run rate, the analytical scale is constantly in use, both for Actemra and Rituxan. The current scale is broken and there is no secondary scale.	Execute	Scott Fields	TBD	TBD	Tyrone White
96174	Fall Protection Phase II			Global	TBD	SHE and K-Directives	TBD			Idea	TBD	Marcus Espinoza	TBD	Marcus Espinoza
65040	Sci&Eng Cryofreezer			Global	TBD	Stay in Business	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD
65048	Process Maintenance Boroscope			Global	TBD	Stay in Business	Reliability and Value			Execute	Scott Fields	TBD	TBD	Dennis Chavez
96177	Efficiency Projects			Global	TBD	Improvements and Efficiencies	Reliability and Value			Placeholder	Scott Fields	TBD	TBD	TBD
TBD	Piping Corrosion			Individual	TBD	Stay in Business	Reliability and Value			Execute	Scott Fields	TBD	TBD	Samuel Calhoun
96178	Process VSD and SOV Replacement - Phase 2	Asset Replacement - CRB heavely driven	10/26/15 Project rolled-over to 74487.	Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Idea	Deidre Dunham	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A
96179	Process VSD and SOV Replacement - Phase 3	Asset Replacement - CRB heavely driven		Individual	QSP	Stay in Business	Highly Capable Workforce		Both SOV and VSD problem create a great risk to reliable operations. The 2016 SD is a window opportunity to perform some or all of the identified equipment replacements.	Idea	Deidre Dunham	Tucker Creighton	Alister Hufton	Jonathan Clark					No	N/A	N/A	N/A
96180	TMAC Waste System Improvements	SHE Identified Project on 5/9/16		Individual	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96181	Fall Protection Phase 3	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96183	Site Signage Upgrade	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96184	Conference Center	SHE Identified Project on 5/9/16		Global	RTO	TBD	TBD			Idea	TBD	TBD	TBD	TBD
96188	Eye wash stations in mfg. gowning rooms	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96189	Pipe Labelling	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96191	UPSS Phase 2	SHE Identified Project on 5/9/16		Individual	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96192	Pressure Safety Facility Mitigations	SHE Identified Project on 5/9/16		Individual	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96193	Column Packing Fall Hazard	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96197	Security Systems Upgrade	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	Exceptional Culture			Idea	TBD	TBD	TBD	TBD
96200	Bottle Washing: FIFRA Program	SHE Identified Project on 5/9/16		Global	RTO	TBD	TBD			Idea	TBD	TBD	TBD	TBD
96201	Storm Water BMP for upper lot	SHE Identified Project on 5/9/16		Global	RTO	Stay in Business	TBD			Idea	TBD	TBD	TBD	TBD
96202	Drum Crusher	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96204	322 MRO Racks	SHE Identified Project on 5/9/16		Individual	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96205	Pressure Safety	SHE Identified Project on 5/9/16		Individual	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96206	Lab Earthquake restraints	SHE Identified Project on 5/9/16		Global	RTO	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD
96207	Weigh and Dispense Sink (CAPA1123109)	Submitted after MO5 on 5/9/16.	4/19/16 Submitted but not signed.	Global	RTO	Stay in Business	Reliability and Value			FXNL LT Appr	Scott Fields	TBD	Mel Davis	Joseph Semiklose
65082	RF Sealer Generator	Submitted after MO5 on 5/11/16.		Global	QSP	TBD	Reliability and Value		MFG currently has one RF sealing generator that is shared by Media Prep and Buffer Prep. Sharing of this unit reduces efficiency and the additional transportation and handling of this unit increases risk of malfuntion. We currently don't have a backup unit in the case of malfunction. This project is needed to provide adequate dedicated resources to the areas.	Execute	Scott Fields	TBD	TBD	Mark Maruccia

96991	Asset Replacement 2016 - Engineering (cc642)			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96992	Asset Replacement 2016 - Material Ops (cc484)			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96993	Asset Replacement 2016 - Manufacturing (cc1359)			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96994	Asset Replacement 2016 - Manufacturing			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96995	Asset Replacement 2016 - Quality	See breakdown on the Idea tab.		Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment - The total comes from ARR minus the $393k that were tried to pull-in in 2014 (Project P68) + the new assets that need to be repalced for $396k + 45% escalation	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96996	Asset Replacement 2016 - Technology			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96997	Asset Replacement 2016 - Facilities Ops			Global	QSP	Stay in Business	Fit for Purpose		Asset Replacment	FXNL LT Appr	Zaymar Sedra	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96998	Asset Replacement 2016 - BMSO		BMSO has only one AR on the report- Warehouse Forklift. This is not reflected on this line as it has been identified and it is disclose as a single line P69	Global	QSP	Stay in Business	Reliable		Asset Replacment - The only replacement under this department for 2015 is the Warehouse Forklift which is project P69	FXNL LT Appr	Jim Neeleman	N/A	N/A	Alister Huffton					No	N/A	N/A	N/A
96999	Site Management Adjustments (if any)			Individual						TBD
T															291951700	267347705	24603995

97042	CRB Project Budget Estimating		4/15/15 Estimate for 2015 was adjusted to $360k. $90k billed in Q1, and we assumed that same expedinture for Q2,Q3 & Q4. 6/17/14 - Added budget $178k for the five year outlook per Dave's email. DS	Expense	QSP	Improvements and Efficiencies	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A			N/A	N/A	N/A
97043	Travel Expenses	It is expense. Placeholder for 4368		Expense	QSP	Stay in Business	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A
97001	Lunches			Expense	QSP	Stay in Business	Reliability and Value	A6 Quality of work/life improvements		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A
97002	Office Supplies inc. Laptops			Expense	QSP	Stay in Business	Reliability and Value	A6 Quality of work/life improvements		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A
97044	IMPACT Support		6/17/14 - Added budget for the five year outlook. MD	Expense	QSP	Stay in Business	Reliability and Value	A2 Business Efficiency		Execute	Scott Fields	TBD	TBD	TBD	N/A	N/A	N/A
82000	I&C Engineering and Instrument Configuration Management System Remediation Project (CAPA 982343)		7/15/15 CA Appr. 7/10/15 Changed to CA Submitted. 6/10/15 CA issued.	Expense	CTT	Stay in Business	Reliability and Value	A1 Automation Improvement	With parallel project execution a browser I&C database allows concurrent queries and updates to be made. If nothing is done there is added overhead to maintain and outdated system.	Execute 1	Scott Fields	John Urban	Alister Hufton	Jonathan Clark						0.6	3.4	3.4
97003	MFG Systems Integration Improvement Phase 1 - 2015	This project is an consolidation of MES related projects icl. 74413 that was originally a Capex project.	11/02/15 CA was put on hold, still trying to bring this project to execution. 6/01/15 CA issued. 04/23/15 PMT Appr. 03/05/15 Project name changed from MES Enhancement Project - 2015 to current.	Expense	CTT	Improvements and Efficiencies	Reliability and Value	A1 Automation Improvement	Process Waste: Currently no ability to waste process materials that don’t exist in Syncade. When material cannot be wasted, it must be scrapped which requires justification and labor intensive forms.QC Sample Plan:Sample Plans have no user-viewable format specific to material and type that can be stored and managed in the DCA. Precludes that ability to use the DCA workflow for document approval. Order Locator: Inability to filter EBR review based on batch information creates inefficient process. The system is flooded with batch reports each day which makes targeting reports ready for review extremely difficult.	Execute 1	Scott Fields	N/A	N/A	Eric Davis						2.2999999999999998	2.2000000000000002	15.3
97005	MCS Peripheral Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Ravi Medandravu
97006	MCS Peripheral Asset Replacement - 2019			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97063	MCS Peripheral Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97007	Automation System Lifecycle MCS Upgrade	9/02/15 Renamed Automation System Lifecycle MCS Upgrade. 6/15/15 Originally called PCS Upgrade - 2015. Changed name and consolidated with MES Upgrade 2015. It was decided all three will be governed by P2 and paid by the site. Which is further reason to combine them into one project. 74427. /01/15 Per Steven, only PI/CD Phase will be done in 2015. The project will proceed with the PI Phase for a feed study. Since the requested amount is expense and less than $500k, a CA is not required. A PO will be requested for $300k. Eric Fallon will be added to the approval chain to endorse the project as the functional leader before the authorized approvers review the shopping cart. When the project returns for the next phase of funding, it should be split into two projects. The MES and PCS activities will become one project while the infrastructure activities will be the other.	11/30/15 Changed to Execution as the shopping cart was approved by AW for the PI phase for PCS Asset Replacement and the MCS Network Infrastructure. 9/02/15 Classified as Capex per Steven and changed name to PCS Asset Replacement 2016. 7/2/15 PMT Appr only feed study. 6/15/15 Name changed and consolidated.	Expense	QSP	Improvements and Efficiencies	Reliability and Value			Execute	Scott Fields	TBD	TBD	Myles Sumlin						4.5999999999999996	3	27.6
97008	PCS Asset Replacement - 2019			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97064	PCS Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97009	MES Asset Replacement - 2017		9/02/15 This project comes back as a single and deferred to 2017. Roughly originally estimated for $1.1M 6/15/15 Rolled over to Automation System Lifecycle MCS Upgrade - E07.	Expense	QSP	Stay in Business	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	Ravi Medandravu
97010	MES Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97012	Site Data Historian Asset Replacement - 2017	8/7/15 Per Myles' email this project has been deferred to 2017.		Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Myles Sumlin
97013	Site Data Historian Asset Replacement - 2019	9/02/15 Per Steven this projects has been deferred to 2019.		Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin
97065	Site Data Historian Asset Replacement - 2021			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin
97015	MCS Backup System Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			FXNL LT Appr	Zaymar Sedra	TBD	TBD	Myles Sumlin
97016	MCS Backup System Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Myles Sumlin
97018	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2017			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97019	PDFx Lab and Pilot Plant DeltaV Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			FXNL LT Appr	Deidre Dunham	TBD	TBD	Ravi Medandravu
97020	Trailers (inc. fluor mods space and PacVan, janitorial, coffe/tea, mat services, pest control)			Expense	QSP	Stay in Business	Reliability and Value	A6 Quality of work/life improvements		Execute	Scott Fields	TBD	TBD	Alister Huffton	N/A	N/A	N/A
97030	MFG Systems Integration Improvement Phase 3 - 2017	Including MES/SAP System Integration - Real time Manufacturing Scheduling in SAP		Expense	QSP	Improvements and Efficiencies	Fit for Purpose	A1 Automation Improvement		Canceled	Zaymar Sedra	TBD	TBD	TBD
97031	MCS Data Analytics Asset Replacement - 2017			Expense	QSP	Stay in Business	Fit for Purpose			Idea	Zaymar Sedra	TBD	TBD	TBD
97032	MCS Data Analytics Asset Replacement - 2020			Expense	QSP	Stay in Business	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD
97033	PCS Automated Documentation Upgrade			Expense	QSP	New Technologies	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD
97066	PCS Automated Documentation Asset Replacement - 2021			Expense	QSP	New Technologies	Reliable			Idea	Deidre Dunham	TBD	TBD	TBD
97037	Recipe Reconfiguration Alignment for Operating Systems			Expense	QSP	Improvements and Efficiencies	Launch and Commercial Excellence		Current automation recipe design is not aligned to Network SAP Planning & Scheduling platform. The misalignment results in delayed material consumptions, elevated raw material inventory, inadequate detailed production schedules, multiple manual alternate mechanisms and increased risk to production. Accelerated production run rates and product launch add a new level of complexity which demands appropriate alignment of operating systems to minimize risk exposure, ensure success and align with network supply chain processes.	FXNL LT Appr	Jim Neeleman	TBD	N/A	Marco Baca						2.7	4.2	13
97038	PCS Functional Specification Development Project (CAPA 960297)		6/26/15 Classified as Expense according to Automation Team. 4/13/15 SS Submitted. 3/19/15 SS in progress	Expense	RTO	Strategic	Reliability and Value		PCS Functional Specification do not exist for the majority of the existing process systems at OCN, incurring in human errors. Creating of FSs for all impact system will ensure robust documentation on the integration of equipment, utilities, manual procedures, instrumentation and process control logic at the site.	FXNL LT Appr	Scott Fields	TBD	Alister Hufton	Sarah Maruccia						2.2999999999999998	3	13.5
97039	PCS Remediation for EBR Review by Exception - PI	Technology - Project identified during SBP Review.	4/15/16 Project start slides to 2017, to be confirmed with SH. 11/23/15 No approved SS. 6/26/15 Classified as Expense according to Automation Team.	Expense	QSP	Improvements and Efficiencies	Highly Capable Workforce	A1 Automation Improvement		Idea	Melanie Yevilov	John Urban	Alister Hufton	Malou Jacinto / Stephanie Huntress						2.7	4.2	13
97040	Tech Transfer: Master Data Management		12/15/15 Reduced 2016 amount by $306k and moved into 2017 per Dave Stewart. 11/23/15 Feed Study to be paid by cc 644 (Eric Fallon).	Expense	RTO	Tech Transfers	Launch and Commercial Excellence		Creates a single source of information that will standardized and streamline the business process of importing and exporting data. OCN will soon become a Launch Facility with the completion of P2 and having a validated system to manage the new/existing data is imperative to reduce errors and create user accountability.	FXNL LT Appr	Jim Neeleman	N/A	N/A	Marco Baca						4.0999999999999996	3	24.3
97045	Site Exterior Lighting Upgrade - Title 24	4/15/16 Follow up with Charles Fuller for updated SS.	6/27/14 Per Maria's email, this project is expense. 6/26/14 Is it a EXPENSE or not? Each light will be under $5k. It is a replacement 6/25/14 CRB doing the estimate Mel working with Tucker/Mike for the SS. DS 6/17/14 - Need Scope Sheet. Jim will work with the SME	Expense	CTT	SHE and K-Directives	Reliability and Value		This is retrofitting the existing light mounts and poles with new LED fixtures. It is energy savings. Title 24 requires that once you change 10% of your exterior lighting, you need to do the remainder - about half of the lighting is being changed due to the solar project so this will change out the remainder.	FXNL LT Appr	Scott Fields	TBD	Mel Davis	Charles Fuller
97046	Hazardous Waste Storage Bunker	2015 Cap $40k; 2016 Cap $40k		Expense	QSP	SHE and K-Directives	Reliable			Execute	Jim Neeleman	Marcus Espinoza	Mel Davis	Marcus Espinoza						0.8	1	6
97047	Flammable Storage Cabinets Upgrade			Expense	RTO	SHE and K-Directives	Reliable		Replace current cabinet with one that complies with Fire Code. If nothing is done the cite remains at risk of citation which could result in fines.	Execute	Jim Neeleman	Marcus Espinoza	Mel Davis	Marcus Espinoza						0.5	0.4	3.9
97048	Arc Flash Prevention		11/23/15 Check with Marcus on monthly cash flow. 11/05/15 PMT Endorsed.	Expense	RTO	SHE and K-Directives	Highly Capable Workforce		Multiple device settings, ciurcuit breakers and cable feeds were identified as being undersized operating above 95% of their operating capacity rate.	Execute	Melanie Yevilov	John Urban	Mel Davis	Marcus Espinoza						0.9	2.5	5.9
97049	SIMCA Online - Downstream Application		10/30/15 IMPACT e-reviwed.	Expense	QSP	New Technologies	TBD			Execute	Jim Neeleman	N/A	N/A	Chris Johnson
97051	MFG Electronic Use Logs (Syncade)			Expense	RTO	Strategic	Launch and Commercial Excellence			Placeholder	Deidre Dunham	TBD	TBD	Ravi Medandravu						1.1000000000000001	2.5	6.8
97052	MFG P1 Actemra Horiba Replacement			Expense	TBD	Stay in Business	TBD			Placeholder	TBD	TBD	TBD	TBD
97053	Pressure Safety Program - PI Phase			Expense	TBD	SHE and K-Directives	TBD			Idea	TBD	TBD	TBD	TBD						1.4	2.5	8.8000000000000007
97054	HVAC Retro Commissioning	Below the line - Budget Cap $25k Exp $5k 2015.	10/1/15 Project renamed from Reduce Reheat Requirements. 12/18/14 Changed to On Hold. 11/10/14 Project reviewed.	Expense	CTT	Stay in Business	Reliability and Value		Project wll reduce energy consumption as a requirement of K-18. Projected annual savings of $220k in energy costs and reduced CO2 emissions of approx. 1210 metric tons.	FXNL LT Appr	Scott Fields	TBD	TBD	Geoff Wing / Scott Breier					No	2	1	15.6
97057	Conference Room 315 Expansion			Expense	TBD	Improvements and Efficiencies	Exceptional Culture			Idea	Deidre Dunham	TBD	Alister Hufton	N/A
97058	Parking Pavement Repair			Expense	CTT	Stay in Business	Reliability and Value			Execute	Scott Fields	Blake Brown	Mel Davis	Sumner Tison
97059	B311 & B321 Gowning Room Modifications		3/17/16 Project amount changed from $75k to $131k.	Expense	RTO	Stay in Business	Reliability and Value		Revised manufacturing gowning SOP becomes effective in February 2016, necessitating modifications to existing lockers and shoe storage to support this SOP.	Execute	Scott Fields	TBD	Mel Davis	TBD
97060	QC Gas Cabinet Removal			Expense	QSP	TBD	TBD		QC cold storage capacity demand increases each year. Therefore additional space is required for cold storage equipment.	FXNL LT Appr	TBD	TBD	Mel Davis	Joe Molon
97061	Tangential Flow Filtration Cassettes Management		11/20/15 Automation does not have resources to support project until 2017. Priority projects will be to complete current CAPA and shutdown related projects for 2016.	Expense	RTO	Improvements and Efficiencies	Reliability and Value		An inspection could bring the problem to surface that not full genealogy is followed for the TFF cassettes which are product contacting. Human error in data input could impact ability to continue production under validated cassettes use.	FXNL LT Appr	Scott Fields	N/A	Juan Pacio	Stephanie Huntress						5.4	1.6	40
97062	PI- Ammonia RMP Study	SHE Identified Project on 5/9/16		Expense	RTO	TBD	TBD			Idea	TBD	TBD	TBD	TBD

E

98001	CMC Continuum	Some of the Tier 1 solutions (and resources) endorsed by PTLT will go into 2015. Deliver a clear, transparent, and streamlined CMC lifecycle management process from start of PhIII Development to end of Warranty Period in order to enhance our capabilities to commercialize new products. In combination with implementation, a realization plan will be developed including the needed shifts in behavior and mindset (WS1 Develop PTx Resource Activity Model to reflect baseline new product commercialization activities across PT, WS2 Create an effective and overlapping handover process from development to commercial for robust and HA acceptable processes, and WS3 Develop designated launch facility(ies) concept and plans)	We need info. Needs SME - MY. Potential fall out from P2.	N/A	QSP	Capacity	Launch Facility			Complete	Deidre Dunham	TBD	TBD	TBD
98005	Empower 3 Rollout	6/10/14 Sent email to SME. Waiting for feedback. Network that needs Capital - MY. OCN must purchase 5 HPLCs b/c Emplower 3 not compatible with our current HPLCs which also are approaching end of life.		N/A	TBD	New Technologies				Hold	TBD	Jessica Justice	TBD	Siu Fai Tsang
98006	GMP Document Lifecycle - 2014/2015	Create a unified definition / process / procedure to define the overall lifecycle of GMP records.	Network Project. Issues with Resource plan.	N/A	RTO	Improvements and Efficiencies	Reliable			Complete	TBD	Dona Bloch	TBD	Esther Pohlscheidt
98009	PTB-006 Material of Construction (MOC) Program (GSP100 Implementation)	Project Addresses New requirements and processes introduced by GSP100 Objective: Fully implement and integrate the MOC Program Proposed Solution (Deliverable): Develop a phased approach for implementation of GSP100		N/A	RTO	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	Carl Hixon
98010	PTB-011 Microbial Task Force (GSP085 Implementation) Project	Revision of Bioburden test methods to align with compendial requirements, including define sample test volumes. Validation of bioburden method across all sites within scope		N/A	QSP	Stay in Business				Hold	TBD	TBD	TBD	TBD
98011	PTQ-xxx PQS: GSP085 - Microbiological Testing of Non-Sterile Material	MCTF will serve as a focused work team to implement GSP085, Microbiological Testing of Non-Sterile Materials.		N/A	RTO	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD
98013	PTB-002 Gentamicin Removal Strategy for Commercial Processes	"Commercial CHO processes utilizing gentamicin -Outside of network: Activase (BIP), Xolair (Novartis, shared with VV starting in 4Q 2014) -Within network: Avastin, Herceptin/Kadcyla, Perjeta, Pulmozyme, Rituxan, TNKase DS (SC/IV formulations and second brands) Multi-product implementation strategy needs to be defined by end of 2013 and communicated to FDA in a Type C meeting in 1Q 2014 ""Kadcyla - 2015 RSTO Avastin - 2018 SSF MabThera/Rituxan - 4Q2014 Samsung; 1-2Q2015 CCP2; 2019 CCP1 (possible that CCP1 might move up pending SC strategy) Xolair - 4Q2016 CCP1 Activase - 2016 BI TNKase - 2016 SSF Herceptin - IP Lonza (IV); 2015 RSTO (SC) Pulmozyme - 2016 SSF Perjeta - 2016 CCP1 NOTE: All new TTs will be G-"""		N/A	QSP	Strategic	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD
98014	PTB-003 Analysis of Global Tank Management Process and System Improvements	To conduct an end to end analysis of the tank management processes and develop a strategy / roadmap of improvement activities that will result in a more predictable performance and higher degree of assurance that tanks will be in the right place at the right time and at the desired level of quality.	5/12/15 Changed to Canceled per Melanie's email.	N/A	QSP		Multi Product			Canceled	TBD	TBD	TBD	TBD
98015	PRC-xxx Visible Particle Method Standardization	All Biologics -- pilot Herceptin first		N/A	TBD	Improvements and Efficiencies				Idea	TBD	TBD	TBD	TBD
98017	PTQ-005 Coremap	Systematically control all records at Roche, regardless of media format, from initial creation to final disposition.		N/A	CTT	Improvements and Efficiencies	Multi Product			Execute	Melanie Yevilov	TBD	TBD	Donna Bloch
98018	PTQ-xxx PQS: GSP034 - Biologics Cleaning Initiative			N/A	QSP	Strategic	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD
98019	PTQ-017 GMP Livelink to Condor	The project includes evaluating and adding new functionality to condor if needed by the business processes currently supported by DocLink and CEDM, migrating data (transactional, master and documents) from GMP LiveLink applications (DocLink, CEDM and BRES) to condor and other repositories, harmonization of document types/units, and decommissioning GMP Livelink when the data migrations are complete.		N/A	QSP	Improvements and Efficiencies	Multi Product			Hold	Melanie Yevilov	TBD	TBD	Donna Bloch
98022	PTQ-002 ALEX LES (Lab Execution System) Project	Reduce current challenges around paper management and simplify analyst activities in Biologics and Small Molecules QC labs.		N/A	CTT	Improvements and Efficiencies	ACCR		Paperless lab system to increase iffeciency and ability to meet demand.	Execute	Scott Fields	TBD	TBD	TBD
98024	PTB-013 Resource Transparency Project	Data will be provided by Danielle Golay			TBD					Canceled	TBD	TBD	TBD	TBD
98026	Launch Capability Program (LCP)			N/A	QSP	Tech Transfers	Launch and Commercial Excellence			Execute	Jim Neeleman	TBD	TBD	TBD
98027	PCR Based Adventitious Agents		Replace all cell-based and growth-based adventitious agents tests with PCR-based detection methods using the same “state-of the art”, fully automated Roche platform (MagNA Pure for nucleic acid purification and LightCycler 480 II for real-time target amplification and detection)							Canceled	TBD	TBD	TBD	TBD
98028	CalMan Replacement		The project will replace CalMan 4 with the current supportable Blue Mountain Regulatory Asset Manager (BMRAM) version R3 SR3. CalMan 4 is utilized by the Genentech regional sites (SSF, HTO, OCN, VAC, KDC), & Roche Singapore Technical Operations (RSTO). Both solutions are owned by vendor Blue Mountain Quality Resources.	N/A	QSP	New Technologies	Reliable		Calibration software replacement	Execute	TBD	TBD	TBD	Mark Martinez
98029	PTA-008 Business Continuity Management			N/A	QSP	Stay in Business	ACCR			Execute	Scott Fields	TBD	TBD	TBD
98031	PTB-016 PDM DS Phase II Project Resource Collection (TL)									Canceled	TBD	TBD	TBD	TBD
98032	PTQ-035: Automating Non-Routine Sample Management in LIMS			N/A		Improvements and Efficiencies				Hold	TBD	TBD	TBD	TBD
98034	PTS201416-Global Warehouse Capacity Management	Original name PTS201416-Global Logistic Transparency and Capacity		N/A	QSP	Stay in Business	Multi Product			Execute	Melanie Yevilov	TBD	TBD	TBD
98035	Biologics Commercial DS Investigation Reduction Project	03/10/15 Original name PTB-009 Investigation Free Lots. Changed to current per Melanie's email.		N/A	QSP	Strategic	Reliable		Improvement, root-cause analysis to reduce volume of products held up for investigation.	Idea	Jim Neeleman	TBD	TBD	TBD
98036	REMIS Pilot		6/25/2015 SS submitted.	N/A	RTO	New Technologies	Launch Facility		Support the global initiative, lead the network for data management inovation and effeciency. Data aggregation and analysis is manual and labor intensive. All data for validation and process monitoring must be manually compliance check by Quality.	FXNL LT Appr	Deidre Dunham	TBD	TBD	TBD
98037	PTB-023: Rapid Bioburden Method for Pre-filtration Media			N/A	QSP	Stay in Business	Multi Product		A rapid bioburden method for pre-filtration media is needed at DS sites to stay within bioburden limits, reduce holds steps, prevent loss of batches and increase reliability of fermentation processes by early detection of contaminated media.	Execute	TBD	TBD	TBD	TBD
98038	PTB-025: Warehouse Business Continuity Mgt			N/A	CTT	Stay in Business	ACCR		The NA DS supply network is currently subject to constraints that limit our ability to ransport and store product. In times of crisis or during demand shifts, these limitations increase our risks of not having enough supply and/or not having the right product in the right amoutns in the right places at the right times.	Execute	Scott Fields	TBD	TBD	TBD
98039	PTB-028: Global Implementation of Anaerobic Bioburden Assay			N/A	RTO	Stay in Business	Reliable		There have been 9 drug substance investigations related to P. acnes, an aerotolerant anaerobe, within the past ~1.5 years across multiple sites in the network resulting in a multisite significant investigation (DMS# 931144). There is a risk that P. acnes may elude our DS detection systems as it is not typically detected by the aerobic bioburden assay. Detection of these contaminations has occured via 1) mycoplasma test 2) low DO2 alarms or 3) microscopic visual examination (MVE). This has been identified as one of the top 5 cGMP compliance risks for the BIO OU.	Execute	TBD	TBD	TBD	TBD
98040	PTQ-038: Quality Compliance Scorecard (QCS) Phase 2			N/A	CTT	Stay in Business	Agile		Compliance Scorecard is a critical system used by PTQ to track identified issues with potential Health Authority impact. This system is used by all PT sites and provides key compliance metrics to PT LT. This project will focus on improving the system for users by simplifying the workflow and improving the usability. Reports will also be adapted based on the updated workflow.	Execute	TBD	TBD	TBD	TBD
98041	PTQ-041: Simply Core for PT			N/A	CTT	New Technologies	ACCR		The Simply Core IT project covers the migration of documents to future repositorites meeting the Coremap requirements from LiveLink/ShareWeb (non-validated instances only) and shared drivers (V:, G: Drive). The legacy repository will be decommissioned. Reduction of number of repositories supported by IT and PT and annual cost savings of 4-5.5 mil CHF.	Execute	TBD	TBD	TBD	TBD
98042	PTQ-046: Quality and Compliance Risk roll up			N/A	QSP	Stay in Business	Agile		Quality and Compliance risks are consolidated and rolled up to different levels of the organization (including PTLT) where business decisions on the top risks including prioritization for resource allocation are made. A simplified, more integrated business process will allow an easier process to collect, consolidate, and report critical Quality and Compliance risks for making these decisions with increased visibility throughout the PT organization.	Execute	TBD	TBD	TBD	TBD
98043	PTQ-050: QC Network Capacity Model			N/A	QSP	Strategic	ACCR		Insufficient QC capacity has been identified as a #1 PT risk. No standard QC capacity plannning and management model exists across the Bio and SM network. Inputs to existing capacity planning models/tools are compromised by workload volatility, absence of strategies within labs to level this workload and sub-optimal historical averages rather than standard work.	Execute	TBD	TBD	TBD	TBD
98044	PTQ-051: FileNet Replacement Assessment			N/A	CTT	Strategic	ACCR		Project will provide a global scalable image storage solution that will allow the destruction of paper files which reduces the costs and resources needed to maintain paper files.	Execute	TBD	TBD	TBD	TBD
98045	PTB-022: LER De-Masking			N/A	CTT	Stay in Business	ACCR			Execute	TBD	TBD	TBD	TBD

99001	SMART: 5 Day PCO Goal				RTO	Strategic	Reliable		Enhance multiple product capabilities for partially overlapping campaign modes (attain and maintain ≤ 5 days PCO, update documentation, define segregation, etc.) by Q2.	Execute	Cary Weisenberger			Robert Safarik
99002	SMART: Multi Product Segregation				RTO	Tech Transfers	Reliable		Enhance multiple product capabilities for partially overlapping campaign modes (attain and maintain ≤ 5 days PCO, update documentation, define segregation, etc.) by Q2.	Execute	Cary Weisenberger			Lou Luna
99003	SMART: Asset Replacement Plan				RTO		Reliable		World Class manufacturing is driven by planned, predictable performance. Asset Replacement Planning ensures the facility is sustainable for its intended purpose. A thorough and realistic analysis enables short and long term risk analysis and capital planning to support future objectives in the OCN site and network business plan.	Complete	Cary Weisenberger			Carl Hixon
99004	SMART: FOS PM Slow Down Assessment				RTO		Reliable		Currently the site has 3 weeks allocated in the master schedule to slow down production to 1.0 run per week (RPW) for 3 weeks each year, with a full shutdown for 1 week every third year, to allow time for routine Preventive Maintenance (PM) activities that cannot be performed during higher run rates. This results in a potential loss of up to 6 runs per year (up to 15 runs every 3 years). The exact slow down duration and run rate has not been validated against the planned work to be done to allow for the maximum annual production.	Complete	Cary Weisenberger			Tracy Tyler
99005	SMART: Spare Parts Stocking Strategy	through 2016			RTO	Strategic	Reliable		Oceanside is contributing to network targets by increasing plant capacity through DBX activities. Oceanside needs to be able to consistently deliver product on time, in full at run rates higher than previously demonstrated. If there is an adverse event at the site, the entire supply chain is in jeopardy. Spare parts are needed to avoid failure, shutdown, which can impact the supply chain and eventually the supply to the patient.	Execute	Cary Weisenberger			Carl Hixon
99006	SMART: Cycle Time Analysis				RTO	Improvements and Efficiencies	Reliable		OCN SMART goal to attain and sustain operational capability at 3.0 rpw for MRA SC and RIT.	Execute	Cary Weisenberger			Mark Baldwin
99007	SMART: Validation Enhancement				RTO	Improvements and Efficiencies	Reliable		World Class companies build flexible manufacturing to support changing markets. This facilitates on time and full delivery of the right product to the network at the right time and ultimately to the patient. Flexible production systems allow quick adjustments to changing needs.	Execute	Cary Weisenberger			Amr Ragui
99008	New Worker Cycle Time				QSP	Improvements and Efficiencies	Reliable		The Oceanside strategic goals are facilitated by timely arrival of incoming qualified, ready to work people. Complex processes under local, network, and corporate control challenge that timeliness.	Execute	Cary Weisenberger
99009	Class A Sustainment: Business Process Maintenance	through 2016			QSP	Strategic	Agile	A3 Class A Sustainment	Sustainment of Class A at the site has been a result of the efforts of those that went through certification and inertia. Moving forward, a refresh, maintenance, and update to the site's business processes, related metrics and behavior required to execute will prepare the site to become a launch facility.	Execute	Scott Fields
99010	Class A Sustainment: Governance Update	through 2016			QSP	Strategic	Reliable		Class A Behaviors and Performance provide a foundation to execute Oceanside’s vision and strategy	Execute	Cary Weisenberger
99011	Class A Sustainment: Site Refresh	through 2016			QSP	Strategic	Agile	A3 Class A Sustainment	Sustainment of Class A at the site has been a result of the efforts of those that went through certification and inertia. Moving forward, a refresh, maintenance, and update to the site's business processes, related metrics and behavior required to execute will prepare the site to become a launch facility.	Idea	Zaymar Sedra			Cary Weisenberger / Scott Fields
99012	PIF Development and Engagement	through 2016			QSP	Strategic	Agile	A4 Continuous Improvements	There is a need for a distribution of engaged employees with the skill sets to lead and foster a culture of Continuous Improvement. Our leadership has made a commitment to invest in the development of its people that have the attitude and aptitude to become champions of change.	Execute	Scott Fields
99013	OCN IFL Project Portfolio Support				RTO	Strategic	Reliable		Production Performance (PP) is the primary reliability measure for the DS manufacturing plants. The baseline performance analysis of PP showed that Investigation was the primary driver of poor performance. By their nature, Investigations are inherently “special cause” so to improve overall IFL performance we need to address the major themes at the site with coordinated improvement actions. OCN has IFL improvement as a 2015 strategic goal.	Execute	Scott Fields
99015	LCP/P2 Process Assessment Support	through 2017			QSP	Tech Transfers	Launch Facility		A launch facility concept here in OCN is new and untested. We must effectively transition to a launch facility, becoming capable of manufacturing and globally licensing new products while concurrently manufacturing mature commercial products. LCP will help us meet our network wide capacity goals so that we can continue to reliably deliver the pipeline and ensure uninterrupted supply of quality products to our patients. OE/BPM methods and tools will need to be effectively deployed to maximize LCP and P2 potential.	Idea	Deidre Dunham			Scott Fields
99016	Causal Analysis and Human Factor Assesment				RTO	Improvements and Efficiencies	Reliable		Discrepancy events have direct cost to Oceanside operations in the form of rework, lost product, and increased lead time. At best, actions to address human error (e.g. retraining or counseling) may reduce the number of events, but will not prevent occurrence. High, systemic discrepancy rates which conclude human error may be challenged by Health Authorities, posing a risk to maintaining our Right to Operate and ability to Supply Quality Product to patients.	Execute	Scott Fields

## 'file:///C:/Users/webster5/AppData/Roaming/Microsoft/Excel/2016%20Master%20Project%20Portfolio%20BU%20110%20(version%201).xlsb'#2016_Budget_by_FIN_CYCLE
6DM					786250				3202844.7000000007			3325311.2750000004			3657842.4025000008	0	0	4023626.642750001	0	0	4425989.3070250014	1385000		1385000	24387494.327275004		2554107	24450	2578556	477848	0	3325311	0	0	3657842	0	0	4023627	0	0	4425989	1385000		1385000	19134416	3149795.0000000005	28849.7	3178644.7000000007	927504.60000000009	0	3325311.2750000004	0	0	3657842.4025000008	0	0	4023626.642750001	0	0	4425989.3070250014	1385000		1385000	24363294.327275004	880407	0	880407	2179954.7000000002	0	2179954.7000000002	1270000		1270000	1305000		1305000	1345000		1345000	1385000		1385000				8738101.6999999993	2554107	24450	2578556	477848	0	3325311	0	0	3657842	0	0	4023627	0	0	4425989	1385000		1385000	19134416
90024					9765687				2402033.7000000002			1790552.2250000001			1969607.4475000002	3300000.0000000005	0	2166568.1922500003	3784000.0000000005	0	2383225.0114750005	5979000		5979000	40883893.576224998		2028821	22286	2051107	0	0	1790552	0	0	1969607	0	0	2166568	0	0	2383225	5979000		5979000	13866135	2379242.8000000003	22790.9	2402033.7000000002	3432000.0000000005	0	1790552.2250000001	3432000.0000000005	0	1969607.4475000002	3300000.0000000005	0	2166568.1922500003	3784000.0000000005	0	2383225.0114750005	5979000		5979000	40883893.576224998	1753651	245995	1999646	1170172.3	28902.500000000004	1199074.8	5785440		5785440	5786069		5786069	5805000		5805000	5979000		5979000				28516797.800000001	2028821	22286	2051107	0	0	1790552	0	0	1969607	0	0	2166568	0	0	2383225	5979000		5979000	13866135

64899					66881.47				4011			0			0			0			0			0	70892.47				0			0			0			0			0			0	75000	4011		4011			0			0			0			0			0	70892.47	75000		75000			0			0			0			0			0				75000			0			0			0			0			0			0	75000
64901					223217.34				99984			0			0			0			0			0	323201.33999999997		100000		100000			0			0			0			0			0	425200	99984		99984			0			0			0			0			0	323201.33999999997	225000	100000	325000			0			0			0			0			0				325000	100000		100000			0			0			0			0			0	425200
64914					87069.6				18930			0			0			0			0			0	105999.6		106000		106000			0			0			0			0			0	106000	18930		18930			0			0			0			0			0	105999.6	106000		106000			0			0			0			0			0				106000	106000		106000			0			0			0			0			0	106000
64923					44115.12				15885			0			0			0			0			0	60000.12		60000		60000			0			0			0			0			0	60000	15885		15885			0			0			0			0			0	60000.12			0			0			0			0			0			0				0	60000		60000			0			0			0			0			0	60000
64925					21531			0			0			0			0			0	21531				0			0			0			0			0			0	28350	21531		21531			0			0			0			0			0	21531			0			0			0			0			0			0				0			0			0			0			0			0			0	28350
64927					12340				2660			0			0			0			0			0	15000		15000		15000			0			0			0			0			0	15000	2660		2660			0			0			0			0			0	15000			0			0			0			0			0			0				0	15000		15000			0			0			0			0			0	15000
73356					1420588.61				157774			0			0			0			0			0	1836668.6400000001		200000		200000			0			0			0			0			0	1674665	157774		157774			0			0			0			0			0	1836668.6400000001	1864000		1864000	200000		200000			0			0			0			0				2064000	200000		200000			0			0			0			0			0	1674665
73367					476777.69				26719			0			0			0			0			0	749689.52		10000		10000			0			0			0			0			0	733193	26719		26719			0			0			0			0			0	749689.52	602000		602000			0			0			0			0			0				602000	10000		10000			0			0			0			0			0	733193
73384					1420.63				12000			0			0			0			0			0	13420.630000000001		9000		9000			0			0			0			0			0	51106	11541	459	12000			0			0			0			0			0	13420.630000000001	34000		34000			0			0			0			0			0				51106	9000		9000			0			0			0			0			0	51106
73387					41873.57				5000			0			0			0			0			0	50791.27		5000		5000			0			0			0			0			0	52000	5000		5000			0			0			0			0			0	50791.27	43000	5000	48000			0			0			0			0			0				48000	5000		5000			0			0			0			0			0	52000
73388					262943.27				0			0			0			0			0			0	262943.27		58000		58000			0			0			0			0			0	344000			0			0			0			0			0			0	262943.27	298664	22495	321159			0			0			0			0			0				321159	58000		58000			0			0			0			0			0	344000
73398					13346.82				204700			0			0			0			0			0	218046.82		95000		95000			0			0			0			0			0	211000	204700		204700			0			0			0			0			0	218046.82	253487		253487	20000		20000			0			0			0			0				273487	95000		95000			0			0			0			0			0	211000
73399					18993.990000000002				206950			0			0			0			0			0	225943.99		108000	15000	123000			0			0			0			0			0	138000	191950	15000	206950			0			0			0			0			0	225943.99	48000		48000	91000	15000	106000			0			0			0			0				154000	108000	15000	123000			0			0			0			0			0	138000
73406					32020.92				17477			0			0			0			0			0	49497.919999999998				0			0			0			0			0			0	60000	17477		17477			0			0			0			0			0	49497.919999999998	20000		20000			0			0			0			0			0				20000			0			0			0			0			0			0	60000
73409					132223.26999999999				305902			0			0			0			0			0	438125.27		271000		271000			0			0			0			0			0	455000	305902		305902			0			0			0			0			0	438125.27	379500.00000000006	61500	441000.00000000006			0			0			0			0			0				441000.00000000006	271000		271000			0			0			0			0			0	455000
74119					3555498.8000000003				7038874.6043231441			4885118.0190100148			0			0			0			0	15479491.423333159		7233192	28727	7261919	1057804	56618	1114422			0			0			0			0	12909963	7001376.6177719198	37497.986551224472	7038874.6043231441	4833863.557572254	51254.461437760481	4885118.0190100148			0			0			0			0	15479491.423333159	4422093	111529.41	4533622.41	9645276	194535	9839811	1057804	56618	1114422			0			0			0				15487855.41	7233192	28727	7261919	1057804	56618	1114422			0			0			0			0	12909963
74127					0				125000			2275000			0			0			0			0	2400000		125000		125000	2275000		2275000			0			0			0			0	2400000	125000		125000	2275000		2275000			0			0			0			0	2400000			0	800000		800000	1600000		1600000			0			0			0				2400000	125000		125000	2275000		2275000			0			0			0			0	2400000
74268					58484942.089999996				93651797.428839236			34280135			0			0			0			0	193115993.21883923		104650502	825644	105476146	29469907	2950438	32420345			0			0			0			0	187356818	92403605.467262	1248191.9615772367	93651797.428839236	33364075	916060	34280135			0			0			0			0	193115993.21883923	46838234	2675210	49513444	119331552.45	2898925	122230477.45	14062863.220000001	1541104	15603967.220000001			0			0			0				187347888.66999999	104650502	825644	105476146	29469907	2950438	32420345			0			0			0			0	187356818
74277					0				4461207			40280925			6754868			0			0			0	51497000		8000000		8000000	44445136		44445136			0			0			0			0	52445136	4461207		4461207	40280925		40280925	6754868		6754868			0			0			0	51497000			0	8000000		8000000	44445136		44445136			0			0			0				52445136	8000000		8000000	44445136		44445136			0			0			0			0	52445136
74278					0				0			603000			4828000	4828000		4828000	500000		500000			0	10759000				0	528000	75000	603000	4828000		4828000	4828000		4828000	500000		500000			0	10759000			0	528000	75000	603000	4828000		4828000	4828000		4828000	500000		500000			0	10759000			0	528000		528000	4828000		4828000	4828000		4828000	500000		500000			0				10684000			0	528000	75000	603000	4828000		4828000	4828000		4828000	500000		500000			0	10759000
74279					1984354.07				4812654			1602703			0			0			0			0	8923144.4399999995		5444000		5444000	1588000		1588000			0			0			0			0	9106000	4810886	1768	4812654	1602703		1602703			0			0			0			0	8923144.4399999995	3259000	2000	3261000	4120000		4120000	1588000		1588000			0			0			0				8969000	5444000		5444000	1588000		1588000			0			0			0			0	9106000
74302					470098.91				369680			51636			0			0			0			0	2086231.25		435000		435000			0			0			0			0			0	945000	369680		369680	51636		51636			0			0			0			0	2086231.25	574000		574000	1292000		1292000			0			0			0			0				1866000	435000		435000			0			0			0			0			0	945000
74368					56152.62				10000			0			0			0			0			0	555477.47		10000		10000			0			0			0			0			0	66000	10000		10000			0			0			0			0			0	555477.47	69000		69000			0			0			0			0			0				69000	10000		10000			0			0			0			0			0	66000
74371					0				0			750000			4750000			0			0			0	5500000				0	1000000		1000000	4000000	500000	4500000			0			0			0	5600000			0	750000		750000	4250000	500000	4750000			0			0			0	5500000	100000		100000	1000000		1000000	4000000		4000000			0			0			0				5100000			0	1000000		1000000	4000000	500000	4500000			0			0			0	5600000
74373					6525760.0800000001				5536208			0			0			0			0			0	13800942.15		5342000	12500	5354500			0			0			0			0			0	11609722	5523133	13075	5536208			0			0			0			0			0	13800942.15	8959000	134000	9093000	2740000	2000	2742000			0			0			0			0				11835000	5342000	12500	5354500			0			0			0			0			0	11609722
74382					6008631.6200000001				6690211			488779			0			0			0			0	13187621.620000001		7008000	393000	7401000			0			0			0			0			0	12673000	6232184	458027	6690211	488779		488779			0			0			0			0	13187621.620000001	9335000	300000	9635000	2914000	172000	3086000			0			0			0			0				12721000	7008000	393000	7401000			0			0			0			0			0	12673000
74385					0				250000			2750000			0			0			0			0	3000000		500000		500000	2500000		2500000			0			0			0			0	3000000	250000		250000	2750000		2750000			0			0			0			0	3000000			0			0			0			0			0			0				0	500000		500000	2500000		2500000			0			0			0			0	3000000
74392					179085.31				162102			0			0			0			0			0	341187.31		676000		676000	800000		800000			0			0			0			0	1656000	162102		162102			0			0			0			0			0	341187.31	1166000		1166000	514000		514000			0			0			0			0				1680000	676000		676000	800000		800000			0			0			0			0	1656000
74404					265047.06				200613			0			0			0			0			0	483390.85		330000		330000			0			0			0			0			0	592000	201044	-431	200613			0			0			0			0			0	483390.85	597000	20000	617000			0			0			0			0			0				617000	330000		330000			0			0			0			0			0	592000
74406					103025.36				1596303			83733			0			0			0			0	1783061.36		1812000		1812000			0			0			0			0			0	1910000	1596303		1596303	83733		83733			0			0			0			0	1783061.36	1279000		1279000	622000	52000	674000			0			0			0			0				1953000	1812000		1812000			0			0			0			0			0	1910000
74409					0				0			332000			1592000			0			0			0	1924000		1902000	22000	1924000			0			0			0			0			0	2014000			0	310000	22000	332000	1592000		1592000			0			0			0	1924000	415000	40000	455000	968000	50000	1018000			0			0			0			0				1473000	1902000	22000	1924000			0			0			0			0			0	2014000
74416					36658.910000000003				142115			400000			0			0			0			0	578773.91		99000		99000			0			0			0			0			0	132392	142115		142115	400000		400000			0			0			0			0	578773.91	555000		555000			0			0			0			0			0				555000	99000		99000			0			0			0			0			0	132392
74418					224745.66				2031122			1568006			0			0			0			0	3823873.66		3675000		3675000			0			0			0			0			0	3888000	1918122	113000	2031122	1568006		1568006			0			0			0			0	3823873.66	3145000		3145000	1016000		1016000			0			0			0			0				4161000	3675000		3675000			0			0			0			0			0	3888000
74426					194621.07				495036			0			0			0			0			0	689657.07000000007		489000		489000			0			0			0			0			0	692000	495036		495036			0			0			0			0			0	689657.07000000007	707000		707000			0			0			0			0			0				707000	489000		489000			0			0			0			0			0	692000
74427					0				1944000			0			0			0			0	2340000		2340000	4284000		1944000		1944000			0			0			0			0			0	1951000	1944000		1944000			0			0			0			0	2340000		2340000	4284000	500000		500000	1450000		1450000			0			0			0			0				1950000	1944000		1944000			0			0			0			0			0	1951000
74428					0				0			200000			900000	900000		900000	935000		935000			0	2935000				0	950000	8000	958000	950000	8000	958000	935000		935000			0			0	2851000			0		200000	200000	900000		900000	900000		900000	935000		935000			0	2935000			0			0	950000	8000	958000	950000	8000	958000	935000		935000			0				2851000			0	950000	8000	958000	950000	8000	958000	935000		935000			0			0	2851000
74429					242656.43				198196			22991			0			0			0			0	463843.43		350000		350000			0			0			0			0			0	661000	198196		198196	22991		22991			0			0			0			0	463843.43	416000		416000	246000		246000			0			0			0			0				662000	350000		350000			0			0			0			0			0	661000
74431					0				442000			0			0			0			0			0	442000		442000		442000			0			0			0			0			0	442000	442000		442000			0			0			0			0			0	442000	100000		100000	428000	30000	458000			0			0			0			0				558000	442000		442000			0			0			0			0			0	442000
74432					0				0			3000000			6650000	6000000		6000000	3650000		3650000			0	19300000				0	2650000	350000	3000000	6650000		6650000	6000000		6000000	3650000		3650000			0	19300000			0	2650000	350000	3000000	6650000		6650000	6000000		6000000	3650000		3650000			0	19300000			0			0	2650000		2650000	6650000		6650000	5650000		5650000	3650000		3650000				18600000			0	2650000	350000	3000000	6650000		6650000	6000000		6000000	3650000		3650000			0	19300000
74435					0				500000			1049000			0			0			0			0	1549000		1549000		1549000			0			0			0			0			0	1549000			0	1549000		1549000			0			0			0			0	1549000			0			0	378000		378000	776102		776102			0			0				1154102	1549000		1549000			0			0			0			0			0	1549000
74453					581240.17000000004				687427.66669221583			3878.4368383351375			0			0			0			0	1272546.273530551		452919	10802	463721			0			0			0			0			0	1009121	684544.93881129124	2882.7278809245568	687427.66669221583	3878.4368383351375	0	3878.4368383351375			0			0			0			0	1272546.273530551	545400		545400	649000		649000			0			0			0			0				1194400	452919	10802	463721			0			0			0			0			0	1009121
74454					1387337.02				1096397.5510770674			354625.13559947704			0			0			0			0	2838359.7066765446		938961	10802	949763	177848	9518	187366			0			0			0			0	1899375	954866.6826566474	141530.86842042001	1096397.5510770674	352549.86539349984	2075.2702059771923	354625.13559947704			0			0			0			0	2838359.7066765446	755170	7075.52	762245.52	1621678	32708	1654386	177848	9518	187366			0			0			0				2603997.52	938961	10802	949763	177848	9518	187366			0			0			0			0	1899375
74455					1535901.73				2071221.9501828777			113875.87411313188			0			0			0			0	3720999.5542960097		2328891	27591	2356482	254209	13607	267816			0			0			0			0	3713805	2027438.0355123219	43783.914670555758	2071221.9501828777	113412.05591518244	463.81819794944471	113875.87411313188			0			0			0			0	3720999.5542960097	1079394	10112.549999999999	1089506.55	2292065	72611	2364676	254209	13607	267816			0			0			0				3721998.55	2328891	27591	2356482	254209	13607	267816			0			0			0			0	3713805
74486					0				2294000			110000			0			0			0			0	2404000		2404000		2404000	1546000		1546000	2092000		2092000			0			0			0	6042000	2294000		2294000	110000		110000			0			0			0			0	2404000	450000		450000	1000000		1000000	2275000		2275000	2275000		2275000			0			0				6000000	2404000		2404000	1546000		1546000	2092000		2092000			0			0			0	6042000
74487					0				3599318			2943031			0			0			0			0	6542349		4542000	7000	4549000	7408000	18000	7426000	5427000	20000	5447000			0			0			0	17422000	3599318		3599318	2925031	18000	2943031			0			0			0			0	6542349	500000		500000	3294314		3294314	3749999		3749999			0			0			0				7544313	4542000	7000	4549000	7408000	18000	7426000	5427000	20000	5447000			0			0			0	17422000
74489					2701000				686850			0			0			0			0			0	3387850		688000		688000			0			0			0			0			0	3388000	686850		686850			0			0			0			0			0	3387850	2700000		2700000			0			0			0			0			0				2700000	688000		688000			0			0			0			0			0	3388000
74490					860037.97				422881			0			0			0			0			0	1282918.97		460000		460000			0			0			0			0			0	1242000	422881		422881			0			0			0			0			0	1282918.97	734000		734000	734000		734000			0			0			0			0				1468000	460000		460000			0			0			0			0			0	1242000
74491					0				6211694			12836630			3347374	487190	20600	507790	61490	4800	66290			0	22969778		7015007	200000	7215007	11618688	254750	11873438	2915160	82980	2998140	232200	61920	294120	20640	47520	68160			0	22448865	6094794	116900	6211694	12701630	135000	12836630	3267374	80000	3347374	487190	20600	507790	61490	4800	66290			0	22969778			0	8400000	50000	8450000	8400000	50000	8450000			0			0			0				16900000	7015007	200000	7215007	11618688	254750	11873438	2915160	82980	2998140	232200	61920	294120	20640	47520	68160			0	22448865
74510					0				1746027			149000			0			0			0			0	1895027		1869000		1869000			0			0			0			0			0	1869000	1745958	69	1746027	149000		149000			0			0			0			0	1895027			0			0			0			0			0			0				0	1869000		1869000			0			0			0			0			0	1869000
				800000			0			0			0			0			0	800000					800000	800000			0			0			0			0			0	800000
74511					0				1943300			3074500			0			0			0			0	5017800		2457000	45000	2502000	2471000		2471000			0			0			0			0	4973000	1943300		1943300	3074500		3074500			0			0			0			0	5017800			0			0			0			0			0			0				0	2457000	45000	2502000	2471000		2471000			0			0			0			0	4973000
74512					0				0			355555.55555555556			444444.44444444438			0			0			0	800000				0	650000	50000	700000			0			0			0			0	700000			0	333333.33333333331	22222.222222222223	355555.55555555556	416666.66666666663	27777.777777777777	444444.44444444438			0			0			0	800000			0			0			0			0			0			0				0			0	650000	50000	700000			0			0			0			0	700000
74513					0				0			730000			0			0			0			0	730000				0	712000	18000	730000			0			0			0			0	730000			0	712000	18000	730000			0			0			0			0	730000			0			0			0			0			0			0				0			0	712000	18000	730000			0			0			0			0	730000
76643					126474.11				143425			0			0			0			0			0	269899.11		128000		128000			0			0			0			0			0	196000	143425		143425			0			0			0			0			0	269899.11	167000		167000	186000		186000			0			0			0			0				353000	128000		128000			0			0			0			0			0	196000
96069					0				0			144407			0			0			0			0	144407				0	144407		144407			0			0			0			0	144407			0	144407		144407			0			0			0			0	144407	144407		144407			0			0			0			0			0				144407			0	144407		144407			0			0			0			0	144407
74524					0				8519			550000			0			0			0			0	558519		12000		12000	550000		550000	550000		550000			0			0			0	1112000		8519	8519		550000	550000			0			0			0			0	558519			0			0	550000		550000	550000		550000			0			0				1100000	12000		12000	550000		550000	550000		550000			0			0			0	1112000
96105					0				0			0			0			0			0			0	0				0	575000		575000			0			0			0			0	575000			0			0			0			0			0			0	0			0			0			0	575000		575000			0			0				575000			0	575000		575000			0			0			0			0	575000
96109					0				0			600000			2100000	900000		900000	2400000		2400000			0	6000000				0	600000		600000	2100000		2100000	900000		900000	2400000		2400000			0	6000000			0	600000		600000	2100000		2100000	900000		900000	2400000		2400000			0	6000000			0			0	600000		600000	2100000		2100000	900000		900000	2400000		2400000				6000000			0	600000		600000	2100000		2100000	900000		900000	2400000		2400000			0	6000000
96112					0				0			0			0	500000		500000	2500000		2500000			0	3000000				0	1000000		1000000	2000000		2000000			0			0			0	3000000			0	500000		500000	2500000		2500000			0			0			0	3000000			0			0			0			0			0			0				0			0	1000000		1000000	2000000		2000000			0			0			0	3000000
96113					0				0			0			0			0	10000000		10000000			0	10000000				0			0			0			0	10000000		10000000			0	10000000			0			0			0			0	10000000		10000000			0	10000000			0			0			0			0			0	10000000		10000000				10000000			0			0			0			0	10000000		10000000			0	10000000
96114					0				0			600000			2600000	1000000		1000000	3000000		3000000			0	7200000				0	600000		600000	2600000		2600000	1000000		1000000	3000000		3000000			0	7200000			0	600000		600000	2600000		2600000	1000000		1000000	3000000		3000000			0	7200000			0			0	600000		600000	2600000		2600000	1000000		1000000	3000000		3000000				7200000			0	600000		600000	2600000		2600000	1000000		1000000	3000000		3000000			0	7200000
96116					0				0			0			1500000	750000	750000	1500000			0			0	3000000				0	750000	750000	1500000	750000	750000	1500000			0			0			0	3000000			0			0	750000	750000	1500000	750000	750000	1500000			0			0	3000000			0			0	750000	750000	1500000	750000	750000	1500000			0			0				3000000			0	750000	750000	1500000	750000	750000	1500000			0			0			0	3000000
96117					0				0			0			0			0	440000		440000			0	440000				0			0			0	440000		440000			0			0	440000			0			0			0			0	440000		440000			0	440000			0			0			0			0	440000		440000			0				440000			0			0			0	440000		440000			0			0	440000
74527					0				0			4859000			0			0			0			0	4859000		2646000		2646000	11013000		11013000			0			0			0			0	13659000			0	4859000		4859000			0			0			0			0	4859000			0			0			0			0			0			0				0	2646000		2646000	11013000		11013000			0			0			0			0	13659000
96124					0				0			8940664			78779345	1376100	55330	1431430	349305	19800	369105	38280	40920	79200	89599744				0	8000000	50000	8050000	8400000	50000	8450000			0			0			0	16500000			0	8793594	147070	8940664	78610055	169290	78779345	1376100	55330	1431430	349305	19800	369105	38280	40920	79200	89599744			0			0	8000000	50000	8050000	8400000	50000	8450000			0			0				16500000			0	8000000	50000	8050000	8400000	50000	8450000			0			0			0	16500000
96125					0				0			0			0	8793594	147070	8940664	24767311.854391322	6402538.1456086803	31169850	1376100	55330	1431430	41541944				0			0	8000000	50000	8050000	8400000	50000	8450000			0			0	16500000			0			0			0	8793594	147070	8940664	31000560	169290	31169850	1376100	55330	1431430	41541944			0			0			0	8000000	50000	8050000	8400000	50000	8450000			0				16500000			0			0	8000000	50000	8050000	8400000	50000	8450000			0			0	16500000
96126					0				0			0			0			0	8793594	147070	8940664	22558263.79257828	6194763.20742172	28753027	37693691				0			0			0	8000000	50000	8050000	8400000	50000	8450000			0	16500000			0			0			0			0	8793594	147070	8940664	28583737	169290	28753027	37693691			0			0			0			0	8000000	50000	8050000	8400000	50000	8450000				16500000			0			0			0	8000000	50000	8050000	8400000	50000	8450000			0	16500000
74546					0				261000			624000			0			0			0			0	885000		210000		210000			0			0			0			0			0	210000	100000		100000	785864		785864			0			0			0			0	885864			0	210000		210000			0			0			0			0				210000	210000		210000			0			0			0			0			0	210000
96133					0				0			210000			0			0			0			0	210000				0	210000		210000			0			0			0			0	210000			0	210000		210000			0			0			0			0	210000			0			0			0			0			0			0				0			0	210000		210000			0			0			0			0	210000
96135					0				23000			0			0			0			0			0	23000		327522		327522			0			0			0			0			0	327522	23000		23000			0			0			0			0			0	23000			0			0			0			0			0			0				0	327522		327522			0			0			0			0			0	327522
96136					0				0			120000			120000			0			0			0	240000				0	240000		240000			0			0			0			0	240000			0	120000		120000	120000		120000			0			0			0	240000			0	240000		240000			0			0			0			0				240000			0	240000		240000			0			0			0			0	240000
96137					0				175000			0			0			0			0			0	175000		250000		250000			0			0			0			0			0	250000	175000		175000			0			0			0			0			0	175000			0			0			0			0			0			0				0	250000		250000			0			0			0			0			0	250000
96139					0				0			200000			0			0			0			0	200000		200000		200000			0			0			0			0			0	200000			0	200000		200000			0			0			0			0	200000			0			0			0			0			0			0				0	200000		200000			0			0			0			0			0	200000
65066					0				73000			0			0			0			0			0	73000				0	80000		80000			0			0			0			0	80000	73000		73000			0			0			0			0			0	73000			0			0			0			0			0			0				0			0	80000		80000			0			0			0			0	80000
65021					0				19424			0			0			0			0			0	19424				0			0			0			0			0			0	18000	19424		19424			0			0			0			0			0	19424			0			0			0			0			0			0				0			0			0			0			0			0			0	18000
96159					0				150000			0			0			0			0			0	150000		150000		150000			0			0			0			0			0	150000	150000		150000			0			0			0			0			0	150000			0			0			0			0			0			0				0	150000		150000			0			0			0			0			0	150000
96165					0				0			2000000			0			0			0			0	2000000				0	2000000		2000000			0			0			0			0	2000000			0	2000000		2000000			0			0			0			0	2000000			0			0			0			0			0			0				0			0	2000000		2000000			0			0			0			0	2000000
96163					0				0			400000			0			0			0			0	400000				0	300000	100000	400000			0			0			0			0	400000			0	300000	100000	400000			0			0			0			0	400000			0			0			0			0			0			0				0			0	300000	100000	400000			0			0			0			0	400000
96164					0				0			30000			0			0			0			0	30000		30000		30000			0			0			0			0			0	30000			0	30000		30000			0			0			0			0	30000			0			0			0			0			0			0				0	30000		30000			0			0			0			0			0	30000
96167					0				25000			0			0			0			0			0	25000		25000		25000			0			0			0			0			0	25000	25000		25000			0			0			0			0			0	25000			0			0			0			0			0			0				0	25000		25000			0			0			0			0			0	25000
96168					0				20000			0			0			0			0			0	20000		20000		20000			0			0			0			0			0	20000	20000		20000			0			0			0			0			0	20000			0			0			0			0			0			0				0	20000		20000			0			0			0			0			0	20000
74526					0				1190000			510000			0			0			0			0	1700000		1700000		1700000			0			0			0			0			0	1700000	1190000		1190000	510000		510000			0			0			0			0	1700000			0			0			0			0			0			0				0	1700000		1700000			0			0			0			0			0	1700000
98026					0				800000			0			0			0			0			0	800000			800000	800000			0			0			0			0			0	800000		800000	800000			0			0			0			0			0	800000			0			0			0			0			0			0				0		800000	800000			0			0			0			0			0	800000
74525					0				0			0			0	0		0			0			0	0			400000	400000	1000000		1000000	2000000		2000000	1000000		1000000			0			0	4400000			0			0			0			0			0			0	0			0			0			0	1000000		1000000	2000000		2000000	1000000		1000000				4000000		400000	400000	1000000		1000000	2000000		2000000	1000000		1000000			0			0	4400000
65005					0				24238			0			0			0			0			0	24238					24238		24238			0			0			0			0			0	24238			0			0			0			0			0			0				0
65009					0				34000			0			0			0			0			0	34000			25000	25000			0			0			0			0			0	25000	30000	4000	34000			0			0			0			0			0	34000			0			0			0			0			0			0				0		25000	25000			0			0			0			0			0	25000
65020					0				27987			0			0			0			0			0	27987					27987		27987			0			0			0			0			0	27987			0			0			0			0			0			0				0
65023					0				56795			0			0			0			0			0	56795					56795		56795			0			0			0			0			0	56795			0			0			0			0			0			0				0
65018					0				320000			0			0			0			0			0	320000					320000		320000			0			0			0			0			0	320000			0			0			0			0			0			0				0
65015					0				245000			0			0			0			0			0	245000					245000		245000			0			0			0			0			0	245000			0			0			0			0			0			0				0
65024					0				140000			488779			0			0			0			0	628779					140000		140000	488779		488779			0			0			0			0	628779			0			0			0			0			0			0				0
96169					0				70000			0			0			0			0			0	70000					70000		70000			0			0			0			0			0	70000
74535					0				306000			654000			0			0			0			0	960000					306000		306000	654000		654000			0			0			0			0	960000
65044					0				62000			0			0			0			0			0	62000					62000		62000			0			0			0			0			0	62000
65037					0				23914			0			0			0			0			0	23914					23914		23914			0			0			0			0			0	23914
96174					0				135000			0			0			0			0			0	135000					135000		135000			0			0			0			0			0	135000
65040					0				20185			0			0			0			0			0	20185					20185		20185			0			0			0			0			0	20185
65048					0				37000			0			0			0			0			0	37000					37000		37000			0			0			0			0			0	37000
96177					0				0			3000000			3000000	3000000		3000000	3000000		3000000	3000000		3000000	15000000					0	3000000		3000000	3000000		3000000	3000000		3000000	3000000		3000000	3000000		3000000	15000000
96178					0			0			2500000	3000000		3000000			0			0	5500000					0			0	2500000		2500000	3000000		3000000			0			0	5500000
96179					0			0			0	458000		458000	5000000		5000000			0	5458000					0			0			0	458000		458000	5000000		5000000			0	5458000
96180					0			1500000			0			0			0			0	1500000					0	1500000		1500000			0			0			0			0	1500000
96181					0			100000			0			0			0			0	100000					0	100000		100000			0			0			0			0	100000
96183					0			200000			0			0			0			0	200000					0	200000		200000			0			0			0			0	200000			0			0			0			0			0			0
96184					0			200000			0			0			0			0	200000					0	200000		200000			0			0			0			0	200000
96188					0			20000			0			0			0			0	20000					0	20000		20000			0			0			0			0	20000
96189					0			100000			0			0			0			0	100000					0	100000		100000			0			0			0			0	100000
96191					0			2000000			0			0			0			0	2000000					0	2000000		2000000			0			0			0			0	2000000			0			0			0			0			0			0
96192					0			2500000			0			0			0			0	2500000					0	2500000		2500000			0			0			0			0	2500000
96193					0			300000			0			0			0			0	300000					0	300000		300000			0			0			0			0	300000
96197					0			200000			0			0			0			0	200000					0	200000		200000			0			0			0			0	200000
96200					0			30000			0			0			0			0	30000					0	30000		30000			0			0			0			0	30000
96201					0			200000			0			0			0			0	200000					0	200000		200000			0			0			0			0	200000
96202					0			25000			0			0			0			0	25000					0	25000		25000			0			0			0			0	25000
96204					0			500000			0			0			0			0	500000					0	500000		500000			0			0			0			0	500000
96205					0			3500000			0			0			0			0	3500000					0	3500000		3500000			0			0			0			0	3500000
96206					0			20000			0			0			0			0	20000					0	20000		20000			0			0			0			0	20000
96207					30000			0			0			0			0			0	30000					25000	5000	30000			0			0			0			0			0	30000			0			0			0			0			0			0
65082					22000			0			0			0			0			0	22000					17250		17250			0			0			0			0			0	17250

				0			0			0			0			0			0
96991					1007097			0			0			0			0			0	1007097		987350	19747	1007097			0			0			0			0			0	1007097	987350	19747	1007097			0			0			0			0			0	1007097					987350	19747	1007097			0			0			0			0			0	1007097
96992					126480			0			0			0			0			0	126480		124000	2480	126480			0			0			0			0			0	126480	124000	2480	126480			0			0			0			0			0	126480					124000	2480	126480			0			0			0			0			0	126480
96993					50375			0			0			0			0			0	50375		50375		50375			0			0			0			0			0	50375	50375		50375			0			0			0			0			0	50375					50375		50375			0			0			0			0			0	50375
96994					268268			0			0			0			0			0	268268		263008	5260	268268			0			0			0			0			0	268268	263008	5260	268268			0			0			0			0			0	268268			0	502793		502793			0			0			0			0				502793	263008	5260	268268			0			0			0			0			0	268268
96995					407893			0			0			0			0			0	407893		407893		407893			0			0			0			0			0	668893	407893		407893			0			0			0			0			0	407893	261000		261000	407893		407893			0			0			0			0				668893	407893		407893			0			0			0			0			0	668893
96996					0			0			0			0			0			0	0				0			0			0			0			0			0	0			0			0			0			0			0			0	0			0	0		0			0			0			0			0				0			0			0			0			0			0			0	0
96997					31233			0			0			0			0			0	31233		31233		31233			0			0			0			0			0	31233	31233		31233			0			0			0			0			0	31233			0	1028658	10075	1038733			0			0			0			0				1038733	31233		31233			0			0			0			0			0	31233
96998					0			0			0			0			0			0	0				0			0			0			0			0			0	0			0			0			0			0			0			0	0			0	359226	1200	360426			0			0			0			0				360426			0			0			0			0			0			0	0
96999					-10661762.4				-2167416.5			0			0			0			0			0	-16676381.060000001		-8348298	235000	-8113298			0			0			0			0			0	-22622263	-1487179.5	-197487	-1684666.5			0			0			0			0			0	-16193631.060000001	-10661762.4		-10661762.4	-21328357		-21328357			0			0			0			0				-35837321.560000002	-8348298	235000	-8113298			0			0			0			0			0	-22622263
T					157482175.70111454			150619972.0211165			119866031.44444445	31992884	973000	32965884	65396700.854391322	6574208.1456086803	71970909	29312643.79257828	6291013.20742172	35603657	568508629.16667545		175557472	3085553	178643025	140163999	4703931	144867930	53262160	1460980	54723140	31735200	161920	31897120	27970640	97520	28068160				516038841	157460138	3639273.4591003614	161099411.45910099	149174690.24905258	2607145.7720639091	151781836.0211165	120838963.66666667	1527067.7777777778	122366031.44444445	31492884	973000	32465884	69129949	340960	69470909	35338117	265540	35603657	568987493.16667497	95955861.599999994	3842276.48	99798138.079999983	161289098.44999999	3644779	183513664.44999999	103595053.22	2553847	106148900.22	46504102	858000	47362102	31575000	100000	31675000	28450000	50000	28500000				497714304.74999994	175557472	3085553	178643025	140163999	4703931	144867930	53262160	1460980	54723140	31735200	161920	31897120	27970640	97520	28068160				516038841

82000					70227.429999999993				933708			781722			0			0			0			0	1785657.43			1180000	1180000			0			0			0			0			0	1220000		933708	933708		781722	781722			0			0			0			0	1785657.43		540000	540000		980000	980000			0			0			0			0				1520000		1180000	1180000			0			0			0			0			0	1220000
97001					4000					0			0			0	4000			5000	5000			0			0			0			0			0	10000		4000	4000					0			0			0	4000		5000	5000		5000	5000					0			0				10000		5000	5000			0			0			0			0			0	10000
97002					45000					0			0			0	45000			50000	50000			0			0			0			0			0	100000		45000	45000					0			0			0	45000		50000	50000		50000	50000					0			0				100000		50000	50000			0			0			0			0			0	100000
97003					443000			0			0			0			0			0	443000			443000	443000			0			0			0			0			0	458000		443000	443000			0			0			0			0			0	443000		290000	290000		514000	514000			0			0			0			0				804000		443000	443000			0			0			0			0			0	458000
97005					0			312000			0			0			0			0	312000				0		312000	312000			0			0			0			0	312000			0		312000	312000			0			0			0			0	312000			0			0		312000	312000			0			0			0				312000			0		312000	312000			0			0			0			0	312000
97006					0			0			0		332000	332000			0			0	332000				0			0			0		332000	332000			0			0	332000			0			0			0		332000	332000			0			0	332000			0			0			0			0		332000	332000			0				332000			0			0			0		332000	332000			0			0	332000
97063					0			0			0			0			0	351000		351000	351000					0			0			0			0			0	351000		351000	351000
97007					295169			0			0			0			0			0	295169			270000	270000			0			0			0			0			0	270000		295169	295169			0			0			0			0			0	295169	600000	300000	900000	200000	1900000	2100000			0			0			0			0				3000000		270000	270000			0			0			0			0			0	270000
97008					0			0			487500		487500	487500			0			0	975000				0			0			0		975000	975000		975000	975000			0	1950000			0			0		487500	487500		487500	487500			0			0	975000			0			0			0		975000	975000		975000	975000			0				1950000			0			0			0		975000	975000		975000	975000			0	1950000
97064					0			0			0			0			0		463000	463000	463000					0			0			0			0			0		463000	463000	463000
97009					0			400000			575000			0			0			0	975000				0		500000	500000		1126000	1126000			0			0			0	1626000			0		400000	400000		575000	575000			0			0			0	975000			0			0			0			0			0			0				0			0		500000	500000		1126000	1126000			0			0			0	1626000
97010					0			0			0			0		500000	500000		525000	525000	1025000				0			0			0		926000	926000		926000	926000			0	1852000			0			0			0			0		500000	500000		525000	525000	1025000			0			0			0		926000	926000		926000	926000			0				1852000			0			0			0		926000	926000		926000	926000			0	1852000
97012					0			366000			0			0			0			0	366000				0		366000	366000			0			0			0			0	366000			0		366000	366000			0			0			0			0	366000			0		366000	366000			0			0			0			0				366000			0		366000	366000			0			0			0			0	366000
97013					0			0			0		488000	488000			0			0	488000				0			0			0		488000	488000			0			0	488000			0			0			0		488000	488000			0			0	488000			0			0			0		488000	488000			0			0				488000			0			0			0		488000	488000			0			0	488000
97065					0			0			0			0			0		488000	488000	488000					0			0			0			0			0		488000	488000	488000
97015					0			390000			0			0			0			0	390000				0		390000	390000			0			0			0			0	390000			0		390000	390000			0			0			0			0	390000			0			0		390000	390000			0			0			0				390000			0		390000	390000			0			0			0			0	390000
97016					0			0			0			0		439000	439000			0	439000				0			0			0			0		439000	439000			0	439000			0			0			0			0		439000	439000			0	439000			0			0			0			0			0		439000	439000				439000			0			0			0			0		439000	439000			0	439000
97018					0			0			488000			0			0			0	488000				0		488000	488000			0			0			0			0	488000			0			0		488000	488000			0			0			0	488000			0			0		488000	488000			0			0			0				488000			0		488000	488000			0			0			0			0	488000
97019					0			0			0			0		488000	488000			0	488000				0			0			0			0		488000	488000			0	488000			0			0			0			0		488000	488000			0	488000			0			0			0			0			0		488000	488000				488000			0			0			0			0		488000	488000			0	488000
97020					0			0			0			0			0			0	0				0			0			0			0			0			0	300000			0			0			0			0			0			0	0		300000	300000			0			0			0			0			0				300000			0			0			0			0			0			0	300000
97030					0			1625000			0			0			0			0	1625000				0		1625000	1625000			0			0			0			0	1625000			0		1625000	1625000			0			0			0			0	1625000			0			0		1625000	1625000			0			0			0				1625000			0		1625000	1625000			0			0			0			0	1625000
97031					0			325000			0			0			0			0	325000				0		325000	325000			0			0			0			0	325000			0		325000	325000			0			0			0			0	325000			0			0		325000	325000			0			0			0				325000			0		325000	325000			0			0			0			0	325000
97032					0			0			0			0		360000	360000			0	360000				0			0			0			0		360000	360000			0	360000			0			0			0			0		360000	360000			0	360000			0			0			0			0			0		360000	360000				360000			0			0			0			0		360000	360000			0	360000
97033					0			0			325000			0			0			0	325000				0			0		325000	325000			0			0			0	325000			0			0		325000	325000			0			0			0	325000			0			0			0		325000	325000			0			0				325000			0			0		325000	325000			0			0			0	325000
97066					0			0			0			0			0		360000	360000	360000					0			0			0			0			0		360000	360000	360000
97037					0			3750000			0			0			0			0	3750000				0		3750000	3750000			0			0			0			0	3750000			0		3750000	3750000			0			0			0			0	3750000			0		3750000	3750000			0			0			0			0				3750000			0		3750000	3750000			0			0			0			0	3750000
97038					0			4750000			3250000			0			0			0	8000000			1000000	1000000		3750000	3750000		3250000	3250000			0			0			0	8000000		0	0		4750000	4750000		3250000	3250000			0			0			0	8000000			0		2000000	2000000		3000000	3000000		3000000	3000000			0			0				8000000		1000000	1000000		3750000	3750000		3250000	3250000			0			0			0	8000000
97039					0			250000			2250000		3375000	3375000			0			0	5875000			250000	250000		2250000	2250000		3375000	3375000			0			0			0	5875000			0		250000	250000		2250000	2250000		3375000	3375000			0			0	5875000			0		500000	500000		2250000	2250000		3375000	3375000			0			0				6125000		250000	250000		2250000	2250000		3375000	3375000			0			0			0	5875000
97040					0			0			0			0			0			0	0			250000	250000		305750	305750			0			0			0			0	555750		0	0			0			0			0			0			0	0			0		555750	555750			0			0			0			0				555750		250000	250000		305750	305750			0			0			0			0	555750
97042					250400			0			0			0			0			0	250400			360000	360000			0			0			0			0			0	720000		250400	250400			0			0			0			0			0	250400		360000	360000		360000	360000			0			0			0			0				720000		360000	360000			0			0			0			0			0	720000
97043					10000			0			0			0			0			0	10000			200000	200000			0			0			0			0			0	400000		10000	10000			0			0			0			0			0	10000		200000	200000		200000	200000			0			0			0			0				400000		200000	200000			0			0			0			0			0	400000
97044					8000			0			0			0			0			0	8000			12000	12000			0			0			0			0			0	24000		8000	8000			0			0			0			0			0	8000		12000	12000		12000	12000			0			0			0			0				24000		12000	12000			0			0			0			0			0	24000
97045					100000			100000			0			0			0			0	200000			200000	200000			0			0			0			0			0	200000		100000	100000		100000	100000			0			0			0			0	200000			0			0			0			0			0			0				400000		200000	200000			0			0			0			0			0	200000
97046					0			0			0			0			0			0	0				0			0			0			0			0			0	157000			0			0			0			0			0			0	0			0			0			0			0			0			0				0			0			0			0			0			0			0	157000
97047					0			0			0			0			0			0	0				0			0			0			0			0			0	90000			0			0			0			0			0			0	0			0			0			0			0			0			0				0			0			0			0			0			0			0	90000
97048					319456			0			0			0			0			0	319456			318000	318000			0			0			0			0			0	366000		319456	319456			0			0			0			0			0	319456			0			0			0			0			0			0				0		318000	318000			0			0			0			0			0	366000
97049					0			0			0			0			0			0	0				0			0			0			0			0			0	327000			0			0			0			0			0			0	0			0			0			0			0			0			0				0			0			0			0			0			0			0	327000
97053					100000			0			0			0			0			0	100000			100000	100000			0			0			0			0			0	100000		100000	100000			0			0			0			0			0	100000			0			0			0			0			0			0				0		100000	100000			0			0			0			0			0	100000
97054					0			113000			44000			0			0			0	157000				0		131250	131250	43750		43750			0			0			0	175000			0		113000	113000		44000	44000			0			0			0	157000			0			0			0			0			0			0				0			0		131250	131250	43750		43750			0			0			0	175000
97057					108000			192000			0			0			0			0	300000			300000	300000			0			0			0			0			0	300000		108000	108000		192000	192000			0			0			0			0	300000			0			0			0			0			0			0				0		300000	300000			0			0			0			0			0	300000
97058					245040			0			0			0			0			0	245040			80000	80000			0			0			0			0			0	200000		245040	245040			0			0			0			0			0	245040			0			0			0			0			0			0				0		80000	80000			0			0			0			0			0	200000
97059					107000			0			0			0			0			0	107000				0			0			0			0			0			0	0		107000	107000			0			0			0			0			0	107000			0			0			0			0			0			0				0			0			0			0			0			0			0	0
97060					75000			0			0			0			0			0	75000					75000	75000			0			0			0			0			0	75000			0			0			0			0			0			0				0
97061					0				0			550000			0			0			0			0	550000				0		491216	491216			0			0			0			0	491216			0		550000	550000			0			0			0			0	550000			0			0			0			0			0			0				0			0		491216	491216			0			0			0			0	491216
TBD					3091211			3000000			3000000			0			0			0	9091211					3091211	3091211		3000000	3000000		3000000	3000000			0			0			0	9091211
97062					0			0			0			0			0			0	0					0			0			0			0			0			0	0			0			0			0			0			0			0

				0			0			0			0			0			0	0					0			0			0			0			0			0				0
97999					0			0			0			0			0	0			-2125000	-2125000			0			0			0			0			0	0			0			0			0			0			0			0	0			0					0			0			0			0				0		-2125000				0			0			0			0			0	0
E					6134984			16904722			10419500	0	4682500	4682500	0	1787000	1787000	351000	1836000	2187000	42185933.43		0	2918000	5043000	0	14684216	14684216	43750	8076000	8119750	0	2721000	2721000	0	3188000	3188000				36139966	0	6134984	6134984	0	16904722	16904722	0	10419500	10419500	0	4682500	4682500	0	1787000	1787000	351000	1836000	2187000	42185933.43	600000	2362000	2962000	200000	13447750	13647750	0	8390000	8390000	0	9089000	9089000	0	2233000	2233000	0	1775000	1775000				38681750	0	2918000	5043000	0	14684216	14684216	43750	8076000	8119750	0	2721000	2721000	0	3188000	3188000				36139966

				163087054.10111457			155735835.5211165			125493481.29444444	35292884	973000	39156078.835000001	69180700.854391322	6574208.1456086803	78780123.318499997	36676643.79257828	6291013.20742172	42967657	718799948.48017573

				163087054.10111457

## 'file:///C:/Users/webster5/AppData/Roaming/Microsoft/Excel/2016%20Master%20Project%20Portfolio%20BU%20110%20(version%201).xlsb'#Resource_2016_
64777					9.833333333333337E-2
64786					0
64901					0
65044					0.125
73328					0
73356					0
73367					0.30499999999999999
73368					0
73377					0
73383					0.14083333333333334
73387					0
73388					0
73398					0
73399					0.11166666666666668
73406					0
73409					2.1666666666666667E-2
74119					2.2974999999999999
74127					0
74244					0.42083333333333334
74268					21.207500000000007
74278					0.35583333333333328
74279					5.1508333333333338
74280					1.5000000000000005E-2
74302					0.83333333333333315
74371					0.2
74373					3.0833333333333335
74382					1.1333333333333333
74385					2.2789115646258504
74386					0.19666666666666668
74392					0.47083333333333338
74404					1.1666666666666667E-2
74406					0.10875000000000001
74409					5.6666666666666664E-2
74416					6.1224489795918359E-2
74418					0.28061224489795916
74426					0.29666666666666675
74427					0.29250000000000004
74428					0
74429					0.21
74431					9.4166666666666676E-2
74432					5.000000000000001E-2